## QA Folder Structure
QA Folder Structure
Site QA
Installation
Basements
B4
B3
B2
B1
|  | Ground |  |  | Ground Checklist
Office Floors (expanded out below)
|  |  | 1-36 (EXCEPT FOR 13, 25 and 37) |  | Office Floors Checklist
Plant Rooms
|  |  | 13 |  | Plant Room Checklist
|  |  | 25 |  | Plant Room Checklist
|  |  | 37 |  | Plant Room Checklist
Pre-commissioning
Basements
B4
B3
B2
B1
Ground
|  |  | Pipe Pressure Testing |  | Pipe Pressure Testing Checklist
|  |  | Pipe Flushing |  | Pipe Flushing and Cleaning Checklist
Office Floors (expanded out below)
1-36 (EXCEPT FOR 13, 25 and 37)
|  |  |  | Pipe Pressure Testing | Pipe Pressure Testing Checklist
|  |  |  | Pipe Flushing | Pipe Flushing and Cleaning Checklist
Plant Rooms
13
|  |  |  | Pipe Pressure Testing | Pipe Pressure Testing Checklist
|  |  |  | Pipe Flushing | Pipe Flushing and Cleaning Checklist
25
|  |  |  | Pipe Pressure Testing | Pipe Pressure Testing Checklist
|  |  |  | Pipe Flushing | Pipe Flushing and Cleaning Checklist
37
|  |  |  | Pipe Pressure Testing | Pipe Pressure Testing Checklist
|  |  |  | Pipe Flushing | Pipe Flushing and Cleaning Checklist
Commissioning
Basements
B4
B3
B2
B1
|  | Ground |  |  | Commissioning Checklist
Office Floors (expanded out below)
|  |  | 1-36 (EXCEPT FOR 13, 25 and 37) |  | Commissioning Checklist
Plant Rooms
|  |  | 13 |  | Commissioning Checklist
|  |  | 25 |  | Commissioning Checklist
|  |  | 37 |  | Commissioning Checklist

## ITPs Checklists
type | name | values | prefix | postfix
checklist-flat | Ground Checklist
checkpoint | Ductwork
checkpoint | VAV
checkpoint | PAC
tickbox | Condensate Drains
checkpoint | Risers
checklist-flat | Office Floors Checklist
checkpoint | Ductwork
checkpoint | VAV
checkpoint | FCU
tickbox | Condensate Drains
checkpoint | Risers (Chilled)
checkpoint | Risers (Hot)
checkpoint | Floor Pipe
checkpoint | Fire Dampers
checkpoint | Control Dampers / VCD
checkpoint | Cushion Boxes
checklist-flat | Plant Room Checklist
checkpoint | Ductwork
checkpoint | Fans
checkpoint | Pipework
checkpoint | Coils
checkpoint | Valves
checkpoint | Pumps
checkpoint | AHU
checklist | Pipe Pressure Testing Checklist
checkpoint | Testing Details - Pass once entered
text | Testing Date
select | Test No. | 1,2,3
select | Pipe system under test | Heating Hot water,Chilled Water,Steam,Condensate,Condenser Water
text | Area/Section under test
text | System Test Pressure (kPa)
text | First Reading (kPa)
text | Time of Test
text | Second Reading (kPa)
text | Time of Test
checkpoint | Testing Complete
holdpoint | Click to add Signature Sign-Off's
checklist | Pipe Flushing and Cleaning Checklist
checkpoint | Manufacturers pump curve(s)
checkpoint | Procedure - All balancing, control, & isolating valves in the appropriate position for the test
checkpoint | All coils installed
checkpoint | System filled with treated water & circulated through system
checkpoint | Stop Pump & isolate valves
checkpoint | Inspect coils for debris
checkpoint | Back flush coils if required
checkpoint | Refill system with treated water and bleed
checkpoint | Completion - Dump residual water from temporary test rig prior to testing other areas
holdpoint | Click to add Signature Sign-Off's
checklist | Commissioning Checklist
checkpoint | Air Balance Completed
label | NEBB sheet completed
checkpoint | Water Balance Completed
label | NEBB sheet completed
checkpoint | Chillers commissioned by manufacturer - If applicable
checkpoint | Heating Hot Water Boilers commissioned by manufacturer - If applicable
checkpoint | Steam Boilers commissioned by manufacturer - If applicable