## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Data cabling and outlets |  |  |  |  | Yes | Data cabling and outlets | 08441299-ecff-4432-b09b-8f0c96cb5856
checkpoint-group |  |  | section | Rough In
checkpoint-status |  |  | checkpoint | Confirm that the cable support system has been completed as per documentation
checkpoint-status |  |  | checkpoint | Data cabling has been selected as per drawings and specifications (Cat6/CatA & brand)
checkpoint-status |  |  | checkpoint | Mechanical protection has been provided to minimise the likelihood of physical damage to cabling
checkpoint-status |  |  | checkpoint | Cabling has been concealed where possible in ceiling spaces, wall cavities or risers
checkpoint-status |  |  | checkpoint | All outlets have been wired as per drawings
checkpoint-status |  |  | checkpoint | All data outlets have been numbered and marked on the site as built drawing
checkpoint-status |  |  | checkpoint | Height and location have been confirmed for each outlet
checkpoint-group |  |  | section | Fit Off & Commission
checkpoint-status |  |  | checkpoint | Equipment/materials have been selected and installed as per drawings/specifications
checkpoint-status |  |  | checkpoint | Terminations have been checked and all terminations are correct and secure in all outlets
checkpoint-status |  |  | checkpoint | Outlets have all been secured in place and levelled
checkpoint-status |  |  | checkpoint | All cabling has been tested using the Fluke data tester
checkpoint-status |  |  | checkpoint | Each cable has been correctly installed and terminated in the patch panel
checkpoint-status |  |  | checkpoint | Each outlet has been labelled
checkpoint-status |  |  | checkpoint | Each outlet marked on the site as built
checklist-flat |  |  | checklist | Toolbox Safety Talks Meeting Minutes |  |  |  |  | Yes | Toolbox Safety Talks Meeting Minutes | 1bd7de47-4f8f-4806-ab4f-33c89ef67b9e
checkpoint-status |  |  | checkpoint | Toolbox Safety meeting completed
text | 2a89c104-f7e9-5149-b1b3-f0b716afab44 |  | textbox | Location:
text | 418dc8ac-d145-5638-871a-fc7587bb5e0e |  | textbox | Date:
text | 358f1937-df0b-587e-8f48-8070e79972a9 |  | textbox | Client:
text | 8b0f244c-659e-5be6-8e40-18518758e711 |  | textbox | Supervisor:
text | 9c7f2b34-9642-5c10-86f0-fc6cc8aa28cc |  | textbox | Subject:
text | 9fae3c6d-f41a-57a3-bc49-cd8c33425315 |  | textbox | Duration:
text | d87e0f1f-3abf-5db1-ab36-aaab268d4663 |  | textbox | Persons present
text | 22d0c969-9512-5e57-8214-1e6d63a88dd7 |  | textbox | Comments & points raised
checkpoint-status |  |  | checkpoint | Signed off by Ergo Group Supervisor
checklist-sectioned |  |  | checklist | Electrical Installation Testing |  |  |  |  | Yes | Electrical Installation Testing | 34b1e1a9-484a-459b-89f7-81027d1dd3ec
checkpoint-group |  |  | section | Test Point/ Circuit Number
checkpoint-status |  |  | checkpoint | Main earth tested
text | 9d6c9fee-7fa3-5a60-b4ee-7a147a672a1e |  | textbox | Conductor Sizes (mm²) Actives/Earths
text | b2104591-3d44-534b-a811-a8bf4e85fbb8 |  | textbox | MCB (Rating & Type)
checkpoint-group |  |  | section | Continuity
checkpoint-status |  |  | checkpoint | Continuity tested
text | 52257cca-a18d-5dc8-b27d-df487aaa126b |  | textbox | Active Conductor (Rph)
text | dc41095d-088a-5c2b-80fb-bef183acef45 |  | textbox | Earth Conductor (Re)
checkpoint-group |  |  | section | IR
checkpoint-status |  |  | checkpoint | IR tested
text | ad330d9a-c85e-5de2-88c0-af879dfc4a8c |  | textbox | Insulation Resistance (MΩ)
checkpoint-group |  |  | section | CCC
checkpoint-status |  |  | checkpoint | Correct Circuit Connections
checkpoint-group |  |  | section | Polarity
checkpoint-status |  |  | checkpoint | Polarity tested
checkpoint-group |  |  | section | Fault Loop Impedance
checkpoint-status |  |  | checkpoint | Measured Loop Value R
checkpoint-status |  |  | checkpoint | Maximum Permitted Loop Value
checkpoint-group |  |  | section | RCD
checkpoint-status |  |  | checkpoint | RCD tested
checklist-flat |  |  | checklist | Installation of steel tray/basket |  |  |  |  | Yes | Installation of steel tray/basket | 44277964-8508-4821-aa58-193d344347ba
checkpoint-status |  |  | checkpoint | Confirm that the cable support system has been selected as per drawings and specifications
button | d09814f6-abc2-561d-af63-a7f80bcc9fd1 | DataPoint is missing 'button' values | button | Cable support system has been selected to correctly hold the required weight
button | a59656ec-becc-5c43-ab53-0cc8fe42c6d2 | DataPoint is missing 'button' values | button | Each cable support has sufficient room for future expansion
button | e4808caa-383b-5c8e-bc51-5759a7760286 | DataPoint is missing 'button' values | button | Cable support system has been correctly installed and is secure in place
button | f69c12b1-9b9d-5f69-b0ed-10a91b70e1c7 | DataPoint is missing 'button' values | button | Height of cable support system has been confirmed and installed to that height in all areas
button | 4c32af73-4183-5464-ac99-47652577780c | DataPoint is missing 'button' values | button | Cable support system is as per shop drawings and not impacting any other services
checkpoint-status |  |  | checkpoint | All threaded rods have been cut off to correct size
checkpoint-status |  |  | checkpoint | All nuts/bolts/channel nuts have been tightened
checkpoint-status |  |  | checkpoint | Any changes to drawings have been noted on the site as built drawings
checkpoint-status |  |  | checkpoint | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
checklist-flat |  |  | checklist | Temporary DB Monthly Testing |  |  |  |  | Yes | Temporary DB Monthly Testing | 59ab9ae4-7d08-4acd-9fef-bc6efa8d5155
checkpoint-status |  |  | checkpoint | Operating time of RCD’s (note trip times in comments)
checkpoint-status |  |  | checkpoint | RCD Push button Operation
checkpoint-status |  |  | checkpoint | General condition of DB (must include a photo)
checkpoint-status |  |  | checkpoint | Photo of completed tag on DB
checklist-flat |  |  | checklist | Cable Support System |  |  |  |  | Yes | Cable Support System | 747da5ea-bba5-44fe-af30-72d44378ce4b
checkpoint-status |  |  | checkpoint | Confirm that the cable support system has been selected as per drawings and specifications
checkpoint-status |  |  | checkpoint | Cable support system has been selected to correctly hold the required weight
checkpoint-status |  |  | checkpoint | Each cable support has sufficient room for future expansion
checkpoint-status |  |  | checkpoint | Cable support system has been correctly installed and is secure in place
checkpoint-status |  |  | checkpoint | Height of cable support system has been confirmed and installed to that height in all areas
checkpoint-status |  |  | checkpoint | Cable support system is as per shop drawings and not impacting any other services
checkpoint-status |  |  | checkpoint | All threaded rods have been cut off to correct size
checkpoint-status |  |  | checkpoint | All nuts/bolts/channel nuts have been tightened
checkpoint-status |  |  | checkpoint | Any changes to drawings have been noted on the site as built drawings
checklist-sectioned |  |  | checklist | Lighting cabling and outlets |  |  |  |  | Yes | Lighting cabling and outlets | 7b708e4d-2fc5-4bb2-8995-b133d0816127
checkpoint-group |  |  | section | Rough In
checkpoint-status |  |  | checkpoint | Confirm that the cable support system has been completed as per documentation
checkpoint-status |  |  | checkpoint | Electrical cables have been appropriately sized and selected to ensure that they will support currently installed and future equipment
checkpoint-status |  |  | checkpoint | Mechanical protection has been provided to minimise the likelihood of physical damage to cabling
checkpoint-status |  |  | checkpoint | Cabling has been concealed where possible in ceiling spaces, wall cavities or risers
checkpoint-status |  |  | checkpoint | All lights have been wired as per drawings
checkpoint-status |  |  | checkpoint | All lights and switches have been marked on the site as built drawing
checkpoint-status |  |  | checkpoint | Height and location have been confirmed for each switch
checkpoint-status |  |  | checkpoint | Lighting control system has been confirmed (DALI/240v)
checkpoint-status |  |  | checkpoint | Ceiling supports have been installed where required (ceiling fans/pendants)
checkpoint-group |  |  | section | Fit Off & Commission
checkpoint-status |  |  | checkpoint | Equipment/materials have been selected and installed as per drawings/specifications
checkpoint-status |  |  | checkpoint | Terminations have been checked and all terminations are correct and secure in all outlets
checkpoint-status |  |  | checkpoint | Switches have all been secured in place and levelled
checkpoint-status |  |  | checkpoint | All lights are sitting flush and/or been levelled
checkpoint-status |  |  | checkpoint | All cabling has been tested for insulations resistance and continuity
checkpoint-status |  |  | checkpoint | Each circuit is terminated at the DB and protected by the correct protective device
checkpoint-status |  |  | checkpoint | Each switch has been labelled
checkpoint-status |  |  | checkpoint | Functional test carried out on each switch and light
checkpoint-status |  |  | checkpoint | Each circuit has been marked on the site as built
checklist-flat |  |  | checklist | Contractor |  |  |  |  | Yes | Contractor | 881a87e4-6a93-4bbc-b46d-6b2d2023e9a5
checkpoint-status |  |  | checkpoint | Has contractors ITP been received - Please take a photo / upload checklist
checklist-sectioned |  |  | checklist | Main Switchboard & Termination of Cables ITP002 |  |  |  |  | Yes | Main Switchboard & Termination of Cables ITP002 | 8f60d9d1-68b1-483f-ba1b-642d389b37be
checkpoint-group |  |  | section | Preparation
checkpoint-status |  |  | checkpoint | Locate & fix switchboard into position - check for clearances fix correctly
checkpoint-status |  |  | checkpoint | Determine cable sizes for cable glands & mark out gland plate (check cable O.D's for cable size glands)
button | e7ca2fbf-317b-5a75-b294-6f3c1b25ce25 | DataPoint is missing 'button' values | button | Install cable glands & cables
button | 7d963947-46e3-5815-a41b-e58390cd8960 | DataPoint is missing 'button' values | button | Install lugs & terminate
checkpoint-status |  |  | checkpoint | Clean & vacuum out board - please take a photo
checkpoint-status |  |  | checkpoint | Check all circuits are terminated & safe at the other end or disconnect
checkpoint-status |  |  | checkpoint | Final visual inspection of board - please take a photo
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Test earth continuity & resistance
button | ec352df0-953f-5905-8f1f-9d506e8749d0 | DataPoint is missing 'button' values | button | Test insulation resistance
button | 849a3f28-3c87-5ae5-a216-1ba2c87d936c | DataPoint is missing 'button' values | button | Test polarity
button | 63a81a9c-fc10-5685-bd77-d1cf22cef3ba | DataPoint is missing 'button' values | button | Test phase rotation
checkpoint-status |  |  | checkpoint | Attach prescribed certificate of electrical safety. Organise inspection by inspector (Add photo or attached certification
checkpoint-status |  |  | checkpoint | Isolate / lock off/ dange tag all outgoing circuits - please take a photo
button | eb2ebf74-0c98-5945-8710-12ebe80a4851 | DataPoint is missing 'button' values | button | Ensure labelling is complete & accurate
checkpoint-status |  |  | checkpoint | Energise system
button | dda91080-f391-5f79-be45-68a3abe684f9 | DataPoint is missing 'button' values | button | Check phase rotation
button | 11c902b1-3047-527d-ab2e-1d49dac3c1f2 | DataPoint is missing 'button' values | button | Check switchboard as installed as per drawings
text | b5405aa3-9837-584f-bf7c-392bcd98c9a3 |  | textbox | Drawing & revision number(s)
checkpoint-status |  |  | checkpoint | Ensure any modifications to shop drawings are matched to existing & returned to office / attach drawings
checkpoint-status |  |  | checkpoint | Ensure switch room is left clean - please take a photo
checkpoint-status |  |  | checkpoint | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
checklist-flat |  |  | checklist | Temp Board Install Checklist |  |  |  |  | Yes | Temp Board Install Checklist | 9a65d0fe-0b70-4c4a-8d74-327a4d317c10
checkpoint-status |  |  | checkpoint | Are all final circuits protected by an RCD
checkpoint-status |  |  | checkpoint | Are all DB doors lockable
checkpoint-status |  |  | checkpoint | Are all DB’s securely fixed in position
checkpoint-status |  |  | checkpoint | Are all switchboards labelled correctly
checkpoint-status |  |  | checkpoint | Are all final circuits labelled at board
checkpoint-status |  |  | checkpoint | Are all live parts at DB inaccessible
checkpoint-status |  |  | checkpoint | Are socket outlets in DB in good working order
checkpoint-status |  |  | checkpoint | Are empty glands and holes covered over
checkpoint-status |  |  | checkpoint | Is switchboard door lockable, fitted with a retaining bar, and unable to be removed without the use of a tool
checkpoint-status |  |  | checkpoint | Is emergency lighting provided adjacent to switchboard
checkpoint-status |  |  | checkpoint | CCEW form been completed? (Take photo of each page)
checklist-flat |  |  | checklist | Emergency Lighting Testing Evidence |  |  |  |  | Yes | Emergency Lighting Testing Evidence Checklist | aae9d413-2944-4600-8850-d4813a364b85
checkpoint-status |  |  | checkpoint | Pass once image is uploaded
checklist-flat |  |  | checklist | Test and Tag Register |  |  |  |  | Yes | Test and Tag Register | b16cd7e1-5119-4e1e-a5d6-8562afb5a62c
checkpoint-status |  |  | checkpoint | Test and Tag register completed (upload picture of each page)
checklist-flat |  |  | checklist | Mains, Sub Mains Cable in Conduits or on Trays ITP004 |  |  |  |  | Yes | Mains, Sub Mains Cable in Conduits or on Trays ITP004 | c2841402-2bca-40c3-a83f-8211fb409be7
checkpoint-status |  |  | checkpoint | Measure cable runs with appropriate accurate measuring instrument (eg tape measure, wheel)
checkpoint-status |  |  | checkpoint | Check cable sizes resistance of protective earth conductor - shall be low enough to permit passage of current necessary to operate protective device
checkpoint-status |  |  | checkpoint | Confirm length of cable if sub contract item & order
text | 47da33a3-732f-58dd-a02e-46534f217408 |  | textbox | Record length of cable
checkpoint-status |  |  | checkpoint | Install cable in appliance method (EG. Cable stands, electric winch, pulleys etc.) - ANY CABLE NOT TERMINATED IMMEDIATELY MUST HAVE THE ENDS TAPED COVERING THE BARE COPPER - please take a photo
checkpoint-status |  |  | checkpoint | Trefoil cables & tie cables to support system (ensure spacing)
button | 2d2cf6ac-a0fb-5ce3-bfad-c95efe2520ac | DataPoint is missing 'button' values | button | Check requirements for cable identification & install
checkpoint-status |  |  | checkpoint | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
checklist-sectioned |  |  | checklist | Power cabling and outlets |  |  |  |  | Yes | Power cabling and outlets | c6d75ba0-d81b-4062-9ebf-0c82473d54dd
checkpoint-group |  |  | section | Rough In
checkpoint-status |  |  | checkpoint | Confirm that the cable support system has been completed as per documentation
checkpoint-status |  |  | checkpoint | Electrical cables have been appropriately sized and selected to ensure that they will support currently installed and future equipment
checkpoint-status |  |  | checkpoint | Mechanical protection has been provided to minimise the likelihood of physical damage to cabling
checkpoint-status |  |  | checkpoint | Cabling has been concealed where possible in ceiling spaces, wall cavities or risers
checkpoint-status |  |  | checkpoint | All outlets have been wired as per drawings
checkpoint-status |  |  | checkpoint | All outlets have been marked on the site as built drawing
checkpoint-status |  |  | checkpoint | Height and location have been confirmed for each outlet
checkpoint-group |  |  | section | Fit Off & Commission
checkpoint-status |  |  | checkpoint | Equipment/materials have been selected and installed as per drawings/specifications
checkpoint-status |  |  | checkpoint | Terminations have been checked and all terminations are correct and secure in all outlets
checkpoint-status |  |  | checkpoint | Outlets have all been secured in place and levelled
checkpoint-status |  |  | checkpoint | All cabling has been tested for insulations resistance and continuity
checkpoint-status |  |  | checkpoint | Each circuit is terminated at the DB and protected by the correct protective device
checkpoint-status |  |  | checkpoint | Each outlet has been labelled
checkpoint-status |  |  | checkpoint | Functional test carried out on each outlet
checkpoint-status |  |  | checkpoint | Each outlet marked on the site as built
checklist-sectioned |  |  | checklist | Underground Conduits ITP001 |  |  |  |  | Yes | Underground Conduits ITP001 | d7ac1072-05e1-4c3b-a26e-c63f9f08b22d
checkpoint-group |  |  | section | Preparation
checkpoint-status |  |  | checkpoint | Check clear of other services (The Clearance for gas pipes is 300mm & other services 100mm)
checkpoint-status |  |  | checkpoint | Check cable size to verify conduit size & determine size of trench
checkpoint-status |  |  | checkpoint | Organise barricades, webbing, plates, warning lights (if applicable prior to excavation) - please take a photo
checkpoint-status |  |  | checkpoint | Determine spoil removal, backfill material, compaction, cable marking protection & installment requirements
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Confirm area of work is accessible & acceptable to commence (If not comment below)
checkpoint-status |  |  | checkpoint | Setout & alignment as per drawing (include revision below)
text | 3c136668-9f6b-5f3d-9f53-dd2994589ae6 |  | textbox | Drawing & revision number(s)
checkpoint-status |  |  | checkpoint | Mark out trench route - Arrange saw cutting if required
checkpoint-status |  |  | checkpoint | Excavate trench & install barricades as required - please take a photo
checkpoint-status |  |  | checkpoint | Determine which way cable will be installed & lay coupling in no friction direction, install conduit glue.
button | 9ff6684c-639c-503b-9a93-21490c0e51d9 | DataPoint is missing 'button' values | button | Install draw wire if required
checkpoint-status |  |  | checkpoint | Inspect trench by supply authority if applicable
button | 776a1162-e402-5f4a-84b5-171c293cdbdf | DataPoint is missing 'button' values | button | Inspect & backfill trench
button | ec179fe9-98cc-555c-9573-795fc52bd3f4 | DataPoint is missing 'button' values | button | Reinstate & clean area
checkpoint-status |  |  | checkpoint | Install direction marker if applicable
checkpoint-status |  |  | checkpoint | Mark up DGR for future as builts
checkpoint-status |  |  | checkpoint | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
checklist-flat |  |  | checklist | Install Distribution Boards -Terminate Cables ITP006 |  |  |  |  | Yes | Install Distribution Boards -Terminate Cables ITP006 | fa171847-b784-4935-9c16-73394359c554
checkpoint-status |  |  | checkpoint | Setout & alignment as per drawing (include revision below)
text | 62938eee-e776-5138-b9f4-6f659b9e4c7e |  | textbox | Drawing & revision number(s)
checkpoint-status |  |  | checkpoint | Check delivery of distribution board - Check for damage (paint finish, dimensions & door against drawing) - Please take a photo
checkpoint-status |  |  | checkpoint | Locate & fix into position
checkpoint-status |  |  | checkpoint | Install sub mains cabling as appropriate (glands, tray & duct)
checkpoint-status |  |  | checkpoint | Install lugs & terminate
checkpoint-status |  |  | checkpoint | Install sub circuit & terminate (if circuit not complete at the other end, it must not be terminated)
checkpoint-status |  |  | checkpoint | Clean & vacuum area - please take a photo
text | dda2648f-8494-54d4-905f-df3ab48ec56a |  | textbox | Record results
checkpoint-status |  |  | checkpoint | Clearly identify services
checkpoint-status |  |  | checkpoint | Energise system
checkpoint-status |  |  | checkpoint | Check phase rotation
checkpoint-status |  |  | checkpoint | Check switchboard as installed as per drawings
checkpoint-status |  |  | checkpoint | Check typed schedule for accuracy & install
checkpoint-status |  |  | checkpoint | Ensure switchboard cupboard & area is left clean - Please take a photo
checkpoint-status |  |  | checkpoint | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)