## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Cable Support System |  |  |  |  | Yes | Cable Support System | 10af0ecc-c489-430d-bbf4-b6f0c70dbbb6
checkpoint-status |  |  | checkpoint | Confirm that the cable support system has been selected as per drawings and specifications
checkpoint-status |  |  | checkpoint | Cable support system has been selected to correctly hold the required weight
checkpoint-status |  |  | checkpoint | Each cable support has sufficient room for future expansion
checkpoint-status |  |  | checkpoint | Cable support system has been correctly installed and is secure in place
checkpoint-status |  |  | checkpoint | Height of cable support system has been confirmed and installed to that height in all areas
checkpoint-status |  |  | checkpoint | Cable support system is as per shop drawings and not impacting any other services
checkpoint-status |  |  | checkpoint | All threaded rods have been cut off to correct size
checkpoint-status |  |  | checkpoint | All nuts/bolts/channel nuts have been tightened
checkpoint-status |  |  | checkpoint | Any changes to drawings have been noted on the site as built drawings
checklist-flat |  |  | checklist | Temp Board Install Checklist |  |  |  |  | Yes | Temp Board Install Checklist | 13dec25a-773d-4c5a-948c-f1115169cae1
checkpoint-status |  |  | checkpoint | Are all final circuits protected by an RCD
checkpoint-status |  |  | checkpoint | Are all DB doors lockable
checkpoint-status |  |  | checkpoint | Are all DB’s securely fixed in position
checkpoint-status |  |  | checkpoint | Are all switchboards labelled correctly
checkpoint-status |  |  | checkpoint | Are all final circuits labelled at board
checkpoint-status |  |  | checkpoint | Are all live parts at DB inaccessible
checkpoint-status |  |  | checkpoint | Are socket outlets in DB in good working order
checkpoint-status |  |  | checkpoint | Are empty glands and holes covered over
checkpoint-status |  |  | checkpoint | Is switchboard door lockable, fitted with a retaining bar, and unable to be removed without the use of a tool
checkpoint-status |  |  | checkpoint | Is emergency lighting provided adjacent to switchboard
checkpoint-status |  |  | checkpoint | CCEW form been completed? (Take photo of each page)
checklist-flat |  |  | checklist | Test and Tag Register |  |  |  |  | Yes | Test and Tag Register | 3907c67d-7b53-421d-bf0a-a4efaa38670d
checkpoint-status |  |  | checkpoint | Test and Tag register completed (upload picture of each page)
checklist-sectioned |  |  | checklist | Electrical Installation Testing |  |  |  |  | Yes | Electrical Installation Testing | 52939610-50f1-4c05-bd52-e244bb367d79
checkpoint-group |  |  | section | Test Point/ Circuit Number
checkpoint-status |  |  | checkpoint | Main earth tested
text | 9d6c9fee-7fa3-5a60-b4ee-7a147a672a1e |  | textbox | Conductor Sizes (mm²) Actives/Earths
text | b2104591-3d44-534b-a811-a8bf4e85fbb8 |  | textbox | MCB (Rating & Type)
checkpoint-group |  |  | section | Continuity
checkpoint-status |  |  | checkpoint | Continuity tested
text | 52257cca-a18d-5dc8-b27d-df487aaa126b |  | textbox | Active Conductor (Rph)
text | dc41095d-088a-5c2b-80fb-bef183acef45 |  | textbox | Earth Conductor (Re)
checkpoint-group |  |  | section | IR
checkpoint-status |  |  | checkpoint | IR tested
text | ad330d9a-c85e-5de2-88c0-af879dfc4a8c |  | textbox | Insulation Resistance (MΩ)
checkpoint-group |  |  | section | CCC
checkpoint-status |  |  | checkpoint | Correct Circuit Connections
checkpoint-group |  |  | section | Polarity
checkpoint-status |  |  | checkpoint | Polarity tested
checkpoint-group |  |  | section | Fault Loop Impedance
checkpoint-status |  |  | checkpoint | Measured Loop Value R
checkpoint-status |  |  | checkpoint | Maximum Permitted Loop Value
checkpoint-group |  |  | section | RCD
checkpoint-status |  |  | checkpoint | RCD tested
checklist-sectioned |  |  | checklist | Lighting cabling and outlets |  |  |  |  | Yes | Lighting cabling and outlets | 5f2d3d1f-a671-4887-b8fa-f057bcbf77d2
checkpoint-group |  |  | section | Rough In
checkpoint-status |  |  | checkpoint | Confirm that the cable support system has been completed as per documentation
checkpoint-status |  |  | checkpoint | Electrical cables have been appropriately sized and selected to ensure that they will support currently installed and future equipment
checkpoint-status |  |  | checkpoint | Mechanical protection has been provided to minimise the likelihood of physical damage to cabling
checkpoint-status |  |  | checkpoint | Cabling has been concealed where possible in ceiling spaces, wall cavities or risers
checkpoint-status |  |  | checkpoint | All lights have been wired as per drawings
checkpoint-status |  |  | checkpoint | All lights and switches have been marked on the site as built drawing
checkpoint-status |  |  | checkpoint | Height and location have been confirmed for each switch
checkpoint-status |  |  | checkpoint | Lighting control system has been confirmed (DALI/240v)
checkpoint-status |  |  | checkpoint | Ceiling supports have been installed where required (ceiling fans/pendants)
checkpoint-group |  |  | section | Fit Off & Commission
checkpoint-status |  |  | checkpoint | Equipment/materials have been selected and installed as per drawings/specifications
checkpoint-status |  |  | checkpoint | Terminations have been checked and all terminations are correct and secure in all outlets
checkpoint-status |  |  | checkpoint | Switches have all been secured in place and levelled
checkpoint-status |  |  | checkpoint | All lights are sitting flush and/or been levelled
checkpoint-status |  |  | checkpoint | All cabling has been tested for insulations resistance and continuity
checkpoint-status |  |  | checkpoint | Each circuit is terminated at the DB and protected by the correct protective device
checkpoint-status |  |  | checkpoint | Each switch has been labelled
checkpoint-status |  |  | checkpoint | Functional test carried out on each switch and light
checkpoint-status |  |  | checkpoint | Each circuit has been marked on the site as built
checklist-flat |  |  | checklist | Emergency Lighting Testing Evidence |  |  |  |  | Yes | Emergency Lighting Testing Evidence Checklist | 7cd6303c-1e54-4c87-83dd-30b8c65f60a3
checkpoint-status |  |  | checkpoint | Pass once image is uploaded
checklist-sectioned |  |  | checklist | Power cabling and outlets |  |  |  |  | Yes | Power cabling and outlets | a7eaebea-17df-43df-9f94-ef515f9b4af6
checkpoint-group |  |  | section | Rough In
checkpoint-status |  |  | checkpoint | Confirm that the cable support system has been completed as per documentation
checkpoint-status |  |  | checkpoint | Electrical cables have been appropriately sized and selected to ensure that they will support currently installed and future equipment
checkpoint-status |  |  | checkpoint | Mechanical protection has been provided to minimise the likelihood of physical damage to cabling
checkpoint-status |  |  | checkpoint | Cabling has been concealed where possible in ceiling spaces, wall cavities or risers
checkpoint-status |  |  | checkpoint | All outlets have been wired as per drawings
checkpoint-status |  |  | checkpoint | All outlets have been marked on the site as built drawing
checkpoint-status |  |  | checkpoint | Height and location have been confirmed for each outlet
checkpoint-group |  |  | section | Fit Off & Commission
checkpoint-status |  |  | checkpoint | Equipment/materials have been selected and installed as per drawings/specifications
checkpoint-status |  |  | checkpoint | Terminations have been checked and all terminations are correct and secure in all outlets
checkpoint-status |  |  | checkpoint | Outlets have all been secured in place and levelled
checkpoint-status |  |  | checkpoint | All cabling has been tested for insulations resistance and continuity
checkpoint-status |  |  | checkpoint | Each circuit is terminated at the DB and protected by the correct protective device
checkpoint-status |  |  | checkpoint | Each outlet has been labelled
checkpoint-status |  |  | checkpoint | Functional test carried out on each outlet
checkpoint-status |  |  | checkpoint | Each outlet marked on the site as built
checklist-flat |  |  | checklist | Toolbox Safety Talks Meeting Minutes |  |  |  |  | Yes | Toolbox Safety Talks Meeting Minutes | b26edbe3-b953-476f-bd63-ac14fd528651
checkpoint-status |  |  | checkpoint | Toolbox Safety meeting completed
text | 2a89c104-f7e9-5149-b1b3-f0b716afab44 |  | textbox | Location:
text | 418dc8ac-d145-5638-871a-fc7587bb5e0e |  | textbox | Date:
text | 358f1937-df0b-587e-8f48-8070e79972a9 |  | textbox | Client:
text | 8b0f244c-659e-5be6-8e40-18518758e711 |  | textbox | Supervisor:
text | 9c7f2b34-9642-5c10-86f0-fc6cc8aa28cc |  | textbox | Subject:
text | 9fae3c6d-f41a-57a3-bc49-cd8c33425315 |  | textbox | Duration:
text | d87e0f1f-3abf-5db1-ab36-aaab268d4663 |  | textbox | Persons present
text | 22d0c969-9512-5e57-8214-1e6d63a88dd7 |  | textbox | Comments & points raised
checkpoint-status |  |  | checkpoint | Signed off by Ergo Group Supervisor
checklist-flat |  |  | checklist | Temporary DB Monthly Testing |  |  |  |  | Yes | Temporary DB Monthly Testing | cee8fb5a-fdd0-4a1b-8c1f-e8b50284ec89
checkpoint-status |  |  | checkpoint | Operating time of RCD’s (note trip times in comments)
checkpoint-status |  |  | checkpoint | RCD Push button Operation
checkpoint-status |  |  | checkpoint | General condition of DB (must include a photo)
checkpoint-status |  |  | checkpoint | Photo of completed tag on DB
checklist-sectioned |  |  | checklist | Data cabling and outlets |  |  |  |  | Yes | Data cabling and outlets | dff3f9a3-b25d-4faf-ab69-f0711ce10c5c
checkpoint-group |  |  | section | Rough In
checkpoint-status |  |  | checkpoint | Confirm that the cable support system has been completed as per documentation
checkpoint-status |  |  | checkpoint | Data cabling has been selected as per drawings and specifications (Cat6/CatA & brand)
checkpoint-status |  |  | checkpoint | Mechanical protection has been provided to minimise the likelihood of physical damage to cabling
checkpoint-status |  |  | checkpoint | Cabling has been concealed where possible in ceiling spaces, wall cavities or risers
checkpoint-status |  |  | checkpoint | All outlets have been wired as per drawings
checkpoint-status |  |  | checkpoint | All data outlets have been numbered and marked on the site as built drawing
checkpoint-status |  |  | checkpoint | Height and location have been confirmed for each outlet
checkpoint-group |  |  | section | Fit Off & Commission
checkpoint-status |  |  | checkpoint | Equipment/materials have been selected and installed as per drawings/specifications
checkpoint-status |  |  | checkpoint | Terminations have been checked and all terminations are correct and secure in all outlets
checkpoint-status |  |  | checkpoint | Outlets have all been secured in place and levelled
checkpoint-status |  |  | checkpoint | All cabling has been tested using the Fluke data tester
checkpoint-status |  |  | checkpoint | Each cable has been correctly installed and terminated in the patch panel
checkpoint-status |  |  | checkpoint | Each outlet has been labelled
checkpoint-status |  |  | checkpoint | Each outlet marked on the site as built
checklist-flat |  |  | checklist | Install Distribution Boards -Terminate Cables ITP006 |  |  |  |  | Yes | Install Distribution Boards -Terminate Cables ITP006 | ebb8b4d2-cb26-429d-a853-185b1f2e5643
checkpoint-status |  |  | checkpoint | Setout & alignment as per drawing (include revision below)
text | 62938eee-e776-5138-b9f4-6f659b9e4c7e |  | textbox | Drawing & revision number(s)
checkpoint-status |  |  | checkpoint | Check delivery of distribution board - Check for damage (paint finish, dimensions & door against drawing) - Please take a photo
checkpoint-status |  |  | checkpoint | Locate & fix into position
checkpoint-status |  |  | checkpoint | Install sub mains cabling as appropriate (glands, tray & duct)
checkpoint-status |  |  | checkpoint | Install lugs & terminate
checkpoint-status |  |  | checkpoint | Install sub circuit & terminate (if circuit not complete at the other end, it must not be terminated)
checkpoint-status |  |  | checkpoint | Clean & vacuum area - please take a photo
text | dda2648f-8494-54d4-905f-df3ab48ec56a |  | textbox | Record results
checkpoint-status |  |  | checkpoint | Clearly identify services
checkpoint-status |  |  | checkpoint | Energise system
checkpoint-status |  |  | checkpoint | Check phase rotation
checkpoint-status |  |  | checkpoint | Check switchboard as installed as per drawings
checkpoint-status |  |  | checkpoint | Check typed schedule for accuracy & install
checkpoint-status |  |  | checkpoint | Ensure switchboard cupboard & area is left clean - Please take a photo
checkpoint-status |  |  | checkpoint | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)