## Sheet1
conqa | Site fitout QA
|  | zone 2 | Walls | Areas
ITP 2GA
|  |  |  | ITP2GB | Samples |  | refer LL sample register
|  |  |  | ITP 2GC | Materials |  | Meet specifications of Internal material schedule -is checked at delivery and stored in a safe manner
ITP 2GD
|  |  |  | ITP 21A | Set out |  | As per partition drawings including marked expansion joints and required fire/accoustic details
ITP 21B
|  |  |  | ITP 21C | Framing
|  |  |  | ITP 22A |  | High level walls | Floor and ceiling tracks installed with siesmic considerations-as per Rondo design specification- fixings @ 600mm centres-noggin track- penetration requirements for Fire rated / accoustic systems as set out and marked by service trades
|  | zone 3 | Walls | ITP 3GA
|  |  |  | ITP 3GB |  | Walls/Doors | Floor and ceiling tracks installed with siesmic considerations-as per Rondo design specification- fixings @ 600mm centres-noggin track- penetration requirements for Fire rated / accoustic systems as set out and marked by service trades- Doors installed as per detail-plumb and correct
ITP 3GC
ITP 31A
ITP 31B
ITP 31C
[5 empty] | Inspection |  | HOLD POINT - Expoconti inspection non-conformances noted and rectified-Supplier inspection report if applicable
[5 empty] | Noggins |  | installed as per service trade set out and marked studs- trades to confirm location and requirements
Fire rated wall noggins as per detail
[5 empty] | Pre Sheet sign off |  | HOLD POINT-Signed as per LL system
[5 empty] | Insulation |  | As per wall type/acoustic /thermal requirements -tight with no gaps
[5 empty] | Linings |  | As per wall type /acoustic and fire reports- installed flush, square and plumb- fixings at manufacturers specification- detailed finishes completed as specified
[5 empty] | Specialised linings |  | As per wall type requirements - installed as per manufactures recommendations
[5 empty] | Stopping /Sanding |  | As per manufacturers specifications
[5 empty] | Penetrations / caulking |  | As per required specifications- Fire / acoustic /pressure considerations
Ensure sheets have 10-15mm gap between substrate
[5 empty] | Speed panel |  | installed as per manufacturers recommendations
[5 empty] | Defect |  | Inspect - identify - rectify defects prior to finish paint coat
[5 empty] | Final Inspection |  | This is to confirm that an Expoconti representative has carried out all necessary inspections and verifies that the work has been completed and conforms to the contract specifications
conqa | Site fitout QA |  |  | areas
|  | zone 2 | Ceilings | ITP 2GA | Samples |  | refer LL sample register
|  |  |  | ITP2GB | Materials |  | Meet specifications of Internal material schedule -is checked at delivery and stored in a safe manner
ITP 2GC
|  |  |  | ITP 2GD | Set out |  | As per RCP drawing including marked expansion joints and required fire/accoustic details
ITP 21A
|  |  |  | ITP 21B | Framing
|  |  |  | ITP 21C |  | Concealed system | Installed with siesmic considerations-as per Rondo design specification- wall fixings-spacings as per design: Allowances for duct-access panels- lighting
ITP 22A
[6 empty] | Exposed grid | Installed with siesmic considerations-as per Rondo design specification- wall trims-spacings as per design: Allowances for duct-access panels- lighting :
|  | zone 3 | Ceilings | ITP 3GA
ITP 3GB
|  |  |  | ITP 3GC | Inspection |  | HOLD POINT - Expoconti inspection non-conformances noted and rectified-Supplier inspection report if applicable
ITP 31A
|  |  |  | ITP 31B | Noggins |  | Installed as per service trade set out and markings- trades to confirm location and requirements
ITP 31C
[5 empty] | Pre Sheet sign off |  | HOLD POINT -Signed as per LL system
[5 empty] | Insulation |  | As per wall type/acoustic /thermal requirements -tight with no gaps
[5 empty] | Linings |  | As per ceiling type /acoustic and fire reports- installed flush, square and level- fixings at manufacturers specification- detailed finishes completed as specified
[5 empty] | Specialised linings |  | As per ceiling type- installed as per manufactures recommendations
[5 empty] | Stopping /Sanding |  | As per manufacturers specifications- three coat system- square set corners: sanded flat /smooth
Acess panels- air grills-lighting as marked by service trades
[5 empty] | Penetrations |  | As per required specifications- Fire / acoustic /pressure considerations
Ensure sheets have 10-15mm gap between substrate
[5 empty] | Service tiles |  | Installed as per RCP/combined services drawings
[5 empty] | Defect |  | Inspect - identify - rectify defects prior to finish paint coat
[5 empty] | Bulk Tiling |  | Installed as per requirements.
[5 empty] | Final Inspection |  | This is to confirm that an Expoconti representative has carried out all necessary inspections and verifies that the work has been completed and conforms to the contract specifications