## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Speedpanel |  |  |  |  | Yes | Speedpanel Checklist | 161ae259-ec89-4846-b055-9737b4c3ac0c
checkpoint-status |  |  | checkpoint | Set out - As per current drawing revision
checkpoint-status |  |  | checkpoint | Install speed panel - Ensure C-Track is fixed at every 500mm centres. Ensure ripped panel is a minimum of 100mm wide. Ensure Panels are screwed directly into panel joints at 1000mm vertical centres and 250mm horizontal centres
checkpoint-status |  |  | checkpoint | Caulking - Fire rated - Ensure all gaps and joins are fully sealed
checkpoint-status |  |  | checkpoint | Pressure rised shafts caulking - Ensure all gaps and joins are fully sealed
checkpoint-status |  |  | checkpoint | Expo Sign Off/Hold Point
checklist-flat |  |  | checklist | Enter Level/Apartment/Description |  |  |  |  | Yes | Record Hold-Up | b33435c6-16a4-4dd2-8bb1-01d95d2d364c
checkpoint-status |  |  | checkpoint | Decription of Hold Up
label | 5e0751f9-320c-4de6-84d9-cea2d37df381 |  | note | (See Photos & Comments Attached Below)
checklist-flat |  |  | checklist | Site Inspection Report |  |  |  |  | Yes | NF1209 Site Inspection Report | ba0d4f4c-c906-4621-976f-67a8c06cc318
checkpoint-no-status |  |  | checkpoint | Site Inspection Report:
text | e1bfbf8b-d2f5-4952-9984-b963bf5dd36d |  | textbox | Project Name
text | 91a3c2d2-9258-42be-b44e-fbf661fe9aa3 |  | textbox | Address
text | 2366c202-5391-406d-9044-42c445d0be7b |  | textbox | Reference/Project No.
text | 8b165331-484f-4f0c-856a-25a211887936 |  | textbox | Date of Inspection:
text | 4a3fd7d5-c019-4b95-a8e2-68c885282670 |  | textbox | Start Time:
text | 8c75df6d-2062-4688-95a5-54acb1a5e738 |  | textbox | End Time:
text | a785e45a-399f-4666-aab2-61936ee1ca1e |  | textbox | Rondo Representative
text | 554a626e-913a-4002-8c9a-7c4edfd44c30 |  | textbox | Company Site Foreman: Contact
text | f5d8baca-7eae-49de-b4e2-1cda8159b53f |  | textbox | Construction Status
button | 697fe55c-8a8c-4288-8b23-1dbf514f5f41 |  | button | System Inspected | DUO, External, Other , Stud Framing: Internal,Keylock
button | 38b9272e-9e92-4a0b-99b9-8afa6f7e2230 |  | button | Inspection Requirements: | Fortnightly, Monthly,Weekly
checkpoint-no-status |  |  | checkpoint | Site Safety
button | 82e14e2a-cfd0-4cbf-911d-868e62802a6f |  | button | Inducted to site | No,Yes
text | 8f4b5580-5e68-4243-ba37-c56a68622414 |  | textbox | Date:
button | c1ed08bf-c482-4b27-9d85-2e96fdaf43f7 |  | button | Rondo supplied the required PPE for the visit | No,Yes
button | 0ac0e7cc-1191-4ba6-ab17-b56897d6e9e6 |  | button | Replacement PPE required | No,Yes
text | 2db02555-bdc2-4e0a-9015-ce0e6a07bc50 |  | textbox | Items:
button | 50e68217-3254-4353-8f61-83eb04b9ffd5 |  | button | Hazards or Near/Miss witnessed while on site | No,Yes
button | e4fa70fe-1c6e-450a-87cd-57d2a3510199 |  | button | a) Incident reported to Site Mgt | No,Yes
button | 0181e0ab-332a-41fd-a834-559ccabb84ec |  | button | b) Rondo Hazard report raised | No,Yes
text | efa00653-0191-4ecd-9840-daa6489b48dc |  | textbox | Report No.
text | 3a9c5f27-012e-45c3-865a-d71c9566a310 |  | textbox | General Notes:
checkpoint-status |  |  | checkpoint | 1
text | 39cf6a57-cd44-4e38-a09c-3b7f19613601 |  | textbox | Area/Zone
text | ed5a7b68-94e7-40d0-9438-c821f73e4166 |  | textbox | Construction Type
button | c9cc5a36-6b09-49c8-b527-8b0a603c5c14 |  | button | Installed as per Rondo’s installation guide | No,Yes
button | b0280e7f-c4d4-4ad4-9a46-655acd64e4ea |  | button | Rectification required | No,Yes
text | 46b4ae61-258a-4ec1-b735-3998c1c7a90a |  | textbox | Action
checkpoint-status |  |  | checkpoint | 2
text | 7752b1a1-860a-4d99-8a42-f383fe207bb6 |  | textbox | Area/Zone
text | ac9b8752-69a3-4f42-aa21-74f113274d36 |  | textbox | Construction Type
button | db381810-13e1-4cee-bb83-a1da56f3b3a9 |  | button | Installed as per Rondo’s installation guide | No,Yes
button | ce29f70d-001d-42bb-8dcc-9da8ae250017 |  | button | Rectification required | No,Yes
text | d1648c29-0a16-4a7d-9193-98d3a9eb007b |  | textbox | Action
checkpoint-status |  |  | checkpoint | 3
text | 7cc7c629-ce17-4f25-84ea-b31184a560b0 |  | textbox | Area/Zone
text | edbbe215-2404-4639-a97d-9a1bcc96112d |  | textbox | Construction Type
button | 5ffcda41-00a6-4d7e-86f6-4d64d8c25dfa |  | button | Installed as per Rondo’s installation guide | No,Yes
button | 649ef762-bd1e-45e2-8dfd-a1fde5c7ab40 |  | button | Rectification required | No,Yes
text | ee63c6d8-2f41-4c2d-a420-22e1c20ba569 |  | textbox | Action
checkpoint-status |  |  | checkpoint | 4
text | d926222c-6d42-43a0-9308-2edb418a19b8 |  | textbox | Area/Zone
text | f3330ea5-a23b-4a46-82e2-1944b09c90cc |  | textbox | Construction Type
button | 11dbdbb7-e173-42b9-81ae-ee8707e3c483 |  | button | Installed as per Rondo’s installation guide | No,Yes
button | 66a9be8f-351c-4b2a-a749-ce9b59ec6fd3 |  | button | Rectification required | No,Yes
text | b2f79d4f-b0ae-4e67-b412-f89ae08247e5 |  | textbox | Action
checkpoint-status |  |  | checkpoint | 5
text | e0d9c37f-d239-4fab-a037-16d597f7ebf1 |  | textbox | Area/Zone
text | 5d1acc45-518f-4a31-9aed-d7659b7506e1 |  | textbox | Construction Type
button | 64832285-9394-4ea3-8c2f-87f204a74d23 |  | button | Installed as per Rondo’s installation guide | No,Yes
button | 1119c1dd-e533-4199-8923-a3de3cb6ec2c |  | button | Rectification required | No,Yes
text | cb5b8db0-9252-435f-8edc-87a49797bedb |  | textbox | Action
checkpoint-status |  |  | checkpoint | 6
text | 8cf79ac1-5b1c-44f2-8516-dcc50c77c1ec |  | textbox | Area/Zone
text | 85d5da16-888b-4650-b77c-1154f94f2fa3 |  | textbox | Construction Type
button | dc322c04-3521-4d97-8916-adef13b23703 |  | button | Installed as per Rondo’s installation guide | No,Yes
button | a581e88b-f69b-4003-ad2d-a51bea0b4550 |  | button | Rectification required | No,Yes
text | 6f8624b3-b0c2-4fb9-963c-eba77d252434 |  | textbox | Action
checkpoint-status |  |  | checkpoint | 7
text | a07251eb-9620-43d7-96d2-7b661172074b |  | textbox | Area/Zone
text | 4f4d7dc3-be38-4038-857a-6bcd9dc7c1aa |  | textbox | Construction Type
button | 4f2a5b47-3f02-47f3-b7cf-bf730003c8a3 |  | button | Installed as per Rondo’s installation guide | No,Yes
button | 93380546-588c-4a4b-8448-3e2c818aabbf |  | button | Rectification required | No,Yes
text | cb42bb9b-a13c-4f2a-ad44-62e3d17687e8 |  | textbox | Action
checkpoint-status |  |  | checkpoint | 8
text | 598786f8-99dd-4ca6-9e44-8835bc522425 |  | textbox | Area/Zone
text | 1d6c6cf7-e49c-4e64-9e4d-ce86f6140594 |  | textbox | Construction Type
button | 384bbf96-7119-4e62-9735-7f3f938d706d |  | button | Installed as per Rondo’s installation guide | No,Yes
button | c449563c-ffab-4cc3-a910-1f54b68d72ec |  | button | Rectification required | No,Yes
text | ba542d6b-620d-4a12-acd0-452b4b3cf800 |  | textbox | Action
checkpoint-status |  |  | checkpoint | 9
text | bf23aa3e-8d21-409b-a463-c49cb1492299 |  | textbox | Area/Zone
text | 8d158662-2859-4d69-bb95-b02fe56c8689 |  | textbox | Construction Type
button | 9dc600e5-d77b-486c-867f-a17f555bb954 |  | button | Installed as per Rondo’s installation guide | No,Yes
button | db1ed197-48d0-40dc-8fb7-653acbc6a512 |  | button | Rectification required | No,Yes
text | 205806e6-73d9-4d84-b7f0-6c2efc56389f |  | textbox | Action
checkpoint-status |  |  | checkpoint | 10
text | dc4de241-d83c-43d1-95e8-7f982a59c4f7 |  | textbox | Area/Zone
text | 95bb7742-0725-4e1e-9444-b23a1cf32d96 |  | textbox | Construction Type
button | b82569b7-17f0-4f49-9f96-3e992b7e7de1 |  | button | Installed as per Rondo’s installation guide | No,Yes
button | 43f2c80a-8a0c-4b93-9876-9dff1db24360 |  | button | Rectification required | No,Yes
text | 70ecd065-48bd-4bd0-84d6-129bd53f3090 |  | textbox | Action
checkpoint-status |  |  | checkpoint | 11
text | 61bc33b9-439e-40e1-abf8-193ed4d71774 |  | textbox | Area/Zone
text | cdeb44df-34d1-4988-aed6-cd631441a55b |  | textbox | Construction Type
button | 026a8c0f-b42b-4978-b65c-33467ebaf00c |  | button | Installed as per Rondo’s installation guide | No,Yes
button | 9e659343-19b2-4352-a84b-d483ab4ea3fd |  | button | Rectification required | No,Yes
text | 354d8f8b-e91c-49b1-9faf-e4c294844c53 |  | textbox | Action
checkpoint-status |  |  | checkpoint | 12
text | df8946fb-0761-4566-951a-3855b8d074b2 |  | textbox | Area/Zone
text | d0a26c64-05f2-4a1d-bb06-c59ff5ef5709 |  | textbox | Construction Type
button | 250f1ed9-e89c-4926-8214-d16cb7ff5acd |  | button | Installed as per Rondo’s installation guide | No,Yes
button | 717561e1-5859-418d-95ce-46c9f607b45a |  | button | Rectification required | No,Yes
text | ade06157-822e-4485-83c9-21d8723de707 |  | textbox | Action
checkpoint-status |  |  | checkpoint | 13
text | 5d775bbb-1931-43b3-9c2e-4b89b977f87a |  | textbox | Area/Zone
text | 5d5c69e9-f3bf-4641-9237-b67ae1647a74 |  | textbox | Construction Type
button | e1af02ac-134b-40a4-ae98-5fdf8659aec0 |  | button | Installed as per Rondo’s installation guide | No,Yes
button | a7b1c36b-2388-4391-8b43-a981de68e825 |  | button | Rectification required | No,Yes
text | 767e53ae-4aa5-4a1e-95e6-508ad84ec304 |  | textbox | Action
checkpoint-status |  |  | checkpoint | 14
text | 3a042ab4-e7e6-4180-a246-2ed58eb81bc3 |  | textbox | Area/Zone
text | 9da9bf7e-f910-4bbd-9350-dda4dd879244 |  | textbox | Construction Type
button | 9b21d9be-4294-40a7-9dd8-cef7a7a3dde9 |  | button | Installed as per Rondo’s installation guide | No,Yes
button | 3bba3499-7323-4749-a62e-b0be2cd1efcf |  | button | Rectification required | No,Yes
text | 26bfc981-33b1-4769-a284-86c5f9ffbe21 |  | textbox | Action
checkpoint-status |  |  | checkpoint | 15
text | 49729ad1-e507-493a-ae00-56a532ed9072 |  | textbox | Area/Zone
text | 9bae8a6a-1828-4b73-8d23-337b1780077b |  | textbox | Construction Type
button | 395f74c8-c94a-432d-9b47-e5ef6341fdcf |  | button | Installed as per Rondo’s installation guide | No,Yes
button | 2a0b36d8-bd9a-464e-9161-3ee21f94a6bd |  | button | Rectification required | No,Yes
text | 026ba44a-6068-4f3d-8edf-b83f12707df6 |  | textbox | Action
checkpoint-status |  |  | checkpoint | 16
text | 406a6d57-d02a-4217-a3c8-9b8c8c8c6834 |  | textbox | Area/Zone
text | 6cec82dd-1f09-430c-91d3-0563578254ac |  | textbox | Construction Type
button | bfdd6193-ca67-4a1b-bb18-d70981b0e5ba |  | button | Installed as per Rondo’s installation guide | No,Yes
button | 5a7bfa58-a771-4403-866f-d9e385a6fd89 |  | button | Rectification required | No,Yes
text | a3e99190-23f0-4977-809b-47d7c3fc58ff |  | textbox | Action
checkpoint-status |  |  | checkpoint | 17
text | ccaf0cfa-af75-4b06-96bd-3011c40969d0 |  | textbox | Area/Zone
text | f89c586f-f1e4-4b69-aa73-432c30e5f4c7 |  | textbox | Construction Type
button | 53b763b0-907f-48a8-bd8f-e2436d2c204a |  | button | Installed as per Rondo’s installation guide | No,Yes
button | 0b4859e6-3bce-4180-a252-d44c0096a6f6 |  | button | Rectification required | No,Yes
text | 7ae3bd67-b8ef-4255-8ce1-f1f707691867 |  | textbox | Action
checkpoint-status |  |  | checkpoint | 18
text | 51e9ad70-f60b-484b-81b4-9eaba6231bf4 |  | textbox | Area/Zone
text | c29ffc4e-9913-495d-b344-2861a8bd2985 |  | textbox | Construction Type
button | 86a2a5b5-f5d1-49da-9d12-c4f8a0beac29 |  | button | Installed as per Rondo’s installation guide | No,Yes
button | 03ac4cbd-7e9a-4a65-a27d-e2303b9ec504 |  | button | Rectification required | No,Yes
text | 72dacd68-72ae-4c49-b5f9-cc83d2bdd8d2 |  | textbox | Action
checkpoint-status |  |  | checkpoint | Inspected by:
text | 251de64a-473f-4855-b31b-32232d0d1b3d |  | textbox | Inspected by (print name):
holdpoint |  |  | signoff | Add Signature
checkpoint-status |  |  | checkpoint | Accepted by:
text | 82c61b09-b4c8-4dd5-b30c-1eb80b398e5d |  | textbox | Accepted by (print name):
text | 1c4f6dc1-870b-4172-977e-bc18d39e85fa |  | textbox | Company:
label | df7e3c16-661f-4eee-8470-29917ededd3d |  | note | By signing this form, the receiver acknowledges that they understand the works to be undertaken and instructions given herein.
holdpoint |  |  | signoff | Add Signature
checkpoint-no-status |  |  | checkpoint | NOTE
label | 54093aca-1511-43a6-8339-3885c17dd96b |  | note | All other works have generally been installed as per Rondo’s Design Manual.
label | 6eab6a54-4ab8-4f26-b928-1be9a18224ae |  | note | This inspection is limited to the products supplied by Rondo. All track fixings to be confirmed by the fastener supplier as per Rondo’s recommendations.
label | f6e14d00-3369-45d4-bf39-79f0a5d74874 |  | note | This inspection does not preclude the possibility of non-conforming works elsewhere and does not relieve any other party of responsibility.
label | 055cbbab-79b4-4abb-8747-3c167431c563 |  | note | FIXING DISCLAIMER
label | 499252dd-7ebc-46fc-9a11-9116dabddcd0 |  | note | For safety critical fastening applications, Rondo provides a recommended solution in accordance with AS5216. This is only a recommendation and does not preclude the possibility of alternative solutions being available within the market place. Should the installer have a preferred alternate fastener supplier Rondo can supply the design loads; however, Rondo recommends the fastener supplier provide the required documentation for the alternate fastener in accordance with the nominated loads and the relevant Australian Standards.
checklist-flat | b093e9f0-641a-4cd0-b017-201cc3e27a41 |  | checklist | Deliveries Checklist |  |  |  |  | Yes | Deliveries Checklist | c7e12496-fa6b-4821-a62b-bf8a969a2fec
checkpoint-status | b08fa207-e446-4d03-931a-8ee8bb5ba2f6 |  | checkpoint | Delivery Received
checklist-flat |  |  | checklist | Common Area |  |  |  |  | Yes | Common Area Checklist | ef589fbc-a548-4052-ad49-4ae43588ae75
checkpoint-status |  |  | checkpoint | Set out - as per current drawing revision
checkpoint-status |  |  | checkpoint | Install foil board to soffit
checkpoint-status |  |  | checkpoint | Entry door/Fire box - Door Installed as per MPX instruction after floor survey. Perimeter of the firebox has been fully sealed
checkpoint-status |  |  | checkpoint | Frame walls - Floor and ceiling track to be secured to the structure at no less than 600mm centres internally and 100mm from ends & ensure noise clips are installed.
checkpoint-status |  |  | checkpoint | All required hydraulic, electrical, sanitary and joinery noggins installed into the wall - Ensure noggins are installed as per specifications
checkpoint-status |  |  | checkpoint | Thermal and Acoustic Insulation installed
checkpoint-status |  |  | checkpoint | Sheet walls - CSR plasterboard to be installed as per Gyprock specifications. Non Tiled areas = field screws at 300mm max centres. Tiled areas = field screws at 200mm max centres (Weights to be confirmed). Tiled areas = field screws at 100mm max centres (Weights to be confirmed).
checkpoint-status |  |  | checkpoint | Firecaulk - Ensure all gaps and joins are fully sealed
checkpoint-status |  |  | checkpoint | Frame ceilings - Ensure framing is installed as per Studco Drywall Ceiling System specifications. Perimeter tracks to be fastened at no more than 600mm centres and no more than 50mm from the stud location.
checkpoint-status |  |  | checkpoint | Sheet ceilings - Installed as per Gyprock specifications
checkpoint-status |  |  | checkpoint | Install A/P's
checkpoint-status |  |  | checkpoint | Stop & Sand
checkpoint-status |  |  | checkpoint | Area clean & Handed over
checklist-flat |  |  | checklist | Common Area |  |  |  |  | Yes | Common Area - Tower 2 - Hotel | ef651940-ef27-4592-8ef8-45c3e40a4560
checkpoint-status |  |  | checkpoint | Floors - Loaded material
checkpoint-status |  |  | checkpoint | Set out complete
checkpoint-status |  |  | checkpoint | Speed panel installed
checklist-flat |  |  | checklist | Apartment: |  |  |  |  | Yes | Apartment Checklist | efdca757-83d9-46a7-b053-0458ea2ac27a
checkpoint-status |  |  | checkpoint | Set out - as per current drawing revision
checkpoint-status |  |  | checkpoint | Install foil board to soffit
checkpoint-status |  |  | checkpoint | Entry door/Fire box - Door Installed as per MPX instruction after floor survey. Perimeter of the firebox has been fully sealed
checkpoint-status |  |  | checkpoint | Frame walls - Floor and ceiling track to be secured to the structure at no less than 600mm centres internally and 100mm from ends & ensure noise clips are installed.
checkpoint-status |  |  | checkpoint | All required hydraulic, electrical, sanitary and joinery noggins installed into the wall - Ensure noggins are installed as per specifications
checkpoint-status |  |  | checkpoint | Thermal and Acoustic Insulation installed
checkpoint-status |  |  | checkpoint | Sheet walls - CSR plasterboard to be installed as per Gyprock specifications. Non Tiled areas = field screws at 300mm max centres. Tiled areas = field screws at 200mm max centres (Weights to be confirmed). Tiled areas = field screws at 100mm max centres (Weights to be confirmed).
checkpoint-status |  |  | checkpoint | Firecaulk - Ensure all gaps and joins are fully sealed
checkpoint-status |  |  | checkpoint | Frame ceilings - Ensure framing is installed as per Studco Drywall Ceiling System specifications. Perimeter tracks to be fastened at no more than 600mm centres and no more than 50mm from the stud location.
checkpoint-status |  |  | checkpoint | Sheet ceilings - Installed as per Gyprock specifications
checkpoint-status |  |  | checkpoint | Install A/P's
checkpoint-status |  |  | checkpoint | Stop & Sand
checkpoint-status |  |  | checkpoint | Area clean & Handed over