## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Internal |  |  |  |  | Yes | Internal | 0ad96371-3aa7-4267-9d56-388bd62cb603
checkpoint-status |  |  | checkpoint | Area clean and accessible
checkpoint-status |  |  | checkpoint | Set out as per drawings
checkpoint-status |  |  | checkpoint | Entry door header installed
checkpoint-status |  |  | checkpoint | Top track installed
checkpoint-status |  |  | checkpoint | Loading materials receieved
checkpoint-status |  |  | checkpoint | Partition framing
checkpoint-status |  |  | checkpoint | Wall framing
checkpoint-status |  |  | checkpoint | Pre sheeting for second wall
holdpoint |  |  | signoff | Signed by Expoconti Rep
checkpoint-status |  |  | checkpoint | Noggins installed
checkpoint-status |  |  | checkpoint | Wall insulation installed
checkpoint-status |  |  | checkpoint | Lobby wall fire wall sheeting
holdpoint |  |  | signoff | Signed by Expoconti Rep
checkpoint-status |  |  | checkpoint | Fire wall caulking installed
checkpoint-status |  |  | checkpoint | Signed by Expoconti Rep
checkpoint-status |  |  | checkpoint | Inter tenancy wall sheeting 1
holdpoint |  |  | signoff | Signed by Expoconti Rep
checkpoint-status |  |  | checkpoint | Inter tenancy wall insulation installed
holdpoint |  |  | signoff | Signed by Expoconti Rep
checkpoint-status |  |  | checkpoint | Inter tenancy wall sheeting 2
holdpoint |  |  | signoff | Signed by Expoconti Rep
checkpoint-status |  |  | checkpoint | Bathroom wall insulation
holdpoint |  |  | signoff | Signed by Expoconti Rep
checkpoint-status |  |  | checkpoint | Incapsulate bathrooms
holdpoint |  |  | signoff | Signed by Expoconti Rep
checkpoint-status |  |  | checkpoint | Frame ceiling
checkpoint-status |  |  | checkpoint | Ceiling insulation
holdpoint |  |  | signoff | Signed by Expoconti Rep
checkpoint-status |  |  | checkpoint | Sheet ceilings
checkpoint-status |  |  | checkpoint | Access panel insulation
checkpoint-status |  |  | checkpoint | Stop up walls/ceilings
checkpoint-status |  |  | checkpoint | Sand walls/ceilings
holdpoint |  |  | signoff | Signed by Expoconti Rep
checkpoint-status |  |  | checkpoint | Install pelmets
checkpoint-status |  |  | checkpoint | Clean up
checklist-flat |  |  | checklist | Common Area |  |  |  |  | Yes | Common Area - Tower 2 - Hotel | 89a0f987-05e1-49ee-abdb-213fbdfbd5ad
checkpoint-status |  |  | checkpoint | Floors - Loaded material
checkpoint-status |  |  | checkpoint | Set out complete
checkpoint-status |  |  | checkpoint | Speed panel installed
checklist-flat |  |  | checklist | Delivery: |  |  |  |  | Yes | Add Delivery Checklist | 360b929a-e403-42ad-a686-0a44b4256f9c
checkpoint-status |  |  | checkpoint | Delivery docket attached
checklist-flat |  |  | checklist | Pre Fab Walls |  |  |  |  | Yes | Pre Fab Walls | 5475b2b2-4ff8-4679-bee9-3cc25a72ea57
checkpoint-status |  |  | checkpoint | Hobs square and straight
checkpoint-status |  |  | checkpoint | Walls check plumb and square
checkpoint-status |  |  | checkpoint | Top track/haus anchors
checkpoint-status |  |  | checkpoint | Bottom fixings/caulking to fixings
checkpoint-status |  |  | checkpoint | Sec fire wall screwed and caulked
checklist-flat |  |  | checklist | Speedpanel |  |  |  |  | Yes | Speedpanel | aca86011-217e-4281-8a89-1b0d0caa220b
checkpoint-status |  |  | checkpoint | Speedpanel
checkpoint-status |  |  | checkpoint | Set out speed panel
checkpoint-status |  |  | checkpoint | Install panels and flashing head track
checkpoint-status |  |  | checkpoint | Caulk and flashing head track
checkpoint-status |  |  | checkpoint | Clean up
checklist-sectioned |  |  | checklist | Retail |  |  |  |  | Yes | Retail Checklist | f5d89684-0430-42a6-8ce9-bc41f02152a5
checkpoint-group |  | checkpoint-group must be display flat but was undefined | section | Area
checkpoint-status |  |  | checkpoint | Wall set out
checkpoint-status |  |  | checkpoint | Soffit insulation
checkpoint-status |  |  | checkpoint | Speed Panel - Installed
checkpoint-status |  |  | checkpoint | Speed Panel - Caulking
checkpoint-status |  |  | checkpoint | Speed Panel - Door Frames
checkpoint-status |  |  | checkpoint | Frame Walls - Installed
checkpoint-status |  |  | checkpoint | Frame Walls - Noggins
checkpoint-status |  |  | checkpoint | Frame Walls - Door Frames
checkpoint-status |  |  | checkpoint | Wall Lining - Insulation Installed
checkpoint-status |  |  | checkpoint | Wall Lining - Caulking
checkpoint-status |  |  | checkpoint | Plaster Ceilings - Ceilings set out
checkpoint-status |  |  | checkpoint | Plaster Ceilings - Noggins
checkpoint-status |  |  | checkpoint | Plaster Ceilings - Access Panels
checkpoint-status |  |  | checkpoint | Feature Ceilings - Noggins
checkpoint-status |  |  | checkpoint | Feature Ceilings - Access Panels
checkpoint-group |  |  | section | Wet Area
checkpoint-status |  |  | checkpoint | Set out
checkpoint-status |  |  | checkpoint | Soffit insulation
checkpoint-status |  |  | checkpoint | Frame Walls - Noggins
checkpoint-status |  |  | checkpoint | Frame Walls - Door Frames
checkpoint-status |  |  | checkpoint | Wall Lining - Insulation installed
checkpoint-status |  |  | checkpoint | Wall Lining - Caulking
checkpoint-status |  |  | checkpoint | Plaster Ceiling - Noggins
checkpoint-status |  |  | checkpoint | Plaster Ceiling - Access Panels
checkpoint-status |  |  | checkpoint | Pelmets - Bulk heads installed
checklist-flat |  |  | checklist | Site Inspection Report |  |  |  |  | Yes | NF1209 Site Inspection Report | ba26d64e-f8da-4798-9711-a7dbdb0b37db
checkpoint-no-status |  |  | checkpoint | Site Inspection Report:
text | e1bfbf8b-d2f5-4952-9984-b963bf5dd36d |  | textbox | Project Name
text | 91a3c2d2-9258-42be-b44e-fbf661fe9aa3 |  | textbox | Address
text | 2366c202-5391-406d-9044-42c445d0be7b |  | textbox | Reference/Project No.
text | 8b165331-484f-4f0c-856a-25a211887936 |  | textbox | Date of Inspection:
text | 4a3fd7d5-c019-4b95-a8e2-68c885282670 |  | textbox | Start Time:
text | 8c75df6d-2062-4688-95a5-54acb1a5e738 |  | textbox | End Time:
text | a785e45a-399f-4666-aab2-61936ee1ca1e |  | textbox | Rondo Representative
text | 554a626e-913a-4002-8c9a-7c4edfd44c30 |  | textbox | Company Site Foreman: Contact
text | f5d8baca-7eae-49de-b4e2-1cda8159b53f |  | textbox | Construction Status
button | 697fe55c-8a8c-4288-8b23-1dbf514f5f41 |  | button | System Inspected | DUO, External, Other , Stud Framing: Internal,Keylock
button | 38b9272e-9e92-4a0b-99b9-8afa6f7e2230 |  | button | Inspection Requirements: | Fortnightly, Monthly,Weekly
checkpoint-no-status |  |  | checkpoint | Site Safety
button | 82e14e2a-cfd0-4cbf-911d-868e62802a6f |  | button | Inducted to site | No,Yes
text | 8f4b5580-5e68-4243-ba37-c56a68622414 |  | textbox | Date:
button | c1ed08bf-c482-4b27-9d85-2e96fdaf43f7 |  | button | Rondo supplied the required PPE for the visit | No,Yes
button | 0ac0e7cc-1191-4ba6-ab17-b56897d6e9e6 |  | button | Replacement PPE required | No,Yes
text | 2db02555-bdc2-4e0a-9015-ce0e6a07bc50 |  | textbox | Items:
button | 50e68217-3254-4353-8f61-83eb04b9ffd5 |  | button | Hazards or Near/Miss witnessed while on site | No,Yes
button | e4fa70fe-1c6e-450a-87cd-57d2a3510199 |  | button | a) Incident reported to Site Mgt | No,Yes
button | 0181e0ab-332a-41fd-a834-559ccabb84ec |  | button | b) Rondo Hazard report raised | No,Yes
text | efa00653-0191-4ecd-9840-daa6489b48dc |  | textbox | Report No.
text | 3a9c5f27-012e-45c3-865a-d71c9566a310 |  | textbox | General Notes:
checkpoint-status |  |  | checkpoint | 1
text | 39cf6a57-cd44-4e38-a09c-3b7f19613601 |  | textbox | Area/Zone
text | ed5a7b68-94e7-40d0-9438-c821f73e4166 |  | textbox | Construction Type
button | c9cc5a36-6b09-49c8-b527-8b0a603c5c14 |  | button | Installed as per Rondo’s installation guide | No,Yes
button | b0280e7f-c4d4-4ad4-9a46-655acd64e4ea |  | button | Rectification required | No,Yes
text | 46b4ae61-258a-4ec1-b735-3998c1c7a90a |  | textbox | Action
checkpoint-status |  |  | checkpoint | 2
text | 7752b1a1-860a-4d99-8a42-f383fe207bb6 |  | textbox | Area/Zone
text | ac9b8752-69a3-4f42-aa21-74f113274d36 |  | textbox | Construction Type
button | db381810-13e1-4cee-bb83-a1da56f3b3a9 |  | button | Installed as per Rondo’s installation guide | No,Yes
button | ce29f70d-001d-42bb-8dcc-9da8ae250017 |  | button | Rectification required | No,Yes
text | d1648c29-0a16-4a7d-9193-98d3a9eb007b |  | textbox | Action
checkpoint-status |  |  | checkpoint | 3
text | 7cc7c629-ce17-4f25-84ea-b31184a560b0 |  | textbox | Area/Zone
text | edbbe215-2404-4639-a97d-9a1bcc96112d |  | textbox | Construction Type
button | 5ffcda41-00a6-4d7e-86f6-4d64d8c25dfa |  | button | Installed as per Rondo’s installation guide | No,Yes
button | 649ef762-bd1e-45e2-8dfd-a1fde5c7ab40 |  | button | Rectification required | No,Yes
text | ee63c6d8-2f41-4c2d-a420-22e1c20ba569 |  | textbox | Action
checkpoint-status |  |  | checkpoint | 4
text | d926222c-6d42-43a0-9308-2edb418a19b8 |  | textbox | Area/Zone
text | f3330ea5-a23b-4a46-82e2-1944b09c90cc |  | textbox | Construction Type
button | 11dbdbb7-e173-42b9-81ae-ee8707e3c483 |  | button | Installed as per Rondo’s installation guide | No,Yes
button | 66a9be8f-351c-4b2a-a749-ce9b59ec6fd3 |  | button | Rectification required | No,Yes
text | b2f79d4f-b0ae-4e67-b412-f89ae08247e5 |  | textbox | Action
checkpoint-status |  |  | checkpoint | 5
text | e0d9c37f-d239-4fab-a037-16d597f7ebf1 |  | textbox | Area/Zone
text | 5d1acc45-518f-4a31-9aed-d7659b7506e1 |  | textbox | Construction Type
button | 64832285-9394-4ea3-8c2f-87f204a74d23 |  | button | Installed as per Rondo’s installation guide | No,Yes
button | 1119c1dd-e533-4199-8923-a3de3cb6ec2c |  | button | Rectification required | No,Yes
text | cb5b8db0-9252-435f-8edc-87a49797bedb |  | textbox | Action
checkpoint-status |  |  | checkpoint | 6
text | 8cf79ac1-5b1c-44f2-8516-dcc50c77c1ec |  | textbox | Area/Zone
text | 85d5da16-888b-4650-b77c-1154f94f2fa3 |  | textbox | Construction Type
button | dc322c04-3521-4d97-8916-adef13b23703 |  | button | Installed as per Rondo’s installation guide | No,Yes
button | a581e88b-f69b-4003-ad2d-a51bea0b4550 |  | button | Rectification required | No,Yes
text | 6f8624b3-b0c2-4fb9-963c-eba77d252434 |  | textbox | Action
checkpoint-status |  |  | checkpoint | 7
text | a07251eb-9620-43d7-96d2-7b661172074b |  | textbox | Area/Zone
text | 4f4d7dc3-be38-4038-857a-6bcd9dc7c1aa |  | textbox | Construction Type
button | 4f2a5b47-3f02-47f3-b7cf-bf730003c8a3 |  | button | Installed as per Rondo’s installation guide | No,Yes
button | 93380546-588c-4a4b-8448-3e2c818aabbf |  | button | Rectification required | No,Yes
text | cb42bb9b-a13c-4f2a-ad44-62e3d17687e8 |  | textbox | Action
checkpoint-status |  |  | checkpoint | 8
text | 598786f8-99dd-4ca6-9e44-8835bc522425 |  | textbox | Area/Zone
text | 1d6c6cf7-e49c-4e64-9e4d-ce86f6140594 |  | textbox | Construction Type
button | 384bbf96-7119-4e62-9735-7f3f938d706d |  | button | Installed as per Rondo’s installation guide | No,Yes
button | c449563c-ffab-4cc3-a910-1f54b68d72ec |  | button | Rectification required | No,Yes
text | ba542d6b-620d-4a12-acd0-452b4b3cf800 |  | textbox | Action
checkpoint-status |  |  | checkpoint | 9
text | bf23aa3e-8d21-409b-a463-c49cb1492299 |  | textbox | Area/Zone
text | 8d158662-2859-4d69-bb95-b02fe56c8689 |  | textbox | Construction Type
button | 9dc600e5-d77b-486c-867f-a17f555bb954 |  | button | Installed as per Rondo’s installation guide | No,Yes
button | db1ed197-48d0-40dc-8fb7-653acbc6a512 |  | button | Rectification required | No,Yes
text | 205806e6-73d9-4d84-b7f0-6c2efc56389f |  | textbox | Action
checkpoint-status |  |  | checkpoint | 10
text | dc4de241-d83c-43d1-95e8-7f982a59c4f7 |  | textbox | Area/Zone
text | 95bb7742-0725-4e1e-9444-b23a1cf32d96 |  | textbox | Construction Type
button | b82569b7-17f0-4f49-9f96-3e992b7e7de1 |  | button | Installed as per Rondo’s installation guide | No,Yes
button | 43f2c80a-8a0c-4b93-9876-9dff1db24360 |  | button | Rectification required | No,Yes
text | 70ecd065-48bd-4bd0-84d6-129bd53f3090 |  | textbox | Action
checkpoint-status |  |  | checkpoint | 11
text | 61bc33b9-439e-40e1-abf8-193ed4d71774 |  | textbox | Area/Zone
text | cdeb44df-34d1-4988-aed6-cd631441a55b |  | textbox | Construction Type
button | 026a8c0f-b42b-4978-b65c-33467ebaf00c |  | button | Installed as per Rondo’s installation guide | No,Yes
button | 9e659343-19b2-4352-a84b-d483ab4ea3fd |  | button | Rectification required | No,Yes
text | 354d8f8b-e91c-49b1-9faf-e4c294844c53 |  | textbox | Action
checkpoint-status |  |  | checkpoint | 12
text | df8946fb-0761-4566-951a-3855b8d074b2 |  | textbox | Area/Zone
text | d0a26c64-05f2-4a1d-bb06-c59ff5ef5709 |  | textbox | Construction Type
button | 250f1ed9-e89c-4926-8214-d16cb7ff5acd |  | button | Installed as per Rondo’s installation guide | No,Yes
button | 717561e1-5859-418d-95ce-46c9f607b45a |  | button | Rectification required | No,Yes
text | ade06157-822e-4485-83c9-21d8723de707 |  | textbox | Action
checkpoint-status |  |  | checkpoint | 13
text | 5d775bbb-1931-43b3-9c2e-4b89b977f87a |  | textbox | Area/Zone
text | 5d5c69e9-f3bf-4641-9237-b67ae1647a74 |  | textbox | Construction Type
button | e1af02ac-134b-40a4-ae98-5fdf8659aec0 |  | button | Installed as per Rondo’s installation guide | No,Yes
button | a7b1c36b-2388-4391-8b43-a981de68e825 |  | button | Rectification required | No,Yes
text | 767e53ae-4aa5-4a1e-95e6-508ad84ec304 |  | textbox | Action
checkpoint-status |  |  | checkpoint | 14
text | 3a042ab4-e7e6-4180-a246-2ed58eb81bc3 |  | textbox | Area/Zone
text | 9da9bf7e-f910-4bbd-9350-dda4dd879244 |  | textbox | Construction Type
button | 9b21d9be-4294-40a7-9dd8-cef7a7a3dde9 |  | button | Installed as per Rondo’s installation guide | No,Yes
button | 3bba3499-7323-4749-a62e-b0be2cd1efcf |  | button | Rectification required | No,Yes
text | 26bfc981-33b1-4769-a284-86c5f9ffbe21 |  | textbox | Action
checkpoint-status |  |  | checkpoint | 15
text | 49729ad1-e507-493a-ae00-56a532ed9072 |  | textbox | Area/Zone
text | 9bae8a6a-1828-4b73-8d23-337b1780077b |  | textbox | Construction Type
button | 395f74c8-c94a-432d-9b47-e5ef6341fdcf |  | button | Installed as per Rondo’s installation guide | No,Yes
button | 2a0b36d8-bd9a-464e-9161-3ee21f94a6bd |  | button | Rectification required | No,Yes
text | 026ba44a-6068-4f3d-8edf-b83f12707df6 |  | textbox | Action
checkpoint-status |  |  | checkpoint | 16
text | 406a6d57-d02a-4217-a3c8-9b8c8c8c6834 |  | textbox | Area/Zone
text | 6cec82dd-1f09-430c-91d3-0563578254ac |  | textbox | Construction Type
button | bfdd6193-ca67-4a1b-bb18-d70981b0e5ba |  | button | Installed as per Rondo’s installation guide | No,Yes
button | 5a7bfa58-a771-4403-866f-d9e385a6fd89 |  | button | Rectification required | No,Yes
text | a3e99190-23f0-4977-809b-47d7c3fc58ff |  | textbox | Action
checkpoint-status |  |  | checkpoint | 17
text | ccaf0cfa-af75-4b06-96bd-3011c40969d0 |  | textbox | Area/Zone
text | f89c586f-f1e4-4b69-aa73-432c30e5f4c7 |  | textbox | Construction Type
button | 53b763b0-907f-48a8-bd8f-e2436d2c204a |  | button | Installed as per Rondo’s installation guide | No,Yes
button | 0b4859e6-3bce-4180-a252-d44c0096a6f6 |  | button | Rectification required | No,Yes
text | 7ae3bd67-b8ef-4255-8ce1-f1f707691867 |  | textbox | Action
checkpoint-status |  |  | checkpoint | 18
text | 51e9ad70-f60b-484b-81b4-9eaba6231bf4 |  | textbox | Area/Zone
text | c29ffc4e-9913-495d-b344-2861a8bd2985 |  | textbox | Construction Type
button | 86a2a5b5-f5d1-49da-9d12-c4f8a0beac29 |  | button | Installed as per Rondo’s installation guide | No,Yes
button | 03ac4cbd-7e9a-4a65-a27d-e2303b9ec504 |  | button | Rectification required | No,Yes
text | 72dacd68-72ae-4c49-b5f9-cc83d2bdd8d2 |  | textbox | Action
checkpoint-status |  |  | checkpoint | Inspected by:
text | 251de64a-473f-4855-b31b-32232d0d1b3d |  | textbox | Inspected by (print name):
holdpoint |  |  | signoff | Add Signature
checkpoint-status |  |  | checkpoint | Accepted by:
text | 82c61b09-b4c8-4dd5-b30c-1eb80b398e5d |  | textbox | Accepted by (print name):
text | 1c4f6dc1-870b-4172-977e-bc18d39e85fa |  | textbox | Company:
label | df7e3c16-661f-4eee-8470-29917ededd3d |  | note | By signing this form, the receiver acknowledges that they understand the works to be undertaken and instructions given herein.
holdpoint |  |  | signoff | Add Signature
checkpoint-no-status |  |  | checkpoint | NOTE
label | 54093aca-1511-43a6-8339-3885c17dd96b |  | note | All other works have generally been installed as per Rondo’s Design Manual.
label | 6eab6a54-4ab8-4f26-b928-1be9a18224ae |  | note | This inspection is limited to the products supplied by Rondo. All track fixings to be confirmed by the fastener supplier as per Rondo’s recommendations.
label | f6e14d00-3369-45d4-bf39-79f0a5d74874 |  | note | This inspection does not preclude the possibility of non-conforming works elsewhere and does not relieve any other party of responsibility.
label | 055cbbab-79b4-4abb-8747-3c167431c563 |  | note | FIXING DISCLAIMER
label | 499252dd-7ebc-46fc-9a11-9116dabddcd0 |  | note | For safety critical fastening applications, Rondo provides a recommended solution in accordance with AS5216. This is only a recommendation and does not preclude the possibility of alternative solutions being available within the market place. Should the installer have a preferred alternate fastener supplier Rondo can supply the design loads; however, Rondo recommends the fastener supplier provide the required documentation for the alternate fastener in accordance with the nominated loads and the relevant Australian Standards.
checklist-sectioned |  |  | checklist | South Tower |  |  |  |  | Yes | South Tower Checklist | 755b0dcf-fcba-4959-ab3e-a7179dd42933
checkpoint-group |  | checkpoint-group must be display flat but was undefined | section | Office
checkpoint-status |  |  | checkpoint | Set out walls
checkpoint-status |  |  | checkpoint | Soffit insulation
checkpoint-status |  |  | checkpoint | Speed Panel - Installed
checkpoint-status |  |  | checkpoint | Speed Panel - Caulking
checkpoint-status |  |  | checkpoint | Speed Panel - Door Frames
checkpoint-status |  |  | checkpoint | Frame Walls - Installed
checkpoint-status |  |  | checkpoint | Frame Walls - Noggins
checkpoint-status |  |  | checkpoint | Frame Walls - Door Frames
checkpoint-status |  |  | checkpoint | Wall Lining - Insulation Installed
checkpoint-status |  |  | checkpoint | Wall Lining - Wall Sheet
checkpoint-status |  |  | checkpoint | Wall Lining - Trowel & Sand
checkpoint-status |  |  | checkpoint | Wall Lining - Caulking
checkpoint-status |  |  | checkpoint | Ceilings - Ceiling/pelmet set out
checkpoint-status |  |  | checkpoint | Ceilings - Pelmet - Bulkhead
checkpoint-status |  |  | checkpoint | Ceilings - Grid Ceiling installed
checkpoint-status |  |  | checkpoint | Ceilings - Bulk Ceiling Tiles
checkpoint-group |  |  | section | Wet Area
checkpoint-status |  |  | checkpoint | Set out walls
checkpoint-status |  |  | checkpoint | Soffit insulation
checkpoint-status |  |  | checkpoint | Frame Walls - Fire walls
checkpoint-status |  |  | checkpoint | Frame Walls - Noggins
checkpoint-status |  |  | checkpoint | Frame Walls - Door Frames
checkpoint-status |  |  | checkpoint | Wall Lining - Insulation installed
checkpoint-status |  |  | checkpoint | Wall Lining - Caulking
checkpoint-status |  |  | checkpoint | Wall Lining - Fireseal
checkpoint-status |  |  | checkpoint | Plaster Ceiling - Installed
checkpoint-status |  |  | checkpoint | Plaster Ceiling - Noggins
checkpoint-status |  |  | checkpoint | Plaster Ceiling - Access Panels
checkpoint-status |  |  | checkpoint | Pelmets - Bulk heads installed
checkpoint-group |  |  | section | Stairs 1-2
checkpoint-status |  |  | checkpoint | Wall Frame - Noggins
checkpoint-status |  |  | checkpoint | Ceiling Frame
checkpoint-status |  |  | checkpoint | Plaster Lining
checklist-flat | b093e9f0-641a-4cd0-b017-201cc3e27a41 |  | checklist | Deliveries Checklist |  |  |  |  | Yes | Deliveries Checklist | 3b809863-ec5a-46cf-bfa9-08fb1693c9c8
checkpoint-status | b08fa207-e446-4d03-931a-8ee8bb5ba2f6 |  | checkpoint | Delivery Received
checklist-sectioned |  |  | checklist | Apartment # |  |  |  |  | Yes | Apartment | 1cfcaaa1-28a2-42e1-b30a-11db9881cf63
checkpoint-group |  |  | section | Wall Setout
checkpoint-status |  |  | checkpoint | Setout All Walls (Party & Internal)
checkpoint-status |  |  | checkpoint | Install Top Plates
checkpoint-status |  |  | checkpoint | Clean Up
checkpoint-group |  |  | section | Party Walls / Internal Walls / Ceilings
checkpoint-status |  |  | checkpoint | Party / Internal Wall Stud Framing
checkpoint-status |  |  | checkpoint | Install Wall Noggins
checkpoint-status |  |  | checkpoint | Install all Plastic Noise Clips
holdpoint |  |  | signoff | Hold Point
checkpoint-status |  |  | checkpoint | Wall Insulation (Acoustic, Thermal, Etc)
checkpoint-status |  |  | checkpoint | Sheet Walls
checkpoint-status |  |  | checkpoint | Fire Caulk (Party Walls)
checkpoint-status |  |  | checkpoint | Frame Ceilings
checkpoint-status |  |  | checkpoint | Install Ceiling Noggins
checkpoint-status |  |  | checkpoint | Ceiling Insulation (Acoustic, Thermal, Etc)
holdpoint |  |  | signoff | Hold Point
checkpoint-status |  |  | checkpoint | Sheet Apartment Walls / Ceilings
checkpoint-status |  |  | checkpoint | Stop Up Walls & Ceilings
checkpoint-status |  |  | checkpoint | Sand Walls & Ceilings
checkpoint-status |  |  | checkpoint | Install Access Panels
checkpoint-status |  |  | checkpoint | Patch Walls
checkpoint-status |  |  | checkpoint | Clean Up
checkpoint-group |  |  | section | Defect Rectification
checkpoint-status |  |  | checkpoint | Check Ceilings
checkpoint-status |  |  | checkpoint | Check Walls
checkpoint-status |  |  | checkpoint | Clean Up
checklist-flat |  |  | checklist | Hotel |  |  |  |  | Yes | Hotel Checklist | 11bbb524-ad26-4ba9-9e0f-ae3e61d0aebd
checkpoint-status |  |  | checkpoint | Set out walls
checkpoint-status |  |  | checkpoint | Soffit Insulation
checkpoint-status |  |  | checkpoint | Speed Panel - Caulking
checkpoint-status |  |  | checkpoint | Speed Panel - Door Frames
checkpoint-status |  |  | checkpoint | Frame Walls - Firewalls
checkpoint-status |  |  | checkpoint | Frame Walls - Noggins
checkpoint-status |  |  | checkpoint | Frame Walls - Door Frames
checkpoint-status |  |  | checkpoint | Wall Lining - Insulation Installed
checkpoint-status |  |  | checkpoint | Wall Lining - Caulking
checkpoint-status |  |  | checkpoint | Wall Lining - Fireseal
checkpoint-status |  |  | checkpoint | Plaster Ceilings - Set out ceilings
checkpoint-status |  |  | checkpoint | Plaster Ceilings - Noggins
checkpoint-status |  |  | checkpoint | Plaster Ceilings - Access Panels
checkpoint-status |  |  | checkpoint | Feature Ceiling - Noggins
checkpoint-status |  |  | checkpoint | Feature Ceilings - Access Panels
checklist-flat |  |  | checklist | Enter Level/Apartment/Description |  |  |  |  | Yes | Record Hold-Up | 1f227e54-60c6-4556-ad0a-b557d1cc40c8
checkpoint-status |  |  | checkpoint | Decription of Hold Up
label | 5e0751f9-320c-4de6-84d9-cea2d37df381 |  | note | (See Photos & Comments Attached Below)