## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | ITP 03 - Partition Walls |  |  |  |  | Yes | ITP 03 - Partition Walls | 0fd662f9-bc26-4b0a-80ce-49f31d1af2b5
checkpoint-status |  |  | checkpoint | Set out walls
label | 7aa7afa3-e348-55c7-977b-28c596267a65 |  | note | Wall Types Plan and Wall Type & Setout Plan approved by Kapitol. Studco Wall design & installation manual Volume 3.2 Australian Standard: AS/NZS 4600:2005 , AS/NS 1170:2002
checkpoint-status |  |  | checkpoint | Furring channel to walls
label | f0ec7198-d377-5c1b-9304-ea237ad200c7 |  | note | Wall Types Plan and Wall Type & Setout Plan approved by Kapitol. Studco Wall design & installation manual Volume 3.2 Australian Standard: AS/NZS 4600:2005 , AS/NS 1170:2002
checkpoint-status |  |  | checkpoint | Metal stud wall frame
label | aed5c61b-a89a-5475-9340-bbb109c71a39 |  | note | Wall Types Plan and Wall Type & Setout Plan approved by Kapitol. Studco Wall design & installation manual Volume 3.2 Australian Standard: AS/NZS 4600:2005 , AS/NS 1170:2002
checkpoint-status |  |  | checkpoint | Noggins
label | 498937a0-eadf-5afc-ad7e-3bc2838fa5cb |  | note | As per scope of work. Studco Wall design & installation manual Volume 3.2 Studco Wall design & installation manual
label | f6b0fe28-0fab-59f0-b476-cded925f32f1 |  | note | Volume 3.2 Architectural Specification – 0522 Partition – Framed and Lined Australian Standard: AS/NZS 4600:2005 , AS/NS 1170:2002
checkpoint-status |  |  | checkpoint | Check no screws in deflection head
label | e36db3b3-0ac2-5c39-b6fb-6b0d90ef9394 |  | note | No screws in deflection head
checkpoint-status |  |  | checkpoint | Service Check for pre installation of sheets
label | b96df76b-d0e3-54bf-b21e-1dd287067c53 |  | note | All service checklists are signed off by relevant trades
label | a3e84183-316a-57dc-a9e6-67ffc44f38ce |  | note | Central Equity and Building Surveyor Sign Off's attached below
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | Sheet all walls
label | 78b0f33e-b352-584b-aac8-2f1f548362c6 |  | note | Wall Types Plan and Wall Type & Setout Plan approved by Kapitol. Check wall types before installation (F/R, Acoustic, Wet Area, PBD etc).
label | e6301aab-b925-5501-8a50-88d26c1134d7 |  | note | Boral installation manual revision 2016 and, Ecowool insulation installation guide. Australian Standard: AS/NZS 2589.1:1997
checkpoint-status |  |  | checkpoint | Caulking
label | 8fd60736-a5fb-54dd-9373-638c7fd77905 |  | note | Boral installation manual revision 2016 Australian Standard: AS 1530.4-2014, AS4072.1-2005, AS1157-1972
checkpoint-status |  |  | checkpoint | Check insulation in walls
label | 98c85149-4708-5325-9a1c-d30454d1704c |  | note | Wall Types Plan and Wall Type & Setout Plan approved by Kapitol. Ecowool Installation Guidelines Australian Standard: AS/NZS 4859:1 – 2018, AS/NZS 1530.3 : 1999, AS/NZS1530 Part 1: 1994
checkpoint-status |  |  | checkpoint | Stopping to walls
label | df463a4e-d871-59cb-a47e-f0bcc83d6e74 |  | note | Boral installation manual revision 2016 Australian Standard: AS/NZS 2589.1:1997
checkpoint-status |  |  | checkpoint | Sanding to walls
label | eeaa1778-951a-562f-aaf5-7334aab1d6e2 |  | note | Boral installation manual revision 2016 Australian Standard: AS/NZS 2589.1:1997
checkpoint-status |  |  | checkpoint | Clean up
label | 1ebf5441-dbdd-50b9-9501-706140a15e09 |  | note | Waste all cleaned. Tools and materials placed well.
checkpoint-status |  |  | checkpoint | Check walls for patching
label | a22ecc9e-c990-5b32-87cc-8faba2a221ab |  | note | Wall Types Plan and Wall Type & Setout Plan approved by Kapitol.
checkpoint-status |  |  | checkpoint | Materials Receipt Inspection
label | ffe6f776-4716-50f0-991c-35efec085e2f |  | note | Refer to ITP No: 5 Incoming Goods
checkpoint-status |  |  | checkpoint | Kapitol Group Acknowledgment of Works
holdpoint |  |  | signoff | Request Sign Off
checklist-flat |  |  | checklist | ITP 04 - Suspended Ceiling Revision |  |  |  |  | Yes | ITP 04 - Suspended Ceiling Revision | 15d6d1f0-b203-47f7-8a99-7235c898d25a
checkpoint-status |  |  | checkpoint | Frame ceilings
label | 565bf082-2c4d-54cb-b884-ab161de99ef6 |  | note | Reflected Ceiling Plan approved by Kapitol. Studco installation guide. Australian Standard AS/NZS 2785:2000
checkpoint-status |  |  | checkpoint | Bulkhead framing
label | 6d4ec3b5-1a95-5d2e-a200-c6e706e88767 |  | note | Reflected Ceiling Plan approved by Kapitol. Studco installation guide. Australian Standard AS/NZS 2785:2000
checkpoint-status |  |  | checkpoint | Trim out access panels
label | c402f676-bdf2-5166-90ed-77d87f5b2787 |  | note | Reflected Ceiling Plan approved by Kapitol. Studco installation guide. Australian Standard - AS1530.4:2014
checkpoint-status |  |  | checkpoint | Insulation to ceilings
label | 116c1342-2837-5ffd-a661-563c034d979f |  | note | Reflected Ceiling Plan approved by Kapitol. Ecowool insulation installation guide Acoustic Specification approved by
label | 062e2a36-1d8a-5d69-87ef-4c6fc25533aa |  | note | SLR Global Environmental Solutions Australian Standard: AS/NZS 4859:1 – 2018, AS/NZS 1530.3 : 1999, AS/NZS1530 Part 1: 1994
checkpoint-status |  |  | checkpoint | Service Check for pre installation of sheets
label | e6ade3ac-23fc-53ab-a673-61cbd570225b |  | note | All service checklists are signed off by relevant trades
label | 870bf51b-899e-5fae-95fb-595deee26cbc |  | note | Central Equity and Building Surveyor Sign Off's attached below
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | Sheets to ceiling
label | ee1a8eb4-6b1f-5dc0-b629-983362c30b7f |  | note | Reflected Ceiling Plan approved by Kapitol. Acoustic Specification approved by SLR Global Environmental Solutions Australian Standard AS/NZS 2785:2000
checkpoint-status |  |  | checkpoint | Stopping to ceilings
label | 6f73c7fa-9192-5745-b96e-348916611672 |  | note | Boral installation manual revision 2016. Australian Standard AS/NZS 2785:2000
checkpoint-status |  |  | checkpoint | Sanding to ceilings
label | bc39ecbd-fcc7-5ff3-9a73-2dada2d7c298 |  | note | Boral installation manual revision 2016. Australian Standard AS/NZS 2785:2000
checkpoint-status |  |  | checkpoint | Fit access hatch frame
label | f7156664-4b66-541a-aeff-fb639d4f9c65 |  | note | Reflected Ceiling Plan approved by Kapitol. Australian Standard - AS1530.4:2014
checkpoint-status |  |  | checkpoint | Cut out for lights
label | d300f33d-9676-5a42-846d-1b2818f44c82 |  | note | Reflected Ceiling Plan approved by Kapitol.
checkpoint-status |  |  | checkpoint | Clean up
label | a8172b59-4e8c-51a8-881d-20bf53ec0af9 |  | note | Waste all cleaned. Tools and materials placed well.
checkpoint-status |  |  | checkpoint | Check ceilings for patching
label | 51e4eb40-d9d7-595b-bf10-5387217f18a1 |  | note | Reflected Ceiling Plan approved by Kapitol.
checkpoint-status |  |  | checkpoint | Materials Receipt Inspection
label | 2e38fd0a-ffbc-556e-aacf-7a580fcc9297 |  | note | Refer to ITP No: 5 Incoming Goods
checkpoint-status |  |  | checkpoint | Kapitol Group Acknowledgment of Works
holdpoint |  |  | signoff | Request Sign Off
checklist-flat |  |  | checklist | ITP 02 - Speedpanel |  |  |  |  | Yes | ITP 02 - Speedpanel | 6ab90f66-950a-43bb-8101-87efa3a1d305
checkpoint-status |  |  | checkpoint | Set out Speedpanel walls
label | b5e797e5-7284-5e62-87ea-783de2c8f821 |  | note | Wall Type and Wall types & Setout drawings approved by Kapitol and Architectural Specification
label | 6a431812-b412-5421-8cea-f76694da0c18 |  | note | Speedpanel installation guide revision 1. Australian Standard AS1530.4
checkpoint-status |  |  | checkpoint | Install Speedpanel
label | 6b421474-59f2-5eb9-9da0-52709e588939 |  | note | Wall Type and Wall types & Setout drawings approved by Kapitol and Architectural Specification
label | 06c60769-0b00-587c-8fe6-c11f66755a57 |  | note | Speedpanel installation guide revision 1. Australian Standard AS1530.4
checkpoint-status |  |  | checkpoint | Caulking
label | fb53785d-5bed-544a-9084-e38f5d78b633 |  | note | Speedpanel installation guide revision 1 Australian Standard AS1530.4
checkpoint-status |  |  | checkpoint | Clean up
label | b7f1b952-4c4d-5b66-96d9-b30f116b56ab |  | note | Waste all cleaned. Tools and materials placed well.
checkpoint-status |  |  | checkpoint | Materials Receipt Inspection
label | 2d897fc5-0675-5ffe-9f86-42c70259a235 |  | note | Refer to ITP No: 5 Incoming Goods
checkpoint-status |  |  | checkpoint | Kapitol Group Acknowledgment of Works
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | ITP 05 - Incoming Goods |  |  |  |  | Yes | ITP 05 - Incoming Goods | b7525990-b560-470f-a352-4c9fabb0d8b3
checkpoint-status |  |  | checkpoint | Check the items
label | f9b7e3d6-3cca-5141-b2b0-6647912903c4 |  | note | • The items received match the description on the order • Appearance of master carton and unit package is intact • The items are not damaged/deteriorative/wet • The items are not dirty/dusty
checkpoint-status |  |  | checkpoint | Check Quantity
label | d277d515-7d9c-5357-a454-c11b4b676be4 |  | note | • The correct items were shipped • No items are missing • Quantity of items received matches quantity indicated on invoice • Quantity of items received matches quantity requested on order
checkpoint-status |  |  | checkpoint | Check the label
label | 462f79c3-0365-566c-9f68-a7da8dddc159 |  | note | • Manufacturer/Distributor's name is not missing • "upwards", "moisture proof" marking or label is not missing • Warning statement is not missing
checkpoint-status |  |  | checkpoint | Material Receipt Inspection
label | d388a812-3bd2-5d95-a927-8e223778a736 |  | note | • Foreman/Leading Hand to keep a record for all material delivery receipt
checkpoint-status |  |  | checkpoint | Kapitol Group Acknowledgment of Works
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | ITP 01 - Rigid Board |  |  |  |  | Yes | ITP 01 - Rigid Board | dc4819ee-03e6-4471-9be0-85c62a44e37c
checkpoint-status |  |  | checkpoint | Set out Rigid Board
label | 39c00b11-1723-599c-888c-9eef81bd40a1 |  | note | Reflected Ceiling Plan and JV3 report provided by Wood&Grieve Engineers and Kapitol. Australia Standard AS/NZS 4859.1:2018
checkpoint-status |  |  | checkpoint | Install Rigid Board
label | ae221eac-84bf-5531-a88e-49d60de6641d |  | note | Reflected Ceiling Plan and JV3 report provided by Wood&Grieve Engineers and Kapitol. Australia Standard AS/NZS 4859.1:2018
checkpoint-status |  |  | checkpoint | Tape & Seal
label | 970c76da-b7cd-51cd-9f30-460036d85351 |  | note | Rigid Board installation guide and Australia Standard AS/NZS 4859.1:2018
checkpoint-status |  |  | checkpoint | Clean up
label | 7b18ab29-f401-5c3c-bbcc-102158da39d1 |  | note | Waste all cleaned. Tools and materials placed well.
checkpoint-status |  |  | checkpoint | Kapitol Group Acknowledgment of Works
holdpoint |  |  | signoff | Request Signoff