## Sheet1
323 e Huia road | Titrangi
Ground Floor
Kitchennete
|  |  |  | Kitchen Sink | First Fix Checklist
Guest Bathroom
|  |  | Toilet | Toilet checklist
|  |  | Shower | Showercheclist
|  |  | Hand Basin | First Fix Checklist
Powder Room
|  |  | Toilet | Toiet checklist
|  |  | Hand basin | First Fix Checklist
Main Bathroom
|  |  | Bath | Bath checklist
|  |  | Shower | Shower checklist
|  |  | Toilet | toilet checklist
|  |  | Double Hand basin | First Fix Checklist
Master Ensuite
|  |  | Bath | Bath checklist
|  |  | Shower | shower checklist
|  |  | Toilet | toilet checklist
|  |  | Double Hand basin | First Fix Checklist
Scullery
|  |  | Sink | First Fix Checklist
Kitchen
|  |  | sink | First Fix Checklist
|  |  | zenith | Photo
|  |  | dishwasher | Photo
|  |  | fridge | Photo
Laundry
|  |  | Sink | First Fix Checklist
|  |  | Washing Machine | Photo
Other
|  |  | Hose taps | First Fix Checklist
|  |  | Hot Water Cylinder | Cylider Checklist
Pool Bathroom
|  |  | Toilet | Toilet Check list
|  |  | Sink | First Fix Checklist
|  |  | Shower | Shower Checklist

## Sheet2
Drainage Checklist
Is Pipe Sitting On Bedding
Is Pipe Installed To Correct Falls On Plan
Has Pipe Been Photographed For Q + A
Is Pipe Free From Debree
Has Fines Been Installed On Top Of Pipe
First Fix Checklist
Nogging For All Fixtures
Check Plan To Confirm Heights And Centres
Check Water Hammer, Silicone Pipes
Acoustic Lagging
Test All Pipework To 1500Kpa
Hot Water Cylinder Checklist
Cold Feed With Isolator
Hot And Cold Installed
Tundish In
Has Nogs Been Installed For Seismics
Correct Positioning & Heights
Accesible Shower Bathroom Checklist
Set-Out Meets Code
Silicone To Prevent Water Hammer
Test To 1500Kpa
Shower Checklist
Mixer Sticking Out The Correct Length
Mixer Wingback Above 1700 To Prevent Backflow
Toilet Checklist
Wingback Installed To Correct Height
Waste Installed Correct Distance From Wall
Underslung Pvc
Pvc installed To Correct Gradient
Flood Tested (Add Photos Of Test)
Take Photos Of Testing
Downpipes + Decks Checklist
Flanges Installed
Domes Installed
All Through Installed
Stacks + Vents Checklist
Inspection Junction Installed For Testing
Pipe Labels Installed
Mid Level Supports
Write On Test Cap Date Of Test
Acoustic Lagging Checklist
Relevant Pipework Lagged
Lagging Tape Around Joints
Blue Strapping And Buckles Every 1 Metre
Pipe Labels After Lagging
Stormwater Checklist
Relevant Pipework Lagged
Lagging Tape Around Joints
Blue Strapping And Buckles Every 1 Metre
Pipe Labels After Lagging
Pipe Tested For Leaks
Gas Checklist
Pipe Tested To 7Kpa
Pipe Clearly Labelled Gas
Pressure Testing Checklist
Pump Up To 1500kpa Minimum
Take Photos Of Testing