## Project Structure
Folder Structure |  |  |  | Checklists | #NAME?
Site QA
Switchboard's
Plant Room
|  |  | DB 4/3 Ward Fitout | Switchboards
|  |  | DB 4/4 Ward Fitout | Switchboards
|  |  | MCC ESS WEST-2 | Switchboards
Cable Tray
Level 1
|  |  | Areas 1-8 | Cable Tray
|  |  | Areas 9-14 | Cable Tray
|  |  | Areas 25-32 | Cable Tray
First Fix
Level 1
|  |  | 1- Single Delux Bedroom | First Fix Electrical
|  |  | 1a- Ensuite | First Fix Electrical
|  |  | 2- Single Delux Bedroom | First Fix Electrical
|  |  | 2a- Ensuite | First Fix Electrical
|  |  | 3- Single Bedroom | First Fix Electrical
|  |  | 3a- Ensuite | First Fix Electrical
|  |  | 4- Single Bedroom | First Fix Electrical
|  |  | 4a- Ensuite | First Fix Electrical
|  |  | 5- Single Bedroom | First Fix Electrical
|  |  | 5a- Ensuite | First Fix Electrical
|  |  | 6-Single Bedroom | First Fix Electrical
|  |  | 6a- Ensuite | First Fix Electrical
|  |  | 7- Single Bedroom | First Fix Electrical
|  |  | 7a- Ensuite | First Fix Electrical
|  |  | 8- Single Bedroom | First Fix Electrical
|  |  | 8a- Ensuite | First Fix Electrical
|  |  | 9- Double Bedroom | First Fix Electrical
|  |  | 9a- Ensuite | First Fix Electrical
|  |  | 10- Double Bedroom | First Fix Electrical
|  |  | 10a- Ensuite | First Fix Electrical
|  |  | 11- Double Bedroom | First Fix Electrical
|  |  | 11a- Ensuite | First Fix Electrical
|  |  | 12- Double Bedroom | First Fix Electrical
|  |  | 12a- Ensuite | First Fix Electrical
|  |  | 13- Double Bedroom | First Fix Electrical
|  |  | 13a- Ensuite | First Fix Electrical
|  |  | 14- ACC WC | First Fix Electrical
|  |  | 15- Patient Meals | First Fix Electrical
|  |  | 16- Whanau Room | First Fix Electrical
|  |  | 17- Medication Room | First Fix Electrical
|  |  | 18- Dirty Utility | First Fix Electrical
|  |  | 19- Store | First Fix Electrical
|  |  | 20- Linen | First Fix Electrical
|  |  | 21- Linen | First Fix Electrical
|  |  | 22- Resus | First Fix Electrical
|  |  | 23- Equipment Store | First Fix Electrical
|  |  | 24- Cleaners | First Fix Electrical
|  |  | 25- Handover | First Fix Electrical
|  |  | 26- Nurses Station | First Fix Electrical
|  |  | 27- CNM Office | First Fix Electrical
|  |  | 28- Data | First Fix Electrical
|  |  | 29- Staff Locker | First Fix Electrical
|  |  | 30- Staff WC | First Fix Electrical
|  |  | 31- Staff Tea | First Fix Electrical
|  |  | 32- Corridor | First Fix Electrical
Second Fix
Level 1
|  |  | 1- Single Delux Bedroom | Second Fix
|  |  | 1a- Ensuite | Second Fix
|  |  | 2- Single Delux Bedroom | Second Fix
|  |  | 2a- Ensuite | Second Fix
|  |  | 3- Single Bedroom | Second Fix
|  |  | 3a- Ensuite | Second Fix
|  |  | 4- Single Bedroom | Second Fix
|  |  | 4a- Ensuite | Second Fix
|  |  | 5- Single Bedroom | Second Fix
|  |  | 5a- Ensuite | Second Fix
|  |  | 6-Single Bedroom | Second Fix
|  |  | 6a- Ensuite | Second Fix
|  |  | 7- Single Bedroom | Second Fix
|  |  | 7a- Ensuite | Second Fix
|  |  | 8- Single Bedroom | Second Fix
|  |  | 8a- Ensuite | Second Fix
|  |  | 9- Double Bedroom | Second Fix
|  |  | 9a- Ensuite | Second Fix
|  |  | 10- Double Bedroom | Second Fix
|  |  | 10a- Ensuite | Second Fix
|  |  | 11- Double Bedroom | Second Fix
|  |  | 11a- Ensuite | Second Fix
|  |  | 12- Double Bedroom | Second Fix
|  |  | 12a- Ensuite | Second Fix
|  |  | 13- Double Bedroom | Second Fix
|  |  | 13a- Ensuite | Second Fix
|  |  | 14- ACC WC | Second Fix
|  |  | 15- Patient Meals | Second Fix
|  |  | 16- Whanau Room | Second Fix
|  |  | 17- Medication Room | Second Fix
|  |  | 18- Dirty Utility | Second Fix
|  |  | 19- Store | Second Fix
|  |  | 20- Linen | Second Fix
|  |  | 21- Linen | Second Fix
|  |  | 22- Resus | Second Fix
|  |  | 23- Equipment Store | Second Fix
|  |  | 24- Cleaners | Second Fix
|  |  | 25- Handover | Second Fix
|  |  | 26- Nurses Station | Second Fix
|  |  | 27- CNM Office | Second Fix
|  |  | 28- Data | Second Fix
|  |  | 29- Staff Locker | Second Fix
|  |  | 30- Staff WC | Second Fix
|  |  | 31- Staff Tea | Second Fix
|  |  | 32- Corridor | Second Fix
FEL SM Weekly Site Checklist
| 2022-08-08 |  |  | FEL SM Weekly Site Checklist
| 2022-08-15 |  |  | FEL SM Weekly Site Checklist
| 2022-08-22 |  |  | FEL SM Weekly Site Checklist
| 2022-08-29 |  |  | FEL SM Weekly Site Checklist
| 2022-09-05 |  |  | FEL SM Weekly Site Checklist
| 2022-09-12 |  |  | FEL SM Weekly Site Checklist
| 2022-09-19 |  |  | FEL SM Weekly Site Checklist
| 2022-09-26 |  |  | FEL SM Weekly Site Checklist
| 2022-10-03 |  |  | FEL SM Weekly Site Checklist
| 2022-10-10 |  |  | FEL SM Weekly Site Checklist
| 2022-10-17 |  |  | FEL SM Weekly Site Checklist
| 2022-10-24 |  |  | FEL SM Weekly Site Checklist
| 2022-10-31 |  |  | FEL SM Weekly Site Checklist
| 2022-11-07 |  |  | FEL SM Weekly Site Checklist
| 2022-11-14 |  |  | FEL SM Weekly Site Checklist
| 2022-11-21 |  |  | FEL SM Weekly Site Checklist
| 2022-11-28 |  |  | FEL SM Weekly Site Checklist
| 2022-12-05 |  |  | FEL SM Weekly Site Checklist
| 2022-12-12 |  |  | FEL SM Weekly Site Checklist
| 2022-12-19 |  |  | FEL SM Weekly Site Checklist

## First Fix Electrical
type | name
checklist | QA - First Fix
section | Flush Boxes
checkpoint | Height as per plan
checkpoint | Location as per plan
checkpoint | Fire rated boxes installed where necessary
checkpoint | Acoustic boxes installed where necessary
section | Cabling
checkpoint | Power cables installed correctly
checkpoint | Lighting cables installed correctly
checkpoint | Power cables wired from correct RCD location
checkpoint | Power circuits comply with medical regulations
checkpoint | Circuits clearly labelled
checkpoint | Separation between Data and Power at 300mm or as specified
checkpoint | All cables secured via cable ties with ends cut
section | Cable Tray
checkpoint | Minimum 25% spare capacity left on cable tray
section | QA - Lights
checkpoint | Setout Correct
checkpoint | Cabling in correct location
checkpoint | Emergency/ Exit Lighting
checkpoint | Nogging installed for Electrical Services
section | Photos

## Cable Tray
Section | Cable Tray
Checkpoint | Unistrutt Filed & Painted
Checkpoint | Hangers Spaced as Specified
Checkpoint | Correct Size Ladder Installed
Checkpoint | Tray Joined Correctly
Checkpoint | Hangers Sceismicly Restrained as per Design
Checkpoint | Tray Fastened to Hangers
Checkpoint | Correct Anchors used fixing to Ceiling / Walls
Checkpoint | Cable Tray Bonded
section | Photos

## Switchboards
section | Switchboard
checkpoint | Spatial certificate signed if required
checkpoint | Fixings installed in wall correctly if board is wall mounted
checkpoint | All clearances sighted to ensure location is compliant
checkpoint | All cables correctly installed in protection device and earth and neutral bars and fully secured
checkpoint | Cables neatly dressed
checkpoint | Phase tabs on chassy covered
checkpoint | All earths and neutrals labelled to match phase numbers
checkpoint | Switchboard is clean on the inside and outside
checkpoint | Masking blanks installed
checkpoint | DB legend installed
checkpoint | Feisst label on the door installed
section | Photos

## Second Fix Electrical
type | name | values
checklist | QA - Second fix
section | Power Outlets
checkpoint | Correct type installed ( to comply with medical regulations)
checkpoint | Correctly installed with terminations all secured properly
checkpoint | Outlet Installed level
checkpoint | Circuit Tested and results recorded
checkpoint | Description Labelled on the outlet face with vivid and with dymo labeller on cover plate and ensure label is level
section | Light Switches
checkpoint | Correct type installed
checkpoint | Correctly installed with terminations all secured properly
checkpoint | Light switch Installed level
checkpoint | Circuit Tested and results recorded
checkpoint | Description Labelled on the outlet face with vivid and with dymo labeller on cover plate and ensure label is level
section | Light Fixtures
checkpoint | Correct type installed
checkpoint | Correctly installed with terminations all secured properly
checkpoint | Tested for operation
checkpoint | Correctly installed with stainless screws & 90 / 45 angle
section | Photos

## SM Weekly Checklist
type | name
checklist | FEL SM Weekly Site Checklist
section | Monday
checkpoint | Prestart Meeting with Team
checkpoint | Health Check
checkpoint | Review Tasks for the week
checkpoint | Identify Targets Including Hours
checkpoint | Approve hours by 9AM for previous week
checkpoint | Sign off Subcontractor Hours & Submit
checkpoint | Review SWMS
checkpoint | Site Toolbox Meeting
checkpoint | SSSP in Order
section | Tuesday
checkpoint | Follow up outstanding RFI's with PM
section | Wednesday
checkpoint | Review Roadblocks & Follow Up if still unresolved
checkpoint | QAs up to date
section | Thursday
checkpoint | Weekly planner filled out for week ahead
checkpoint | Roadblocks identified and actioned
checkpoint | Materials organized for week ahead
checkpoint | Plans printed with any relevant notes added
section | Friday
checkpoint | Submit Toolbox minutes to main contractor and FEL office
checkpoint | Job Cards up to date and submitted
checkpoint | Team tasks for week ahead filled out on whiteboard