## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | CST - S - Completion Documents |  |  |  |  | Yes | CST - S - Completion Documents | 36034eaf-df7a-4806-be63-2f5125e8c033
checkpoint-status |  |  | checkpoint | All relevant Compliance Documentation completed and attached above
button | 8e73a666-4ca3-5890-bbed-ac874faa0b0f |  | button | LBP Memorandum/ Record of works filled out, signed and attached | Yes, N/A
button | 4d86bf7d-8373-5b3d-9195-80dc0b2b045a |  | button | Any Additional Compliance Documentation - Completed and Attached | Yes, N/A
label | 82150eb3-2346-54f6-a3db-bf166bfdd460 |  | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint |  |  | signoff | Request Sign Off
checklist-flat |  |  | checklist | Post - S - Painting |  |  |  |  | Yes | Post - S - Painting | 4340f366-7e0c-4391-ac1a-48a68f7bf96b
checkpoint-status |  |  | checkpoint | Any prep work & sealer coat completed
checkpoint-status |  |  | checkpoint | Light inspection completed and approved to continue
checkpoint-status |  |  | checkpoint | Any additional prep work completed (stopping, filling, sanding etc)
checkpoint-status |  |  | checkpoint | First top coat completed
checkpoint-status |  |  | checkpoint | Additional top coat applications completed
checkpoint-status |  |  | checkpoint | Final coat completed as per specifications
checkpoint-status |  |  | checkpoint | Painting work completed - specified level of finish achieved
holdpoint |  |  | signoff | Request Sign-Off