## Stage 1 - B01
|  |  | Project Breakdown |  | Checklist
Francis Norton - Kevin Hickman
Stage 1 - B01
Ground Floor - Area A
Café
|  |  |  | Pre-populate | FC - S - Hatches
|  |  |  | Pre-populate | FC - S - Flashing Installation
|  |  |  | Pre-populate | FC- S - Soffits
|  |  |  | Pre-populate | POST - S - Installation of Aluminium Joinery
|  |  |  | Pre-populate | FC - S - Windows, Sliders and Sealants
|  |  |  | Pre-populate | POST - S - Fire door installation
|  |  |  | Pre-populate | POST - S - Internal door installation
|  |  |  | Pre-populate | POST- S - Handrails
|  |  |  | Pre-populate | POST - S - Hardware Installation
|  |  |  | Pre-populate | POST - S - Skirting/Architraves & Trims
|  |  |  | Pre-populate | POST - S -Installation of Internal carpentry items - Bathroom
|  |  |  | Pre-populate | FC - S - Brick Lintel bars installation
Toilet Lobby
|  |  |  | Pre-populate | FC - S - Hatches
|  |  |  | Pre-populate | FC - S - Flashing Installation
|  |  |  | Pre-populate | FC- S - Soffits
|  |  |  | Pre-populate | POST - S - Installation of Aluminium Joinery
|  |  |  | Pre-populate | FC - S - Windows, Sliders and Sealants
|  |  |  | Pre-populate | POST - S - Fire door installation
|  |  |  | Pre-populate | POST - S - Internal door installation
|  |  |  | Pre-populate | POST- S - Handrails
|  |  |  | Pre-populate | POST - S - Hardware Installation
|  |  |  | Pre-populate | POST - S - Skirting/Architraves & Trims
|  |  |  | Pre-populate | POST - S -Installation of Internal carpentry items - Bathroom
FC - S - Brick Lintel bars installation
ACC WC
|  |  |  | Pre-populate | FC - S - Hatches
|  |  |  | Pre-populate | FC - S - Flashing Installation
|  |  |  | Pre-populate | FC- S - Soffits
|  |  |  | Pre-populate | POST - S - Installation of Aluminium Joinery
|  |  |  | Pre-populate | FC - S - Windows, Sliders and Sealants
|  |  |  | Pre-populate | POST - S - Fire door installation
|  |  |  | Pre-populate | POST - S - Internal door installation
|  |  |  | Pre-populate | POST- S - Handrails
|  |  |  | Pre-populate | POST - S - Hardware Installation
|  |  |  | Pre-populate | POST - S - Skirting/Architraves & Trims
|  |  |  | Pre-populate | POST - S -Installation of Internal carpentry items - Bathroom
|  |  |  | Pre-populate | FC - S - Brick Lintel bars installation
WC
|  |  |  | Pre-populate | FC - S - Hatches
|  |  |  | Pre-populate | FC - S - Flashing Installation
|  |  |  | Pre-populate | FC- S - Soffits
|  |  |  | Pre-populate | POST - S - Installation of Aluminium Joinery
|  |  |  | Pre-populate | FC - S - Windows, Sliders and Sealants
|  |  |  | Pre-populate | POST - S - Fire door installation
|  |  |  | Pre-populate | POST - S - Internal door installation
|  |  |  | Pre-populate | POST- S - Handrails
|  |  |  | Pre-populate | POST - S - Hardware Installation
|  |  |  | Pre-populate | POST - S - Skirting/Architraves & Trims
|  |  |  | Pre-populate | POST - S -Installation of Internal carpentry items - Bathroom
|  |  |  | Pre-populate | FC - S - Brick Lintel bars installation
WC
|  |  |  | Pre-populate | FC - S - Hatches
|  |  |  | Pre-populate | FC - S - Flashing Installation
|  |  |  | Pre-populate | FC- S - Soffits
|  |  |  | Pre-populate | POST - S - Installation of Aluminium Joinery
|  |  |  | Pre-populate | FC - S - Windows, Sliders and Sealants
|  |  |  | Pre-populate | POST - S - Fire door installation
|  |  |  | Pre-populate | POST - S - Internal door installation
|  |  |  | Pre-populate | POST- S - Handrails
|  |  |  | Pre-populate | POST - S - Hardware Installation
|  |  |  | Pre-populate | POST - S - Skirting/Architraves & Trims
|  |  |  | Pre-populate | POST - S -Installation of Internal carpentry items - Bathroom
|  |  |  | Pre-populate | FC - S - Brick Lintel bars installation
Sales Office 1
|  |  |  | Pre-populate | FC - S - Hatches
|  |  |  | Pre-populate | FC - S - Flashing Installation
|  |  |  | Pre-populate | FC- S - Soffits
|  |  |  | Pre-populate | POST - S - Installation of Aluminium Joinery
|  |  |  | Pre-populate | FC - S - Windows, Sliders and Sealants
|  |  |  | Pre-populate | POST - S - Fire door installation
|  |  |  | Pre-populate | POST - S - Internal door installation
|  |  |  | Pre-populate | POST- S - Handrails
|  |  |  | Pre-populate | POST - S - Hardware Installation
|  |  |  | Pre-populate | POST - S - Skirting/Architraves & Trims
|  |  |  | Pre-populate | POST - S -Installation of Internal carpentry items - Bathroom
|  |  |  | Pre-populate | FC - S - Brick Lintel bars installation
Sales Office 2
|  |  |  | Pre-populate | FC - S - Hatches
|  |  |  | Pre-populate | FC - S - Flashing Installation
|  |  |  | Pre-populate | FC- S - Soffits
|  |  |  | Pre-populate | POST - S - Installation of Aluminium Joinery
|  |  |  | Pre-populate | FC - S - Windows, Sliders and Sealants
|  |  |  | Pre-populate | POST - S - Fire door installation
|  |  |  | Pre-populate | POST - S - Internal door installation
|  |  |  | Pre-populate | POST- S - Handrails
|  |  |  | Pre-populate | POST - S - Hardware Installation
|  |  |  | Pre-populate | POST - S - Skirting/Architraves & Trims
|  |  |  | Pre-populate | POST - S -Installation of Internal carpentry items - Bathroom
|  |  |  | Pre-populate | FC - S - Brick Lintel bars installation
Cleaner Stairs
|  |  |  | Pre-populate | FC - S - Hatches
|  |  |  | Pre-populate | FC - S - Flashing Installation
|  |  |  | Pre-populate | FC- S - Soffits
|  |  |  | Pre-populate | POST - S - Installation of Aluminium Joinery
|  |  |  | Pre-populate | FC - S - Windows, Sliders and Sealants
|  |  |  | Pre-populate | POST - S - Fire door installation
|  |  |  | Pre-populate | POST - S - Internal door installation
|  |  |  | Pre-populate | POST- S - Handrails
|  |  |  | Pre-populate | POST - S - Hardware Installation
|  |  |  | Pre-populate | POST - S - Skirting/Architraves & Trims
|  |  |  | Pre-populate | POST - S -Installation of Internal carpentry items - Bathroom
|  |  |  | Pre-populate | FC - S - Brick Lintel bars installation
Stair 1
|  |  |  | Pre-populate | FC - S - Hatches
|  |  |  | Pre-populate | FC - S - Flashing Installation
|  |  |  | Pre-populate | FC- S - Soffits
|  |  |  | Pre-populate | POST - S - Installation of Aluminium Joinery
|  |  |  | Pre-populate | FC - S - Windows, Sliders and Sealants
|  |  |  | Pre-populate | POST - S - Fire door installation
|  |  |  | Pre-populate | POST - S - Internal door installation
|  |  |  | Pre-populate | POST- S - Handrails
|  |  |  | Pre-populate | POST - S - Hardware Installation
|  |  |  | Pre-populate | POST - S - Skirting/Architraves & Trims
|  |  |  | Pre-populate | POST - S -Installation of Internal carpentry items - Bathroom
|  |  |  | Pre-populate | FC - S - Brick Lintel bars installation
Entry
|  |  |  | Pre-populate | FC - S - Hatches
|  |  |  | Pre-populate | FC - S - Flashing Installation
|  |  |  | Pre-populate | FC- S - Soffits
|  |  |  | Pre-populate | POST - S - Installation of Aluminium Joinery
|  |  |  | Pre-populate | FC - S - Windows, Sliders and Sealants
|  |  |  | Pre-populate | POST - S - Fire door installation
|  |  |  | Pre-populate | POST - S - Internal door installation
|  |  |  | Pre-populate | POST- S - Handrails
|  |  |  | Pre-populate | POST - S - Hardware Installation
|  |  |  | Pre-populate | POST - S - Skirting/Architraves & Trims
|  |  |  | Pre-populate | POST - S -Installation of Internal carpentry items - Bathroom
|  |  |  | Pre-populate | FC - S - Brick Lintel bars installation
Reception Desks
|  |  |  | Pre-populate | FC - S - Hatches
|  |  |  | Pre-populate | FC - S - Flashing Installation
|  |  |  | Pre-populate | FC- S - Soffits
|  |  |  | Pre-populate | POST - S - Installation of Aluminium Joinery
|  |  |  | Pre-populate | FC - S - Windows, Sliders and Sealants
|  |  |  | Pre-populate | POST - S - Fire door installation
|  |  |  | Pre-populate | POST - S - Internal door installation
|  |  |  | Pre-populate | POST- S - Handrails
|  |  |  | Pre-populate | POST - S - Hardware Installation
|  |  |  | Pre-populate | POST - S - Skirting/Architraves & Trims
|  |  |  | Pre-populate | POST - S -Installation of Internal carpentry items - Bathroom
|  |  |  | Pre-populate | FC - S - Brick Lintel bars installation
Managers
|  |  |  | Pre-populate | FC - S - Hatches
|  |  |  | Pre-populate | FC - S - Flashing Installation
|  |  |  | Pre-populate | FC- S - Soffits
|  |  |  | Pre-populate | POST - S - Installation of Aluminium Joinery
|  |  |  | Pre-populate | FC - S - Windows, Sliders and Sealants
|  |  |  | Pre-populate | POST - S - Fire door installation
|  |  |  | Pre-populate | POST - S - Internal door installation
|  |  |  | Pre-populate | POST- S - Handrails
|  |  |  | Pre-populate | POST - S - Hardware Installation
|  |  |  | Pre-populate | POST - S - Skirting/Architraves & Trims
|  |  |  | Pre-populate | POST - S -Installation of Internal carpentry items - Bathroom
|  |  |  | Pre-populate | FC - S - Brick Lintel bars installation
General Office
|  |  |  | Pre-populate | FC - S - Hatches
|  |  |  | Pre-populate | FC - S - Flashing Installation
|  |  |  | Pre-populate | FC- S - Soffits
|  |  |  | Pre-populate | POST - S - Installation of Aluminium Joinery
|  |  |  | Pre-populate | FC - S - Windows, Sliders and Sealants
|  |  |  | Pre-populate | POST - S - Fire door installation
|  |  |  | Pre-populate | POST - S - Internal door installation
|  |  |  | Pre-populate | POST- S - Handrails
|  |  |  | Pre-populate | POST - S - Hardware Installation
|  |  |  | Pre-populate | POST - S - Skirting/Architraves & Trims
|  |  |  | Pre-populate | POST - S -Installation of Internal carpentry items - Bathroom
|  |  |  | Pre-populate | FC - S - Brick Lintel bars installation
Meeting Room
|  |  |  | Pre-populate | FC - S - Hatches
|  |  |  | Pre-populate | FC - S - Flashing Installation
|  |  |  | Pre-populate | FC- S - Soffits
|  |  |  | Pre-populate | POST - S - Installation of Aluminium Joinery
|  |  |  | Pre-populate | FC - S - Windows, Sliders and Sealants
|  |  |  | Pre-populate | POST - S - Fire door installation
|  |  |  | Pre-populate | POST - S - Internal door installation
|  |  |  | Pre-populate | POST- S - Handrails
|  |  |  | Pre-populate | POST - S - Hardware Installation
|  |  |  | Pre-populate | POST - S - Skirting/Architraves & Trims
|  |  |  | Pre-populate | POST - S -Installation of Internal carpentry items - Bathroom
|  |  |  | Pre-populate | FC - S - Brick Lintel bars installation
Valve Room
|  |  |  | Pre-populate | FC - S - Hatches
|  |  |  | Pre-populate | FC - S - Flashing Installation
|  |  |  | Pre-populate | FC- S - Soffits
|  |  |  | Pre-populate | POST - S - Installation of Aluminium Joinery
|  |  |  | Pre-populate | FC - S - Windows, Sliders and Sealants
|  |  |  | Pre-populate | POST - S - Fire door installation
|  |  |  | Pre-populate | POST - S - Internal door installation
|  |  |  | Pre-populate | POST- S - Handrails
|  |  |  | Pre-populate | POST - S - Hardware Installation
|  |  |  | Pre-populate | POST - S - Skirting/Architraves & Trims
|  |  |  | Pre-populate | POST - S -Installation of Internal carpentry items - Bathroom
|  |  |  | Pre-populate | FC - S - Brick Lintel bars installation
Corridor - Grid 12-15
|  |  |  | Pre-populate | FC - S - Hatches
|  |  |  | Pre-populate | FC - S - Flashing Installation
|  |  |  | Pre-populate | FC- S - Soffits
|  |  |  | Pre-populate | POST - S - Installation of Aluminium Joinery
|  |  |  | Pre-populate | FC - S - Windows, Sliders and Sealants
|  |  |  | Pre-populate | POST - S - Fire door installation
|  |  |  | Pre-populate | POST - S - Internal door installation
|  |  |  | Pre-populate | POST- S - Handrails
|  |  |  | Pre-populate | POST - S - Hardware Installation
|  |  |  | Pre-populate | POST - S - Skirting/Architraves & Trims
|  |  |  | Pre-populate | POST - S -Installation of Internal carpentry items - Bathroom
|  |  |  | Pre-populate | FC - S - Brick Lintel bars installation
Corridor - Grid 15-22
|  |  |  | Pre-populate | FC - S - Hatches
|  |  |  | Pre-populate | FC - S - Flashing Installation
|  |  |  | Pre-populate | FC- S - Soffits
|  |  |  | Pre-populate | POST - S - Installation of Aluminium Joinery
|  |  |  | Pre-populate | FC - S - Windows, Sliders and Sealants
|  |  |  | Pre-populate | POST - S - Fire door installation
|  |  |  | Pre-populate | POST - S - Internal door installation
|  |  |  | Pre-populate | POST- S - Handrails
|  |  |  | Pre-populate | POST - S - Hardware Installation
|  |  |  | Pre-populate | POST - S - Skirting/Architraves & Trims
|  |  |  | Pre-populate | POST - S -Installation of Internal carpentry items - Bathroom
|  |  |  | Pre-populate | FC - S - Brick Lintel bars installation
Lift 1
|  |  |  | Pre-populate | FC - S - Hatches
|  |  |  | Pre-populate | FC - S - Flashing Installation
|  |  |  | Pre-populate | FC- S - Soffits
|  |  |  | Pre-populate | POST - S - Installation of Aluminium Joinery
|  |  |  | Pre-populate | FC - S - Windows, Sliders and Sealants
|  |  |  | Pre-populate | POST - S - Fire door installation
|  |  |  | Pre-populate | POST - S - Internal door installation
|  |  |  | Pre-populate | POST- S - Handrails
|  |  |  | Pre-populate | POST - S - Hardware Installation
|  |  |  | Pre-populate | POST - S - Skirting/Architraves & Trims
|  |  |  | Pre-populate | POST - S -Installation of Internal carpentry items - Bathroom
|  |  |  | Pre-populate | FC - S - Brick Lintel bars installation
Lift 2
|  |  |  | Pre-populate | FC - S - Hatches
|  |  |  | Pre-populate | FC - S - Flashing Installation
|  |  |  | Pre-populate | FC- S - Soffits
|  |  |  | Pre-populate | POST - S - Installation of Aluminium Joinery
|  |  |  | Pre-populate | FC - S - Windows, Sliders and Sealants
|  |  |  | Pre-populate | POST - S - Fire door installation
|  |  |  | Pre-populate | POST - S - Internal door installation
|  |  |  | Pre-populate | POST- S - Handrails
|  |  |  | Pre-populate | POST - S - Hardware Installation
|  |  |  | Pre-populate | POST - S - Skirting/Architraves & Trims
|  |  |  | Pre-populate | POST - S -Installation of Internal carpentry items - Bathroom
|  |  |  | Pre-populate | FC - S - Brick Lintel bars installation
Flat Lift
|  |  |  | Pre-populate | FC - S - Hatches
|  |  |  | Pre-populate | FC - S - Flashing Installation
|  |  |  | Pre-populate | FC- S - Soffits
|  |  |  | Pre-populate | POST - S - Installation of Aluminium Joinery
|  |  |  | Pre-populate | FC - S - Windows, Sliders and Sealants
|  |  |  | Pre-populate | POST - S - Fire door installation
|  |  |  | Pre-populate | POST - S - Internal door installation
|  |  |  | Pre-populate | POST- S - Handrails
|  |  |  | Pre-populate | POST - S - Hardware Installation
|  |  |  | Pre-populate | POST - S - Skirting/Architraves & Trims
|  |  |  | Pre-populate | POST - S -Installation of Internal carpentry items - Bathroom
|  |  |  | Pre-populate | FC - S - Brick Lintel bars installation
Chemical Store
|  |  |  | Pre-populate | FC - S - Hatches
|  |  |  | Pre-populate | FC - S - Flashing Installation
|  |  |  | Pre-populate | FC- S - Soffits
|  |  |  | Pre-populate | POST - S - Installation of Aluminium Joinery
|  |  |  | Pre-populate | FC - S - Windows, Sliders and Sealants
|  |  |  | Pre-populate | POST - S - Fire door installation
|  |  |  | Pre-populate | POST - S - Internal door installation
|  |  |  | Pre-populate | POST- S - Handrails
|  |  |  | Pre-populate | POST - S - Hardware Installation
|  |  |  | Pre-populate | POST - S - Skirting/Architraves & Trims
|  |  |  | Pre-populate | POST - S -Installation of Internal carpentry items - Bathroom
|  |  |  | Pre-populate | FC - S - Brick Lintel bars installation
Inward Goods
|  |  |  | Pre-populate | FC - S - Hatches
|  |  |  | Pre-populate | FC - S - Flashing Installation
|  |  |  | Pre-populate | FC- S - Soffits
|  |  |  | Pre-populate | POST - S - Installation of Aluminium Joinery
|  |  |  | Pre-populate | FC - S - Windows, Sliders and Sealants
|  |  |  | Pre-populate | POST - S - Fire door installation
|  |  |  | Pre-populate | POST - S - Internal door installation
|  |  |  | Pre-populate | POST- S - Handrails
|  |  |  | Pre-populate | POST - S - Hardware Installation
|  |  |  | Pre-populate | POST - S - Skirting/Architraves & Trims
|  |  |  | Pre-populate | POST - S -Installation of Internal carpentry items - Bathroom
|  |  |  | Pre-populate | FC - S - Brick Lintel bars installation
Buggy Room
|  |  |  | Pre-populate | FC - S - Hatches
|  |  |  | Pre-populate | FC - S - Flashing Installation
|  |  |  | Pre-populate | FC- S - Soffits
|  |  |  | Pre-populate | POST - S - Installation of Aluminium Joinery
|  |  |  | Pre-populate | FC - S - Windows, Sliders and Sealants
|  |  |  | Pre-populate | POST - S - Fire door installation
|  |  |  | Pre-populate | POST - S - Internal door installation
|  |  |  | Pre-populate | POST- S - Handrails
|  |  |  | Pre-populate | POST - S - Hardware Installation
|  |  |  | Pre-populate | POST - S - Skirting/Architraves & Trims
|  |  |  | Pre-populate | POST - S -Installation of Internal carpentry items - Bathroom
|  |  |  | Pre-populate | FC - S - Brick Lintel bars installation
Comms Room
|  |  |  | Pre-populate | FC - S - Hatches
|  |  |  | Pre-populate | FC - S - Flashing Installation
|  |  |  | Pre-populate | FC- S - Soffits
|  |  |  | Pre-populate | POST - S - Installation of Aluminium Joinery
|  |  |  | Pre-populate | FC - S - Windows, Sliders and Sealants
|  |  |  | Pre-populate | POST - S - Fire door installation
|  |  |  | Pre-populate | POST - S - Internal door installation
|  |  |  | Pre-populate | POST- S - Handrails
|  |  |  | Pre-populate | POST - S - Hardware Installation
|  |  |  | Pre-populate | POST - S - Skirting/Architraves & Trims
|  |  |  | Pre-populate | POST - S -Installation of Internal carpentry items - Bathroom
|  |  |  | Pre-populate | FC - S - Brick Lintel bars installation
Waste Room
|  |  |  | Pre-populate | FC - S - Hatches
|  |  |  | Pre-populate | FC - S - Flashing Installation
|  |  |  | Pre-populate | FC- S - Soffits
|  |  |  | Pre-populate | POST - S - Installation of Aluminium Joinery
|  |  |  | Pre-populate | FC - S - Windows, Sliders and Sealants
|  |  |  | Pre-populate | POST - S - Fire door installation
|  |  |  | Pre-populate | POST - S - Internal door installation
|  |  |  | Pre-populate | POST- S - Handrails
|  |  |  | Pre-populate | POST - S - Hardware Installation
|  |  |  | Pre-populate | POST - S - Skirting/Architraves & Trims
|  |  |  | Pre-populate | POST - S -Installation of Internal carpentry items - Bathroom
|  |  |  | Pre-populate | FC - S - Brick Lintel bars installation
MSB Room
|  |  |  | Pre-populate | FC - S - Hatches
|  |  |  | Pre-populate | FC - S - Flashing Installation
|  |  |  | Pre-populate | FC- S - Soffits
|  |  |  | Pre-populate | POST - S - Installation of Aluminium Joinery
|  |  |  | Pre-populate | FC - S - Windows, Sliders and Sealants
|  |  |  | Pre-populate | POST - S - Fire door installation
|  |  |  | Pre-populate | POST - S - Internal door installation
|  |  |  | Pre-populate | POST- S - Handrails
|  |  |  | Pre-populate | POST - S - Hardware Installation
|  |  |  | Pre-populate | POST - S - Skirting/Architraves & Trims
|  |  |  | Pre-populate | POST - S -Installation of Internal carpentry items - Bathroom
|  |  |  | Pre-populate | FC - S - Brick Lintel bars installation

## Checklist
type | name | values
Checklist | FC - S - Exterior Timber Framing
checkpoint | Setout completed, checked & accurate (no clashes & wall locations clearly marked)
checkpoint | Framing Dimensions/ locations checked & accurate (openings considered where applicable)
checkpoint | All frames have been installed square, straighn and plumb
checkpoint | DPC installed (if required) correctly
checkpoint | Fixings are correct to specification including any seismic/bracing requirements (attach relevant photos)
checkpoint | All Nogs (Service/Specialty) & penetrations - installed, checked & correct (consider acoustic & fire rating requirements)
checkpoint | All timber framing completed correctly to specification & within tolerance in respective area(s)
holdpoint | Request sign off
type | name | values
Checklist | FC - S - External Envelope
checkpoint | Eco ply taped nailing checked
label | Supplied & installed by others
checkpoint | RAB board fixing and spacings checked in accordance with manufacturers specs (photo attached)
checkpoint | Fire strip installed (Photos attached)
checkpoint | Soffit checked and accurate (Photos attached)
checkpoint | Garage reveals checked and accurate (Photos attached)
checkpoint | DPC installed checked and accurate (Photos attached)
holdpoint | Request sign off
type | name | values
Checklist | PRE - S - Timber Framing
checkpoint | Building square placed in all internal corners
checkpoint | All walls area parallel
checkpoint | All door opening correct
checkpoint | Check levels and straight edges
checkpoint | All DPC installed to walls
checkpoint | All internal corners have appropriate fixings for plasterboard
checkpoint | Appropriate deflection head gap
checkpoint | Timber frame installation completed and acceptable
holdpoint | Request sign off
type | name | values
Checklist | ST - S - Roof structure - Timber Trusses
checkpoint | Truss hardware completed as specified
checkpoint | All fixings in place
checkpoint | Truss seating checked and accurate
checkpoint | Tile battens installed acceptable
checkpoint | Underlay completed and acceptable
checkpoint | Pre-tile checks completed and no issues identified
checkpoint | Load tiles completed and acceptable
checkpoint | Installation and recheck completed and no issues identified
checkpoint | Lay capping completed and acceptable
checkpoint | Ridges installed and acceptable
checkpoint | Facia gutters installed and acceptable
checkpoint | Trusses are installed correctly and acceptable
holdpoint | Request sign off
type | name | values
checklist | FC - S - Hatches
checkpoint | Setout completed, checked & accurate (no clashes & wall locations clearly marked)
checkpoint | Framing Dimensions/ locations checked & accurate (openings considered where applicable)
checkpoint | All frames have been installed square, straighn and plumb
checkpoint | DPC installed (if required) correctly
checkpoint | Fixings are correct to specification including any seismic/bracing requirements (attach relevant photos)
checkpoint | All Nogs (Service/Specialty) & penetrations - installed, checked & correct (consider acoustic & fire rating requirements)
checkpoint | All timber framing completed correctly to specification & within tolerance in respective area(s)
holdpoint | Request sign off
type | name | values
checklist | FC - S - Gutters
checkpoint | Setout completed, checked & accurate (no clashes & wall locations clearly marked)
checkpoint | Framing Dimensions/ locations checked & accurate (openings considered where applicable)
checkpoint | All frames have been installed square, straight and plumb
checkpoint | DPC installed (if required) correctly
checkpoint | Fixings are correct to specification including any seismic/bracing requirements (attach relevant photos)
checkpoint | All Nogs ( Service/Specialty) & penetrations - installed, checked & correct (consider acoustic & fire rating requirements)
checkpoint | All timber framing completed correctly to specification & within tolerance in respective area(s)
holdpoint | Request sign off
type | name | values
Checklist | FC - S - Flashing Installation
checkpoint | Head flashing installed with sealant at windows and doors (STO system)
checkpoint | Rainsheild installed between joinery and lintel (brick)
checkpoint | DPC and WANZ bar installed at the bottom of the joinery (see fixing) as per manufacturer's spec
checkpoint | Aluminium window jamb side flashings are installed
checkpoint | All flashing installed at windows and doors to specification & within tolerance in respective area(s)
holdpoint | Request sign off
type | name | values
Checklist | FC - S - RAB
checkpoint | Fixing and spacings checked in accordance with manufactuers specs
checkpoint | White MS sealant for air seals between RAB board and concrete horizontal and vertical joints
checkpoint | 3M taping around windows and external corners and vertical joints and horizontal flashing checked
checkpoint | Vaproshield to interfloor installed after vertical taping
checkpoint | Bracing checked and accurate
checkpoint | Penetrations and punctures sealed with flashing tape
checkpoint | Sealing joints over internal and external joints
checkpoint | Battern on RAB Board for cladding fixings
checkpoint | All RAB Board installation completed to specification & within tolerance in respective area(s)
holdpoint | Request sign off
type | name | values
checklist | FC- S - Soffits
section | Pre-Installation Checks
checkpoint | Wiring in and anchored down for downlights,checked and accurate
checkpoint | Air conditinoning pre wire and pipe completed and acceptable
checkpoint | Fire sprinklers droppers installed and acceptable
section | Soffits works checks
checkpoint | Framing completed, checked and accurate including sheet joints/blocking
checkpoint | Framing centre correct at 600mm centres, including set out to allow all sheets joints to be fully supported
checkpoint | Villaboard installed, stopped and painted, checked and acceptable
checkpoint | Plaster installed as per spec and painted and acceptable
checkpoint | All soffits completed and acceptable
holdpoint | Request sign off
type | name | values
checklist | POST - S - Installation of Aluminium Joinery
checkpoint | External Aluminium joinery units including taping to aluminium joinery works completed
checkpoint | Installation of WANZ bars for aluminium joinery units completed
checkpoint | Installation of door stoppers to wall/ Paver as necessary
checkpoint | All installation of Aluminium joinery works completed in respective area(s)
holdpoint | Request sign off
type | name | values
Checklist | FC - S - Windows, Sliders and Sealants
checkpoint | Fixings and clearance around opening min 6mm & max 18mm and PEF rod/air seal are within acceptable tolerance level
checkpoint | Check taping around, before installing the windows and sliders
checkpoint | Packers to be correctly used and set back to allow continous air seal
checkpoint | Jambs level and straight for finishing lines on the side
checkpoint | Door and window jambs flush to GIB Board
checkpoint | Check air seal is provided at the rear of the window reveal
checkpoint | All joints detailed as per attached Detail Document
checkpoint | All framing completed correctly within tolerance in respective area
checkpoint | Sil support fixing bars installed for all joinery within acceptable tolerance level
checkpoint | All windows, sliders and sealant installation completed to specification & within tolerance in respective area(s)
holdpoint | Request sign off
type | name | values
checklist | POST - S - Fire door installation
checkpoint | Door Number(s) / Location checked and accurate
checkpoint | Floor clearance - Adeqaute for proposed floor coverings
checkpoint | Services/Mechanisms & FRR/Acoustic requirements considered & applied (where applicable)
checkpoint | Fixings- consider Jamb/Hinges, all installed & secure (size & type)
checkpoint | Door leaf to jamb gaps parallel & correct (consider paint thickness(s))
checkpoint | Door opening as required & is plumb
checkpoint | Door tags installed
checkpoint | All doors installed, damage free & completed correctly to specification in respective area(s)
holdpoint | Request sign off
type | name | values
checklist | POST - S - Internal door installation
checkpoint | Door Number(s) / Location checked and accurate
checkpoint | Floor clearance - Adeqaute for proposed floor coverings
checkpoint | Fixings- consider Jamb/Hinges, all installed & secure (size & type)
checkpoint | Door leaf to jamb gaps parallel & correct (consider paint thickness(s))
checkpoint | Door opening as required & is plumb
checkpoint | All doors installed, damage free & completed correctly to specification in respective area(s)
holdpoint | Request sign off
type | name | values
checklist | POST- S - Handrails
checkpoint | Area & substrate acceptable
checkpoint | All handrails install comepleted correctly within tolerance in respective area (photos attached)
holdpoint | Request sign off
type | name | values
checklist | POST - S - Hardware Installation
checkpoint | Area accessible and ready to install the hardware
checkpoint | All handrails install comepleted correctly within tolerance in respective area (photos attached)
holdpoint | Request sign off
type | name | values
checklist | POST - S - Skirting/Architraves & Trims
checkpoint | Architraves / skirting & trims are the correct size and profile
checkpoint | Skirting boards have been properly scribed, sanded, glued and mitred
checkpoint | Architraves/skirting & trims have been installed with consistent even margins
checkpoint | Skirting/Architraves & trim work completed - specified level of finish achieved
holdpoint | Request sign off
type | name | values
checklist | POST - S -Installation of Internal carpentry items - Bathroom
checkpoint | Area & substrate acceptable
checkpoint | Install all wall hung vanities and mirror cabinets
checkpoint | Vanity checked (photos attached)
checkpoint | Mirror checked (Photos attached)
checkpoint | Toothbrush holder checked (Photos attached)
checkpoint | Toilet roll holder checked (Photos attached)
checkpoint | Towel Rings checked (Photos attached)
checkpoint | Robe hook checked (Photos attached)
checkpoint | Robe hook installed (Photos attached)
checkpoint | Laundry shelves installed and checked (Photos attached)
checkpoint | All relevant bathroom checks completed correctly within tolerance in respective area
holdpoint | Request sign off
type | name | values
checklist | FC - S - Brick Lintel bars installation
checkpoint | Horizontal shelf angles & lintel bars installed and correctly fixed where required - Cosider horizontal and vertical alignment
holdpoint | Request sign off