## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-01-013 - General Concrete Paving | [5 empty] | ITP-01-013 - General Concrete Paving REV1
section | 1 - Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: ITP Signed
label | – – – – – – – – –
label | HP*
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer / Site Foreman
label | – – – – – – – – –
text | DATE:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is:
label | • OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | – – – – – – – – –
label | REFERENCE DOCUMENTS:
label | • OHSCP
label | • PHSCP
label | • PCMP
label | • EMP
label | • ECP
label | • CEMP
label | • ERA
label | • QMP
label | • CHMP
label | • SWMS
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual Inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: ITP Signed
label | – – – – – – – – –
label | HP*
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer / Site Foreman
label | – – – – – – – – –
text | DATE:
checkpoint | 1.3 Submission & Approval of Concrete Mix Design
label | FREQUENCY: Prior to first concrete pour
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • The Contractor shall submit the concrete mix design details for review by the Superintendent not less than 4 weeks prior to the placement of concrete.
label | • Concrete shall not be placed until the mix design has been reviewed by the Superintendent, and allocated a registration number on the Register of VicRoads approved concrete mixes.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 610.07(b)
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY:
label | • ITP Signed
label | • Mix design approval
label | – – – – – – – – –
label | HP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer / Superintendent
label | – – – – – – – – –
text | DATE:
holdpoint | HOLD POINT AUTHORITY
section | 2 - Construction Works
checkpoint | 2.1 Setting Out
label | FREQUENCY: Prior to start
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 703.17
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP Signed
label | – – – – – – – – –
label | HP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer / Superintendent
label | – – – – – – – – –
text | DATE:
holdpoint | HOLD POINT AUTHORITY
checkpoint | 2.2 Excavation Permit
label | FREQUENCY: Each lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • An excavation permit must be issued prior to any excavation commencing.
label | • Plant and equipment shall be appropriate for the task.
label | • Excavation operations shall not disturb areas outside the limit of excavation
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: Excavation permit
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: ITP Signed
label | – – – – – – – – –
label | HP*
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 2.3 Excavation
label | FREQUENCY: Each Lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Excavation completed to required depth to allow placement of the bedding layer
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 703.2
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: ITP Signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 2.4 Bedding
label | FREQUENCY: Each Lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: All bedding material used shall be as follows:
label | – 100mm thick layer of 20mm Class 3 crushed rock bedding for median infill
label | – 150mm thick layer of 20mm Class 4 crushed rock bedding for footpath/pram crossing
label | – Bedding trimmed, moistened, and compacted as per Section 304
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 703.21 Drawings
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual Inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: ITP Signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Foreman
label | – – – – – – – – –
text | DATE:
checkpoint | 2.5 Formwork
label | FREQUENCY: Each Lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Formwork shall comply with the requirements of AS 3610
label | – – – – – – – – –
label | REFERENCE DOCUMENTS:
label | • 703.12
label | • AS 3610
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: ITP Signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 2.6 Reinforcement
label | FREQUENCY: Each Lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Reinforment used shall consist of SL82 mesh is to be placed with a minimum cover of 50mm from the top (unless shown otherwise on drawings).
label | • Reinforcement must comply with the requirements of AS/NZS 4671.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 703.13
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: ITP Signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 2.7 Concrete Placement
label | FREQUENCY: Each Lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Concrete shall be thoroughly compaction via contious tamping and internal vibration. Where concrete is unformed it shall be hand tamped to a smooth surface and screeded in accordance with the construction drawings.
label | • Where fresh concrete is being placed against concrete which has taken initial set a properly formed construction joint must be used.
label | – N25 for median infills
label | – N32 for pram crossings/footpath
label | – – – – – – – – –
label | REFERENCE DOCUMENTS:
label | • 703.05(a)
label | • 703.08
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual Inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: ITP Signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer / Site Foreman
label | – – – – – – – – –
text | DATE:
checkpoint | 2.8 Record location of each batch
label | FREQUENCY: Each concrete pour
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Batch location recorded on Load Batch Traceability Checklist
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 610.15
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Checklist
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP Signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 2.9 Surface Finish
label | FREQUENCY: Each Lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Concrete elements shall have a Class 3 surface finish for external surfaces and a Class 4 surface finish for permanently hidden surfaces in accordance with AS 3610.
label | • Footpaths and other Surfacing shall be compelted with a wooden float.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 703.25
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual Inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP Signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 2.10 Pram Crossings
label | FREQUENCY: Each Lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Ensure that pram crossings are constructed in accordance with requirements for access and mobility.
label | – For pram crossings within concrete kerb refer to Figure 24A of AS 1428.1
label | – Pram crossings within bluestone kerb shall be constructed as per relevant standard drawings (1P 50406 for City of Melbourne)
label | – – – – – – – – –
label | REFERENCE DOCUMENTS:
label | • Figure 24A AS1428.1
label | • SD 1P 50406
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP Signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer / Site Foreman
label | – – – – – – – – –
text | DATE:
checkpoint | 2.11 Joints
label | FREQUENCY: Each Joint
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Expansion joints shall be installated at 10m regular intervals using 15mm wide cork or bituminous imtergrate particle board.
label | • Control joints at 2.5m regular intervals, 25% of pavement depth and 5mm wide
label | • Prevent bonding between edging and surfacing. Either paint back of edging with bitumen or use a strip of bituminous felt material.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 703.26
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual Inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP Signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer / Site Foreman
label | – – – – – – – – –
text | DATE:
checkpoint | 2.12 Protection of concrete
label | FREQUENCY: Each Lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
label | • Vehicles equal to or less than 1.5 tonnes in weight may be permitted to cross after 4 days, vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 703.27
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP Signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Foreman
label | – – – – – – – – –
text | DATE:
checkpoint | 2.13 Curing
label | FREQUENCY: Each Lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Concrete shall be cured immediately either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these.
label | • Curing compounds shall comply with AS 3799. The curing compound shall be applied in two coats using a fine spray at the rate stated on the certificate of compliance
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 703.1
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP Signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer / Site Foreman
label | – – – – – – – – –
text | DATE:
checkpoint | 2.14 Ambient Weather
label | FREQUENCY: Prior to commencing any activity
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Concreting operations shall comply with the requirements of clauses 610.17(a), 610.17(b), 610.17(c) and 610.17(d) for limits, restrictions and treatments to be applied for concreting in hot, cold and wet weather, except that curing shall be in accordance with clause 703.10.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS:
label | • 610.17(a)
label | • 610.17(b)
label | • 610.17 (c)
label | • 610.17(d)
label | • 703.09
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP Signed
label | – – – – – – – – –
label | HP*
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer / Site Foreman
label | – – – – – – – – –
text | DATE:
section | 3 - Completion
checkpoint | 3.1 Carry out sampling of concrete - strength and consistency
label | FREQUENCY: Each 50m3
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Sampling and testing of the strength of concrete shall be carried out in accordance with Clause 6.2 of AS 1379.
label | • The consistency of the concrete shall be determined by a slump test of each concrete strength sample in accordance with AS 1012.3 and Clause 5.2 of AS 1379
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 703.11
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Checklist
label | – – – – – – – – –
label | RECORD OF CONFORMITY: ITP Signed/Test Records
label | – – – – – – – – –
label | TP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 3.2 Tolerances
label | FREQUENCY: Each Lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Where matching in with existing surface levels, the new surface shall be within ± 5mm existing.
label | • Section dimensions shall be constructed within the following tolerances:
label | – 5mm and 15mm for width; or
label | – ±3mm for dimensions less than 25mm.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 703.15 Drawings
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual Inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP Signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer / Site Foreman
label | – – – – – – – – –
text | DATE:
checkpoint | 3.3 Backfilling
label | FREQUENCY: Each Lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • After curing, no earlier than 3 days, backfilling shall be completed as per the below:
label | – Topsoil compacted in layers < 150mm
label | – Width ≥ 300mm behind edging to top of edging
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 703.29
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP Signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Foreman
label | – – – – – – – – –
text | DATE:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: