## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-01-016 - Sign Installation | [5 empty] | ITP-01-016 - Sign Installation
section | 1 - Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | WP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is:
label | • OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | – – – – – – – – –
label | REFERENCE DOCUMENTS:
label | • OHSCP
label | • PHSCP
label | • PCMP
label | • EMP
label | • ECP
label | • CEMP
label | • ERA
label | • QMP
label | • CHMP
label | • SWMS
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual Inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | WP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 1.3 Signage Conformance
label | FREQUENCY: Before commencement of activity
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Ensure sign size and immage correspond with contract drawings and meets specification
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: Drawings AS 1742
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | WP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 1.4 Service Identification
label | FREQUENCY: Prior to start
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Check for any services in proximity to points of installation or coring for spigots
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: DBYD, Service chart
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | WP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
section | 2 - Construction Works
checkpoint | 2.1 Setting Out
label | FREQUENCY: Prior to start
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: Drawings
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual Inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 2.2 Post & Foundations
label | FREQUENCY: Prior to Start
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • The required positions of all posts and signs shall be as directed by the Superintendent who shall confirm the positions before the erection of posts commences.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 714.06
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | HP
label | – – – – – – – – –
label | RESPONSIBILITY: Superintendent
label | – – – – – – – – –
text | DATE:
holdpoint | HOLD POINT AUTHORITY
checkpoint | 2.3 Signage Install
label | FREQUENCY: Each Sign
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Sign to be installed as per most current drawings, local council documentation, and to the correct height and position.
label | • Spigot embedment shall be within +/- 5mm of design horizontal position and +10mm of vertical design position
label | • Signs specified to be re used are to comply with AS 1742 standards, and must be replaced if deemed in unsatisfactory condition
label | – – – – – – – – –
label | REFERENCE DOCUMENTS:
label | • AS 1742
label | • TS 1313
label | • Drawings
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | WP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: