## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-01-019 - Line Marking | [5 empty] | ITP-01-019 - Line Marking REV2
section | 1 - Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | WP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is:
label | PSP, EMP, TMP, JSEA, SWMS & WP
label | – – – – – – – – –
label | REFERENCE DOCUMENTS:
label | • PSP
label | • EMP
label | • TMP
label | • JSEA
label | • SWMS
label | • WP
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual Inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | WP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
section | 2 - Construction Works
checkpoint | 2.1 Setting Out
label | FREQUENCY: Prior to start
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: Drawings
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual Inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 2.2 Position of Markings
label | FREQUENCY: Prior to application
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Painting/ application of material shall not commence unitll the Superintenent has inpsected the setout and given approval to proceed, unless an exemeption is granted.
label | • Works shall be set out as required in clause 721.A03, that is: the dimensions and colour of pavement markings shall conform to the VicRoads Traffic Engineering Manual Volume 2
label | – – – – – – – – –
label | REFERENCE DOCUMENTS:
label | • VicRoads Traffic Engineering Manual Volume 2 Drawings
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | HP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer & Superintendent
label | – – – – – – – – –
text | DATE:
holdpoint | HOLD POINT AUTHORITY
checkpoint | 2.3 Materials
label | FREQUENCY: Prior to commencement
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • All paints shall be approved under the Australian Paint Approval Scheme (APAS).
label | • Paint shall comply with the requirements of AS 4049.1 for solvent‑borne paint or AS/NZS 4049.3 for water‑borne paint as listed in Section 175.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 712.A04(c)
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | HP*
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 2.4 General Markings
label | FREQUENCY: Prior to commencement
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Linemarking shall be applied by a self propelled machine, and stencils shall be used with all roadmarking.
label | • All work must be undertaken by a contractor eligible for accreditation under the Painting Contractors Certification Programme (PCCP).
label | • This programme is administered by the CSIRO.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 712.D01(c)
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | HP*
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
section | 3 - Completion
checkpoint | 3.1 Tolerances
label | FREQUENCY: Each marking
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • The Contractor shall comply with the tolerances as shown in Table 721.A101 when installing pavement markings.
label | (i) Distance between centreline of marking and set out marks <30mm
label | (ii) Width of completed paint markings <15mm
label | (iii) Length of completed stripes and blocks 0 to +10% of specified length
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: Table 712.A101
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | HP*
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 3.2 As-Built
label | FREQUENCY: Post Completion
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: As built survey recorded to confirm installation within tolerances in the latest IFC drawings.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS:
label | • IFC Drawings
label | • Survey Records
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Document Review
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | SCP
label | – – – – – – – – –
label | RESPONSIBILITY: Project Engineer/Surveyor
label | – – – – – – – – –
text | DATE:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: