## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-027 - Pile Footing Construction | [5 empty] | ITP-027 - Pile Footing Construction REV1
section | 1 - Design and Submissions
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | HP*
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is:
label | • PSP, EMP, TMP, SWMS & WP
label | – – – – – – – – –
label | REFERENCE DOCUMENTS:
label | • PSP
label | • EMP
label | • TMP
label | • JSEA
label | • SWMS
label | • WP
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual Inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | HP*
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 1.3 Approval of mix design
label | FREQUENCY: Prior to the first concrete pour
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Structural Concrete Design & Submission ITP completed and signed.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 610.07
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 1.4 Reinforcement schedule
label | FREQUENCY: Prior to concrete pour
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Reinforcement schedule has been prepared for the reinforcement supply, to ensure that it achieves the specified tolerances on member dimensions, concrete cover and specified locations
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 611.04
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
section | 2 - Construction/Erection of Formwork
checkpoint | 2.1 Excavation (Pile)
label | FREQUENCY: Prior to concrete pour
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • The Contractor shall notify the Superintendent for inspection of the pile excavation by the Superintendent.
label | • Prior to inspection, the pile excavation shall be de‑watered and the walls and base of the pile cleaned out, including the internal surface of the casing, to remove all mud, loose or foreign material.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 606.05
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Inspect
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | HP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer / Suprintendant
label | – – – – – – – – –
text | DATE:
holdpoint | HOLD POINT AUTHORITY
checkpoint | 2.2 Construction Methodology
label | FREQUENCY: Prior to erection
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Designed and constructed in such a manner so it can be removed without damage to the concrete. Formwork/shoring shall be placed in locations where steel reinforcement and other fixtures can be inspected, and sufficiently tight at joints to prevent loss of slurry
label | – – – – – – – – –
label | REFERENCE DOCUMENTS:
label | • 614.04
label | • 614.06
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 2.3 Construction Methodology (Pile)
label | FREQUENCY: Prior to construction
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Further to the requirements of clause 611.10 spacers and supports for bored pile steel reinforcement shall be placed at intervals of no more than 2 m along the full length of the steel reinforcement cage to ensure that the specified concrete cover to the steel reinforcement is maintained.
label | • Concrete shall be placed through a tremie tube and shall not be dropped from a height greater than 2 m through air.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS:
label | • 611.10
label | • 606.06
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
section | 3 - Pre-Pour Planning and Inspection
checkpoint | 3.1 Cleaning formwork
label | FREQUENCY: Each concrete pour
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Concrete shall not be placed until all foreign material has been completely removed from the forms
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 610.18 (a) (iii)
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan
label | – – – – – – – – –
text | DATE:
checkpoint | 3.2 Correct forms, reinforcements, rag bolt assembly and embedments
label | FREQUENCY: Prior to concrete pour
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Superintendent confirms that the inspected formwork, reinforcement, rag bolt assembly and embedments comply with the project drawings and specifications.
label | • Pre-pour checklist completed and signed.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 610.18 (a)
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed & Pre-Pour checklist completed
label | – – – – – – – – –
label | HP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan / Superintendent
label | – – – – – – – – –
text | DATE:
holdpoint | HOLD POINT AUTHORITY
checkpoint | 3.3 Reinforcement assembly of piles
label | FREQUENCY: Prior to concrete pour
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Reinforcement and/or concrete shall not be placed until the proposed method of removing mud, loose rock or similar materials has been reviewed by the Superintendent.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 610.17 (b), (c), (d)
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | HP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan
label | – – – – – – – – –
text | DATE:
holdpoint | HOLD POINT AUTHORITY
checkpoint | 3.4 Monitoring weather
label | FREQUENCY: Prior to concrete pour
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Concrete shall not be place when temperature is <5°C or > 35°C
label | • All steel components that are in contact with the concrete shall be cooled to below 32°C before concrete is placed
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 610.17 (b), (c), (d)
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan
label | – – – – – – – – –
text | DATE:
section | 4 - Placing and Finishing Concrete
checkpoint | 4.1 Carry out sampling of concrete
label | FREQUENCY: Each concrete pour
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Sampling in accordance with 610.16
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 610.16
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Checklist
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan
label | – – – – – – – – –
text | DATE:
checkpoint | 4.2 Discharge time
label | FREQUENCY: Each concrete pour
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Discharge time (concrete placed and compacted) < 90 minutes from batch time unless approved otherwise. Batch to be used has a discharge time of 180 minutes. Boral VR400/40 (SCC) (180min')
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 610.13
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY:
label | • This ITP signed.
label | • Accurate Site Notes & Load Mapping
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan
label | – – – – – – – – –
text | DATE:
checkpoint | 4.3 Methodology of placement (structural)
label | FREQUENCY: Each concrete pour
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Concrete shall be tansported, handled and placed in a manner that will prevent segregation or loss of materials
label | • In continuous pours the max. time lag between truckloads on site is 25 minutes
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 610.18
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan
label | – – – – – – – – –
text | DATE:
checkpoint | 4.4 Methodology of placement (piles)
label | FREQUENCY: Each concrete pour
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Unless otherwise approved by the Superintendent, temporary casing shall be used to prevent collapse of holes during the excavation operation.
label | • Care shall be taken to prevent soil and rock dislodging from the side of the hole and contaminating the concrete forming the minimum cover to the reinforcement.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS:
label | • 606.03(b)
label | • 606.05
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan
label | – – – – – – – – –
text | DATE:
section | 5 - Post-Pour Details and Inspection
checkpoint | 5.1 Curing
label | FREQUENCY: Each concrete pour
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Sufficient time shall be given for the concrete to cure prior to loading.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 610.23
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan
label | – – – – – – – – –
text | DATE:
checkpoint | 5.2 Formwork removal
label | FREQUENCY: Each concrete pour
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Formwork shall be removed carefully and in such a manner as to avoid damage to the member or the concrete surfaces and maintain safety at all stages of removal. Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 610.25
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan
label | – – – – – – – – –
text | DATE:
checkpoint | 5.3 Positional tolerance and dimensions of concrete members and piles
label | FREQUENCY: Each concrete pour
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: The centre of the pile head shall be in the specified plan position ±75 mm;
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 607.06
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY:
label | • This ITP signed
label | • Post Pour Checklist completed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan
label | – – – – – – – – –
text | DATE:
checkpoint | 5.4 Concrete Sampling and Testing Self-Compacting Concrete VR400/40
label | FREQUENCY: Prior to lot closure
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Concrete sampled and tested for Compressive Strength:
label | – 2 cylinders @ 28 days for VPV=13% & Compressive Strength=40MPa – 1 cylinders @ 7 days for Compressive Strength=26MPa
label | • Slump flow of 550 - 800mm spread
label | • T500 of 1 to 5 seconds
label | • Passing Ability of less than or equal to 10mm
label | – – – – – – – – –
label | REFERENCE DOCUMENTS:
label | • 610.05
label | • 610.06
label | • 610.13
label | • 610.16
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | TP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan
label | – – – – – – – – –
text | DATE:
checkpoint | 5.5 Protection of Adjacent Piles
label | FREQUENCY: Prior to commencing any piling
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • No pile construction shall be commenced within 2.5 m clear distance of a newly cast pile until the concrete in the pile has attained a strength of 15 MPa.
label | • Installation of piles by methods which involve driven temporary casing or result in significant vibration shall not be carried out within the distance 2.5 m to 9.0 m until the concrete in the pile has attained a strength of 15 MPa and set for a minimum of 24 hours.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS:
label | • 606.04(a)
label | • 606.04©
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | HP*
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan
label | – – – – – – – – –
text | DATE:
checkpoint | 5.6 Testing Post-Pour
label | FREQUENCY: Prior to lot closure
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Where necessary, piles shall be tested in accordance with 606.07; integrity testing, static load testing & dynamic testing
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 606.07
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | TP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan
label | – – – – – – – – –
text | DATE:
checkpoint | 5.7 As Built Drawings
label | FREQUENCY: Prior to lot closure
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Recorded of as-built drawings
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: Fulton Hogan Procedure
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan
label | – – – – – – – – –
text | DATE:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: