## res_ITP-01-012 - Hot Mix Asphal
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-01-013 - General Concrete Paving | itp |  |  |  |  | ITP-01-013 - General Concrete Paving
section | 1 - Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: ITP Signed
label | – – – – – – – – –
label | HP*
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer/ Site Foreman
label | – – – – – – – – –
text | DATE:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is:
label | • OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | – – – – – – – – –
label | REFERENCE DOCUMENTS:
label | • OHSCP
label | • PHSCP
label | • PCMP
label | • EMP
label | • ECP
label | • CEMP
label | • ERA
label | • QMP
label | • CHMP
label | • SWMS
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual Inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: ITP Signed
label | – – – – – – – – –
label | HP*
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer/ Site Foreman
label | – – – – – – – – –
text | DATE:
checkpoint | 1.3 Submission & Approval of Concrete Mix Design
label | FREQUENCY: Prior to first concrete pour
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • The Contractor shall submit the concrete mix design details for review by the Superintendent not less than 4 weeks prior to the placement of concrete.
label | • Concrete shall not be placed until the mix design has been reviewed by the Superintendent, and allocated a registration number on the Register of VicRoads approved concrete mixes.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 610.07(b)
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: ITP Signed, Mix design approval
label | – – – – – – – – –
label | HP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer/ Superintendent
label | – – – – – – – – –
text | DATE:
holdpoint | HOLDPOINT AUTHORITY
section | 2 - Construction Works
checkpoint | 2.1 Setting Out
label | FREQUENCY: Prior to start
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Set out work in accordance with drawings.
label | • The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work.
label | • No survey/level pegs to be removed by any persons until completion of works.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 703.17
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP Signed
label | – – – – – – – – –
label | HP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer/ Superintendent
label | – – – – – – – – –
text | DATE:
holdpoint | HOLDPOINT AUTHORITY
checkpoint | 2.2 Excavation Permit
label | FREQUENCY: Each lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • An excavation permit must be issued prior to any excavation commencing.
label | • Plant and equipment shall be appropriate for the task.
label | • Excavation operations shall not disturb areas outside the limit of excavation
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: Excavation permit
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: ITP Signed
label | – – – – – – – – –
label | HP*
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 2.3 Excavation
label | FREQUENCY: Each Lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Excavation completed to required depth to allow placement of the bedding layer
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 703.20
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: ITP Signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 2.4 Bedding
label | FREQUENCY: Each Lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • All bedding material used shall be as follows:
label | – 100mm thick layer of 20mm Class 3 crushed rock bedding for median infill
label | – 150mm thick layer of 20mm Class 4 crushed rock bedding for footpath/pram crossing
label | – Bedding trimmed, moistened, and compacted as per Section 304
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 703.21 Drawings
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual Inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: ITP Signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Foreman
label | – – – – – – – – –
text | DATE:
checkpoint | 2.5 Formwork
label | FREQUENCY: Each Lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Formwork shall comply with the requirements of AS 3610
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 703.12 AS 3610
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: ITP Signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 2.6 Reinforcement
label | FREQUENCY: Each Lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Reinforment used shall consist of SL82 mesh is to be placed with a minimum cover of 50mm from the top (unless shown otherwise on drawings).
label | • Reinforcement must comply with the requirements of AS/NZS 4671.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 703.13
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: ITP Signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 2.7 Concrete Placement
label | FREQUENCY: Each Lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Concrete shall be thoroughly compaction via contious tamping and internal vibration. Where concrete is unformed it shall be hand tamped to a smooth surface and screeded in accordance with the construction drawings.
label | • Where fresh concrete is being placed against concrete which has taken initial set a properly formed construction joint must be used.
label | – N25 for median infills
label | – N32 for pram crossings/footpath
label | – – – – – – – – –
label | REFERENCE DOCUMENTS:
label | • 703.05(a)
label | • 703.08
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual Inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: ITP Signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer/ Site Foreman
label | – – – – – – – – –
text | DATE:
checkpoint | 2.8 Record location of each batch
label | FREQUENCY: Each concrete pour
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Batch location recorded on Load
label | • Batch Traceability Checklist
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 610.15 CL001D
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Checklist
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP Signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 2.9 Surface Finish
label | FREQUENCY: Each Lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Concrete elements shall have a Class 3 surface finish for external surfaces and a Class 4 surface finish for permanently hidden surfaces in accordance with AS 3610.
label | • Footpaths and other Surfacing shall be compelted with a wooden float.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 703.25
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual Inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP Signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 2.10 Pram Crossings
label | FREQUENCY: Each Lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Ensure that pram crossings are constructed in accordance with requirements for access and mobility.
label | – For pram crossings within concrete kerb refer to Figure 24A of AS 1428.1
label | – Pram crossings within bluestone kerb shall be constructed as per relevant standard drawings (1P 50406 for City of Melbourne)
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: Figure 24A AS1428.1 SD 1P 50406
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP Signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer/ Site Foreman
label | – – – – – – – – –
text | DATE:
checkpoint | 2.11 Joints
label | FREQUENCY: Each Joint
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Expansion joints shall be installated at 10m regular intervals using 15mm wide cork or bituminous imtergrate particle board.
label | • Control joints at 2.5m regular intervals, 25% of pavement depth and 5mm wide
label | • Prevent bonding between edging and surfacing. Either paint back of edging with bitumen or use a strip of bituminous felt material.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 703.26
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual Inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP Signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer/ Site Foreman
label | – – – – – – – – –
text | DATE:
checkpoint | 2.12 Protection of concrete
label | FREQUENCY: Each Lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
label | • Vehicles equal to or less than 1.5 tonnes in weight may be permitted to cross after 4 days, vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 703.27
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP Signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Foreman
label | – – – – – – – – –
text | DATE:
checkpoint | 2.13 Curing
label | FREQUENCY: Each Lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Concrete shall be cured immediately either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these.
label | • Curing compounds shall comply with AS 3799. The curing compound shall be applied in two coats using a fine spray at the rate stated on the certificate of compliance
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 703.10
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP Signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer/ Site Foreman
label | – – – – – – – – –
text | DATE:
section | 3 - Completion
checkpoint | 3.1 Carry out sampling of concrete - strength and consistency
label | FREQUENCY: Each 50m3
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Sampling and testing of the strength of concrete shall be carried out in accordance with Clause 6.2 of AS 1379.
label | • The consistency of the concrete shall be determined by a slump test of each concrete strength sample in accordance with AS 1012.3 and Clause 5.2 of AS 1379
label | – – – – – – – – –
label | REFERENCE DOCUMENTS:
label | • 703.11
label | • CL001B
label | • CL001C
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Checklist
label | – – – – – – – – –
label | RECORD OF CONFORMITY: ITP Signed/Test Records
label | – – – – – – – – –
label | TP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 3.2 Tolerances
label | FREQUENCY: Each Lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Where matching in with existing surface levels, the new surface shall be within ± 5mm existing.
label | • Section dimensions shall be constructed within the following tolerances:
label | – 5mm and 15mm for width; or
label | – ±3mm for dimensions less than 25mm.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 703.15 Drawings
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual Inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP Signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer/ Site Foreman
label | – – – – – – – – –
text | DATE:
checkpoint | 3.3 Backfilling
label | FREQUENCY: Each Lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • After curing, no earlier than 3 days, backfilling shall be completed as per the below:
label | – Topsoil compacted in layers < 150mm
label | – Width ≥ 300mm behind edging to top of edging
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 703.29
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP Signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Foreman
label | – – – – – – – – –
text | DATE:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: