## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # FHC-ITP-020
[11 empty] | Revision : 001 | Date : 21/04/2022
Client: |  | MRPA |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  |  |  | Fencing |  | Name: Martin Syawish |  | Name: Patrick Fagan |  |  | Name: Shaun Kent
Job No: |  |  |  | Specifications:
|  |  |  | Structure / Component: Fencing |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: |  | Date : 20/04/2022 |  | Date : 20/04/2022 |  |  | Date : 20/04/2022
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | •Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings | Drawings and drawing registers | Visual inspection | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | •All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP | PSP, EMP, TMP, JSEA, SWMS, WP | Visual Inspection | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.3 | Check Materials |  | Prior to commencing any activity | •Unless specified otherwise, all fencing materials and products shall be supplied by the Contractor and shall be of the dimensions, manufacture, quality and structural grade in accordance with the requirements of this specification 707 and drawings. | Fencing Plan | Verify | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.4 | Confirm Footings position |  | Prior to commencing any activity | •Confirm footings are set out to locations specified on design drawings | Fencing Plan | Verify | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
2 | Construction Works
2.1 | Footing Installation |  | Prior to post installation | •Concrete shall be of minimum strength N20 •Concrete footing shall be 600mm x 250mm and have a 65mm steel sleeve set in the concrete | Fencing Plan SD3131 | Verify | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
2.2 | Post Installation |  | Each Lot | •Posts shall be set in concrete footings of the dimensions shown on the drawings •Posts shall be Installed to concrete surface in culvert area with baseplate and bolt assembly | 704.04 (d) AS1554 Fencing Plan | Verify | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
2.3 | Grout Installation |  | Each Lot | •Footing surface shall be cleaned and roughened before application •Non shrink dry pack grout shall be placed under base plate where applicable in culvert area and footpath areas | AS1554 | Visual inspection | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
2.4 | Chainwire mesh fence |  | Each Lot | •End, corner and gate posts shall be braced as shown on the drawings. Line posts shall be braced as shown on the drawings at not more than 120 m intervals. Chain wire shall comply with the requirements of AS 1725. | 704.04 (d) AS1725 | Visual inspection | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
2.4 | Handrails |  | Each Lot | •Handrail to be installed as per design drawings and manufacturers specifications | Manufacturer Specification | Verify | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
2.5 | Farm Fence Installation |  | Each Lot | •Farm Fence to be installed as per design drawings and vicroads standard drawing | Fencing Plan SD3101 | Verify | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
3 | Completion
3.1 | As Built |  | Post Completion | •As Built survey recorded to confirm installation as per design drawings | Fencing Plan | Verify | This ITP signed off | SCP | Project Engineer /Surveyor | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.