## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # FHC-ITP-026
[11 empty] | Revision : 002 | Date : 19/08/2022
Client: |  | MRPA |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  |  |  | Safety Barrier Installation |  | Name: Martin Syawish |  | Name: Patrick Fagan |  |  | Name: Shaun Kent
Job No: |  |  |  | Specifications:
|  |  |  | Structure / Component: Guard Rail |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: |  | Date : 19/08/2022 |  | Date : 19/08/2022 |  |  | Date : 19/08/2022
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | •Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings | Drawings and drawing registers | Visual inspection | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | •All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP | PSP, EMP, TMP, JSEA, SWMS, WP | Visual Inspection | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.3 | Material Approval |  | Prior to commencing any activity | •Only safety barrier products listed in VicRoads Road Design Note 06-04 shall be used, FHC shall submit to the Superintendent all test certificates related to the supply of steel for the Works at least 14 days prior to commencement of installation. | Fencing Plan RD06-04 708.04 708.05 (b) | Verify | This ITP signed off | HP | Fulton Hogan Engineer/Superintendent
1.4 | Location of Works |  | Prior to commencing any activity | •Prior to installation the Contractor shall confirm with the Superintendent the required location and length of all guard fence. | Fencing Plan 708.08 | Verify | This ITP signed off | HP | Fulton Hogan Engineer/Superintendent
2 | Construction Works
2.1 | Inspection of Materials upon Delivery |  | Each Delivery | •Posts shall be inspected upon delivery for compliance and damange. If scratched or missing coating, this may be rectified with a minimum of two coats of a zinc-rich inorganic paint | 708.07 (b) | Verify | This ITP signed off | IP | Fulton Hogan Engineer | N/A
2.2 | Post Installation |  | Each Lot | •Posts shall be installed to the depth, line and spacing shown on the drawings, and to the tolerances in clause 708.07(d). •Posts shall be installed by driving, provided there is no distortion or damage which may reduce their effectiveness. | Fencing Plan 708.08 (a) 708.07(d) | Verify | This ITP signed off | HP* | Fulton Hogan Engineer | N/A
2.3 | W-Beams |  | Each Lot | •The w-beam sections shall be lapped so that the exposed ends face away from near side approaching traffic. The edges of the w-beam section or backing plate adjacent to posts shall be fixed in contact with the post or post blocks and all bolts shall be fully tightened. All bolts on the traffic side of w-beam installations shall be flush with the w-beam | 708.08(b) | Verify | This ITP signed off | HP* | Fulton Hogan Engineer | N/A
2.4 | End Treatments |  | Each Lot | •During installation of wire ropes in the end treatments of w-beam, the Contractor shall ensure that no twisting of the rope occurs. When rope assemblies are used, the nuts at each end of the rope shall be tightened to a minimum torque of 50 Nm on the assemblies or as per the manufacturer’s requirements. The Contractor shall maintain tension in the wire ropes in end treatments until the Date of Completion, by keeping the nuts at both ends tightened to 50 Nm or to manufacturer’s requirements. | 708.08(c) | Verify | This ITP signed off | HP* | Fulton Hogan Engineer | N/A
2.5 | Delineators |  | Each Lot | Delineators shall be fastened to the top of w-beams, comprising of a flexible plastic mounting brackets fitted with 100cm2 of Class 1A retro-reflective material | 708.11 | Verify | This ITP signed off | IP | Fulton Hogan Engineer | N/A
2.6 | Concrete Maintenance Strip |  | Each Lot | •The Contractor shall provide maintenance strips beneath the guard fence and terminals as indicated on the drawings and/or as nominated in Table 708.121. The concrete maintenance strip shall consist of 75 mm depth of N20 strength grade portland cement-based concrete or 20 MPa geopolymer binder-based concrete conforming to the requirements of clause 708.05(g), on 75 mm of compacted Class 3 crushed rock. Where the concrete maintenance strip is adjacent to kerb or pavement, separation from the kerb or pavement by the use of a cork expansion joint (or approved alternative) shall be produced. Full depth expansion joints shall be provided perpendicular to the line of the steel beam guard fence 200 mm each side of every post. | 708.12 708.12 (a) Table 708.121 | Verify | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
3 | Completion
3.1 | Tolerance Conformance |  | Each lot | •W-beam guard fence shall be erected to the following tolerances: (i) Variation from true plan position of posts ±20 mm (ii) Variation of line of w-beams from specified vertical profile ±10 mm (iii) Variation of w-beams from specified horizontal alignment ±20 mm (iv) Variation of posts from vertical +0mm, -15mm (v) Orientation of block &/or postto w-beam +0mm, -15mm (vi) Dimension of holes -0mm, +50mm (vii) Top of bolt head relative to W-Beam -0mm, +5mm | 708.08 (d) | Verify | This ITP signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
3.2 | Certificate of Compliance |  | Prior to practical Completion | •Further to clause 708.07 Installation, and prior to the issue of the Certificate of Practical Completion, the Contractor shall arrange for a safety barrier compliance audit on all proprietary guard fence end treatments constructed under the Contract. | 708.1 | Verify | This ITP signed off | HP | Fulton Hogan Engineer/Superintendent
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.