## res_ITP-01-012 - Hot Mix Asphal
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-01-018 - Landscaping | itp |  |  |  |  | ITP-01-018 - Landscaping
section | 1 - Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | HP*
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer / Site Foreman
label | – – – – – – – – –
text | DATE:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is:
label | • OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP
label | – – – – – – – – –
label | REFERENCE DOCUMENTS:
label | • OHSCP
label | • PHSCP
label | • PCMP
label | • EMP
label | • ECP
label | • CEMP
label | • ERA
label | • QMP
label | • CHMP
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual Inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | HP*
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer / Site Foreman
label | – – – – – – – – –
text | DATE:
checkpoint | 1.3 Submissions and Records
label | FREQUENCY: Prior to commencing any activity
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • The specified inspections, samples, records and certificates shall be made available or submitted to the Superintendent for acceptance prior to the commencement of associated work.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 720.03
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual Inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | HP*
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer / Site Foreman
label | – – – – – – – – –
text | DATE:
checkpoint | 1.4 Permits
label | FREQUENCY: Prior to commencing any activity
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: The Contractor shall obtain all necessary permits and obtain approval from the Superintendent prior to the pruning or removal of local native vegetation.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS:
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual Inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | HP*
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer / Site Foreman
label | – – – – – – – – –
text | DATE:
section | 2 - Construction Works
checkpoint | 2.1 Excavation Permit
label | FREQUENCY: Each lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • An excavation permit must be issued prior to any excavation commencing.
label | • Plant and equipment shall be appropriate for the task.
label | • Excavation operations shall not disturb areas outside the limit of excavation
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: Excavation permit
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP Signed Off
label | – – – – – – – – –
label | HP*
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 2.2 Setting out of landscape softworks
label | FREQUENCY: Each lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: The Contractor shall set out the location and shape of planting areas in accordance with the Landscape Drawings.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 720.06
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual Inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | HP*
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer / Site Foreman
label | – – – – – – – – –
text | DATE:
checkpoint | 2.3 Supply of Materials
label | FREQUENCY: Each Lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • All materials shall be supplied by the Contractor unless otherwise noted.
label | • If any materials are supplied by VicRoads, a joint inspection of the materials shall be made by the Contractor and the Superintendent following delivery of the materials to the site.
label | • The materials, if satisfactory, shall thereafter become the responsibility of the Contractor.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 720.04
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual Inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | WP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer/ Superintendent
label | – – – – – – – – –
text | DATE:
checkpoint | 2.4 Pest and Weed Control
label | FREQUENCY: Each Lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Pre-planting weed control shall be undertaken to ensure that planting areas and new grassed areas are free of visible weeds prior to the commencement of planting and grassing.
label | • Weed control shall be programmed and implemented to deplete the potential weed seed bank within the topsoil to be used in planting beds.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 720.05
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual Inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | HP*
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer / Site Foreman
label | – – – – – – – – –
text | DATE:
checkpoint | 2.4 Fertilisers
label | FREQUENCY: Each Lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Fertilisers for planting areas and advanced trees shall be slow release with a 9‑12 month release period and suitable for the establishment of plant types, sizes and species specified in the plant schedule(s).
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 720.04(f)
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual Inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer / Site Foreman
label | – – – – – – – – –
text | DATE:
checkpoint | 2.5 Mulch
label | FREQUENCY: Each Lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: All wood mulch shall be supplied, delivered, handled and applied in accordance with AS 4454.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS:
label | • 720.04(h)
label | • AS4454
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual Inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | WP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer / Site Foreman
label | – – – – – – – – –
text | DATE:
checkpoint | 2.6 Weed Control Mat and Erosion Control Mat
label | FREQUENCY: Each Lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • The Contractor shall supply and install jute or approved equivalent, biodegradable, fire retardant weed and erosion control mat as indicated on the Drawings or as specified.
label | • Weed Control Mat shall be minimum 700 grams per square metre and Erosion Control Mat shall be 300 grams per square metre.
label | • The surface of the mat shall permit water infiltration.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 720.04(i)
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual Inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer / Site Foreman
label | – – – – – – – – –
text | DATE:
checkpoint | 2.7 Ripping
label | FREQUENCY: Each Lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • The Contractor shall make available each ripped planting area, individual tree planting and grassing area prior to mulching, planting or grassing.
label | • The Contractor shall not proceed until the Superintendent acknowledges requirements for ripping have been met.
label | • In areas where ripping is not practicable, the Contractor shall submit alternative methods to achieve an equivalent result to the Superintendent for review.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 720.07 (b)
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | HP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer/ Superintendent
label | – – – – – – – – –
text | DATE:
holdpoint | HOLDPOINT AUTHORITY
checkpoint | 2.8 Topsoil Finished Surface Levels
label | FREQUENCY: Each Lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • The Contractor shall make available each ripped, topsoiled and cultivated planting area, individual tree planting and grassing area prior to mulching, planting or grassing.
label | • The Contractor shall not proceed until the Superintendent acknowledges requirements for topsoiling and cultivation have been met.
label | • In areas where topsoiling or cultivation is not practicable, the Contractor shall submit alternative methods to achieve an equivalent result to the Superintendent for review.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 720.07 (e)
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | HP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer/ Superintendent
label | – – – – – – – – –
text | DATE:
holdpoint | HOLDPOINT AUTHORITY
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: