## res_ITP-01-012 - Hot Mix Asphal
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-01-026 - Safety Barrier Installation | itp |  |  |  |  | ITP-01-026 - Safety Barrier Installation
section | 1 - Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | HP*
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is:
label | • PSP, EMP, TMP, JSEA, SWMS & WP
label | – – – – – – – – –
label | REFERENCE DOCUMENTS:
label | • PSP
label | • EMP
label | • TMP
label | • JSEA
label | • SWMS
label | • WP
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual Inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | HP*
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 1.3 Material Approval
label | FREQUENCY: Prior to commencing any activity
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Only safety barrier products listed in VicRoads Road Design Note 06-04 shall be used, FHC shall submit to the Superintendent all test certificates related to the supply of steel for the Works at least 14 days prior to commencement of installation.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS:
label | • Fencing Plan
label | • RD06-04
label | • 708.04
label | • 708.05 (b)
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | HP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer/Superintendent
label | – – – – – – – – –
text | DATE:
holdpoint | HOLDPOINT AUTHORITY
checkpoint | 1.4 Location of Works
label | FREQUENCY: Prior to commencing any activity
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Prior to installation the Contractor shall confirm with the Superintendent the required location and length of all guard fence.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: Fencing Plan 708.08
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | HP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer/Superintendent
label | – – – – – – – – –
text | DATE:
holdpoint | HOLDPOINT AUTHORITY
section | 2 - Construction Works
checkpoint | 2.1 Inspection of Materials upon Delivery
label | FREQUENCY: Each Delivery
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Posts shall be inspected upon delivery for compliance and damange. If scratched or missing coating, this may be rectified with a minimum of two coats of a zinc-rich inorganic paint
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 708.07 (b)
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 2.2 Post Installation
label | FREQUENCY: Each Lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Posts shall be installed to the depth, line and spacing shown on the drawings, and to the tolerances in clause 708.07(d).
label | • Posts shall be installed by driving, provided there is no distortion or damage which may reduce their effectiveness.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS:
label | • Fencing Plan
label | • 708.08 (a)
label | • 708.07(d)
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | HP*
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 2.3 W-Beams
label | FREQUENCY: Each Lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • The w-beam sections shall be lapped so that the exposed ends face away from near side approaching traffic.
label | • The edges of the w-beam section or backing plate adjacent to posts shall be fixed in contact with the post or post blocks and all bolts shall be fully tightened.
label | • All bolts on the traffic side of w-beam installations shall be flush with the w-beam
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 708.08(b)
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | HP*
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 2.4 End Treatments
label | FREQUENCY: Each Lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • During installation of wire ropes in the end treatments of w-beam, the Contractor shall ensure that no twisting of the rope occurs.
label | • When rope assemblies are used, the nuts at each end of the rope shall be tightened to a minimum torque of 50 Nm on the assemblies or as per the manufacturer’s requirements.
label | • The Contractor shall maintain tension in the wire ropes in end treatments until the Date of Completion, by keeping the nuts at both ends tightened to 50 Nm or to manufacturer’s requirements.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 708.08 (c)
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | HP*
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 2.5 Delineators
label | FREQUENCY: Each Lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Delineators shall be fastened to the top of w-beams, comprising of a flexible plastic mounting brackets fitted with 100cm2 of Class 1A retro-reflective material
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 708.11
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 2.6 Concrete Maintenance Strip
label | FREQUENCY: Each Lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • The Contractor shall provide maintenance strips beneath the guard fence and terminals as indicated on the drawings and/or as nominated in Table 708.121.
label | • The concrete maintenance strip shall consist of 75 mm depth of N20 strength grade portland cement-based concrete or 20 MPa geopolymer binder-based concrete conforming to the requirements of clause 708.05(g), on 75 mm of compacted Class 3 crushed rock.
label | • Where the concrete maintenance strip is adjacent to kerb or pavement, separation from the kerb or pavement by the use of a cork expansion joint (or approved alternative) shall be produced.
label | • Full depth expansion joints shall be provided perpendicular to the line of the steel beam guard fence 200 mm each side of every post.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS:
label | • 708.12
label | • 708.12 (a)
label | • Table 708.121
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | HP*
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
section | 3 - Completion
checkpoint | 3.1 Tolerance Conformance
label | FREQUENCY: Each lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • W-beam guard fence shall be erected to the following tolerances:
label | (i) Variation from true plan position of posts ±20 mm
label | (ii) Variation of line of w-beams from specified vertical profile ±10 mm
label | (iii) Variation of w-beams from specified horizontal alignment ±20 mm
label | (iv) Variation of posts from vertical +0mm, -15mm
label | (v) Orientation of block &/or postto w-beam +0mm, -15mm
label | (vi) Dimension of holes -0mm, +50mm
label | (vii) Top of bolt head relative to W-Beam -0mm, +5mm
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 708.08 (d)
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 3.2 Certificate of Compliance
label | FREQUENCY: Prior to practical Completion
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Further to clause 708.07 Installation, and prior to the issue of the Certificate of Practical Completion, the Contractor shall arrange for a safety barrier compliance audit on all proprietary guard fence end treatments constructed under the Contract.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 708.1
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | HP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer/Superintendent
label | – – – – – – – – –
text | DATE:
holdpoint | HOLDPOINT AUTHORITY
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: