## res_ITP-01-012 - Hot Mix Asphal
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-01-021 - Type B Fill placement | itp |  |  |  |  | ITP-01-021 - Type B Fill placement REV2
section | 1 - Preliminary Works
checkpoint | 1.1 The current revision drawings/documents are being used including subcontractors copy.
label | FREQUENCY: Prior to commencing
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Current revision drawing/documents are being used including the subcontractors copy.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual Inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP Signed Off
label | – – – – – – – – –
label | HP*
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer / Site Foreman
label | – – – – – – – – –
text | DATE:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to Placement/Each Lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is:
label | • OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | – – – – – – – – –
label | REFERENCE DOCUMENTS:
label | • OHSCP
label | • PHSCP
label | • PCMP
label | • EMP
label | • ECP
label | • CEMP
label | • ERA
label | • QMP
label | • CHMP
label | • SWMS
label | • WP001.02
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual Inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP Signed Off
label | – – – – – – – – –
label | HP*
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer / Site Foreman
label | – – – – – – – – –
text | DATE:
checkpoint | 1.3 Verify Material
label | FREQUENCY: Prior to Placement/Each Lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Type B material shall have a minimum Assigned CBR of 2%, and Assigned Percent Swell less than 2.5% which has been determined in accordance with VicRoads Code of Practice RC 500.20.
label | • Materials that exhibit swells greater than or equal to 2.5% shall be classified as expansive and shall only be used as Type B material if approved by the Superintendent.
label | • Material within the top 400 mm of top of Type B material shall have a swell less than 2.5%.
label | • Materials that exhibit swells of 5% or greater are not permitted.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.04(c)
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Site Inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: Test Record (If silt is observed)
label | – – – – – – – – –
label | HP*
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer / Site Foreman
label | – – – – – – – – –
text | DATE:
checkpoint | 1.4 Excavation Permit
label | FREQUENCY: Each lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • An excavation permit must be issued prior to any excavation commencing including removal of unsuitable material.
label | • Plant and equipment shall be appropriate for the task.
label | • Excavation operations shall not disturb areas outside the limit of excavation
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: Excavation permit
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP Signed Off
label | – – – – – – – – –
label | HP*
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer
label | – – – – – – – – –
text | DATE:
section | 2 - Construction Works
checkpoint | 2.1 Survey set-out
label | FREQUENCY: Prior to Commencing Excavation
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Survey activities undertaken to ensure and validate that all works meet level and location requirements.
label | • The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity.
label | • IFC and latest available revision used
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: Latest IFC Drawings
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Site Inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: Survey records & pegs on the ground
label | – – – – – – – – –
label | SCP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer/ Surveyor
label | – – – – – – – – –
text | DATE:
checkpoint | 2.2 Inspection of fill area
label | FREQUENCY: Each lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Superintendent.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 204.10 (b)
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual Inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP Signed Off
label | – – – – – – – – –
label | HP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer / Superintendent
label | – – – – – – – – –
text | DATE:
holdpoint | HOLDPOINT AUTHORITY
checkpoint | 2.3 Keyed fill layer
label | FREQUENCY: During Excavation
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Placement surface textured to ensure layers keyed into each other.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(d)(i)
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual Inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP Signed Off
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 2.4 Layer Thickness
label | FREQUENCY: During Excavation
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Layers placed and spread in uniform compacted layers not thicker than 200mm.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(d)(iii)
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual Inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP Signed Off
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 2.5 Maximum Lot Size
label | FREQUENCY: During Excavation
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Lot size for testing is to be one day's production or 10,000m2, whichever is lesser.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.142
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual Inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP Signed Off
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 2.6 Type B Placement
label | FREQUENCY: Prior to Placement/Each Lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Type B material shall be placed in locations shown on the drawings, or if surplus Type B material is available, it may be used in locations specified for Type C material.
label | • The highest quality Type B materials available shall be reserved for placement in the higher levels of Type B fills being constructed.
label | • Type B material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm.
label | • Where Type B material contains 25% or more of rock by volume, which will not break down during compaction to meet the maximum particle dimension required for a 200 mm thick layer, the loose thickness of each layer may equal 125% of the typical maximum particle dimension of the rock up to a maximum layer thickness of 500 mm.
label | • Any rock with a maximum particle dimension greater than 80% of the loose thickness of the layer shall be removed.
label | • The material shall be placed and compacted such that voids are completely filled with fine material.
label | • Type B material containing rock with a particle dimension greater than 150 mm after compaction shall not be placed within 400 mm of the top of Type B and/or Type C material zones.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 204.10 (d) (iii).
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual Inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP Signed Off
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer / Site Foreman
label | – – – – – – – – –
text | DATE:
checkpoint | 2.7 Proof Roll
label | FREQUENCY: Each lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
label | – – – – – – – – –
label | REFERENCE DOCUMENTS:
label | • 173.03
label | • 204.12)
label | • 204.10 (b)
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual Inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP Signed Off
label | – – – – – – – – –
label | HP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Foreman/ Superintendent
label | – – – – – – – – –
text | DATE:
holdpoint | HOLDPOINT AUTHORITY
section | 3 - Testing
checkpoint | 3.1 Reduced Test Frequency
label | FREQUENCY: Each lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Initial Testing requirements shall satisfy the full requirements as detailed in the specification.
label | • Once three consecutive lots have achieved specified requirement, Superintendent can agree to reduce frequency of testing of subsequent lots to the reduced testing frequency specified in Table 204.141.
label | • Reduced frequency resets if one lot fails.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.131
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Test Record
label | – – – – – – – – –
label | RECORD OF CONFORMITY: Test Records
label | – – – – – – – – –
label | AP
label | – – – – – – – – –
label | RESPONSIBILITY: Project Engineer/Superintendent
label | – – – – – – – – –
text | DATE:
checkpoint | 3.2 Compaction Testing
label | FREQUENCY: First lot then every Second thereafter
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Type B compaction required for Scale B is 98% Characteristic Value of Density Ratio
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.131
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: Compaction Test Records
label | – – – – – – – – –
label | TP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 3.3 CBR/Swell
label | FREQUENCY: 1 lot test to determine assigned CBR and Swell
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: CBR: ≥ 2%, Swell: ≤ 1.5%
label | – – – – – – – – –
label | REFERENCE DOCUMENTS:
label | • VicRoads Spec.
label | • Cl. 204.14(a)(i)
label | • Table 204.141
label | • Table 204.041
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: CBR/Swell Test Records
label | – – – – – – – – –
label | TP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 3.4 Survey Conformance (at Subgrade Level)
label | FREQUENCY: Each lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • The number of measurements and the tolerances of the mean and standard deviation from the theoretical surface level must comply with Table 204.031
label | ○ Scale B: Range x = +5,-25
label | ○ Max S = 15mm
label | ○ 40 measurements per lot
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 204.03
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Survey conformance point
label | – – – – – – – – –
label | RECORD OF CONFORMITY:
label | • Survey report
label | • Lot Register
label | – – – – – – – – –
label | WP SCP
label | – – – – – – – – –
label | RESPONSIBILITY: Site Engineer & Surveyor
label | – – – – – – – – –
text | DATE:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: