## Sheet1
checkpoint | 4.5 - Cementitious Repair Mortar Test Cubes
label | Frequency: Test Specimens
label | Acceptance Criteria: Three 75 mm test cubes shall be taken from the first batch of material mixed, then three 75 mm cubes for every 100 kg of material used thereafter to test for compressive strength. Test cubes shall be made of steel or polystyrene and shall be fully sealed. | [16 empty] | checkpoint | 2.1 - Assessment of Affected Concrete
label | Cubes: | [16 empty] | label | Frequency: For each element, prior to Works commencing
label | 2 specimens tested at 7 day strength | [16 empty] | label | Acceptance Criteria: Contractor shall assess the affected concrete to determine influence of spalling, deterioration, and honeycombing on the load bearing capacity, serviceability and durability of the structure.
label | 1 specimen tested at 28 day strength | [16 empty] | label | 0
label | 0 | [16 empty] | label | 0
label | 0 | [16 empty] | label | 0
label | 0 | [16 empty] | label | 0
label | 0 | [16 empty] | label | 0
label | Reference Documents: VicRoads Spec. Cl.689.12 (a) Table 689.061 AS1012.8.3 AS1012.9 | [16 empty] | label | 0
label | Inspection / Test Method: Test | [16 empty] | label | 0
label | Record of Conformity: Test Results Signed ITP | [16 empty] | label | Reference Documents: VicRoads Spec. Cl.689.02
label | IP | [16 empty] | label | Inspection / Test Method: Visual Inspection
label | Responsibility: SE/PE | [16 empty] | label | Record of Conformity: Hold point released
holdpoint | HOLD POINT | [16 empty] | label | HP
[18 empty] | label | Responsibility: SE/PE and Superintendent
[5 empty] | PASTE VALUES HERE | [12 empty] | holdpoint | HOLD POINT
[5 empty] | 4.5 |  |  |  | 4.5 | Cementitious Repair Mortar Test Cubes | Test Specimens | Three 75 mm test cubes shall be taken from the first batch of material mixed, then three 75 mm cubes for every 100 kg of material used thereafter to test for compressive strength. Test cubes shall be made of steel or polystyrene and shall be fully sealed. | VicRoads Spec. Cl.689.12 (a) Table 689.061 AS1012.8.3 AS1012.9 | Test | Test Results Signed ITP | IP | SE/PE | checkpoint | 2.2 - Deviations from Manufacturer's TDS and/or Specification
|  |  |  | TASK ACTIVITY | Cementitious Repair Mortar Test Cubes | [6 empty] | Cubes: | [5 empty] | label | Frequency: For each element, prior to Works commencing
|  |  |  | FREQUENCY | Test Specimens | [6 empty] | 2 specimens tested at 7 day strength | [5 empty] | label | Acceptance Criteria: The contractor shall perform concrete repair work in conformity with the manufacturers specifications. Any deviations from manufacturers specification must be submitted for approval as an updated WMS and/or ITP.
|  |  |  | ACCEP CRTIERA | Three 75 mm test cubes shall be taken from the first batch of material mixed, then three 75 mm cubes for every 100 kg of material used thereafter to test for compressive strength. Test cubes shall be made of steel or polystyrene and shall be fully sealed. | [6 empty] | 1 specimen tested at 28 day strength | [5 empty] | label | 0
|  |  |  | ACCEP CRTIERA | Cubes: | [12 empty] | label | 0
|  |  |  | ACCEP CRTIERA | 2 specimens tested at 7 day strength | [12 empty] | label | 0
|  |  |  | ACCEP CRTIERA | 1 specimen tested at 28 day strength | [12 empty] | label | 0
|  |  |  | ACCEP CRTIERA | [13 empty] | label | 0
|  |  |  | ACCEP CRTIERA | [13 empty] | label | 0
|  |  |  | ACCEP CRTIERA | [13 empty] | label | 0
|  |  |  | ACCEP CRTIERA | [13 empty] | label | Reference Documents: VicRoads Spec. Cl.689.08 Product TDS
|  |  |  | ACCEP CRTIERA | [13 empty] | label | Inspection / Test Method: Visual Inspection
|  |  |  | Reference Documents | VicRoads Spec. Cl.689.12 (a) Table 689.061 AS1012.8.3 AS1012.9 | [12 empty] | label | Record of Conformity: Hold point released
|  |  |  | Inspection/test method | Test | [12 empty] | label | HP
|  |  |  | Record of Conformity: | Test Results Signed ITP | [12 empty] | label | Responsibility: SE/PE and Superintendent
|  |  |  | HP/WP/IP | IP | [12 empty] | holdpoint | HOLD POINT
|  |  |  | RESPONS | SE/PE | [12 empty] | checkpoint | 2.3 - Work Method Statement and Inspection and Test Plans
[18 empty] | label | Frequency: Prior to commencing repair
[18 empty] | label | Acceptance Criteria: WMS and ITPs completed by FH should be reviewed and approved by the Superintendent
[18 empty] | label | Reference Documents: VicRoads Spec. Cl.689.13
[18 empty] | label | Inspection / Test Method: Document Review
[18 empty] | label | Record of Conformity: Hold point released
|  | method | freq | category | respons | ver doc | [11 empty] | label | HP
|  | VicRoads Spec. Cl.689.12 (a) Table 689.061 AS1012.8.3 AS1012.9 | Test | Test Results Signed ITP | IP | SE/PE | [11 empty] | label | Responsibility: SE/PE and Superintendent
[18 empty] | holdpoint | HOLD POINT
[18 empty] | checkpoint | 3.1 - Material approval and Reference
[18 empty] | label | Frequency: For each product, prior to Works commencing
4.1 | Surface Preparation | Each element | For all types of patch repair all defective and delaminated concrete and existing repair materials shall be broken back to a sound and dense concrete surface. Defective concrete shall be removed using light hand held percussive equipment or high pressure water jetting | VicRoads Spec. Cl.689.08 (b) and (c) | Visual Inspection | Hold point released Signed ITP | HP | SE/PE | [9 empty] | label | Acceptance Criteria: Is the selected repair mortar material capable of:
|  |  | Resulting cover allowance: | [14 empty] | label | being hand applied in vertical and overhead sections up to 30 mm thick in one application with no slumping;
|  |  | Exposure classification A and B1 = 20mm minimum | [14 empty] | label | achieving a drying shrinkage ≤600 microstrain;
|  |  | Exposure classification B2, C1 and C2 = 50mm minimum | [14 empty] | label | achieving a minimum wet density of 1600kg/m³;
|  |  | All concrete surfaces and mortar substrates shall be sound, clean and free from dust, oils, and grease and surface contaminants. All loose and unsound materials and surface laitance shall be removed | [14 empty] | label | achieving the strengths and bonds conforming to the requirements in Table 689.061.
|  |  | The concrete substrate and any exposed steel reinforcement shall be cleaned by a final wash down or by blowing down with oil free compressed air to ensure removal of all residual contamination. The prepared concrete substrate shall be thoroughly pre-wetted with clean fresh water and shall be surface dry prior to application of repair material | [14 empty] | label | Is the selected fairing coat material capable of:
[18 empty] | label | application to 0-3mm thick;
4.2 | Pre Application of Repair Mortar | Prior to each repair | Reinstatement of prepared areas shall not commence until: | VicRoads Spec. Cl.689.08 (e) | Visual/ Measure | Hold point released | HP | SE/PE | [9 empty] | label | covering a large area without shrinkage cracking.
|  |  | (i) a joint measurement of the repair area by superintendent and Contractor | [14 empty] | label | The following information shall be provided with each batch:
|  |  | (ii) evidence the area conforms with specifications | [14 empty] | label | Manufacturer's name and address
|  |  | (iii) Contractors quality procedures have been sighted by superintendent | [14 empty] | label | Product reference
|  |  | The repair mortar shall be thoroughly mixed in whole bags with potable water prior to commencement of application. | [14 empty] | label | Batch number of identification
|  |  | All materials shall be applied in accordance with the manufacturer’s specifications or instructions for use in a continuous process. | [14 empty] | label | Quantity manufactured in the batch
[18 empty] | label | Certificate of date of manufacture
4.3 | Application of Repair Mortar | Each Repair | Temperature at time of application: | VicRoads Spec. Cl.689.08 (e) | Visual | Signed ITP | IP | SE/PE | [9 empty] | label | Insert TeamBinder Material Approval Number:
|  |  | below 5°C or above 35°C | [14 empty] | label | Reference Documents: VicRoads Spec. Cl.689.08 (a)
|  |  | Repair material shall be applied while the substrate bonding coat is still tacky | [14 empty] | label | Inspection / Test Method: Document Review
|  |  | Where formwork is used to facilitate the patch repair, it shall be pre-treated such that it prevents moisture absorption from the repair mortar and positioned such that it does not inhibit effective compaction of the repair material. | [14 empty] | label | Record of Conformity: Attach repair mortar product TDS Attach fairing coat product TDS Signed ITP
|  |  | Concrete shall be rebuilt to the original surface profile using a cementitious repair material. Where the existing concrete cover to the steel reinforcement is less than the design requirements, the new repair shall be profiled as required to ensure that a minimum cover of polymer modified repair material to the steel reinforcement is achieved as specified in clause 689.08(b). | [14 empty] | label | IP
[18 empty] | label | Responsibility: SE/PE
4.4 | Measuring Tolerances | Each Repair | Tolerances applicable are: | VicRoads Spec. Cl.689.11 | Visual/ Measure | Signed ITP | WP | SE/PE | [9 empty] | checkpoint | 4.1 - Surface Preparation
|  |  | Edges and Surfaces: ±3mm | [14 empty] | label | Frequency: Each element
|  |  | Maximum allowance for irregularities: 3 mm with a 2 m straightedge | [14 empty] | label | Acceptance Criteria: For all types of patch repair all defective and delaminated concrete and existing repair materials shall be broken back to a sound and dense concrete surface. Defective concrete shall be removed using light hand held percussive equipment or high pressure water jetting
|  |  | Maximum allowance for unevenness: 1 mm with a 300 mm straightedge | [14 empty] | label | Resulting cover allowance:
[18 empty] | label | Exposure classification A and B1 = 20mm minimum
4.5 | Cementitious Repair Mortar Test Cubes | Test Specimens | Three 75 mm test cubes shall be taken from the first batch of material mixed, then three 75 mm cubes for every 100 kg of material used thereafter to test for compressive strength. Test cubes shall be made of steel or polystyrene and shall be fully sealed. | VicRoads Spec. Cl.689.12 (a) Table 689.061 AS1012.8.3 AS1012.9 | Test | Test Results Signed ITP | IP | SE/PE | [9 empty] | label | Exposure classification B2, C1 and C2 = 50mm minimum
|  |  | Cubes: | [14 empty] | label | All concrete surfaces and mortar substrates shall be sound, clean and free from dust, oils, and grease and surface contaminants. All loose and unsound materials and surface laitance shall be removed
|  |  | 2 specimens tested at 7 day strength | [14 empty] | label | The concrete substrate and any exposed steel reinforcement shall be cleaned by a final wash down or by blowing down with oil free compressed air to ensure removal of all residual contamination. The prepared concrete substrate shall be thoroughly pre-wetted with clean fresh water and shall be surface dry prior to application of repair material
|  |  | 1 specimen tested at 28 day strength | [14 empty] | label | 0
[18 empty] | label | 0
[18 empty] | label | Reference Documents: VicRoads Spec. Cl.689.08 (b) and (c)
[18 empty] | label | Inspection / Test Method: Visual Inspection
[18 empty] | label | Record of Conformity: Hold point released Signed ITP
[18 empty] | label | HP
[18 empty] | label | Responsibility: SE/PE
[18 empty] | holdpoint | HOLD POINT
[18 empty] | checkpoint | 4.2 - Pre Application of Repair Mortar
[18 empty] | label | Frequency: Prior to each repair
[18 empty] | label | Acceptance Criteria: Reinstatement of prepared areas shall not commence until:
[18 empty] | label | (i) a joint measurement of the repair area by superintendent and Contractor
[18 empty] | label | (ii) evidence the area conforms with specifications
[18 empty] | label | (iii) Contractors quality procedures have been sighted by superintendent
[18 empty] | label | The repair mortar shall be thoroughly mixed in whole bags with potable water prior to commencement of application.
[18 empty] | label | All materials shall be applied in accordance with the manufacturer’s specifications or instructions for use in a continuous process.
[18 empty] | label | 0
[18 empty] | label | 0
[18 empty] | label | Reference Documents: VicRoads Spec. Cl.689.08 (e)
[18 empty] | label | Inspection / Test Method: Visual/ Measure
[18 empty] | label | Record of Conformity: Hold point released
[18 empty] | label | HP
[18 empty] | label | Responsibility: SE/PE
[18 empty] | holdpoint | HOLD POINT
[18 empty] | checkpoint | 4.3 - Application of Repair Mortar
[18 empty] | label | Frequency: Each Repair
[18 empty] | label | Acceptance Criteria: Temperature at time of application:
[18 empty] | label | below 5°C or above 35°C
[18 empty] | label | Repair material shall be applied while the substrate bonding coat is still tacky
[18 empty] | label | Where formwork is used to facilitate the patch repair, it shall be pre-treated such that it prevents moisture absorption from the repair mortar and positioned such that it does not inhibit effective compaction of the repair material.
[18 empty] | label | Concrete shall be rebuilt to the original surface profile using a cementitious repair material. Where the existing concrete cover to the steel reinforcement is less than the design requirements, the new repair shall be profiled as required to ensure that a minimum cover of polymer modified repair material to the steel reinforcement is achieved as specified in clause 689.08(b).
[18 empty] | label | 0
[18 empty] | label | 0
[18 empty] | label | 0
[18 empty] | label | Reference Documents: VicRoads Spec. Cl.689.08 (e)
[18 empty] | label | Inspection / Test Method: Visual
[18 empty] | label | Record of Conformity: Signed ITP
[18 empty] | label | IP
[18 empty] | label | Responsibility: SE/PE
[18 empty] | holdpoint | HOLD POINT
[18 empty] | checkpoint | 4.4 - Measuring Tolerances
[18 empty] | label | Frequency: Each Repair
[18 empty] | label | Acceptance Criteria: Tolerances applicable are:
[18 empty] | label | Edges and Surfaces: ±3mm
[18 empty] | label | Maximum allowance for irregularities: 3 mm with a 2 m straightedge
[18 empty] | label | Maximum allowance for unevenness: 1 mm with a 300 mm straightedge
[18 empty] | label | 0
[18 empty] | label | 0
[18 empty] | label | 0
[18 empty] | label | 0
[18 empty] | label | Reference Documents: VicRoads Spec. Cl.689.11
[18 empty] | label | Inspection / Test Method: Visual/ Measure
[18 empty] | label | Record of Conformity: Signed ITP
[18 empty] | label | WP
[18 empty] | label | Responsibility: SE/PE
[18 empty] | holdpoint | HOLD POINT
[18 empty] | checkpoint | 4.5 - Cementitious Repair Mortar Test Cubes
[18 empty] | label | Frequency: Test Specimens
[18 empty] | label | Acceptance Criteria: Three 75 mm test cubes shall be taken from the first batch of material mixed, then three 75 mm cubes for every 100 kg of material used thereafter to test for compressive strength. Test cubes shall be made of steel or polystyrene and shall be fully sealed.
[18 empty] | label | Cubes:
[18 empty] | label | 2 specimens tested at 7 day strength
[18 empty] | label | 1 specimen tested at 28 day strength
[18 empty] | label | 0
[18 empty] | label | 0
[18 empty] | label | 0
[18 empty] | label | 0
[18 empty] | label | Reference Documents: VicRoads Spec. Cl.689.12 (a) Table 689.061 AS1012.8.3 AS1012.9
[18 empty] | label | Inspection / Test Method: Test
[18 empty] | label | Record of Conformity: Test Results Signed ITP
[18 empty] | label | IP
[18 empty] | label | Responsibility: SE/PE
[18 empty] | holdpoint | HOLD POINT

## Sheet2
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Name:
text | Position:
text | Date Completed:
holdpoint | Sign ITP