## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | ITP 003 - Stripping, Bulk Excavation, Fill Placement to Subgrade | itp |  |  |  | Yes | ITP 003 - Stripping, Bulk Excavation, Fill Placement to Subgrade | 0268cb99-c885-4f54-82ee-22da8f20f23f
checkpoint-status |  |  | checkpoint | 1.1 Check for correct documentation
label | b6b566cb-7166-4223-9629-28c4004b2213 |  | label | FREQUENCY: Prior to commencing works
label | 7dc30e0b-ffb9-488d-a6b9-55f712b2d11b |  | label | ACCEPTANCE CRITERIA: Current revision drawing is being used including the subcontractors copy. Current Revision to be obtained via Aconex.
label | 5533ccbc-adf3-4a02-afc2-8afb4a8fa021 |  | label | REFERENCE DOCUMENTS: Drawings and drawing registers, Aconex
label | 4b40a0f0-5867-4d78-88e6-81bb15ac56e2 |  | label | INSPECTION/TEST METHOD: Verify
label | bb749009-5e21-4661-8357-b42c8d5f190f |  | label | RECORD OF CONFORMITY: Up to date drawing sets and this ITP signed
label | 2ccea956-85f1-4bc6-92ca-356492e18eec |  | label | IP
label | 3624443e-bb7b-4fbe-9984-46ce08bcbbc9 |  | label | RESPONSIBILITY: Project Engineer
text | 5c27b7ec-39b9-4893-b750-ee87a864b865 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 Survey
label | a6e20ea9-c8f1-427a-9962-6f652e2ba8ea |  | label | FREQUENCY: Prior to commencing works
label | 1c7f8417-b2ec-4a5d-8de0-aaff79fe94ae |  | label | ACCEPTANCE CRITERIA: Area has been surveyed, highlighting any areas where excavations should not occur (e.g. exclusion zone)
label | d811cc83-477c-42e1-92d7-701809cf90ce |  | label | REFERENCE DOCUMENTS: Drawings Permits
label | 2ea3a27c-cda0-4c8e-ba23-6f38b33761c6 |  | label | INSPECTION/TEST METHOD: Verify
label | 5e87cd17-fa49-40d4-9aab-08ca420251ca |  | label | RECORD OF CONFORMITY: This ITP signed
label | 7ef5fc3c-8682-419f-9e79-55e6805eac6a |  | label | IP
label | 007853ca-a582-47c7-9ec9-e68b570f972f |  | label | RESPONSIBILITY: Project Engineer
text | 9edd2914-9d33-4449-9162-00c8a87ba230 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 Implementation of all measures and controls
label | 8dde2941-36e0-4ed3-893a-6e38e2e6996b |  | label | FREQUENCY: Prior to works
label | 688b94c9-7eb9-4689-8a25-86934d84a7d5 |  | label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS and WP
label | 1273d6da-6fd2-4717-8f98-5961f132ce5c |  | label | REFERENCE DOCUMENTS: PSP, EMP, TMP, SWMS, WP
label | cc957e10-e42f-4d30-9b6d-e95be664d97a |  | label | INSPECTION/TEST METHOD: Verify
label | dad193e0-a207-438e-93b5-08d46f555ec3 |  | label | RECORD OF CONFORMITY: This ITP signed
label | 08b9abc0-ea1b-4cfe-8a5b-76627a88d35c |  | label | HP*
label | 75cfaa9f-2344-444d-8eab-27ef64e0c185 |  | label | RESPONSIBILITY: Project Engineer
text | 59697087-c166-48c9-b010-5e995380b08f |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.4 APAM Permits & Procedures
label | 29bb4fe8-acdf-4851-ab55-77a60a70934c |  | label | FREQUENCY: Prior to commencing works
label | 634a2350-0b51-4076-99f1-daf7e7354cd9 |  | label | ACCEPTANCE CRITERIA: An Excavation Permit and, if working near HV electrical, an Electricity Supply Isolation form, cabling permit and an Isolation permit has been issued by Melbourne Airport. Fulton Hogan Excavation permit issued to plant operators.
label | d90a83a1-76bc-46cb-a5e9-24499bec106b |  | label | REFERENCE DOCUMENTS: CP17038- LAN-DET- PM-SP-0001 cl. 8.3.4
label | 9f7c54b8-b983-4df1-98f2-d3f51e15baa7 |  | label | INSPECTION/TEST METHOD: Approved permits
label | e6131aaa-58b9-4ceb-8d27-0c5641eb90cb |  | label | RECORD OF CONFORMITY: This ITP signed/ Attached excavati on permit
label | f8c2c347-b156-4f48-b753-f94e32c3f8ef |  | label | HP*
label | e85e012d-ad65-48cc-a570-5b818d2cd3a6 |  | label | RESPONSIBILITY: Project Engineer
text | deb4f314-25a3-4f1b-a50b-a6ec9159c58f |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.5 Maintenance of Pavements
label | a7d0afbb-e845-4cce-b180-ce9199b435f9 |  | label | FREQUENCY: Prior to commencing works
label | 174924b6-36fa-4468-b9a5-831a412886bb |  | label | ACCEPTANCE CRITERIA: Dilapidation Survey carried out with the Principal’s Representative present. Damages to existing pavements are checked and repaired to the satisfaction of the Principals Rep. Include photographic record.
label | 8d28ddf4-0083-4baa-90da-32444e9a1437 |  | label | REFERENCE DOCUMENTS: CP17038- LAN-DET- PM-SP-0001 cl. 2.3.2 Dilapidation Report
label | e55b7253-c087-460f-a1d5-2546eab3ef8e |  | label | INSPECTION/TEST METHOD: Aconex Approval
label | 0c493b84-454a-4e09-b066-2a2af9cdf330 |  | label | RECORD OF CONFORMITY: This ITP signed
label | 5fb4977d-c78a-4c4c-81ea-04b3a6872f83 |  | label | IP
label | 9b24f673-675d-4266-883d-57f0acff1d41 |  | label | RESPONSIBILITY: Project Engineer / Principal’s Representative
text | 797691f6-38fb-4c23-be77-0308f4e01e0e |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.6 Plant and Equipment
label | ab16dbd1-8c61-4dd9-b31d-431fddf343fe |  | label | FREQUENCY: Prior to commencing works
label | e6d7200d-77e1-4597-a2b7-6832b812736e |  | label | ACCEPTANCE CRITERIA: Plant and equipment used in the Works shall comply with relevant specification.
label | 3530aa23-bb9d-40d5-9742-0bdcdc55300a |  | label | REFERENCE DOCUMENTS: CP17038- LAN-DET- PM-SP-0001 cl. 2.6.2
label | 7e5caa24-5f23-4776-991f-986f3bef9a69 |  | label | INSPECTION/TEST METHOD: Visual Inspection
label | 232e89d5-e965-449e-8b28-6944914a14b0 |  | label | RECORD OF CONFORMITY: This ITP Signed
label | ae33d7b5-6849-47aa-81e8-cde793a8afaf |  | label | IP
label | aef41732-d368-4094-8cf0-fa2a9231f90f |  | label | RESPONSIBILITY: Project Engineer
text | b795e54a-5f47-4d85-ac43-34b18e4dec11 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.7 Fill Materials
label | b079fb71-5902-4ed2-9543-f853b2b1bd11 |  | label | FREQUENCY: Select Fill Only
label | 3c8c338f-47ee-4526-aeb9-f3dc77f52935 |  | label | ACCEPTANCE CRITERIA: Principal’s Representative to review details of proposed fill material prior to placement. Compliance to Table 2.3 of CP17038-LAN-DET- PM-SP-0001. Fill material shall comply with Vicroads Spec 204 for a Fill Material Type B. Type B material shall be free of topsoil, deleterious and/or perishable matter.
label | 1a9b8a89-4f75-4890-b4e0-311792943101 |  | label | REFERENCE DOCUMENTS: CP17038- LAN-DET- PM-SP-0001 cl. 2.5.2 Vicroads Spec 204, Table 204.041
label | 3a74bf07-9c18-4967-a01a-9a6d92bcd225 |  | label | INSPECTION/TEST METHOD: Verify Test Results
label | b2e6630d-6e1e-4b86-9b8b-eb862f73e638 |  | label | RECORD OF CONFORMITY: This signed ITP Aconex Test Report
label | e41df94b-04d1-4eea-82ea-f0feef7c010e |  | label | HP*
label | a0304457-b9ae-462a-8278-c799ecbdc1d6 |  | label | RESPONSIBILITY: Project Engineer
text | d8ce7c6f-6cb9-4ab4-af57-f3d24c7b68cb |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.8 Lime Stabilisation
label | 88197191-4edc-419c-bd6d-0254ef93689a |  | label | FREQUENCY: Prior to commencing work
label | a53bef6c-6400-44da-bd8b-ea41989ddfb4 |  | label | ACCEPTANCE CRITERIA: Submitted details (inc spreading rate) of proposed lime stabilisation to Principal’s representative for approval.
label | e4714e20-1d1a-487b-9fc8-57481b45f666 |  | label | Surface level measurement shall be undertaken in lots not exceeding 4000 m2 in accordance with the procedures specified in Section 173 - Examination and Testing of Materials and Work (Roadworks).
label | abfaddc0-b10d-4e0a-95e4-dfefebd550ba |  | label | Quicklime and hydrated lime shall meet the requirements of AS1672 as listed in Section 175.
label | d2f68609-0f77-4fd8-9e5a-598fa64eb247 |  | label | REFERENCE DOCUMENTS: CP17038- LAN-DET- PM-SP-0001 cl. 2.6.1 Vicroads Spec 290
label | 7d7452ec-158c-4a51-81f4-61a235dd52bf |  | label | INSPECTION/TEST METHOD: Approval point
label | 7bea2fad-1dcd-48ae-af56-f8618a27e2f1 |  | label | RECORD OF CONFORMITY: This signed ITP
label | 75c80127-0982-4aa1-b13a-4b4671d60d82 |  | label | AP
label | 0f4ccd3f-170d-4119-961f-89daa5012704 |  | label | RESPONSIBILITY: Project Engineer
text | a33ed1dc-32fb-4153-9170-05c65acd4ac3 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 Protection and Relocation of Services
label | da622c04-458d-4ab9-a9aa-f177eee97e1a |  | label | FREQUENCY: Each Lot
label | 67afe1f8-9e44-458a-b88f-59cace2efbba |  | label | ACCEPTANCE CRITERIA: Protect existing services and ensure sufficient cover to finished surface level otherwise service to be relocated/reinstated if insufficient cover would result following the works; Consult APAM stakeholders regarding any works involving existing services such that operational and safety requirements are maintained.
label | 724063d5-c09a-49ed-8fd2-a866c630fca9 |  | label | REFERENCE DOCUMENTS: CP17038- LAN-DET- PM-SP-0001 cl. 2.3.4
label | 9f22acea-997c-47ac-b9b8-656e643cb2f8 |  | label | INSPECTION/TEST METHOD: Verify
label | aa5ddd04-8c05-4e0c-835a-4b36293287cf |  | label | RECORD OF CONFORMITY: This signed ITP
label | 3eb2e5d6-9674-4235-a420-e90e7f6909c5 |  | label | AP
label | 243ef53c-9f35-421c-9ebc-6602c5aacd0b |  | label | RESPONSIBILITY: Project Engineer
text | b38a15e0-6b31-459c-b977-2843b7d92279 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Drainage
label | 80d9f411-88a5-41a7-ba02-44dbc7b1ad45 |  | label | FREQUENCY: Each lot
label | 862caf8a-131c-4c19-8cfb-f6121a42e8ad |  | label | ACCEPTANCE CRITERIA: All excavation and filling are free draining to low points clear of the Works; All earthworks free from standing water; Temporary pollution control devices/ponds in place to prevent siltation/degradation of water’s quality in existing drainage systems and meet criteria set by EMP.
label | 1950c783-e4e2-43f6-ac0a-94c1601b2f44 |  | label | REFERENCE DOCUMENTS: CP17038- LAN-DET- PM-SP-0001 cl. 2.3.5 CEMP
label | 9b8c954f-aa4b-42ce-a30a-afa07bc8089a |  | label | INSPECTION/TEST METHOD: Verify
label | 65669ccf-37b7-42fb-9104-065330b3c1c2 |  | label | RECORD OF CONFORMITY: This signed ITP
label | 2a3bea77-20a6-4df0-9b5f-b55a3d9a484e |  | label | IP
label | bc844788-f205-4d52-92f5-f293f387b465 |  | label | RESPONSIBILITY: Project Engineer
text | 67e7649d-d87d-4d32-b563-689c6928891a |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Dust Suppression
label | dd4db490-3b1d-4a4e-89f1-63dd80487bc1 |  | label | FREQUENCY: Each Lot
label | ca3f40a0-2460-47b0-bd9a-58d512ec174b |  | label | ACCEPTANCE CRITERIA: Prevention of dust during earthworks and subgrade preparation (Water Cart, tarps etc.); Truck mounted water sprayer keeping dust moist to allow for reliable operation 24 hours per day.
label | aea9166a-a871-4bdf-b465-c74952760ec8 |  | label | REFERENCE DOCUMENTS: CP17038- LAN-DET-PM- SP-0001 cl. 2.3.6
label | 1d89dd91-2664-4668-811b-557532fbce1c |  | label | INSPECTION/TEST METHOD: Visual Inspection
label | 58d7194f-6d8c-4458-9e4a-91c7a5ee6797 |  | label | RECORD OF CONFORMITY: This signed ITP
label | fb18a8f5-73e4-4a75-b58e-111550ccdb0c |  | label | IP
label | 88c12133-5fab-477d-940d-ea2c75a5c1f7 |  | label | RESPONSIBILITY: Project Engineer
text | 30dbaca4-df2e-45b1-afd5-53c80f824b8f |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Stockpiling Material
label | 3fbb53f5-6b8e-42c8-9725-ad5ddb2439fc |  | label | FREQUENCY: Each lot
label | 8b510cd9-e733-4f83-9486-6062ffd7c85c |  | label | ACCEPTANCE CRITERIA: Excavated material placed in appropriate spoil disposal area as per EMP and will be treated as PFAS contaminated unless testing proves otherwise.
label | 9a8a8b45-43f3-44c9-a1b5-ca14177962bc |  | label | REFERENCE DOCUMENTS: CP17038- LAN-DET-PM- SP-0001 cl. 2.4.3.2
label | 8b4bdb9d-83cd-40cc-aa48-a43901a14853 |  | label | INSPECTION/TEST METHOD: Verify
label | a8ba1c5d-8d0b-460b-b6f6-8c35b249594c |  | label | RECORD OF CONFORMITY: This signed ITP Aconex
label | 0f143eef-d8ca-4793-8460-33a3dd0a14a0 |  | label | HP*
label | ada0111c-eef9-4a5f-ae43-075d73c8e4a7 |  | label | RESPONSIBILITY: Project Engineer
text | e4bfa078-0238-4b73-8bfe-cfc9302ed38b |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 Excavation
label | 8acf6cc2-f85d-4443-9f04-34b7c41b2f32 |  | label | FREQUENCY: Each Lot
label | 378225fc-af75-48b3-aa75-b210f352e66c |  | label | ACCEPTANCE CRITERIA: Excavate every type of material encountered within the limit of earthworks to the lines and levels indicated on the drawings. All materials removed to be classified as topsoil, select fill, concrete or unsuitable material.
label | b4822271-53c2-467c-a9da-87630b578d5b |  | label | REFERENCE DOCUMENTS: CP17038- LAN-DET-PM- SP-0001 cl. 2.4.1
label | cb285f63-fb15-441e-aea3-10d6e69179ac |  | label | INSPECTION/TEST METHOD: Inspection Point
label | a360cd08-7e1c-4e4e-9a80-02de57a3994d |  | label | RECORD OF CONFORMITY: This signed ITP
label | 9e5292a2-ff5d-4697-b616-c999f70cf837 |  | label | HP*
label | ab2abbdc-fb43-4317-973a-ef83826652f9 |  | label | RESPONSIBILITY: Project Engineer
text | 50220d09-ae6c-457c-a6a3-1095130c8799 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 Proof Roll
label | d57ef6e2-5dd5-4f41-a4a3-0f969563ae61 |  | label | FREQUENCY: Each Subgrade Lot and Select Fill Layer
label | da2a4f19-c4c5-4f0b-b79a-abfea66817b5 |  | label | ACCEPTANCE CRITERIA: Proof roll required after subgrade following trimming to identify any soft areas.
label | d4e93a8b-e89c-40e2-96ed-167cd38d9407 |  | label | REFERENCE DOCUMENTS: CP17038- LAN-DET-PM- SP-0001 cl. 2.6.1
label | fc009d8e-5e82-4ae5-880e-85e34e9c8470 |  | label | INSPECTION/TEST METHOD: Visual Inspection
label | 76354d18-2a62-4e7e-8e5a-fcc5b17e5fb5 |  | label | RECORD OF CONFORMITY: This signed ITP
label | a85ffd31-345e-4a38-9c34-c9874f4a3309 |  | label | WP*
label | 8cc42d60-d80e-496f-8372-ab6810f031e5 |  | label | RESPONSIBILITY: Project Engineer
text | ad907e2d-5f7a-4709-aead-dfc7f6854d20 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.7 Testing
label | 3e6a9eeb-b681-4bd6-855e-fc5246ab29d5 |  | label | FREQUENCY: Each Subgrade Lot
label | fb333b0e-8647-4de8-b302-14b1bd171fb0 |  | label | ACCEPTANCE CRITERIA: In-field Subgrade CBR is not less than 3%
label | e73eca7a-44d1-4b08-b184-9f7b5028bc78 |  | label | REFERENCE DOCUMENTS: Drawing 3311 Notes
label | ecdcb67a-aaae-4702-8756-f7e8d2b896c4 |  | label | INSPECTION/TEST METHOD: Test Report
label | ee3972d0-1e42-44b9-a4d6-e9dcfee20dff |  | label | RECORD OF CONFORMITY: Test Report
label | 2fd6d168-236a-4972-8a2e-8fac1e29b9b2 |  | label | TP
label | 805ffc42-0c6e-405a-a45c-5dbe8a0a9093 |  | label | RESPONSIBILITY: Project Engineer
text | da205559-aa7f-49eb-8dbc-a722f96a2361 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.8a Lime Stabilisation
label | 545bdc1a-87cb-4a5c-a8e3-c94e8d3df9f9 |  | label | FREQUENCY: Each Subgrade Lot
label | 6bc54695-5545-48fe-b7fd-6365b800ade4 |  | label | ACCEPTANCE CRITERIA: Earthworks materials stabilised with lime to a depth of 300mm or as stated in table below, whichever is greater:
label | 30deaa59-54c4-4406-a048-db914e8b7767 |  | label | CBR Subgrade %: 1.0-1.4 = 400 Min Thickness required (mm)
label | 40c363e3-b209-4bbb-953b-7896abda782a |  | label | CBR Subgrade %: 1.5-1.9 = 300 Min Thickness required (mm)
label | a7b5cbbc-7eff-4f92-89d7-80aaa0164a66 |  | label | CBR Subgrade %: 2.0-2.4 = 200 Min Thickness required (mm)
label | 72d7bcf4-2c19-4b15-b44d-2dc20ba8eae8 |  | label | CBR Subgrade %: 2.5-2.9 = 150 Min Thickness required (mm)
label | 163dd93b-7462-4b6a-9b5c-e700e5151d9f |  | label | REFERENCE DOCUMENTS: CP17038- LAN-DET-PM- SP-0001 cl. 2.6.1 DWG 3311
label | df80b917-fe4a-4857-9fa2-b902d82939ee |  | label | INSPECTION/TEST METHOD: Inspection Point
label | 43bcabbe-5dea-41f3-b363-1c732b3384ff |  | label | RECORD OF CONFORMITY: This signed ITP Docket attached
label | 3d4a29a7-8298-4e74-854b-652e1db254f8 |  | label | IP
label | 728167d6-1689-46ac-8f15-1057ea93f751 |  | label | RESPONSIBILITY: Project Engineer
text | 5ea0e1cc-1059-4d56-93f6-14165d25d1f7 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.8b Lime Stabilisation
label | f91a12c0-d87d-49bd-a73e-4521cf72893d |  | label | FREQUENCY: One test per production day at the point of manufacture.
label | 8ee2face-c570-448e-a1f1-2762b263bf75 |  | label | ACCEPTANCE CRITERIA: Testing as per VicRoads Standards Table 290.131
label | 73a42575-19cf-40b3-808f-20621a4444b4 |  | label | Uniformity of Spreading Rate = A mat or tray test (minimum of three mats or trays as specified in Clause 290.12(a) for each separate continuous spreading run except where calibrated load cell computerised spreading devices are fitted with a system to continuously monitor the lime spreading rate every 100 m.
label | 614aba95-5445-4c74-8c77-0e9e64e18593 |  | label | Average Lime Spreading Rate = Each continuous spreader run with no breaks or pauses in spreading.
label | 28173ef5-0ab4-42d2-a37a-db777cc5ea82 |  | label | Uniformity of Mixing = For each compaction lot – Visual inspection of six random test holes excavated for the full depth of the loose material after mixing of the binder prior to commencement of compaction.
label | 8153d196-5387-42a2-9ef6-6c611c6b8c8b |  | label | Characteristic or Mean Density Ratio = Every second lot subject to the qualifying period as defined in Clause 290.13(b).
label | 4f0988b7-658f-4a6c-a081-328fb56f1491 |  | label | REFERENCE DOCUMENTS: VicRoads Standards Section 290 Table 290.131
label | 8916ddca-d8d1-41a5-9063-5915d7f1d406 |  | label | INSPECTION/TEST METHOD: Test Records / Stabilizing Records
label | f96b3dd6-d837-40ca-b616-e928b752e37e |  | label | RECORD OF CONFORMITY: This ITP signed - Test Records Attached
label | 9863b2ba-e8d4-4247-a386-76c43ceeaef5 |  | label | TP
label | 9129e10c-1a64-42f6-b954-0dd2c3ae586e |  | label | RESPONSIBILITY: Project Engineer
text | ac6a82c2-658d-4c1f-ac1c-16fcea65ae07 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.9a Subgrade Preparation
label | 157e8eba-7f6c-4283-a14b-5d071201f13c |  | label | FREQUENCY: Each Subgrade Lot
label | 45231541-9f05-47e8-a33d-b0a9eb677d99 |  | label | ACCEPTANCE CRITERIA: Identified and replaced soft areas to a minimum depth of 300mm with Select Fill material compacted to 95% or as instructed by the Principal’s rep
label | 8c2fcb7a-692a-4276-b6f1-c154e1c551db |  | label | REFERENCE DOCUMENTS: CP17038- LAN-DET-PM- SP-0001 cl. 2.6.1
label | 7ecdcd99-d983-4c7d-bd96-11b353f08929 |  | label | INSPECTION/TEST METHOD: Survey
label | 031955ca-bb15-4a21-ba11-31fbaa147f6d |  | label | RECORD OF CONFORMITY: This signed ITP / Survey Report
label | 33b6b21f-a88a-455d-8914-c2b87d8655a9 |  | label | IP
label | f9d79d89-24bd-49e7-b9a3-21f15731484a |  | label | RESPONSIBILITY: Project Engineer
text | 6b33ba89-ae38-4ef5-8a76-166f488ade51 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.9b Subgrade Preparation
label | 51a0a9a2-ed92-457d-8250-c5515e3de044 |  | label | FREQUENCY: Each Subgrade Lot
label | 95c1c9fd-51d2-44d5-84c7-a6cc1807c1e0 |  | label | ACCEPTANCE CRITERIA: Subgrade trimmed to tolerances Scale B Tolerance Range +5 to -25 Standard Deviation 15
label | 89b5ff2f-803d-4a5b-ac84-83fe77e23795 |  | label | REFERENCE DOCUMENTS: CP17038- LAN-DET-PM- SP-0001 cl. 2.6.4 T304.062
label | c0aa41b5-b7d2-4d3f-81e4-9efd61d274c8 |  | label | INSPECTION/TEST METHOD: Verify
label | 177bf865-25c3-432f-940f-3608f78dcea6 |  | label | RECORD OF CONFORMITY: This signed ITP
label | 967b2a24-20ab-47b3-a1ce-d46f12b0a8fc |  | label | IP / SCP
label | 4218e507-b512-4a21-917b-c4fb6e31bd84 |  | label | RESPONSIBILITY: Project Engineer
text | d5320981-4df2-4f14-8717-f974fd763be0 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | HOLDPOINT
label | bf0ea628-d8a8-4deb-8dc7-8092e06b86f3 |  | label | FREQUENCY: Each Lot
label | 8f92a501-aa1f-46dc-9906-09662a6ba61a |  | label | ACCEPTANCE CRITERIA: HOLD POINT: The contractor shall provide for the principal’s representative to be present during all test rolling. Unstable areas identified by test rolling by the contractor. Ensure clearly signed on Test Roll Record or Plan.
label | 4e069a6d-8c9a-4200-9cc3-911bd97820e7 |  | label | REFERENCE DOCUMENTS: VicRoads Section 173 Jacobs Cl. 3.8(b)(iv)
label | a0a354db-c773-4746-8d04-0f3fdd577edf |  | label | INSPECTION/TEST METHOD: Visual inspection
label | 98b0d6af-2c65-4f8a-b864-04e7a4622da1 |  | label | RECORD OF CONFORMITY: This ITP signed
label | 193f9dd9-78d1-4075-a270-3765c17da6b7 |  | label | HP
label | 4818bc94-b6a9-46b3-9c24-3077d378d1cc |  | label | RESPONSIBILITY: Project Engineer / Principal’s Represen tative
text | cee8b36d-c4d1-4d5e-8919-ab61cf82ad03 |  | text | Date Completed:
holdpoint |  |  | holdpoint | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 2.10 Placing Select Fill
label | f0b6998e-c898-49fa-8dde-7a85ba64c8cc |  | label | FREQUENCY: Each Lot
label | e8b72c4d-363e-4f46-98cf-4cd1afd607cf |  | label | ACCEPTANCE CRITERIA: Placed in layers not exceeding 200mm and compacted to 98% Modified Maximum Dry Density
label | 9fe104a6-f596-47fb-bac0-8a81e64ecfa4 |  | label | REFERENCE DOCUMENTS: VicRoads Standards Section 204.10(d)(ii)
label | 74781938-32d0-407a-894d-8c2fafccf622 |  | label | INSPECTION/TEST METHOD: Inspection Point
label | 49ca7539-26f1-47c5-991d-b1f9e1540917 |  | label | RECORD OF CONFORMITY: This signed ITP / Test Reports
label | 277184e1-27a9-4fa5-bc84-75d10354e003 |  | label | IP
label | 42a9d9a8-c8eb-4797-bd08-74902801f40e |  | label | RESPONSIBILITY: Project Engineer
text | d7aac374-8d14-4069-8d15-d3b78de0d6e6 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.11a Crushed Rock Working Platform
label | c0b5be85-ecaa-47c1-afe3-6d8e9a9a8eea |  | label | FREQUENCY: As Required
label | 2dc335ed-33a5-4406-af14-64c62a8f625e |  | label | ACCEPTANCE CRITERIA: Crushed rock working platform shall be protected from deterioration and should be kept moist
label | 8e6cb61d-db31-45b0-a056-f1f8f53a37a5 |  | label | REFERENCE DOCUMENTS: CP17038- LAN-DET- PM-SP-0001 cl. 2.6.5
label | 5d32a881-b785-4a4f-8f88-bf3b13306391 |  | label | INSPECTION/TEST METHOD: Inspection Point
label | 648170eb-5db5-4b66-b1b3-7dec43907510 |  | label | RECORD OF CONFORMITY: This signed ITP
label | 32cfdbf5-02fa-4bca-82c2-ad0060a7bccb |  | label | IP
label | 305b9d47-6353-4db2-8d08-cb8bdfb16f05 |  | label | RESPONSIBILITY: Project Engineer
text | 8f7a14fd-09b5-449f-b164-600f95b91efe |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.11b Crushed Rock Working Platform
label | 1a461f49-8088-4f9f-bf42-9677e581bad2 |  | label | FREQUENCY: As Required
label | 46bf910e-9d49-4685-9367-fd77a83b119d |  | label | ACCEPTANCE CRITERIA: Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mixes RC500.02 as listed in Section 175.
label | 3bf1d795-8b40-4f89-a279-9bb615e6e876 |  | label | REFERENCE DOCUMENTS: VicRoads Standards Section 812
label | ab85dc4f-bf6f-43ad-8717-fe0e0693dbae |  | label | INSPECTION/TEST METHOD: Verify
label | 8d35e8e3-0c94-42d8-94d3-8567cc996940 |  | label | RECORD OF CONFORMITY: This signed ITP
label | 98053d47-2a81-4a83-a84e-47aa287a4b9d |  | label | IP
label | 00027d2e-1e3b-4310-98d2-2ab9a43229e4 |  | label | RESPONSIBILITY: Project Engineer
text | 1d22edcb-8a3b-4a00-ab94-6c911c70cf15 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.11c Crushed Rock Working Platform
label | 819fcdda-7e8b-4f0e-b976-85143e5169dd |  | label | FREQUENCY: As Required
label | 246aaf20-8e2e-4221-9540-7cac5e477e0a |  | label | ACCEPTANCE CRITERIA: Characteristic Density Ratio not less than 98% (modified)
label | b7ffe21e-9bd3-4c9f-83f7-8b86cc15acff |  | label | REFERENCE DOCUMENTS: CP17038- LAN-DET- PM-SP-0001 cl. 2.6.3
label | edffaacf-4734-4dd8-9da3-dd093d1f5b04 |  | label | INSPECTION/TEST METHOD: Inspection Point
label | 10cf52c0-2ebd-4881-80a5-c04f9acee9b0 |  | label | RECORD OF CONFORMITY: This signed ITP Test Record
label | 137dadeb-ca1e-40e8-ba07-1926d29768c4 |  | label | IP
label | 28f978a7-2624-4d3a-ad9a-a656f61f6c28 |  | label | RESPONSIBILITY: Project Engineer
text | 4bd0e591-90e1-4696-87c2-e0da8954598f |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.11d Crushed Rock Working Platform
label | e651cba0-f70e-4747-bf09-7ee2a7c88f67 |  | label | FREQUENCY: As Required
label | 8b2a0f6f-8314-4f18-9a4c-b0386916dc90 |  | label | ACCEPTANCE CRITERIA: Surface level tolerance meets Scale B in VicRoads Standards Section 304 Table 304.062
label | feb0ae36-3da0-4f79-b610-084b3a4593a8 |  | label | REFERENCE DOCUMENTS: VicRoads Standards Sec304 T304.062
label | 80bbf4d7-0b55-42bf-a9f6-1cbf3716caf7 |  | label | INSPECTION/TEST METHOD: Verify
label | 945bfa96-47a7-47d6-9cfc-cd59aa8a6900 |  | label | RECORD OF CONFORMITY: This signed ITP
label | 0c8618ea-e89c-4854-a86e-6c8863b35882 |  | label | IP
label | 2dca058a-a7d1-4705-aaa9-690ac30b5b8c |  | label | RESPONSIBILITY: Project Engineer
text | ed3940e3-fd22-4583-bc1f-57334e719b31 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | c929932f-dcc1-49ec-b4a3-3ce1f7bcea89 |  | label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | ac6eb028-7e65-4da0-ad30-c7de8d207f0c |  | text | Print Name:
text | 1f277e15-944c-4f7e-bee1-09763f95ff85 |  | text | Position:
text | 27a149f5-f6ce-4223-b551-ce60c9b0c82f |  | text | Date:
checklist-flat |  |  | checklist | ITP 001 - Airside Fencing & Gates | itp |  |  |  | Yes | ITP 001 - Airside Fencing & Gates | 0c075b4a-1791-46c4-86f8-a7bd4ba3dc14
checkpoint-status |  |  | checkpoint | 1.1 Check for correct documentation
label | d45aed81-6c37-4571-8b4c-87e0af19040f |  | label | FREQUENCY: Prior to commencing any activity
label | c3210bde-8690-4419-b8d8-b19560840da6 |  | label | ACCEPTANCE: CRITERIA: Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision
label | 7dffc634-d52d-4509-814d-d18c7abcce87 |  | label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | ad89df58-f3c9-4781-8468-ac5fe2df22ed |  | label | INSPECTION/TEST METHOD: Visual inspection
label | 8e1051a9-a72b-45bf-8e82-0e9cdcec5dd8 |  | label | RECORD OF CONFORMITY: Up to date drawing sets and this ITP signed
label | c9a3f645-26e8-4420-b70d-91469ea374d7 |  | label | HP*
label | 0c2d7f8d-20da-4d73-a2fb-e4f31565e54f |  | label | RESPONSIBILITY: Project Engineer
text | d148bc7c-7a4f-4f64-b8c4-6b55333780a5 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 Material
label | 8f9048a7-1e58-49b1-92b9-80cc24c1567f |  | label | FREQUENCY: Prior to commencing works
label | 11d396aa-8c1b-4b6c-9597-b2597a4537db |  | label | ACCEPTANCE: CRITERIA: Realigned Airside Fencing and Security Gates shall match existing 2.4m high fence, Airside fence shall have razor-wire top and existing sections of fence are to be retained where possible Compound perimeter fence shall be standard 1.8m high chain-mesh with 3x barbed wire top Compound area security fencing and gates shall be Type ‘K’ as per VR SD 3131 All other fencing shall be standard 7-wire post type in accordance with Hume City Council SD404, with Heavy Duty Galvanised Farm Gates (3m wide), vertically braced.
label | 9fa4a189-17d2-4863-9186-c88010d8990f |  | label | REFERENCE DOCUMENTS: Jacobs CL 9.1 Melbourne Airport Standard Drawing AD83041 VR SD 3131 Hume City Council SD404
label | 1d3ed6fc-6ca2-4070-bf61-70af8928cdbb |  | label | INSPECTION/TEST METHOD: Verify
label | 7dfde15d-b4ba-4619-b338-707559198114 |  | label | RECORD OF CONFORMITY: Aconex Notification
label | e01bd6bc-350f-471f-82cd-827aa068a3c9 |  | label | HP*
label | 972b4eb6-e98c-4e4f-9a7f-f1e39837a846 |  | label | RESPONSIBILITY: Project Engineer
text | 63d47382-6309-465a-a18a-a2426a8fe7f1 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 Implementation of all measures and controls
label | 84cfcf3e-6004-46cb-aa6b-476aee8ddf49 |  | label | FREQUENCY: Prior to works
label | 19b20f6c-1b9d-4876-82eb-e63eb6a1f8f7 |  | label | ACCEPTANCE: CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | 6336facd-093d-45fe-ba43-058e76b39424 |  | label | REFERENCE DOCUMENTS: PSP, EMP, TMP,JSEA, SWMS,WP
label | 3aa19a57-fff3-45de-b027-6f333639f3f5 |  | label | INSPECTION/TEST METHOD: Visual Inspection
label | 045a2ba7-3b62-43b6-baf7-11ddfa8dd74d |  | label | RECORD OF CONFORMITY: Site and Office Inspection
label | 51ca5f12-acc1-42b7-811e-50fc6ede8f4b |  | label | HP*
label | 24de8e77-de32-430f-87bb-0ee0ddd63b90 |  | label | RESPONSIBILITY: Project Engineer/ Site Supervisor
text | d495a5a1-feab-4d74-9e97-3caab23bdfa4 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 SIte Preparation
label | c3b0d748-ad8e-4148-af11-6d60a0fcd337 |  | label | FREQUENCY: Each lot
label | 04dc6fd4-c5cb-46f7-8492-7bf4725e2181 |  | label | ACCEPTANCE: CRITERIA: All logs, stumps, saplings and undergrowth removed within 1m of the fence line. Any high points which interfere with the placing of wire or wire netting shall be cut down to provide the clearance shown on the detailed drawings, Any low spots shall be filled with surplus earth from holes and trimmings to ensure no gaps greater than 50mm under the selvedge.
label | 3c900ecc-279f-4efe-9248-ab5fb3846728 |  | label | REFERENCE DOCUMENTS:
label | 3f1ff64a-e08f-43ac-bfc1-f23d88df8b71 |  | label | INSPECTION/TEST METHOD: Visual Inspection
label | 0a2f2569-3d66-407f-8b12-6f4c8b609946 |  | label | RECORD OF CONFORMITY: This ITP signed
label | e2234b90-85b0-4287-94ba-dd4c90844152 |  | label | IP
label | 3d9087b9-56ff-474e-99e6-caaaa0d279ef |  | label | RESPONSIBILITY: Project Engineer
text | b7ea0886-3137-4ff7-9f67-b79c2e6d87ff |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Post Excavation
label | 37c6f011-6c74-4efc-84e5-91a6b2100c67 |  | label | FREQUENCY: Each lot
label | eb2fca3a-2ce8-4612-81bf-008c80c8f3c6 |  | label | ACCEPTANCE: CRITERIA: Surveyor to set out posts and spaced according to drawings Spacing between posts on a straight: MelAir – 4,500mm Max Compound – 3,330mm Max Council – 7,500mm Max (includes 3 timber droppers) Depths as per drawing: MelAir – 600mm – Intermediate MelAir – 750mm - Corner and Ends MelAir – 600mm – Backstay Compound Fence – 600mm – Intermediate Compound Fence – 900mm – Corner & End Council – 600mm Where required posts to be backfilled with 20Mpa Concrete
label | e0d7fbdc-0279-4a5b-9aae-b3b5087da308 |  | label | REFERENCE DOCUMENTS: Melbourne Airport Standard Drawing AD83041 VR SD 3131 Hume City Council SD404
label | 956ef087-65e9-4574-833c-42539eae1ad0 |  | label | INSPECTION/TEST METHOD: Verify
label | cc9aa9af-c828-494f-a78b-75c37cfb4cdb |  | label | RECORD OF CONFORMITY: This ITP signed
label | 95b38a43-1cea-4942-88eb-e32f2b0aad29 |  | label | IP
label | 7a3a5c36-a59d-45c3-8779-d89a417beed3 |  | label | RESPONSIBILITY: Project Engineer
text | ad428b0b-adf6-4074-b5d6-4d7373c53691 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Fence/Gate Installation
label | 82f1b955-92e3-4160-b30d-f3edf13cf37a |  | label | FREQUENCY: Each lot
label | e51317b4-f724-4a23-8ee1-52764fc9323e |  | label | ACCEPTANCE: CRITERIA: Post Straightness checked with spirit Level Bracing installed as required and as per drawing: Mel Air – 100m intervals Compound – 150m intervals Council – Use Single Strainer Assembly at Gateways Ends and Angles Backstays installed as per drawings
label | 3c2e32c6-7459-4173-a5d6-e6d9f050d63d |  | label | REFERENCE DOCUMENTS: Melbourne Airport Standard Drawing AD83041 VR SD 3131 Hume City Council SD404
label | fafe9ce3-a69c-4d86-96ee-767bbd748e45 |  | label | INSPECTION/TEST METHOD: Verify
label | 0520b1f8-1599-48ad-80b9-65b119448cad |  | label | RECORD OF CONFORMITY: This ITP signed
label | 4dc50536-3a01-46c9-9f7d-303d5edf0673 |  | label | IP
label | 124ea799-469d-40eb-8a65-ac7621505774 |  | label | RESPONSIBILITY: Project Engineer
text | 33c6f9fc-d201-4a85-9779-2f8705987654 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 As Built Survey
label | 7a0e1119-41c3-4bed-b916-5c11e80b87bd |  | label | FREQUENCY: Each Lot
label | 67e2bda3-b923-49bd-9059-d52bc86cf02c |  | label | ACCEPTANCE: CRITERIA: Surveyor to pick up completed conduit runs before backfill with survey report to be submitted with ITP.
label | 128d093e-2860-4bdd-9568-373936775d90 |  | label | REFERENCE DOCUMENTS: FH PQP
label | c6b87250-0da2-4a3b-ad56-d15a77820eae |  | label | INSPECTION/TEST METHOD: Verify / Inspection
label | fcb1e403-c99e-42e1-8253-5e5618f4785f |  | label | RECORD OF CONFORMITY: Survey Report
label | 5d059098-7ba8-4f96-9ec3-e4aba8b4ab2d |  | label | SCP / IP
label | 183e86d0-aab5-4e5e-aefd-39828b04f6c6 |  | label | RESPONSIBILITY: Project Engineer / Surveyor
text | 41944455-fde5-49e5-a0bb-54b008dba6eb |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | a52af54d-20cb-4b93-9d67-028ab7981f5e |  | label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | c9daac31-a8de-42c1-ade9-dc5ce575bd37 |  | text | Name:
text | 4cc5f1a7-3953-4b2a-985a-e36ec01ed424 |  | text | Position:
text | 2981810f-bde0-4506-8f42-b8d1c4466a5a |  | text | Signature:
text | a238337c-aa57-4bae-923c-4c6380d7f4a0 |  | text | Date:
checklist-flat |  |  | checklist | ITP 012 - Lot - | itp |  |  |  | Yes | ITP 012 - Grassing | 22e9e5d5-8a08-4ee9-9531-c7faff3a641c
checkpoint-status |  |  | checkpoint | 1.1 Check for correct documentation
label | 6e177625-0de7-4f38-8379-59ac0bd203b1 |  | label | FREQUENCY: Prior to commencing any activity
label | 0046c4c4-56f0-4992-9f03-8b4581fdffa9 |  | label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | 8a858dae-eecf-4ecd-bed9-247e4fd2183a |  | label | - Using the correct and complete set of drawings
label | b0d28bf5-0740-47f7-8ac4-f7aade4ec571 |  | label | - All drawings are the latest revision
label | a6b93934-9cd5-49ee-9db8-df732bcd21fa |  | label | INSPECTION/TEST METHOD: Visual inspection
label | 0ac6ff90-48c9-4a9f-bf18-29825bd8878d |  | label | RECORD OF CONFORMITY: This signed ITP
label | 1496c06e-404b-4863-bfd3-8f298198f355 |  | label | HP*
label | 8c607616-9cbb-45fe-a297-8caf08cec4a9 |  | label | RESPONSIBILITY: Project Engineer
text | b6ca0d34-8a1d-4e5e-9a91-507f0d87f258 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 Implementation of all measures and controls
label | 195240ab-a88c-44e9-99ac-e144a78bc5c0 |  | label | FREQUENCY: Prior to commencing any activity
label | de7b4335-2e40-40bc-9e8f-7d195308edb5 |  | label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | 8b8bda13-a871-4606-9780-9c58eafae32d |  | label | INSPECTION/TEST METHOD: Inspect
label | b814aeec-145f-4af4-a1cb-97ed5a27378e |  | label | RECORD OF CONFORMITY: This signed ITP
label | be5ef8b7-d2d3-414c-a727-fe753b47cc31 |  | label | HP*
label | d9c026dd-0cb7-4882-b093-a3a7ceb6c148 |  | label | RESPONSIBILITY: Project Engineer
text | 110fbf7a-a515-4533-b613-2a98de90c49d |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 Material Approval
label | 71736c37-ea46-4e13-a559-dcd88cd58e34 |  | label | FREQUENCY: Prior to hydro seeding
label | 12bac7f5-5af3-4691-b026-c8d8aa0d192c |  | label | ACCEPTANCE CRITERIA: Grass mix composition and application rates accompanied with methodology to be submitted via Aconex for approval
label | c5d03d5e-0289-423f-866c-651bfc51ca0b |  | label | INSPECTION/TEST METHOD: Verify
label | 8340440a-3fc8-412c-a6e8-e41e4ab24c2a |  | label | RECORD OF CONFORMITY: Aconex Approval
label | 81ecb4af-24dc-47b9-a5ba-e6b68a253b06 |  | label | HP*
label | 6627a1b9-c1de-44b6-95b6-26bbc9047d49 |  | label | RESPONSIBILITY: Project Engineer / Superintendent
text | e569cf82-f0d5-4bcf-81aa-b85579a31e2a |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 Topsoil
label | 909ac51e-257d-435e-9afa-33a1b500f211 |  | label | FREQUENCY: Prior to topsoil placement
label | 9488b215-6e0d-4e7f-b8cb-bd8536b0977e |  | label | ACCEPTANCE CRITERIA: Topsoil must
label | 22c00937-58b3-4101-97b6-fa515bc44b4b |  | label | - Be an even blended mix of washed coarse sand (70%), topsoil (10%) and organic matter (20%) with a pH 5.5 - 7.5
label | 93432c13-3d5c-4267-bd14-63cf078ed25b |  | label | Be free from:
label | c234c902-37b5-44dc-a96f-5878558067a9 |  | label | - Stones or other material exceeding 25 mm in any dimension;
label | 6d707d35-e5be-4325-b56f-a556d04c99ab |  | label | - Clay clumps;
label | 0d027fa1-dfea-49f3-a92f-267eed608749 |  | label | - Weeds and tree roots;
label | 6d3355e9-0c2e-4c7e-addd-0fe1c55caa32 |  | label | - Sticks and rubbish;
label | 56bc32c7-b3f8-4f9a-ab6d-e64ae990cdee |  | label | - Material toxic to plants; and
label | 8d2ff709-c81a-4acd-a90a-f7b06fb6e707 |  | label | - Comply with the chemical and physical properties of AS 4419 'Soils for landscaping and garden use' and AS 3743 'Potting mixes'.
label | 3aa028a1-50ea-45e7-9766-85a1fc5a7419 |  | label | Soil excavated from site which:
label | 603a0796-a3fe-4c57-b2e1-d81fbdc7feea |  | label | - Contains organic matter;
label | a9ca01dc-b850-450e-88b7-e1cc5fc22185 |  | label | - Supports plant life; and
label | 960d117a-9cdf-4cee-936a-be7bb5855919 |  | label | - Complies with the topsoil requirements set out above, may be used as topsoil for the purposes of the Contract.
label | 1f5e357a-87e1-45e9-8b8d-1121a532cc1c |  | label | INSPECTION/TEST METHOD: Verify
label | 9fae071a-fe43-42df-9da4-dd5940e6bff2 |  | label | RECORD OF CONFORMITY: This Signed ITP
label | 6d7e5c01-16f6-46a2-956b-5a349c522b2f |  | label | IP
label | ce75def8-0952-4768-924b-c8dc4d533c3d |  | label | RESPONSIBILITY: Project Engineer
text | fb2b8d25-0195-437d-b441-ec3e3195a1cf |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3.1 Topsoil Placement
label | 469f4768-64a4-4557-9c41-f17fa17db74f |  | label | FREQUENCY: Each Lot
label | 49de33e4-c459-4799-b4d7-04e97e737870 |  | label | ACCEPTANCE CRITERIA: Filling of grassed areas will comply with specification
label | c5a312c1-bd4f-42b7-9450-482713b07bb3 |  | label | - 150mm thick topsoil
label | b1b688c0-4f6e-4e2a-bdeb-2b704ab3a74a |  | label | - Smooth even profile
label | 9b0614e9-f6b1-4bbc-bb70-e70d36c5bc4c |  | label | - Free of ridges or water pockets
label | 4e95939d-0419-4000-9e01-846e11fef516 |  | label | - Must conform to the requirements of AS 2223 except that the pH value of the imported topsoil shall be within the range of 6.7 - 7
label | 3f95e45a-6d5d-4ab2-8463-106960a03f4d |  | label | INSPECTION/TEST METHOD: Verify
label | 9f3a9cc2-37ef-4b6c-be35-67d1dad3f5f0 |  | label | RECORD OF CONFORMITY: This Signed ITP
label | e5e0abb3-ab01-4b6d-a966-e0f005621df3 |  | label | IP
label | 20a489bf-6e03-4638-b4e2-bff1bcb2f21e |  | label | RESPONSIBILITY: Foreman
text | 82b54372-0336-4ee6-b94f-d15d0c6683f5 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Inspection of topsoil
label | 513fa3d5-ccbb-4ba4-9440-7c74987a94b7 |  | label | FREQUENCY: Prior to hydro seeding
label | e44ac1e4-3496-4d74-a71b-b007ef2f15ca |  | label | ACCEPTANCE CRITERIA: WITNESS POINT Inspection of the completed topsoil works to be undertaken
label | 4c974deb-e926-4883-b209-90cfd1cb8485 |  | label | INSPECTION/TEST METHOD: Verify
label | 06dfe7d2-a243-49bb-a907-f2535db6a712 |  | label | RECORD OF CONFORMITY: This Signed ITP
label | a654c2ba-81ed-4c12-ba6d-b7d1d2355321 |  | label | WP
label | 5279add0-ab7b-4fe4-9958-ed99914908d5 |  | label | RESPONSIBILITY: Project Engineer / Superintendent
text | c76a9520-7cbd-49a2-9848-d6b8b335fcad |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 4.1 Hydro Seeding (if applicable) - Coverage / Tolerances
label | 29e5c05d-fdd6-4e41-a6c1-e9ce622dfb44 |  | label | FREQUENCY: Each Lot
label | a345d3b8-abc7-4769-a533-68ce08ab347a |  | label | ACCEPTANCE CRITERIA: Ensure even coverage across required area
label | bc58147a-9ec7-49fd-9935-96fb4854028b |  | label | - Application rate to be measured, reported and confirmation that the following tolerances have been adhered to:
label | fe01c7c7-de71-458e-a6ed-f1ed05c4cfe9 |  | label | - Grass seed - ±5% by mass
label | 1a2953a3-6e13-4432-abc6-7b57c090a8e0 |  | label | - Fertiliser - ±10% by mass
label | 71cb5542-3693-4ad2-91f2-65aa3f3fcecc |  | label | INSPECTION/TEST METHOD: Visual inspection
label | 5fd31977-3bab-4ab9-ac19-a349562a3381 |  | label | RECORD OF CONFORMITY: This Signed ITP
label | e0a87941-c16e-48c8-a751-e3074baec553 |  | label | IP
label | 026f10e0-326f-4a92-b252-f1c1b3fa4702 |  | label | RESPONSIBILITY: Project Engineer
text | 40a20c1b-f963-48a5-b8df-2427d9d142f9 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Direct Drilling
label | ef3cebae-66a3-4479-a222-f18873d19dc0 |  | label | FREQUENCY: Each Lot
label | ba3f0b61-386e-49c9-b772-697189a5b0bc |  | label | ACCEPTANCE CRITERIA: Ensure plant is suitable for task
label | 63695ed5-1eaa-40f7-b9ae-520e50950fa3 |  | label | Grass to be prosper tall fescue as used on the Taxiway Victor project
label | 26ebf261-5a77-464c-b603-491ba1af71ee |  | label | INSPECTION/TEST METHOD: Verify
label | 11c86341-de25-46e3-a631-1a43404b4e68 |  | label | RECORD OF CONFORMITY: This Signed ITP
label | 6c57ac47-df1e-413c-804e-76a78b3a81f3 |  | label | IP
label | 287532d3-3cf3-4d48-98d8-b3624047a437 |  | label | RESPONSIBILITY: Project Engineer
text | f7c88386-eb52-4351-93f8-66a28421fef7 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 5.1 Grassing Requirements
label | b43451c1-0b64-4924-ba09-f684d15d26c8 |  | label | FREQUENCY: Each Lot
label | 05b0df7a-55c1-43e5-8e01-194b6e709998 |  | label | ACCEPTANCE CRITERIA: Grassing activities recorded and submitted
label | 3c00d63a-576f-47cd-b1f0-9b70c0a3c9ea |  | label | INSPECTION/TEST METHOD: Verify
label | 34eb64bb-7ee2-4b0f-85f8-b0696b9936e2 |  | label | RECORD OF CONFORMITY: Aconex Correspondence
label | 44649661-3d69-4099-9556-ca09bad6512a |  | label | IP
label | 02b267da-992c-476c-9f70-37ca7065c7bf |  | label | RESPONSIBILITY: Project Engineer
text | 62afc8f5-9a70-47ce-8d85-57f49627d78a |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Watering
label | c7c330ca-a2ec-44b6-bfda-db9b13fd317f |  | label | FREQUENCY: Each Lot
label | 9e74379a-9ef2-4bf8-8e27-281f63219114 |  | label | ACCEPTANCE CRITERIA: Following grassing works, the area must be watered as required to maintain the grass in a healthy condition and promote growth
label | 89ccd65c-6241-4f9c-be25-f51270d3df47 |  | label | REFERENCE DOCUMENTS: 60559759-SPIA-0001_0 13.4.4
text | d12bd4b2-133d-45d4-9d63-591f11f952f5 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Maintenance
label | 5df1004e-469f-4c1e-85f0-76d7e4041bb3 |  | label | FREQUENCY: Each Lot
label | 2fd52405-41fa-4102-872b-c38dfa1ae87d |  | label | ACCEPTANCE CRITERIA: Maintenance of grassed areas for the duration of the project
label | 78b660ef-95f9-4204-8631-306dbc670091 |  | label | INSPECTION/TEST METHOD: Verify
label | 1753ca29-811d-4f49-b6cf-74dfe54d0b9c |  | label | RECORD OF CONFORMITY: Docket / Invoice
label | 154dce6d-9691-4897-b93a-553c60d49444 |  | label | IP
label | 4bebfde6-c5c8-4d8e-8a7e-23fa4c4239e9 |  | label | RESPONSIBILITY: Project Engineer
text | c4dd3e3b-df39-4ddc-8212-ef03f258339a |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | fb67ba06-f191-4854-977c-ab1fc4e05f8a |  | label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | 0430e5c5-96b7-4500-9292-e5904cac27bb |  | text | Print Name:
text | 513a4278-3c91-4d91-a2c4-9b398015c476 |  | text | Position:
text | dfc70d8a-d42d-43ab-8fa0-4cbea3f71a44 |  | text | Signature:
text | d7a9f7ed-cf00-402f-9d86-d659eca4e8a2 |  | text | Date:
checklist-flat |  |  | checklist | ITP-012 Line Marking | itp |  |  |  | Yes | ITP 012 - Line Marking | 2e81f021-b387-42a7-bdbf-7a13b1f496b7
checkpoint-status |  |  | checkpoint | 1.1 Check for correct documentation
label | 74082f10-98b9-4d9c-baf7-cbc24dacbf8b |  | label | FREQUENCY: Prior to commencing any activity
label | 4e03c7cc-0f87-4349-9a90-e5f984b4d301 |  | label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are: - using the correct and complete set of drawings - all drawings are the latest revision
label | 01a6994d-1492-4f3e-bda3-0d9434ecce95 |  | label | REFERENCE DOCUMENTS: Drawings & drawing registers
label | 59bb6dfe-9c28-4cf6-9529-49907d6a1ea8 |  | label | INSPECTION/TEST METHOD: Visual inspection
label | c80ffd8c-98bf-497f-920c-9dd2d278c08b |  | label | RECORD OF CONFORMITY: Up to date drawing sets and this ITP signed
label | fade40f5-1322-4863-9a89-b14af7930bf1 |  | label | HP*
label | bc23f302-8187-4144-ab0a-34662341ec08 |  | label | RESPONSIBILITY: Project Engineer
text | a2c69906-cc2c-4d8e-9f69-d00214c1646e |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 Material Classification
label | 74b8fefe-3a86-4d1b-a123-c90bb017629f |  | label | FREQUENCY: Prior to commencing works
label | 899e4b1a-85d8-4371-80cc-9cb5b6451f97 |  | label | ACCEPTANCE CRITERIA: The dimensions and colour of Pavement Markings shall conform to VicRoads Traffic Engineering Manual, Volume 2. All paint used for line-marking shall be long-life, water-borne, white in colour and conform with AS4049.1-2005 unless otherwise noted on the drawings
label | c0b30536-3a98-492e-8ddd-1336ebea62ab |  | label | REFERENCE DOCUMENTS: Jacobs CL 9.6.1 VR721.A05 AS4049.3-2005
label | e8175226-1122-4c9a-a296-da91b12f0a5c |  | label | INSPECTION/TEST METHOD: Verify
label | 069a46c4-9a81-4080-82de-d72f64d814cf |  | label | RECORD OF CONFORMITY: Aconex Notification
label | 50d0a6b3-386d-4301-8937-f90d71cfedaa |  | label | HP*
label | 537c80ac-6cf4-4c9d-9884-32dfe2696da2 |  | label | RESPONSIBILITY: Project Engineer
text | 948ee7ae-82f3-48ab-9e48-0f2fc5190d05 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 Implementation of all measures & controls
label | e18c97bb-6b4f-4dfa-8371-4d2579e80142 |  | label | FREQUENCY: Prior to commencing any activity
label | dabcd16b-2f9b-4650-8663-bd0da62d3a3b |  | label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | 38f89911-c3ff-480a-ac00-f5e393d7822a |  | label | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | 74eef04f-11d6-4c54-ae42-01015ec42aed |  | label | INSPECTION/TEST METHOD: Visual inspection
label | 420a08d5-8fbc-4958-89ef-23eade57cfba |  | label | RECORD OF CONFORMITY: Site & Office Inspection
label | aa8470d1-b17d-4045-9106-f39b0e06244a |  | label | HP*
label | 7c89b58a-eef3-49c7-a9b4-b639de236293 |  | label | RESPONSIBILITY: Project Engineer/Site Supervisor
text | 869f7187-b9a0-4f0e-bb8d-23eb62141ff7 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 Removal of Existing Line Marking
label | 546b98eb-dc6a-441a-b392-33244fe4e7e5 |  | label | FREQUENCY: Each lot
label | 51a0cc26-632d-4fe6-aeec-48cf7b8c0504 |  | label | ACCEPTANCE CRITERIA: Where required all existing line markings, at the locations shown on the Drawings, by grinding, blasting or other methods approved by the Superintendent
label | 732aaef2-c0a5-41fe-a471-6eb897ec9712 |  | label | REFERENCE DOCUMENTS: VR721
label | 05f9d3f0-8995-4342-b7da-e7d8194d8c1e |  | label | INSPECTION/TEST METHOD: Verify
label | 1190fef0-186f-4d7f-901c-152079d19ac8 |  | label | RECORD OF CONFORMITY: This ITP signed
label | f78e7c8d-08ff-4249-9a26-684a6deded52 |  | label | IP
label | ce49e199-2497-40dd-a23f-2c5584025517 |  | label | RESPONSIBILITY: Project Engineer
text | bc7e1f08-598d-49e7-8cb0-254b98f0c8a9 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Weather Conditions
label | e94bd210-d390-4abe-aba2-6782aeed62eb |  | label | FREQUENCY: Each lot
label | d5e20527-ae5f-4900-b142-0723d2350537 |  | label | ACCEPTANCE CRITERIA: Line marking shall not be carried out when there is possibility of the freshly applied pavement markings becoming damaged by rain, fog, or condensation before they have dried or set.
label | a2de229f-60ac-4e36-8ea7-8a77adaed791 |  | label | REFERENCE DOCUMENTS: EMP PQP WP014
label | 6f261e0a-1927-4fdf-a700-ea606c76868f |  | label | INSPECTION/TEST METHOD: Verify & Visual Inspection
label | 7d55fdd2-10a5-4b01-94d9-056aee59b51d |  | label | RECORD OF CONFORMITY: THis ITP signed
label | 7fdbb27d-78ea-4a53-a28e-7181994a524a |  | label | IP
label | 8cb08343-af27-4165-8f88-ec1fd37569a6 |  | label | RESPONSIBILITY: Project Engineer
text | c82751dc-e03c-4d6a-9fa8-bdff2aa5c7d3 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Site Preparation
label | 5d78c673-7f36-41d0-b762-c029ca6460d9 |  | label | FREQUENCY: Each lot
label | f213c399-9cc1-4d4d-93af-1773bddec69c |  | label | ACCEPTANCE CRITERIA: The removal of existing unsound, obsolete or redundant pavement markings The removal of any foreign materials and debris within reasonable limits.
label | 35bc7313-a3d3-4b36-aa40-6d1ac62817d9 |  | label | REFERENCE DOCUMENTS: VR SS 721
label | d0d6d9b7-1808-46c1-a6db-5503b74bd834 |  | label | INSPECTION/TEST METHOD: Visual inspection
label | 256064bf-740e-4665-9c37-2d7794a01f05 |  | label | RECORD OF CONFORMITY: This ITP signed
label | d3bbfe9e-b840-4512-8f0f-62ad64d81054 |  | label | IP
label | c62b20e3-0f2b-41f1-b201-1f4cb3ab6135 |  | label | RESPONSIBILITY: Project Engineer
text | d750fa3c-93cb-486b-8bd4-fdad95083e0f |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Raised Reflective Pavement Markers
label | a544d361-e14a-42b0-aec7-7d1dccfe3640 |  | label | FREQUENCY: As required
label | ce0a35f2-1a85-4089-b9b6-46baecfb6e98 |  | label | ACCEPTANCE CRITERIA: Raised Reflective Pavement Markers (RRPMs) shall be provided and comply with the relevant requirements of AS1906, Part 3. Along road centreline this requires Yellow “two-way” reflectors at 24m interval spacing, reduced to 12m intervals on curves less than 150m radius plus 100m either side on approach to the tangent. RRPMs to be placed 50mm offset from solid lane lines (both sides), and within the gaps of divided lines
label | 548a64b3-83ff-4a69-8720-5e845ea0642c |  | label | REFERENCE DOCUMENTS: Jacobs CI 9.6.2
label | a8d3fd45-a27c-4fd7-a77c-a29032681e8c |  | label | INSPECTION/TEST METHOD: Verify
label | b346910c-c43f-4dd0-a9e4-046ad5410729 |  | label | RECORD OF CONFORMITY: This ITP signed
label | 41d9c5da-fe50-464f-97ef-2eef27f781da |  | label | IP
label | 3fb72f5c-5089-4b41-aa27-26616f443f35 |  | label | RESPONSIBILITY: Project Engineer
text | 2e37bf7c-b438-4f6e-bac5-d5436c39a124 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 Guideposts Spacing
label | eace6606-88ac-40c3-a789-3956376f67d2 |  | label | FREQUENCY: As required
label | 3210238b-0ea0-4be1-9f14-ad6f988a2684 |  | label | ACCEPTANCE CRITERIA: Curve radius (m) On outside of curve (m) On Inside of Curve (m) <100 6 12 100-199 10 20 200-299 15 30 300-399 20 40 400-599 30 60 600-799 40 60 800-1199 60 60 1200-2000 90 90 >2000 including straights 150 150
label | 388f0e56-8f47-46a2-b199-6b15ebaa48b5 |  | label | REFERENCE DOCUMENTS: Jacobs CI 9.6.2
label | 3e9a0b40-db7d-4aa8-bf8b-58aa02f0861b |  | label | INSPECTION/TEST METHOD: Verify
label | dda668ff-5cfa-4b9e-98f1-812534a6003f |  | label | RECORD OF CONFORMITY: This ITP signed
label | 6b8fe01d-5f8f-48ef-89d0-c06feac77c77 |  | label | IP
label | 4abc0863-b39d-449e-aad6-4e6c71c1210b |  | label | RESPONSIBILITY: Project Engineer
text | 3c8349e8-184a-42c1-b20e-163d3df5ca1d |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 Application Rate and Uniformity of Application
label | d64dee60-6b6e-49c4-abad-8288803383fe |  | label | FREQUENCY: Each lot
label | 28eaffc3-d8ad-4abb-88c2-51df28bc55f6 |  | label | ACCEPTANCE CRITERIA: Daily records of paint usage and area covered shall be maintained to ensure that the specified coverage is being obtained consistently All new painted pavement markings shall receive two applications of paint, The second/final application shall be applied between 2-6 weeks after the initital application Glass beads shall be applied to all long life markings. Glass beads shall be sprinkled or sprayed on to the long life material while it is in a fluid state immediately after it has been applied to the pavement to ensure that the beads are embedded by a nominal 60%.
label | d80c9cab-66e5-4ed2-a7a0-f1770ad9def3 |  | label | REFERENCE DOCUMENTS: VR721 -Table 721.E021 VR721.B04 (b)
label | 53e94bc2-1009-4d61-aff8-be6dc9decb0d |  | label | INSPECTION/TEST METHOD: Daily Records
label | 94a9e34c-31ca-43ce-bea6-dfb25f68c92c |  | label | RECORD OF CONFORMITY: This ITP signed
label | be43f7cc-11b3-417d-ae56-50b849334c10 |  | label | IP
label | a76cd0f0-3fb7-47da-8733-eaadf7c772bf |  | label | RESPONSIBILITY: Project Engineer
text | a5e0aa3d-2292-46c5-a553-48d09806d6b9 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.7 As Built Survey
label | dcd9c682-ed0b-4f4b-9d15-5907e32c88c4 |  | label | FREQUENCY: Each lot
label | 417b6dd0-5dcc-4edf-8eeb-91bcfa7abecf |  | label | ACCEPTANCE CRITERIA: Surveyor to mark out and survey completed line marking for As built survey for conformance. Painting/application of material shall not commence until the Superintendent has inspected the set out and given consent to proceed, unless an exemption has been granted in writing by the Superintendent. The Contractor shall comply with pavement marking tolerances when installing pavement marking as per table 721.A101
label | 0496bc5e-6732-42fa-a55e-08ce7ae30379 |  | label | REFERENCE DOCUMENTS: VR SS 721 -Tables 721.A101 721.E02
label | 0b33ed2e-bd26-4d78-a154-519f19c6b486 |  | label | INSPECTION/TEST METHOD: Verify/Visual Inspection
label | 9f577314-ae09-453c-87ff-e5397fd387b4 |  | label | RECORD OF CONFORMITY: Survery Report
label | 82879e86-7ff7-4f5c-9dc0-7606e9c776a9 |  | label | HP
label | 7b614581-389a-49eb-a38c-7313f31bb4aa |  | label | RESPONSIBILITY: Project Engineer/Surveyor
text | 9f4e26ea-3583-4684-828f-ecd3a6c223f1 |  | text | Date Completed:
holdpoint |  |  | holdpoint | Request Signoff
checkpoint-status |  |  | checkpoint | 2.8 Records & Reporting
label | 594a75f8-1db4-4f2c-bda4-c9e6a88a0a97 |  | label | FREQUENCY: Each lot
label | 82116af1-6d67-4de0-baaa-479dc1153c98 |  | label | ACCEPTANCE CRITERIA: For New Markings the contractor shall complete and forward to the superintendent a job completion report for pavement markings
label | 72998355-df7b-40c7-95d0-1b2818a37c08 |  | label | REFERENCE DOCUMENTS: VR SS 721.B06
label | 693919a2-23ef-4356-92f6-d627390c0da1 |  | label | INSPECTION/TEST METHOD: Verify/Inspection
label | 29886fdb-f02b-43ce-848f-0854c43e9d00 |  | label | RECORD OF CONFORMITY: This ITP signed
label | 39762756-27ea-4d40-a855-523ee3170cfd |  | label | IP
label | 3fe517b5-5164-4eac-9000-34671f3ad2db |  | label | RESPONSIBILITY: -
text | 79ee4bfc-9fcd-425d-a496-921e261d79ae |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.9 Acceptance of Work
label | ff97b610-b487-4dba-919f-21c92e1916b8 |  | label | FREQUENCY: Each lot
label | 069756ec-a3c0-4a25-a463-93f3f80ac195 |  | label | ACCEPTANCE CRITERIA: Pavement shall comply with the relevant specified requirements as detailed in NAR Job & Vicroads Specifications for; • Acceptance of Colour • Minimum Requirements (for painted markings) • Minimum Requirements (for long life markings)
label | 4d0d6b33-36cd-482e-87b3-3db0c74137bc |  | label | REFERENCE DOCUMENTS: VRSS 721.A12
label | eb3c14d4-e5ac-489e-ad04-71b45449bc9d |  | label | INSPECTION/TEST METHOD: Verify/Inspection
label | 76df8612-6b44-4244-bd43-c40fbe0f903e |  | label | RECORD OF CONFORMITY: This ITP signed
label | cb46860d-d19b-43ff-934d-1f1c400740f2 |  | label | IP
label | 8f02612c-61d1-4820-a461-8dd0fba2b0d2 |  | label | RESPONSIBILITY: -
text | 7f9eb767-ddbb-476c-bb42-863ee4bf440c |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 546ceed0-d358-45b3-97f2-d962b7964439 |  | label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | dc0f1d2e-a4d2-47e8-be79-3a3aa1f60606 |  | text | Print Name:
text | 6b3e4e23-ce85-450e-b25d-a6e0db9749d8 |  | text | Position:
text | 4011d3a6-cb4b-4134-bcdd-d3a880876703 |  | text | Signature:
text | 521edbe6-77dc-4dc5-98b6-631d60703c9d |  | text | Date:
checklist-flat |  |  | checklist | Order Acceptance Certificate - Lot: | itp |  |  |  | Yes | Order Acceptance Certificate | 346f8644-cede-4c7e-a08b-0655d40f2695
checkpoint-no-status |  |  | checkpoint | Order Acceptance Certificate - Details:
text | aff52a93-5f83-4e1f-af90-a94c164c77a7 |  | text | Subcontractor (full name of Subcontractor, ABN, Subcontractor's ACN and ABN)
text | 25709e53-f8b0-42a7-9600-3f7297f21245 |  | text | Order No.:
text | b4403f3d-1d60-4120-8572-2873d4d463ba |  | text | Delivery Site:
text | 4b602621-52e9-4c8e-b0da-7bfda9471a94 |  | text | Date on which materials delivered:
text | 695583af-6f34-480a-9bf5-55a371c3a38a |  | text | Delivery vehicle (registration number):
text | 8a40a7e2-014c-4fac-9970-fef065e0f3dd |  | text | Subcontractor's delivery personnel (full name)
checkpoint-status |  |  | checkpoint | The Subcontractor has checked all Materials included in this delivery and is satisfied that all of the Materials comply with the Subcontract.
checkpoint-status |  |  | checkpoint | 1)
text | d6b09040-fd60-4400-b8f0-5c00c55287d2 |  | text | Item ID:
text | ee4f221b-530a-4d14-af75-a709c5235f6f |  | text | Item description:
text | 45493357-7e6d-4949-b71d-78ca1aa95c76 |  | text | Units ordered:
text | 319fcfdd-b63e-4311-9b4c-8d3d6907dacc |  | text | Units delivered:
text | 6bc4c191-e712-49b9-9fab-8bd40c3b65ce |  | text | Special Storage/ Handling Requirements?
label | 8f2d271d-d97f-44e9-8e5a-26dfc5667455 |  | label | The following is for completion by Fulton Hogan
text | 91da4c09-4b90-4c58-b19d-1e05d92cdda5 |  | text | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
text | 2f8aa5bc-3aea-4d27-a4c9-edae5be0fcf5 |  | text | QA Docs Delivered?
text | 50835eaa-cb08-418f-93d4-e9854e1c45b8 |  | text | Defective?
text | f300cee9-bd92-4013-b580-a91c315989a0 |  | text | Number Accepted / Number Rejected?
checkpoint-status |  |  | checkpoint | 2)
text | a625fd39-09b4-4178-89d5-fdbb1c731706 |  | text | Item ID:
text | 0c775e20-608c-4557-96c5-f7840384f543 |  | text | Item description:
text | 10f75d1d-37fa-4ac8-b50f-2876d3c0de67 |  | text | Units ordered:
text | 0d697c64-0eb9-4958-a2d0-07e62ec5c8ec |  | text | Units delivered:
text | 71d37a9a-e294-4b95-b9ca-cf63ed551560 |  | text | Special Storage/ Handling Requirements?
label | fb380c7a-252a-4d66-8b2b-f7fc306aa5cb |  | label | The following is for completion by Fulton Hogan
text | ebce679a-16fe-48fa-9f62-049231f2abff |  | text | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
text | 5e323372-0246-425e-8988-34489ec46c03 |  | text | QA Docs Delivered?
text | 1f9ece92-557f-4183-864f-cd897d0626ff |  | text | Defective?
text | 25101864-62cd-4c3e-8044-0ba75e51ce62 |  | text | Number Accepted / Number Rejected?
checkpoint-status |  |  | checkpoint | 3)
text | 766d7677-eb9f-4088-bd60-c467911d2f5e |  | text | Item ID:
text | 742e5725-8365-4fde-bfb9-25feafc36874 |  | text | Item description:
text | bcb5cdf1-886e-4e68-94bd-e2484c259aef |  | text | Units ordered:
text | ba045aaa-cc0d-4371-a865-c21f7ad8b1ca |  | text | Units delivered:
text | a1940aea-eb7f-491a-a8ec-73b31e626d4a |  | text | Special Storage/ Handling Requirements?
label | 1b0be734-60b7-4383-8854-adbe1e857781 |  | label | The following is for completion by Fulton Hogan
text | 37ff5fe3-d6fb-4872-9eb0-415c4b940368 |  | text | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
text | 5e80b0b6-06df-4423-a391-384192fa2efd |  | text | QA Docs Delivered?
text | ba0b94d4-195d-4d3f-a7f7-3769ff45da9f |  | text | Defective?
text | 8e6ef2ad-f8e5-4577-94b9-e3e9234f50e4 |  | text | Number Accepted / Number Rejected?
checkpoint-status |  |  | checkpoint | 4)
text | 34b1c7cb-fc31-4b8a-8ef4-7b9f35003540 |  | text | Item ID:
text | cc11dafc-cd38-446b-bf40-a4fedee79c82 |  | text | Item description:
text | e23b03a8-bc11-4bad-a639-57339ee4f90c |  | text | Units ordered:
text | 07001d35-e567-404e-872d-7d1d40a3309e |  | text | Units delivered:
text | 34889111-f3ae-4c8d-b18e-9cf26e843ece |  | text | Special Storage/ Handling Requirements?
label | 5f48a5bf-6a0f-497b-84a4-e1a70d592822 |  | label | The following is for completion by Fulton Hogan
text | d074a9b5-c50c-4b26-b4c1-38f40afc9af6 |  | text | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
text | 04382026-80fe-4856-9527-ab46fd085d20 |  | text | QA Docs Delivered?
text | 2c7d6f7a-8024-4b9b-b521-46efec889e0c |  | text | Defective?
text | f1d0bac0-ad80-4a8a-bc87-d3e55b0484ad |  | text | Number Accepted / Number Rejected?
checkpoint-status |  |  | checkpoint | 5)
text | f0f0c70c-bb4d-42c5-b26d-527ed4803af2 |  | text | Item ID:
text | 9ae66eae-0ad1-4597-afd3-aa3f631faa04 |  | text | Item description:
text | 199453c2-08d9-49aa-93a4-3260c6295105 |  | text | Units ordered:
text | edbed206-dca6-4944-afb7-453709e7e4bc |  | text | Units delivered:
text | ff5d0180-224f-495b-bfd4-fda1ca78c206 |  | text | Special Storage/ Handling Requirements?
label | e4b1cd09-c797-4d50-88b0-1444f037326f |  | label | The following is for completion by Fulton Hogan
text | c05ff9e1-ee29-40fb-b6ef-d5f37428af8d |  | text | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
text | f638f0fa-2b4f-490b-b6ba-963cd91ac95c |  | text | QA Docs Delivered?
text | b3b90d94-f59a-4a0f-ad25-f5132948c64a |  | text | Defective?
text | 4665ce88-79a0-42ea-9da6-50e3f69bb384 |  | text | Number Accepted / Number Rejected?
checkpoint-status |  |  | checkpoint | 6)
text | 01a51b7b-4006-4423-b8be-d9fd29de264a |  | text | Item ID:
text | baa71d54-e3c1-40e9-829d-828865428e36 |  | text | Item description:
text | aacbde66-09fc-49fd-9ecb-7d795377626a |  | text | Units ordered:
text | 25e3ebda-b80a-458b-91ec-90564c94f4ba |  | text | Units delivered:
text | 6854ee16-abf3-4bc2-b678-1ad7126620b2 |  | text | Special Storage/ Handling Requirements?
label | 20182d8b-fd80-4224-9eaa-90f4f28cf40b |  | label | The following is for completion by Fulton Hogan
text | 019ab10b-9cfe-4973-8cf2-72cc70304bc6 |  | text | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
text | 5101d9c3-ef22-4f7f-8acb-9aec27b43d91 |  | text | QA Docs Delivered?
text | 78cefe81-495e-4577-ac5c-04524a3681f8 |  | text | Defective?
text | 4f755334-5a4a-434f-9858-0bb65aa33e80 |  | text | Number Accepted / Number Rejected?
checkpoint-status |  |  | checkpoint | 7)
text | 07b750ca-05c1-42f7-af14-e45ab1face90 |  | text | Item ID:
text | 46efe783-32a9-468c-829f-ebdee2d41061 |  | text | Item description:
text | 314cd6d2-78c7-4e7c-a785-a19a41d41aa8 |  | text | Units ordered:
text | cf1481a2-f616-4f23-a004-ff424979f815 |  | text | Units delivered:
text | 0e5bb1ba-1358-457b-a55d-dde239d390c5 |  | text | Special Storage/ Handling Requirements?
label | b5c53f46-f073-4c0f-b402-95f5962472e0 |  | label | The following is for completion by Fulton Hogan
text | a772d747-b7b7-40a7-9ee6-aacf51c308bb |  | text | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
text | beaa554a-26cb-4005-b570-adc1ab07d0cf |  | text | QA Docs Delivered?
text | c2f2a68d-19fb-47b5-9829-74e052bf43e4 |  | text | Defective?
text | 9cffefad-cb1b-40da-b3ba-f44e6ed07d43 |  | text | Number Accepted / Number Rejected?
checkpoint-status |  |  | checkpoint | 8)
text | e963c054-8042-4681-9511-80ca1da30b4f |  | text | Item ID:
text | 71e4290e-6ef0-4d0e-a0f1-350f78d70b29 |  | text | Item description:
text | b850724d-f7d8-49e8-9f42-efc6543f2071 |  | text | Units ordered:
text | 478da830-8e99-4af8-a761-96ccf8e38c7d |  | text | Units delivered:
text | c93f7d2e-7a90-4534-8b8d-0b200afb1f74 |  | text | Special Storage/ Handling Requirements?
label | 7477a71f-f9c5-4010-8c94-2f8881796d4c |  | label | The following is for completion by Fulton Hogan
text | e09aa68a-6b06-4fec-a064-cff9a6408be3 |  | text | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
text | ef0166a5-856d-44c1-a319-c595c77a5b28 |  | text | QA Docs Delivered?
text | 326ca8c5-efe5-47f5-9b68-ff3ee24b97b0 |  | text | Defective?
text | 80112e6c-1113-4841-ad84-6da76ddf4725 |  | text | Number Accepted / Number Rejected?
checkpoint-status |  |  | checkpoint | 9)
text | 7d8e163c-b192-4f09-9e0a-6a2ffe63383b |  | text | Item ID:
text | 93813169-812f-4fa4-b581-500fa1e46380 |  | text | Item description:
text | 425c24c5-9c31-4e54-b2ab-dc897c460d7f |  | text | Units ordered:
text | 46617760-835c-4d86-b0a0-2530b7440ccd |  | text | Units delivered:
text | ee433ab8-50b9-4a70-a7ac-4fd017482eb4 |  | text | Special Storage/ Handling Requirements?
label | eaa255b8-4137-4a74-afe8-70b81be77bd0 |  | label | The following is for completion by Fulton Hogan
text | 402e03bf-5d82-47cc-90e6-23d18ad01314 |  | text | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
text | 93587b41-f040-4c90-802d-508ba1ad574c |  | text | QA Docs Delivered?
text | 964c072b-4bb6-4264-879c-5d28e0f2df4f |  | text | Defective?
text | 444ceba8-c95f-4a80-b009-715b1c6eee79 |  | text | Number Accepted / Number Rejected?
checkpoint-status |  |  | checkpoint | 10)
text | 48a3d341-1bd9-4a4d-8cd6-109e34508ccf |  | text | Item ID:
text | 7a8104ca-3f41-4d82-a31a-ec7d93b2ea38 |  | text | Item description:
text | 7a2c1214-ac15-4ce1-8b6e-d55b634412ad |  | text | Units ordered:
text | d3c5bb98-16f8-43ac-a8ec-3f5bdf33e7dc |  | text | Units delivered:
text | 99884a66-291d-4a08-8dc0-916f9d3254d4 |  | text | Special Storage/ Handling Requirements?
label | cc211c7d-b7e2-4662-8a71-93f73ac918e0 |  | label | The following is for completion by Fulton Hogan
text | a904014f-f523-45f2-a3b5-12511417a4b0 |  | text | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
text | e1d676af-4149-44fa-acfc-ec6425c9ea96 |  | text | QA Docs Delivered?
text | 54cfbb8c-efbc-4779-9ea4-9a545141ffee |  | text | Defective?
text | 13a85a2f-c7bf-46f7-90b7-e64f718b9447 |  | text | Number Accepted / Number Rejected?
checklist-flat |  |  | checklist | ITP 001 Spray Seal | itp |  |  |  | Yes | ITP 001 - Spray Seal | 371b1081-0990-4301-a0d1-6cb914f13bde
checkpoint-status |  |  | checkpoint | 1 (a) Adhesion Agent
label | 16723453-a107-4f8a-bb7c-9b0c6e9d349b |  | label | FREQUENCY: Test cert. upon request
label | a36db4ae-2e99-46fd-aeec-464ed7c48254 |  | label | ACCEPTANCE CRITERIA: Satisfactory field performance. When adhesion agent is added to the binder, the total volume of adhesion agent ≤1% of the binder.
label | ffc4a333-7cea-4d8c-b2a0-2246b34b06d1 |  | label | REFERENCE DOCUMENTS: 5.6 (a)
label | d3524fae-be80-4b01-ab02-b003d0d8b104 |  | label | INSPECTION/TEST METHOD: Verify
label | 09188d87-ddd3-40a1-bdb5-e6b0f665fedc |  | label | RECORD OF CONFORMITY: This ITP signed off
label | 5a196c76-5cd3-467c-833a-abdc67dd7a11 |  | label | WP
label | 07d92eed-eb60-4ba6-abbb-eee10a86b6eb |  | label | RESPONSIBILITY: Spray Supervisor
text | b4b2af3b-8923-4f7a-92ba-176025315b98 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1 (b) Aggregate Precoating Materials
label | 934650c9-cd02-450e-ab93-7fa6ee11f66d |  | label | FREQUENCY: Test cert. upon request
label | f1912a92-f936-4e70-a3e0-7b8d1ed36c73 |  | label | ACCEPTANCE CRITERIA: Distillate based product, cutback bitumen, emulsion based product or proprietary product.
label | 1d828e0c-4a50-47c7-b3f1-b69ff31ae20c |  | label | REFERENCE DOCUMENTS: 5.6 (b)
label | 24b329c8-9b0d-4e8c-b0e0-b1b225703df8 |  | label | INSPECTION/TEST METHOD: Verify
label | a8d3a224-a3f4-496b-bed1-07a553a83d0f |  | label | RECORD OF CONFORMITY: This ITP signed off
label | 049712fc-59db-4c31-9dee-67319d3de3c4 |  | label | WP
label | 0bdb5def-d451-42f2-8dc9-c4b6d29bede2 |  | label | RESPONSIBILITY: Spray Supervisor
text | 8ed3c0a7-abe5-4222-bc00-431642469463 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1 (c) Bitumen
label | 693cd022-874a-4746-ac9c-f0c296f738bb |  | label | FREQUENCY: Test cert upon request
label | c7a2dda6-307a-4f00-b83a-50913fc52884 |  | label | ACCEPTANCE CRITERIA: AS (Section 175) for residual bitumen for pavements.
label | d9cefe74-cc1b-404f-af2a-694a227dc374 |  | label | REFERENCE DOCUMENTS: 5.6 (c)
label | 29580508-927a-4286-8a6d-24fcaf3366fc |  | label | INSPECTION/TEST METHOD: Verify
label | 8d974cba-5400-490d-a1f7-7695baf6bb64 |  | label | RECORD OF CONFORMITY: This ITP signed off
label | 52557487-9952-438e-948a-59728412a95a |  | label | IP
label | 111feefd-d681-4686-975a-3280561f89d1 |  | label | RESPONSIBILITY: Lab Manager
text | 400d6e22-0681-4311-b449-a12b77b401d6 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1 (d) Bitumen Emulsion
label | b2aa51d0-3e04-4476-a53a-2eb9ce82f8ca |  | label | FREQUENCY: Test cert. upon request
label | 31d1bd71-0e4f-420f-a8a3-a3e68ca3482c |  | label | ACCEPTANCE CRITERIA: ARS or CRS comply with AS (Section 175) – Bitumen emulsions for the construction and maintenance of pavements
label | 09850b28-e652-45ee-a2d7-d02e3209010b |  | label | REFERENCE DOCUMENTS: 5.6 (d)
label | c0347f67-f62d-4725-a943-d4440f3653da |  | label | INSPECTION/TEST METHOD: Verify
label | 6857d402-0b0f-4ae4-b2dd-78b2e5ecc9a7 |  | label | RECORD OF CONFORMITY: This ITP signed off
label | c23101ed-3e8b-4761-ad65-f53ef1f72b4a |  | label | IP
label | 8347ef40-c948-405a-a6b6-8bb3167af766 |  | label | RESPONSIBILITY: Lab Manager
text | 459032ab-1806-4a37-a231-8a1fac3cd705 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1 (e) Cutback Bitumen
label | 7ef95fd8-ecfb-48ed-a71f-51bc5ff6a2c8 |  | label | FREQUENCY: Test cert upon request
label | 3de8444f-7f03-4988-868c-623fb283c6a8 |  | label | ACCEPTANCE CRITERIA: AS (Section 175) – Cutback Bitumen
label | a9d9d33d-73b2-4a13-b436-279c40a87c15 |  | label | REFERENCE DOCUMENTS: 5.6 (e)
label | fcce5141-52e4-47d3-bb85-a773652f91c4 |  | label | INSPECTION/TEST METHOD: Verify
label | 9270ecd1-8936-4642-938f-1181262bc82c |  | label | RECORD OF CONFORMITY: This ITP signed off
label | a7aad81b-0d6e-48dd-9468-8716f873adc8 |  | label | IP
label | e3eb8433-5742-4229-9646-4e45dd43f5ba |  | label | RESPONSIBILITY: Lab Manager
text | ccd31271-6c31-41fb-9d89-119ca0764f37 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1 (f) Cutter
label | b35d86e9-16fe-41e8-b7f0-952668147f54 |  | label | FREQUENCY: Test cert upon request
label | 93e9fea4-e756-4694-a76d-cbabe4485e00 |  | label | ACCEPTANCE CRITERIA: AS (Section 175) – Oils for reducing the viscosity of residual bitumen for pavements
label | 05f42a95-0a4f-4a7c-8724-b2c040b54727 |  | label | REFERENCE DOCUMENTS: 5.6 (f)
label | 6667d8ea-b9fc-4562-849d-7e3e8424cf65 |  | label | INSPECTION/TEST METHOD: Verify
label | 7ff00750-fcf1-4a12-9d2e-c603e2079ee5 |  | label | RECORD OF CONFORMITY: This ITP signed off
label | 5e9fdd4d-a003-4897-88d9-b8c29fa40c11 |  | label | IP
label | ca1973ee-da9a-4060-a8cb-67f391806eac |  | label | RESPONSIBILITY: Lab Manager
text | 5c04e814-b967-4bea-8dfc-e55da8d2ec67 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1 (h) PMB
label | 62bf9b81-1485-489c-9269-10b536a191b5 |  | label | FREQUENCY: Test cert upon request
label | e56ff6e9-029e-4122-96f0-8777ce2f903d |  | label | ACCEPTANCE CRITERIA: (iv)SAMI - S25E, S18RF, 20PtsCR or alternative as approved by the Principal’s Representative
label | e88e42c2-7278-41ec-9124-d2ff5fb3b7c4 |  | label | REFERENCE DOCUMENTS: 5.6 (i)
label | 9f1b37e6-0ce1-41d6-a21c-6ec3a443df02 |  | label | INSPECTION/TEST METHOD: Verify
label | 538210fe-1978-440a-b21a-e71dc1e9cfea |  | label | RECORD OF CONFORMITY: This ITP signed off
label | cb4117bd-beb3-43e4-b024-413ed25b7fcb |  | label | IP
label | 40aef382-9d3e-403a-884a-88846546f611 |  | label | RESPONSIBILITY: Lab Manager
text | a102b5af-8375-4a65-9616-ebdec72cb4f9 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1 (h) (i) Primer
label | 0bcb314a-e777-46f7-8c5a-a7689cf372d9 |  | label | FREQUENCY: Test cert upon request
label | 3f63f08a-fc7e-4f31-9371-362e81a16dac |  | label | ACCEPTANCE CRITERIA: Cutback bitumen only. NB: bitumen emulsion alternative acceptable upon providing evidence of its characteristics.
label | 6d701f43-9294-40c9-a676-bbaba9b99293 |  | label | REFERENCE DOCUMENTS: 5.6 (j)
label | 5576201a-dec7-46f3-98e5-1a5c31e11563 |  | label | INSPECTION/TEST METHOD: Verify
label | 39373c79-6538-4af4-9109-16fe97a93a71 |  | label | RECORD OF CONFORMITY: This ITP signed off
label | c148b47e-ac9f-46e7-a810-cdf75f5ef798 |  | label | IP
label | 5e426411-5236-43ad-ae67-72d553e4197a |  | label | RESPONSIBILITY: Lab Manager
text | a3c28286-23f6-447b-8dac-e28c4e2d6a16 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1 (h) (ii) Primerbinder
label | 750ba2a0-bf88-478a-a058-edca916d928f |  | label | FREQUENCY: Test cert upon request
label | 9ba37b67-e37e-45bb-99a1-14362cccfbc6 |  | label | ACCEPTANCE CRITERIA: Cutback bitumen or bitumen emulsion
label | 96815937-71d2-473b-8db2-500458ec7c2c |  | label | REFERENCE DOCUMENTS: 5.6 (k) 5.6 (d) 5.6 (e)
label | b5652627-7ee0-4e7e-9f40-78d70852e398 |  | label | INSPECTION/TEST METHOD: Verify
label | f23cdfe3-ea79-495b-a004-1923b62b4ca4 |  | label | RECORD OF CONFORMITY: This ITP signed off
label | 58cc3e11-4d67-4e16-a537-f1e3c6076590 |  | label | IP
label | e9f9f09b-a8d9-40d0-8222-7ce4e98bc802 |  | label | RESPONSIBILITY: Lab Manager
text | 0f885de3-6d69-4e54-8de6-35e41a5b473e |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2 (a) Aggregate Specification
label | 651ed790-056f-40e2-95c6-abf2bc26d6df |  | label | FREQUENCY: Maximum lot size 350t of same class and size
label | ae992335-5d8c-44a5-8cd4-c150dd5393d2 |  | label | ACCEPTANCE CRITERIA: VicRoads Standard Specification Sections: 801 - Source Rock; 831 – Aggregate; and 832 - Sands
label | bbd97310-859e-421e-b44e-ef325b3202dc |  | label | REFERENCE DOCUMENTS: 5.7 (a)
label | 051c74ba-8913-4580-8f46-896875ba25ad |  | label | INSPECTION/TEST METHOD: Testing
label | 7a285c4b-d5ff-44a9-a004-5499ce35d607 |  | label | RECORD OF CONFORMITY: This ITP signed off
label | 1f1ad221-192c-45b8-b7ad-2f12933f7f63 |  | label | HP/C
label | 584dcf77-05dc-4fed-99a3-62fbd1883076 |  | label | RESPONSIBILITY: Lab Manager
text | 3610cbef-aa47-43a3-9f83-9c60fb683648 |  | text | Date Completed:
holdpoint |  |  | holdpoint | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 2 (b) Precoating
label | b88c2ac5-3810-40b6-8a42-7215a76c5771 |  | label | FREQUENCY: All works carried out
label | d32a0fd1-c0ea-4c62-831f-e3803b068497 |  | label | ACCEPTANCE CRITERIA: Supply plant precoated aggregate from supplier or field precoated aggregate from stacksite Aggregate shall be uniformly precoated to the satisfaction of the Principal’s Representative.
label | c678642d-2e62-44fa-b572-0189b74e675f |  | label | REFERENCE DOCUMENTS: 5.7 (b)
label | fb676cc3-0ce4-4c25-9b5f-ef09bc3b8b65 |  | label | INSPECTION/TEST METHOD: Verify
label | a2c9db6c-d31a-4bd9-9485-8d98a37bed51 |  | label | RECORD OF CONFORMITY: This ITP signed off
label | 3e8440f7-e5ce-47eb-a22c-71b1a8256b58 |  | label | IP
label | 011fe33e-3e0b-4c38-9668-aeb16cc06405 |  | label | RESPONSIBILITY: Supervisor
text | 3b6d38c2-567c-4053-9f74-0c39695aa56f |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3 (a) Rates of Application
label | 8710cf60-7429-44a5-bc1a-f67958883722 |  | label | FREQUENCY: All works carried out
label | 7dd9729a-dd48-486f-b69b-9ac0f139c879 |  | label | ACCEPTANCE CRITERIA: In accordance with the current update of the Austroads Sprayed Seal Design Method as listed in Section 175. Rates of application - residual binder at 15°C. Traffic Data and default rates – Appendix C of NAR Design Report 1 week prior, design rates of application, aggregate and rates for pre-treatment to be reviewed by Principal’s Representative.
label | 74e7e91c-d1fe-447a-bc6b-4c6159da74b7 |  | label | REFERENCE DOCUMENTS: 5.8 (a)
label | 7bfaa4fc-f3ca-4752-b68e-cf4c2e9d2724 |  | label | INSPECTION/TEST METHOD: Verify
label | 5c0d2155-8739-4f56-a9d4-73d999ab0379 |  | label | RECORD OF CONFORMITY: This ITP signed off
label | 7f037d16-ec48-4bbd-9ff2-f18093ed0bb0 |  | label | HP/P
label | 74fcef14-e3ff-4d99-96ac-9ef06f3c87f9 |  | label | RESPONSIBILITY: Project Engineer/Principal’s Representative
text | 69463f5e-363a-4487-9758-ea8c185c1ccd |  | text | Date Completed:
holdpoint |  |  | holdpoint | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 3 (b) Surface Pretreatment
label | 7d3eb1ed-10dc-4a96-baa2-a9d84e47706c |  | label | FREQUENCY: All works carried out
label | 4d7e6f08-c4a5-4af7-be32-772cc5cf7253 |  | label | ACCEPTANCE CRITERIA: Refer Table 408.161, 408.122, 408.123
label | d9f7fc0f-23a8-4982-927a-ef916d1e13c7 |  | label | REFERENCE DOCUMENTS: 5.8 (b)
label | 4008c5c6-0278-4155-a40e-a019d072d6ab |  | label | INSPECTION/TEST METHOD: Verify
label | bff4550a-a2db-4a92-94e3-2cc004a98cac |  | label | RECORD OF CONFORMITY: This ITP signed off
label | 29eb38bd-aee8-454f-9b40-8705f9c93b45 |  | label | IP
label | d271ec6a-f2e1-4c9b-b5bc-e7f532453f57 |  | label | RESPONSIBILITY: Supervisor
text | d02e5342-9529-440b-a7a6-870189e14260 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3 (c) Calibration of Bitumen Sprayer
label | 4a198a53-896d-4bab-87b7-c843d0ae04dd |  | label | FREQUENCY: Prior to commencing works
label | 7af42929-8197-4d32-9e6f-24a64b6aa445 |  | label | ACCEPTANCE CRITERIA: Calibration Certificate to be provided upon request, and renewed every 12 months
label | d765aa4e-c7e6-4880-90f1-5878da25ab91 |  | label | REFERENCE DOCUMENTS: 5.5
label | 784abcf0-2fe0-4fe0-bfb5-319946633255 |  | label | INSPECTION/TEST METHOD: Verify
label | 150ec2a4-53b0-4f41-9f95-605d360dbb0b |  | label | RECORD OF CONFORMITY: This ITP signed off
label | c420cb8e-26ed-4e08-b361-bf9ad18dc5d6 |  | label | WP
label | 9e76bb68-3bbc-486d-959a-6f6536be8bef |  | label | RESPONSIBILITY: Supervisor
text | 8bd9448e-4aac-4127-a694-cb241e8c081f |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3 (d) Commencement of works
label | 9ff3f567-98c1-4704-87e3-d7b588b76256 |  | label | FREQUENCY: Prior to commencing works
label | 4cd6edc8-6da5-4d9a-b746-24bb004bcc23 |  | label | ACCEPTANCE CRITERIA: NB: Works shall not commence until the Contractor & Principal’s Representative of works agree that the prepared surface is ready & fit for sealing. Primersealing shall not be carried out within 12 hours of forecast rain. Priming shall not be carried out within 24 hours of forecast rain
label | a92a606e-b99e-427e-8990-0d1484b94b4b |  | label | REFERENCE DOCUMENTS: 5.3
label | 1f8f2990-d460-4120-b9fb-f2c6983153e6 |  | label | INSPECTION/TEST METHOD: Visual Inspection
label | 26b0ec4f-2e7b-4d4c-92b2-8dcbcf594a8c |  | label | RECORD OF CONFORMITY: Site Inspection
label | d115c274-410f-44b4-980f-8a5d173f7184 |  | label | HP/P
label | 921cff86-f654-45aa-98ff-ebb459ede2a9 |  | label | RESPONSIBILITY: Project Engineer/ Superviso and Principal’s Representative
text | f65db8a3-08be-43d0-af36-c8b1c167b7f2 |  | text | Date Completed:
holdpoint |  |  | holdpoint | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 3 (e) Removal of loose aggregate
label | 23f0f399-3a56-4714-95ed-ac620bf7a6ee |  | label | FREQUENCY: All works carried out
label | 16e1bd18-d9a3-458a-b0e2-af338f5c8132 |  | label | ACCEPTANCE CRITERIA: All areas – within 5 days of sealing unless otherwise agreed with the Principal’s Representative. NB: For seal of nominal size ≥ 10mm, < 40 loose stones/m2 to remain after removal of loose aggregate. For seal of nominal size ≤ 7mm, < 60 loose stones/m2 to remain afterwards.
label | 825bac54-82d0-41bc-adbc-5da91184148c |  | label | REFERENCE DOCUMENTS: 5.9
label | 3b96bfe8-30a2-420a-b4e2-83b0abb8986b |  | label | INSPECTION/TEST METHOD: Visual Inspection
label | e992e622-13d4-41aa-8937-b73bfb0c9966 |  | label | RECORD OF CONFORMITY: Site Inspection
label | e208722c-2a06-4d78-bd9c-985a2742d0e1 |  | label | IP
label | 2d43ba23-d3ee-4733-bbeb-bf782086fd04 |  | label | RESPONSIBILITY: Supervisor
text | 38a48084-f63e-4f38-8ece-778ae088aabf |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3 (f) Records
label | 64d7efff-3479-49ef-8e22-bb113b91a851 |  | label | FREQUENCY: Each Lot
label | a382c1cf-dc8f-43d6-85e0-9834f08277e4 |  | label | ACCEPTANCE CRITERIA: Job completed within spec requirements. Job completion report ,i.e. Spray Sheets to be submitted within 7 days of completion of sealing works
label | 5a77766a-8532-4c98-9b17-424ec989c553 |  | label | REFERENCE DOCUMENTS: 5.12
label | 0682f14a-7ba1-4a3c-98c3-70c1a525138d |  | label | INSPECTION/TEST METHOD: Verify
label | 3bb26c79-00e6-4a2e-ba30-9d2a145dc6b3 |  | label | RECORD OF CONFORMITY: This ITP signed off
label | da881e97-1752-417f-8307-c201b260b54a |  | label | WP
label | 778b863b-82e4-4372-853a-aa2512f80157 |  | label | RESPONSIBILITY: Project Engineer
text | 88b2f1c7-25fc-4c96-9891-e46d22388e73 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3 (g) Acceptance of work- Binder rates
label | e64eb7ed-c440-448e-a0af-0a1ccd739765 |  | label | FREQUENCY: Each Lot
label | 07d08930-5813-4d7a-9de6-51e82529f803 |  | label | ACCEPTANCE CRITERIA: Actual vs design rates. Variation between actual & design assessed by Table 408.121
label | fc886b1d-c144-41c9-a877-ccba011fdf62 |  | label | REFERENCE DOCUMENTS: 5.10 (a)
label | 3967f67e-d485-4b1d-8ab9-69fca893df86 |  | label | INSPECTION/TEST METHOD: Verify
label | 759a4a49-fa77-4000-abfa-75e0d8279696 |  | label | RECORD OF CONFORMITY: This ITP signed off
label | 89ab64b2-486a-4608-bd94-c3b6cb4f25ed |  | label | IP
label | 4f6f1b96-f799-4467-b839-aa84bd320ad6 |  | label | RESPONSIBILITY: Project Engineer
text | c8464497-be6a-4d88-b4e8-e5b02aa307f1 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3 (h) Acceptance of work- Surface Texture
label | 05f645be-1ff5-4362-a5af-142ccca8cec5 |  | label | FREQUENCY: Each Lot
label | 4ce80038-1671-4cf6-a154-324e3fc3a3a0 |  | label | ACCEPTANCE CRITERIA: Acceptance - visual assessment or (where required) as per Table 408.122. Lot size shall be 100m ≤ length ≤600m for single traffic lanes. For other than traffic lanes, lot size shall be 400m2 ≤ Area ≤ 2,500m2
label | e410b8eb-2104-49d6-a322-34cdbd390ba4 |  | label | REFERENCE DOCUMENTS: 5.10 (b)
label | f0870cc9-0108-4b26-adea-7975d2a5793c |  | label | INSPECTION/TEST METHOD: Visual Inspection
label | 3fcd3020-bcce-4a77-b79e-7b57a37481b0 |  | label | RECORD OF CONFORMITY: Site Inspection
label | 2613e5fe-e06a-4a0e-a0c5-a8f0042cf4bc |  | label | IP
label | e6d5eb6a-ed9f-45ff-94bd-64ed30bfaebb |  | label | RESPONSIBILITY: Project Engineer
text | 89728f7b-4134-4da9-9c4a-b1139b64fe61 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3 (I) Acceptance of work- Aggregate retention
label | df1dcfe4-d5b1-42f0-98f0-a31ee62bf195 |  | label | FREQUENCY: Each Lot
label | 39b31efa-c232-4c87-a1fe-6ff1c04debfc |  | label | ACCEPTANCE CRITERIA: Acceptance -visual assessment or (where required) as per Table 408.123. Lot size shall be 100m ≤ length ≤600m for single traffic lanes. For other than traffic lanes, lot size shall be 400m2 ≤ Area ≤ 2,500m2
label | 3c4bd5b5-c522-419c-adce-dfba63698b6a |  | label | REFERENCE DOCUMENTS: 5.10 (c)
label | e9423311-0952-482e-93b9-333326b8714e |  | label | INSPECTION/TEST METHOD: Visual Inspection
label | 49b0b3ec-85b8-417f-98c6-1a2334d6b126 |  | label | RECORD OF CONFORMITY: Site Inspection
label | c07b0c7f-5b69-42a9-86b6-3d4c6d5929a2 |  | label | IP
label | 3ede25b6-f16a-410d-94f4-2509c1f3bd97 |  | label | RESPONSIBILITY: Project Engineer
text | 692820dd-3da1-4592-8f44-909c07b5c155 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3 (j) Acceptance of work- Visual Uniformity
label | af3e9d53-b413-43ca-a054-d92d775a5b94 |  | label | FREQUENCY: Each Lot
label | fe217d37-8bd1-494a-9b87-532d885deaa8 |  | label | ACCEPTANCE CRITERIA: Provide a surface with uniform colour, texture and consistent appearance
label | 80840ad4-8dca-4c76-8663-2863d549f0a0 |  | label | REFERENCE DOCUMENTS: 5.10 (d)
label | fe526bec-14ce-463c-8fb7-3712e3313460 |  | label | INSPECTION/TEST METHOD: ) Visual Inspection
label | 2ee6210d-2926-4b7c-ae8d-849deacbf4b2 |  | label | RECORD OF CONFORMITY: Site Inspection
label | 866c788c-f262-4a1b-985d-df3b367a4b9b |  | label | IP
label | d4f3cd91-c751-43f8-9799-092247495ed6 |  | label | RESPONSIBILITY: Project Engineer
text | e3e8c6d8-c265-4664-af08-e0f7fc0ed337 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3 (k) Maintenance of seals
label | bb956891-3e5c-4914-9e4c-f20b50035e68 |  | label | FREQUENCY: All works carried out
label | a314e429-a65e-47c0-9ad9-5f3863e29624 |  | label | ACCEPTANCE CRITERIA: The contractor shall be responsible for the monitoring and maintenance of seals from the time of application until the end of the defects liability period. The Contractor shall advise the Principal’s Representative in writing of the proposed treatment to effect the above work before undertaking the work
label | 3fb70297-fed1-4bc2-974b-50c17ff84dfb |  | label | REFERENCE DOCUMENTS: 5.11
label | 29795116-ff49-49b5-bf02-59da7679404a |  | label | INSPECTION/TEST METHOD: Verify
label | 1eb3f6c0-dcf7-4417-bd90-484017f419af |  | label | RECORD OF CONFORMITY: This ITP signed off
label | ee960815-704b-431b-bcbc-333368828299 |  | label | HP/P
label | 0d0f7387-29b2-4c54-8a3e-475157c31edb |  | label | RESPONSIBILITY: Project Engineer and Principal’s Representative
text | 0cf0382d-e777-4559-b401-1d749c4cf934 |  | text | Date Completed:
holdpoint |  |  | holdpoint | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 3 (L) Maintenance of seals
label | 1b22bd46-1f9b-479e-aa4a-b85930782e84 |  | label | FREQUENCY: All works carried out
label | 6351f24a-1c5f-40ed-acb3-196253f97ad4 |  | label | ACCEPTANCE CRITERIA: Where the treatment for protection or repair of a seal involves the application of a further seal coat, the Contractor shall obtain the agreement of the Principal’s Representative of the proposed treatment before undertaking the work.
label | 5c83b2af-9425-4ba7-b0c7-b5df79559178 |  | label | REFERENCE DOCUMENTS: 5.11
label | 93101417-7d40-4309-874f-0f1b69ab35d2 |  | label | INSPECTION/TEST METHOD: Verify
label | 49476331-7fc0-478b-8624-c8c0a74e5157 |  | label | RECORD OF CONFORMITY: This ITP signed off
label | f423ce1e-3784-48b9-96c6-7ac18bb3b541 |  | label | WP
label | 9418d563-7588-450b-87a7-9b6beff49e6c |  | label | RESPONSIBILITY: Project Engineer and Principal’s Representative
text | 3de4d0f6-055b-499d-87b2-abcb2ebd2e3d |  | text | Date Completed:
holdpoint |  |  | holdpoint | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 3 (m) Defects Liability Period
label | 429175c1-cf45-4a26-96fe-104614f5e6a1 |  | label | FREQUENCY: All works carried out
label | 4957b6cc-32c6-4f6d-801f-6f74da50090a |  | label | ACCEPTANCE CRITERIA: All defects should be rectified six months prior to the conclusion of the Defects liability period. As stated in 408.15
label | d1ec6cbb-762c-440a-880d-030a6015fbcb |  | label | REFERENCE DOCUMENTS: 5.13
label | 96acd655-d4a4-41de-a4dd-9a8e41dabc84 |  | label | INSPECTION/TEST METHOD: Verify
label | 375850ba-7afb-4d76-ae83-253cadb41412 |  | label | RECORD OF CONFORMITY: This ITP signed off
label | 3c51de49-8970-454e-94ca-25f3c3d3d2a2 |  | label | WP
label | 86a0419c-bd5d-48ce-8920-ee2d0a9163c7 |  | label | RESPONSIBILITY: Project Engineer
text | ae081ce4-9b1f-47e5-9da9-479fdae0ba88 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection (Lot conformance sign off)
label | 7117e359-fbe8-4504-ac5a-821056e5a945 |  | label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | efe74833-6061-45a4-8884-36b1c3490b0a |  | text | Print Name:
text | 67af84dd-104b-4c3a-9c07-00f9a080f25c |  | text | Position/Company:
text | 94b2a929-f532-4132-86c4-0347ea85e160 |  | text | Signature:
text | 7c8f058a-ba63-4377-8ff3-15f926ca5e75 |  | text | Date:
checklist-flat |  |  | checklist | ITP-005 Water Main | itp |  |  |  | Yes | ITP 005 - Water Main | 44668c69-77f5-41cd-a40a-b24de9499b46
checkpoint-status |  |  | checkpoint | 1.1 Materials
label | 00f8a356-8639-4953-a53c-ec2c66a24c51 |  | label | FREQUENCY: Prior to start
label | 1cacdc12-7f94-45c5-b8b2-4e42961b1178 |  | label | ACCEPTANCE CRITERIA: Ensure that the correct materials are being used as per drawings and specifications.
label | 7b936f98-8499-426e-959f-901c2eaf1d0c |  | label | PE Pipes:
label | 217805c7-7b4b-4dea-a571-effac136523f |  | label | • PE pipes shall be class PN16 SDR11;
label | 0ba15c63-5912-480e-b0c6-6bdbc98f318e |  | label | • PE pipes shall be PE 100 series 1;
label | 8f5b1620-fc62-4105-b2c2-ee4cb0cce2ef |  | label | • Drinking water pipes shall be solid blue or sheathed blue or black with blue stripes;
label | 91f971e3-1744-4117-be32-44383fb4d8c7 |  | label | • PE pipes for pressure shall have fully welded joints (butt fusion);
label | ac408229-f12f-47c7-8ae7-7c1422594da0 |  | label | • No electro-fusion joints are permitted.
label | e43e84f2-3031-4655-81bb-65fd43fe103a |  | label | REFERENCE DOCUMENTS: Drawings Jacobs Cl 8.2.1
label | 7b4b9705-811b-4665-a773-f448cf614142 |  | label | INSPECTION/TEST METHOD: Verify
label | 476c21b9-224e-439f-875e-000da38aa013 |  | label | RECORD OF CONFORMITY: This ITP signed
label | f3be9913-7a9c-4014-be18-2ba0b1c25b94 |  | label | HP*
label | 8c3d51e6-1219-4077-ba0e-bbf58a1dce61 |  | label | RESPONSIBILITY: Project Engineer
text | effc43f4-6003-40a4-8195-0c0eab960d58 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 Ductile Iron Cement Lined (DICL)
label | 2babae42-2525-4f80-adda-4e17d6233618 |  | label | FREQUENCY: Prior to start
label | 7879aaef-4301-43e7-bc23-da50826a2868 |  | label | ACCEPTANCE CRITERIA: Ensure correct materials are being used with test certificates and test results.
label | 00aea0e6-8c25-40bf-82d0-d5991fcbee7e |  | label | REFERENCE DOCUMENTS: CL 8.2.1.3
label | d552448a-b1c7-4480-8577-0de3ef3c9ec7 |  | label | INSPECTION/TEST METHOD: Verify
label | ce757fac-ea90-4b37-ad5f-75566096264d |  | label | RECORD OF CONFORMITY: Test Reports / Manufacturers Certification
label | b8bde874-ee14-4d84-a15c-08333f39670f |  | label | IP
label | e93f6633-d8a6-40cf-9332-ea1e7d2959e6 |  | label | RESPONSIBILITY: Project Engineer
text | 530edc1d-a38f-4776-91e6-e662f4ce2355 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 Valves
label | 7a128904-2802-4e21-bf4a-eb1403916a30 |  | label | FREQUENCY: Prior to start
label | af64dd1f-4c72-462e-b990-01e1c8b28037 |  | label | ACCEPTANCE CRITERIA: All valves shall be anti-clockwise closing;
label | fd0445ec-acdf-4ee7-9a03-f247b90f15ce |  | label | ACCEPTANCE CRITERIA: Valves and fittings, including air valves and scour valves, shall be installed in the pipeline as specified or directed, in accordance with the type and details shown on the Drawings and in the specification;
label | 50c27745-9af3-4cde-88bc-9b9a31918ab8 |  | label | ACCEPTANCE CRITERIA: Sluice valves shall be PN16;
label | ab689804-f8c2-4fff-a34e-64705690c49c |  | label | ACCEPTANCE CRITERIA: Air Valves shall be PN16.
label | a07df1bd-b0fc-47c3-ae89-bbd9e52ef6ab |  | label | REFERENCE DOCUMENTS: Cl 8.2.2
label | a7d549f9-c608-4bdb-a82c-9b39f410ee91 |  | label | INSPECTION/TEST METHOD: Verify
label | f287732a-6b84-4577-be36-19cec0d23b51 |  | label | RECORD OF CONFORMITY: This ITP signed
label | 95ecf8b1-661b-4875-b5a3-83ba85d54e45 |  | label | IP
label | c48fa7f5-9b23-44f6-8e63-62acf294fc21 |  | label | RESPONSIBILITY: Project Engineer
text | c68e731d-9531-415a-91d2-b86522b1b7a6 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.4 Water Meter & Associated Fittings
label | 765a40c4-f9c0-4b18-8e4e-8b33a6ada0bd |  | label | FREQUENCY: Prior to start
label | cb89812b-837c-4048-86d6-4696ef30eca3 |  | label | ACCEPTANCE CRITERIA: Refer to MRWA standard drawing No.1 (20-25mm General Water Service – Wet Tapping) and to melbourne requirement.
label | 1e97c421-26af-4d3d-ae15-44942fd37f85 |  | label | REFERENCE DOCUMENTS: Drawings
label | 7f323047-2939-46be-b68c-b4d809e32788 |  | label | INSPECTION/TEST METHOD: Verify
label | 36d71e8f-54a9-4a92-a0e0-8f5a32ab0416 |  | label | RECORD OF CONFORMITY: This ITP signed
label | 493a3ff6-01f5-4a29-af24-6c6e6ff4a3f8 |  | label | IP
label | 073b5cb5-e532-48fe-9d33-89c17ae395d2 |  | label | RESPONSIBILITY: Project Engineer
text | 8ab3febc-c158-4765-b9a2-9a6a85f0cfae |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 Setting Out
label | 9f9ffd49-7fdd-4808-ac28-ead6bbd09f7f |  | label | FREQUENCY: Prior to start
label | effd0155-ff88-4afd-87ac-0b8e602147fb |  | label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | d87b1473-fd71-4efb-b396-b5a2d6ce6e58 |  | label | ACCEPTANCE CRITERIA: Using the correct and complete set of drawings;
label | 6371fbee-8d4d-4e1e-8cc7-d470f59c236f |  | label | ACCEPTANCE CRITERIA: All drawings are the latest revision
label | c95dd189-5417-46ea-8131-a2e4116c3c55 |  | label | REFERENCE DOCUMENTS: Drawings/Aconex
label | f38f017b-2c84-4cc6-889b-e59b3fa2d957 |  | label | INSPECTION/TEST METHOD: Verify
label | cb0d284c-20e1-4895-95e1-99e4ad243038 |  | label | RECORD OF CONFORMITY: Drawinfs/Survey Report
label | e2672f3b-b3c3-451f-90d0-4aa6d28575a1 |  | label | SCP
label | d3ae4fca-9d7b-4cd0-9fb3-d0fbd0fc05de |  | label | RESPONSIBILITY: Project Engineer
text | b5b248a1-7393-4f9e-9031-9540b419c1ec |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Site Inspection
label | 55393000-fbd4-4874-8cb6-d144d1855570 |  | label | FREQUENCY: Prior to start
label | c0531f01-8ce6-4f08-8c94-ceb3236d050f |  | label | ACCEPTANCE CRITERIA: Inspection of the site prior to commencing work.
label | 0125c8ce-fc7c-4622-92a7-a37bbb6c4aed |  | label | REFERENCE DOCUMENTS: Cl 8.2.3.7
label | a154e6e2-65d5-4187-9149-06cf4d9a91e2 |  | label | INSPECTION/TEST METHOD: Visual inspection
label | f23bf5d1-bf5a-46c6-b538-6fa6646ae9ac |  | label | RECORD OF CONFORMITY: This ITP signed
label | 6a619a3c-b9c4-4277-a86b-04a3b07d0c77 |  | label | WP
label | 03314566-1d23-46c1-8f0a-414ab7696993 |  | label | RESPONSIBILITY: Project Engineer/Principals Rep
text | 47fa07d2-7ed8-4f16-aa5e-c79c344845c4 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3.1 Existing Service Location
label | c92368ef-5a03-41ff-b4a2-cb7a0136fff2 |  | label | FREQUENCY: Prior to start
label | 963c6636-12cd-4091-b0cb-f350aa29c399 |  | label | ACCEPTANCE CRITERIA: - Location of services to be found and marked on the ground within the works; - Services located within the works area to be exposed;
label | 1c312aca-6904-4a5f-bd33-d88a3ca7b0da |  | label | REFERENCE DOCUMENTS: DBYD/ Drawings
label | 137ce7fc-2dda-41db-8b87-b69407d6dfe3 |  | label | INSPECTION/TEST METHOD: Verify
label | 7f5890e6-2633-4f35-9198-e42da6dfe02d |  | label | RECORD OF CONFORMITY: Melbourne Airport Excavation Permit
label | 0a61755e-1a61-4276-9a79-2fb2ea70ce1a |  | label | IP
label | 0b0bc6eb-8ec7-40bb-b87a-76e89938b1b2 |  | label | RESPONSIBILITY: Project Engineer
text | c960ce17-7c06-4685-8f55-53d1604b9ad0 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Segregation between water services and HV/LV
label | 5282169c-eb6a-41c0-bcd7-7ee7196036e8 |  | label | FREQUENCY: Prior to start
label | 75f396f3-fcc1-46c7-bbfe-445070f9f1b9 |  | label | ACCEPTANCE CRITERIA: Segregation between water services and HV/LV cables is min 500mm, and between HV and LV cables is min 300mm. Refer to Cl 8.1 – Table 8-1 for minimum separation, horizontal and vertical clearances between underground HV/LV.
label | 27235651-c626-493d-a8c5-d86b106fa11f |  | label | REFERENCE DOCUMENTS: Drawings Cl 8.1 – Table 8-
label | 464bc613-9683-4535-b470-024912149a6e |  | label | INSPECTION/TEST METHOD: Verify
label | 34726623-dd83-48af-9275-fe9065495640 |  | label | RECORD OF CONFORMITY: This ITP signed
label | 2df646d5-5f6b-4068-a730-c6ce7b4d554e |  | label | IP
label | 23353d1d-2deb-4966-a37a-c2c3e2db4718 |  | label | RESPONSIBILITY: Project Engineer
text | b720f1e9-4ef0-41ec-861b-11aefce655e0 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 4.1 Excavate Trenches for Pipes
label | a206eeac-dcfe-4cb3-94d9-d822e7d7c790 |  | label | FREQUENCY: Each lot
label | 9332d676-ff43-45f5-ac60-2900275695d1 |  | label | ACCEPTANCE CRITERIA: Depth and width of trench shall be excavated to the requirements specified on the Drawings for each Section. Excavation tolerances shall comply with the drawings. Trench Foundation shall be finished to the approval of the Principals Representative prior to bedding.
label | 8bdc98b1-2d87-42fd-979b-651010825062 |  | label | REFERENCE DOCUMENTS: Cl 8.2.3.2
label | 141e8bec-bb4a-48f0-bfe5-fec09b3a252b |  | label | INSPECTION/TEST METHOD: Verify
label | 875c5d6e-6656-4648-9191-f49cba647dd7 |  | label | RECORD OF CONFORMITY: This ITP signed
label | ce7f7b4e-42f0-49af-bcda-fcd644a7881e |  | label | WP
label | 79dc51c2-63c1-4d3f-b118-69188c61b90b |  | label | RESPONSIBILITY: Project Engineer/Principals Rep
text | db6b01fc-43b9-42c4-93ef-b19d69082cd2 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Horizontal Directional Drilling/Water Main Boring Works (If applicable)
label | d6ddedfa-4588-459c-ad1f-c0e707127219 |  | label | FREQUENCY: Each lot
label | c8337883-cd73-4c26-8874-531a092d1e08 |  | label | ACCEPTANCE CRITERIA: Any water main boring works refer to BTB ITP021 (FH-NAR-PM-ITP021). Subcontractor ITP to be signed off and attached behind ITP005 (If applicable)
label | 942ea52f-d1b0-437e-981f-4c32d2ec7c27 |  | label | REFERENCE DOCUMENTS: FH-NAR-PM-ITP021
label | a96b350d-b3c8-4a0c-ace3-effcdf2c4478 |  | label | INSPECTION/TEST METHOD: Verify
label | 5c562810-da41-4236-b673-d63980fa3e64 |  | label | RECORD OF CONFORMITY: This ITP signed
label | f059fb5f-a0bc-4c89-a5a4-c1ac4aaa8fb1 |  | label | WP
label | 6bb52151-0d7b-486e-9b9b-d764047c1b44 |  | label | RESPONSIBILITY: Project Engineer/Principals Rep
text | dc48f900-ac37-4533-a304-3bfb65eb462c |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Laying & Jointing of Pipes
label | 97325d17-b9e7-4da7-bd83-ceef25ee2f55 |  | label | FREQUENCY: Each lot
label | 8078b798-3562-4c73-9183-cf249083013c |  | label | ACCEPTANCE CRITERIA: All pipes and ducts shall be laid in conformity with the details shown on the Drawings, true to the lines, levels and grades;
label | b589aaa7-3a90-45b5-bdb7-6aebec5d77ce |  | label | ACCEPTANCE CRITERIA: Where any pipe or fitting is marked “TOP”, the pipe shall be laid with this mark uppermost;
label | 3ed1ec19-bebe-459e-bec9-3c546fd303b9 |  | label | ACCEPTANCE CRITERIA: Buried pipes and ducts shall be provided with bedding and surround material as specified;
label | 368b51f8-07a3-4f29-b14b-755cf4b2fbeb |  | label | ACCEPTANCE CRITERIA: Quantity of conduits to be confirmed and entered w/ each lot;
label | 973ac6f2-ddea-4d42-99f5-09aebaaa2ba1 |  | label | ACCEPTANCE CRITERIA: When pipework assembly is not in progress the open ends of pipework shall be closed;
label | 3c5421a9-65ab-4567-80d2-6de635aa56c1 |  | label | ACCEPTANCE CRITERIA: by a watertight plug or cap;
label | 2e98939d-eec9-44fd-b564-0871923ff92f |  | label | ACCEPTANCE CRITERIA: Cut pipes square to the barrel of the pipe with a total deviation of not more than 5mm;
label | aa10fb91-55b4-421e-9846-e83c0f2f97ad |  | label | ACCEPTANCE CRITERIA: Remove jagged edges;
label | 61bd2f5d-58a5-493e-a25c-bb28639f7a55 |  | label | ACCEPTANCE CRITERIA: Bevel cut edges of pipes in accordance with manufacturer’s instructions
label | 64a0a96d-fb95-4403-b854-711f7926d0b9 |  | label | ACCEPTANCE CRITERIA: The Contractor shall joint pipes and fittings in accordance with the manufacturer’s instructions and recommendations;
label | 1854a7d7-7d6d-40c1-a6a5-172a6215e07d |  | label | ACCEPTANCE CRITERIA: The Contractor shall test gravity flow pipes in accordance with the Specification and the Drawings;
label | bf4908af-1ffd-4ac8-8ff5-0d347d7b51e6 |  | label | ACCEPTANCE CRITERIA: Pressure pipework shall be tested in accordance with this Specification and the drawings;
label | 3a40b722-89d3-4c78-96a0-efdfe7f9fd6b |  | label | ACCEPTANCE CRITERIA: Unless otherwise indicated on the drawings, PE pipe shall be jointed by full welding and shall be installed in accordance with AS 2033;
label | f31d19d7-9f31-46c4-92f8-74762f01ddae |  | label | ACCEPTANCE CRITERIA: Unless otherwise indicated on the drawings, PVC-U pipe shall be jointed by solvent welding
label | db0d6a78-2d68-46e2-aaa2-e6c37f1babfa |  | label | REFERENCE DOCUMENTS: Cl 8.2.3.1 Cl 8.2.3.5 Cl 8.2.3.6
label | 2786d20d-6cf7-4fdc-ae8a-235826ba99a9 |  | label | INSPECTION/TEST METHOD: Verify
label | 066abcc6-4ccf-4722-b343-64d3b6af67dc |  | label | RECORD OF CONFORMITY: This ITP signed
label | 4ef1eaea-2453-4447-b1b1-7ebee378f5c9 |  | label | IP
label | cbb25f82-3a0c-4a9a-9b16-4a1f1da0cbcd |  | label | RESPONSIBILITY: Project Engineer/Foreman
text | 6c5e2162-8141-45b8-bb0f-7fdb079e3d2e |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Welding of PE pipes
label | 99d74d85-f217-4469-9b45-92c817e4e704 |  | label | FREQUENCY: Each lot
label | 0e4b5bea-eef1-4ab1-88e8-f940c96d7356 |  | label | ACCEPTANCE CRITERIA: - PE pipes for pressure applications shall have fully welded joints (Butt fusion joint). No electro-fusion joints are permitted. - Unless otherwise indicated on the Drawings, polyethylene pipe shall be jointed by full welding and shall be installed in accordance with AS 2033. - Unless otherwise indicated on the Drawings, PVC-U pipe shall be jointed by solvent welding.
label | a7f70953-2f25-424d-b38c-4914edc2e809 |  | label | REFERENCE DOCUMENTS: Cl 8.2.1.1 Cl 8.2.3.6
label | 541a8344-77b4-4142-b3a0-c279c36e5a30 |  | label | INSPECTION/TEST METHOD: Verify
label | c1b5f724-59d2-4c16-b3ff-e31a9b7dcec1 |  | label | RECORD OF CONFORMITY: This ITP signed
label | a56b7e37-851b-4652-bfc4-c592dc6ead93 |  | label | IP
label | 247bb6f7-3a3e-4831-9028-78fe897f6168 |  | label | RESPONSIBILITY: Project Engineer/Foreman
text | c2a7285b-1eea-428b-b0df-972e43d0df1f |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 Backfilling
label | 735650f2-af90-43a6-942a-f1fdbd09af93 |  | label | FREQUENCY: 1 test per layer/50 lineal meters for each embedment and backfill zone
label | 9662ead8-34f0-4cc6-88dc-fc4a26e6257e |  | label | ACCEPTANCE CRITERIA: Bedding and surround shall be Grade A sand or 5mm crushed rock;
label | 344fca3f-23a7-4a8b-ba87-d992a61c36ee |  | label | ACCEPTANCE CRITERIA: Pipe bedding and surrounding material shall be carefully placed and compacted using mechanical compaction;
label | eea02a83-bff8-4515-9f6c-53c1658df58e |  | label | ACCEPTANCE CRITERIA: Embedment zone 70% min density index ratio for Compaction;
label | 43bc957a-80b7-4596-9208-38b0d89639e7 |  | label | ACCEPTANCE CRITERIA: Backfill 95% min dry density ratio for Compaction to bottom of subgrade
label | 3e554c61-3638-4022-8b02-4cb2c41a0682 |  | label | REFERENCE DOCUMENTS: Cl 8.2.3.3, Cl 8.2.3.4, Drawings
label | 11d9ec0e-d72d-4744-8968-29378e8cc8e3 |  | label | INSPECTION/TEST METHOD: Verify
label | 2f4b2ba6-337b-43ae-983a-5274e55c805e |  | label | RECORD OF CONFORMITY: Visual Inspection / Signed ITP / Test Report
label | 345b125e-a965-473b-8413-091536c0a388 |  | label | IP
label | 25834023-c8e8-4d31-8701-2d11ce6cb3e3 |  | label | RESPONSIBILITY: Project Engineer / Foreman / Principal’s Representative
text | f0d6e602-d686-410c-b089-8e03d3b6fceb |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 4.6 Hydrostatic Testing of Pressure Water Pipework
label | a38ab6b5-73e1-4009-a740-fd1690f700e4 |  | label | FREQUENCY: Each pipeline may be tested in one length, or alternatively hydrostatic testing may be carried out in sections
label | 801dc7da-1c4d-4996-bfda-dfc06ba09ec2 |  | label | ACCEPTANCE CRITERIA: If a pipeline is tested in sections, then care shall be exercised to ensure that the pipe ends of the section under test are adequately secured against movement. Pressure gauge calibration shall be undertaken. The Pipeline Test Pressure for each pipeline, or individual test section, shall be 1.25 times the Design Pressure of 60m at the lowest point of the test section.
label | 7671ddaa-e9e2-4492-b638-27bf7f52dfab |  | label | REFERENCE DOCUMENTS: Jacobs Cl 8.2.4 WSA03 2011-3.1 MRWA Version 2.0, Section 19.4
label | a6b4c4ca-64f5-4d2e-acb4-9008e18871d1 |  | label | INSPECTION/TEST METHOD: Verify
label | ac0b4e11-0e91-426f-be5a-4d84dce3ca14 |  | label | RECORD OF CONFORMITY: Test Report
label | 7850dc08-5357-40ab-98e1-02d3cf4a294e |  | label | TP
label | 3b278c32-671d-408b-83c5-6aabbdc91435 |  | label | RESPONSIBILITY: Project Engineer/Principals Rep
text | 3f0560be-8432-4aea-ae27-0700d4ad76ea |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 4.7 Testing of Gravity Sewer Pipework
label | 2474c773-09e5-48b5-968c-ca2b0159607c |  | label | FREQUENCY: Each lot
label | a07a342d-51fc-4ff9-a90a-9db089c98301 |  | label | ACCEPTANCE CRITERIA: Low pressure testing shall commence after trench backfilling and compaction, and where inspection shaft and connection have been completed.
label | 21d703fc-5afa-4caa-83c9-1a8cfc25808f |  | label | ACCEPTANCE CRITERIA: Pressure gauge calibration shall be undertaken.
label | 9c346dea-7da8-4508-ade3-e488c9db1d9d |  | label | REFERENCE DOCUMENTS: Jacobs Cl 8.2.5, WSA02-2002-2.3 MRWA Version 2.0 , Section 22.4.2.2
label | cf7c3218-08c9-44f2-ad4f-e3f398ffde5f |  | label | INSPECTION/TEST METHOD: Verify
label | ad7ee618-81fa-4a40-8a4e-0c1a90c384e1 |  | label | RECORD OF CONFORMITY: Test Report
label | ef2e8d0e-197e-4326-a03c-5c6b1af69bcc |  | label | TP
label | 6c853c42-80b6-45aa-a499-7d5a0e29c4d3 |  | label | RESPONSIBILITY: Project Engineer/Principal’s Representative
text | 1294738e-eafa-4ee6-9ae8-c6f65574321d |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 4.8 Disinfection of Water Pipelines
label | 4a7ec250-5421-42bc-8dca-a87d74689faf |  | label | FREQUENCY: Each lot
label | cf88fa19-ad82-4d55-b109-8c584a665dde |  | label | ACCEPTANCE CRITERIA: Following a satisfactory hydrostatic pressure test, clean and disinfect the water main prior to connection and use in accordance with the specification;
label | a2342865-851c-48fa-ad4b-df3677402f90 |  | label | ACCEPTANCE CRITERIA: Supply and install all blank ends, etc. necessary to allow testing and disinfection to be carried out as specified.
label | 3d60f1bd-f090-4311-92ab-280701caa8e9 |  | label | REFERENCE DOCUMENTS: Jacobs Cl 8.2.6 WSA03-2011-3.1 MRWA Version.2, Section 20
label | 98f1a8e0-9bef-45d2-a3d8-11e941010cf7 |  | label | INSPECTION/TEST METHOD: Verify
label | cc4f971c-c364-46e7-8bef-ae10a4353e84 |  | label | RECORD OF CONFORMITY: Test Report
label | d7dc7503-b31c-44e0-9a14-dd3c78897daa |  | label | TP
label | b2e00a11-35e9-4305-94a3-cf03e8154e87 |  | label | RESPONSIBILITY: Project Engineer
text | 3e3c2fa3-c13b-43b0-ae8d-b30468cf4661 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 5.1 As Built Survey
label | ba8f09e3-e7aa-4664-8d09-c1f035546fa8 |  | label | FREQUENCY: Prior to backfilling each lot
label | 372512a7-3d51-4c2b-abf2-ff9f47f227a5 |  | label | ACCEPTANCE CRITERIA: Surveyor to pick up completed runs before backfill with survey report to be submitted with ITP.
label | 867e838c-f926-4f8f-8573-69be3bde9a22 |  | label | REFERENCE DOCUMENTS: QMP
label | b4ad25d9-5bc0-498c-85d6-9a2803b3084a |  | label | INSPECTION/TEST METHOD: Verify/Inpection
label | b1e2152c-86b5-4c43-b7ec-b54c892d289b |  | label | RECORD OF CONFORMITY: Survey Report
label | b1b3bd92-1532-436d-9585-473463a5a720 |  | label | SCP/IP
label | 4edad3cf-6e1c-429c-8ed8-9ba246350f44 |  | label | RESPONSIBILITY: Project Engineer/Surveyor
text | 1288da35-db42-48b5-a828-9a32ef62fe8f |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 95db1c8a-5f1d-47d4-825a-fade65e10a03 |  | label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | 865c63d4-7017-46f5-aac6-46e31c4b1f89 |  | text | Print Name:
text | cb4741f0-03cd-41de-91b7-7ce2c0f5b5ea |  | text | Position:
text | bc030e9b-9961-4027-9dd9-2c30870431f3 |  | text | Signature:
text | e9533062-ff44-4440-bfaa-f75e92b4eb3a |  | text | Date:
checklist-flat |  |  | checklist | Defect ID No: |  |  |  |  | Yes | Defect Checklist | 4c63cba6-1125-457f-ba88-0754d421eba2
checkpoint-status |  |  | checkpoint | Defect Identification
text | db5da556-675b-4df0-ad7f-d2c7c0b3bfd9 |  | text | Identified on (date):
text | 0a70099e-d1f2-4ebb-b36b-96bbbdfe3898 |  | text | Identified by:
text | 3b0f8245-5fb9-4182-8623-c53319a6b9c4 |  | text | Process:
text | a86e7d06-f260-46f9-9266-d33558a753d7 |  | text | Area:
text | 50108761-6e46-4082-9bf2-02b2173f17d1 |  | text | Location:
text | a23d1c29-4f5e-44ad-8674-ec7894d2677d |  | text | Client Reference (if any):
text | b5edf653-b0fc-45b1-a282-09d872466cdc |  | text | CAMS NO. (if applicable):
text | 362d4e34-f7a3-43ee-8598-8390f6529580 |  | text | Description
boolean | a88b9d8b-b875-471e-8d1d-821dd1496f2d |  | bool | Photo Attached
checkpoint-status |  |  | checkpoint | Defect Rectification
text | 03fc1ebf-22b7-400f-ab51-3485de58fb8e |  | text | Completion Date:
checkpoint-status |  |  | checkpoint | Defect rectification accepted and closed (signed off by FH & Client)
text | 3c5a0eec-16fb-4126-bf51-2e3e009018c4 |  | text | Date Completed
text | 0c6d088f-5cbe-42b6-a854-2acd301d733d |  | text | Fulton Hogan Representative
text | 1ae7aeb4-b3f9-4789-97cf-4a754a183473 |  | text | Client Representative
text | 73d30093-98ff-45a2-ba60-69ba941ef7ef |  | text | Date Signed off
holdpoint |  |  | holdpoint | Request Approval
checklist-flat |  |  | checklist | ITP 009 - Electrical & Communication Conduits | itp |  |  |  | Yes | ITP 009 - Electrical & Communication Conduits | 51537fb8-dad0-4706-9320-7ee92009848b
checkpoint-status |  |  | checkpoint | 1.1 Materials
label | bed186e4-16e1-4a77-ad40-4554760b3bcb |  | label | FREQUENCY: Prior to Commencing works
label | 5fc60e36-316b-4a62-b4f3-31b773a1ca1d |  | label | ACCEPTANCE CRITERIA: Ensure that the correct materials are being used as per drawings and specifications; Ensure PVC conduits match diameter required.
label | ef180c44-8213-4f97-8dbe-ae6f07542276 |  | label | REFERENCE DOCUMENTS: Drawings/ Specification CH17038-LAN-DET-PM-SP-0001 - Section 8
label | 847ae540-1f49-43b2-a2ac-538907fd9842 |  | label | INSPECTION/TEST METHOD: Verify
label | d84bb135-cf64-457d-8df4-5fb022678e61 |  | label | RECORD OF CONFORMITY: This ITP Signed
label | d2fb27e0-469e-4cfb-9a86-6e1ecd37d881 |  | label | HP*
label | 94985a2b-bb24-43b2-9c78-e1985148e2f2 |  | label | RESPONSIBILITY: Project Engineer
text | 4679c6bb-b12a-451a-b676-744b91a1e679 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 Setting Out for Conduits
label | 25294494-bb43-445b-89d8-c492f9bd9612 |  | label | FREQUENCY: Prior to Commencing works
label | ecb485d0-5ccc-4b13-97a6-3ed5d29b2278 |  | label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are: - Using the correct and complete set of drawings; - All drawings are the latest revision.
label | 98de11d7-56af-4ea5-8cdd-abd7cf38ce6f |  | label | REFERENCE DOCUMENTS: Drawings/ Aconex
label | fcfdac2b-a323-47dc-a45e-df35cde7ece3 |  | label | INSPECTION/TEST METHOD: Verify
label | 122e4aac-132e-4cff-bd70-29fb030004bc |  | label | RECORD OF CONFORMITY: Drawings / Survey Report
label | 432572fe-3dcf-44f1-ad76-e7d684460896 |  | label | HP*
label | c6d3becf-3db5-48fd-b9f2-c700aab9d99e |  | label | RESPONSIBILITY: Project Engineer
text | 321265b6-36e8-4a43-a0d5-63d3f2384a43 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 Existing Service Location
label | 1130810d-29f7-4d53-bc5b-bf5a2225ad1a |  | label | FREQUENCY: Prior to Commencing works
label | 230bb1da-c697-4a37-876c-c169cea0a9b9 |  | label | ACCEPTANCE CRITERIA: - Location of services to be found and marked on the ground within the works; - Services located within the works area to be exposed.
label | 1ba92f84-b570-4eea-8cae-a77350a042b6 |  | label | REFERENCE DOCUMENTS: DBYD/ Drawings
label | 0222a626-a6f2-44f7-ba4e-941f2f34278e |  | label | INSPECTION/TEST METHOD: Verify
label | be0ac634-e736-4af2-a821-ebdb84ab1884 |  | label | RECORD OF CONFORMITY: Melbourne Airport Excavation Permit
label | f5bff86b-ecd7-4179-834c-a84ce8fe4869 |  | label | IP
label | 7a74170e-95a8-4a85-9cad-202af28b406b |  | label | RESPONSIBILITY: Project Engineer
text | fb49b27a-51c0-423f-b2e6-00432fb9358c |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3.1 Excavate Trenches for Conduits
label | 99cad008-b2a0-4a48-ab9a-421ae26c5a0e |  | label | FREQUENCY: Each lot
label | 33db0864-97e9-44f3-9cc3-eab56a1da3e1 |  | label | ACCEPTANCE CRITERIA: Depth and width of trench shall be excavated to the requirements specified on the Drawings for each Section.
label | 9f20ae8d-5aa1-40e2-ac39-36f0bf6e2bc0 |  | label | ACCEPTANCE CRITERIA: Excavations deeper than 3.0m shall be undertaken under the guidance of the Contractor's Geotech Engineer.
label | b01cce2c-1205-4c66-a0bc-359dc99d4f10 |  | label | REFERENCE DOCUMENTS: Drawings/ CH17038-LAN-DET-PM-SP-0001 - Section 2.4
label | 9400ecb5-a78c-4301-97ac-d31265f1abf4 |  | label | INSPECTION/TEST METHOD: Verify
label | 0314e590-8719-40a8-9ec8-6cd04a690483 |  | label | RECORD OF CONFORMITY: Signed ITP
label | af9c12bc-9b3a-4f95-9080-3707718f512e |  | label | IP
label | b8d0fed4-5365-44d7-801c-a1ab9461bb16 |  | label | RESPONSIBILITY: Project Engineer
text | b07fea9e-5215-489b-9975-b4403b85b769 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Laying and Jointing of Conduits
label | 8ad07df1-24b8-46a0-93dc-883914994485 |  | label | FREQUENCY: Each lot
label | e55965bf-c2a9-414f-a3e0-04df9e2d5242 |  | label | ACCEPTANCE CRITERIA: - Comms Conduit to bypass electrical Pits; - Electrical conduit to bypass Comms pits; - Lighting conduit to only enter lighting pits.
label | a152a197-7a63-46ef-ba52-a98c0cb90f67 |  | label | REFERENCE DOCUMENTS: CP17038-LAN-DET-PM-SP-0001 Cl 8.2.3.1 . VicRoads Section 706-Installation of Utility Infrastructure
label | 1ea0cef4-cd32-47c1-a81a-db524c346271 |  | label | INSPECTION/TEST METHOD: Verify
label | d2aaca17-b937-4862-8d96-5e66bc3e59b8 |  | label | RECORD OF CONFORMITY: Signed ITP
label | 2ca41ace-d779-4e06-ad0c-1a78f2699133 |  | label | IP
label | c0f953a8-f74a-414c-9bb2-c977344a1f09 |  | label | RESPONSIBILITY: Project Engineer/Foreman
text | bb489335-93da-4444-b668-77402bd1ad85 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Conduit Layout
label | 23b3b7ee-fd30-4368-a5b4-a97e12c734e5 |  | label | FREQUENCY: Each lot
label | b8504004-a4a2-409e-9e80-6635e358afa0 |  | label | ACCEPTANCE CRITERIA: - Conduit arrangement to suit trench detail; - Conduit to slope towards pit for drainage purposes; - Quantity of conduits to be confirmed and entered w/ each lot.
label | 0c3da5e1-d384-471d-9d44-e7a400868d6a |  | label | REFERENCE DOCUMENTS: CP17038- LAN-DET-EL-3431 VicRoads Section 706-Installation of Utility Infrastructure
label | 160a3e8c-ece1-4ce8-bd59-566b4833fd55 |  | label | INSPECTION/TEST METHOD: Verify
label | 1dc16408-4ecd-4307-9803-605f26f0415a |  | label | RECORD OF CONFORMITY: Signed ITP
label | 55c45e27-dd50-44fa-bc60-d45d11d07ce0 |  | label | IP
label | 7079db80-5ac8-4de3-bd19-c31ab86f7f65 |  | label | RESPONSIBILITY: Project Engineer/Foreman
text | ceaeff77-da24-4675-a2a5-a1a3a61817bc |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 Conduit Pre-Pour
label | e5e8c5ec-5470-45a7-a076-0dbc3a91b866 |  | label | FREQUENCY: Prior to backfill
label | e49c6b0b-6ad8-4ada-98ea-707bf89fb5a4 |  | label | ACCEPTANCE CRITERIA: Layout is to be inspected prior to the commencement of concrete encasement &/or backfilling the conduit.
label | 19785490-6812-4941-8f8e-7f6758d53d73 |  | label | REFERENCE DOCUMENTS: Drawings
label | 36e0f0a6-698d-4286-8420-be478cc9bf68 |  | label | INSPECTION/TEST METHOD: Verify
label | b82b942b-bb50-4e5d-b291-2c7f9b0ba49e |  | label | RECORD OF CONFORMITY: Visual Inspection / Signed ITP
label | c8276554-1500-43b8-86ca-fb15ad792c8a |  | label | IP
label | 4b01f4cf-588d-4de6-8a49-d768500158b4 |  | label | RESPONSIBILITY: Project Engineer/Foreman
text | 119e366b-7d0f-4eaf-8772-1bd21ea5a940 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 Backfilling Conduits
label | 443368c0-8972-40d7-aa5b-946c455e0430 |  | label | FREQUENCY: Each lot
label | cc28abfc-dc73-48ef-bb32-05bd8d048d22 |  | label | ACCEPTANCE CRITERIA: Non Aircraft Pavement AreasBackfill shall be 650mm to top of conduits.
label | 46872d53-b7d1-43ae-a0ba-66469a731aaf |  | label | ACCEPTANCE CRITERIA: Installation of ‘Marker Tape’ both Electrical & Communication shall be minimum 300mm from surface level as per drawings
label | a5e2a760-70f9-4d1d-bf5c-501db1b8a959 |  | label | REFERENCE DOCUMENTS: CP17038-LAN-DET-EL-3431
label | d770a421-dc18-4dde-94e5-ea91a29c5ab6 |  | label | INSPECTION/TEST METHOD: Verify
label | 16c015c3-f67b-49e3-80ef-05684cc88629 |  | label | RECORD OF CONFORMITY: Visual Inspection / Signed ITP
label | fe2a78ef-5891-4a48-bb95-fe7e6eb4be05 |  | label | IP
label | 77257140-e9d7-4e4d-8ead-6e02e5b752a0 |  | label | RESPONSIBILITY: Project Engineer/Foreman
text | d7359870-379f-4e8e-bbbf-4fedf500c943 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3.6 Conduit Draw Cord
label | aa7bd246-04e0-4851-aa33-0b69df00ce25 |  | label | FREQUENCY: Each Lot
label | 00d5a404-bd3e-4e91-a37b-c54f92ae5a94 |  | label | ACCEPTANCE CRITERIA: All electrical conduits shall be fitted with draw cord.
label | 4a92c680-aefe-4c26-9738-dcf4aaa726b0 |  | label | REFERENCE DOCUMENTS: CP17038-LAN-DET-EL-3432
label | bfe1c9e9-d748-4f60-8e5c-cc44a80e5493 |  | label | INSPECTION/TEST METHOD: Visual
label | be302630-64db-4d8b-8615-9f5a5f90b54b |  | label | RECORD OF CONFORMITY: Signed ITP
label | 0631d9c8-859d-4e03-bf02-5914f3e81819 |  | label | IP
label | 4cb3c20a-4371-4bd9-a3a4-9f6cf90fb3f5 |  | label | RESPONSIBILITY: Project Engineer / Foreman
text | 6a459958-d4ed-47fd-92a3-01c58cf9fe3e |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 4.1 As Built Survey
label | 7523594d-b7cc-429c-980d-9d3ca9c37bed |  | label | FREQUENCY: Prior to Backfilling Each Lot
label | 4086d737-c52b-4cad-9643-23487103c8fa |  | label | ACCEPTANCE CRITERIA: Surveyor to pick up completed conduit runs before backfill with survey report to be submitted with ITP. All cables shall be surveyed after installation, with information included on As Built drawings
label | a15a1b6b-52a6-4c7d-8ba6-a888a1620c53 |  | label | REFERENCE DOCUMENTS: FH PMS Section 5.1
label | 15ecf311-578b-4e49-8cd4-bc6bdd43f7de |  | label | INSPECTION/TEST METHOD: Verify / Inspection
label | 758778f0-1c67-422a-bdc2-58c3f474e4c8 |  | label | RECORD OF CONFORMITY: Survey Report
label | f0593e3e-38b8-438d-9675-101bdde31f11 |  | label | SCP/IP
label | ff5eed27-896c-41da-83a2-6873bebe4d12 |  | label | RESPONSIBILITY: Project Engineer/Surveyor
text | 8ebf0a65-914d-409f-87b2-f5b07e4b23ca |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 1aff2f3d-7389-4032-892c-7d631448f43b |  | label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | bda927cf-1a34-41dd-8cc1-fe791f4d1864 |  | text | Print Name:
text | 979432fb-6753-4df6-98ca-e7e6c8ab3c87 |  | text | Position:
text | 06390e5f-f659-4c28-9a1a-31a6249b884d |  | text | Signature:
text | 0559147b-01bc-4d07-9b4b-8d069060e833 |  | text | Date:
checklist-flat |  |  | checklist | ITP-006 Subsoil Drainage | itp |  |  |  | Yes | ITP 006 - Subsoil Drainage | 542fc6a8-b271-4ca7-b17d-a7593a13ae8c
checkpoint-status |  |  | checkpoint | 1.1 Check for correct documentation
label | f8ce199c-6d7e-4437-b8c6-e17f3e321bbe |  | label | FREQUENCY: Prior to commencing any activity
label | b61a3596-d3b5-430f-81c8-00bb82c69516 |  | label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | 52813da0-9589-4650-8d99-26fdfc5c35f0 |  | label | ACCEPTANCE CRITERIA: Using the correct and complete set of drawings
label | ccd42dd9-910e-4319-b47e-abf35b351fb6 |  | label | ACCEPTANCE CRITERIA: All drawings are the latest revision
label | 942433cc-8d60-4460-86d3-af0726ed0e30 |  | label | REFERENCE DOCUMENTS: Drawings & drawing registers
label | 5e3c344a-96c5-483d-a051-5507dbaa1c44 |  | label | INSPECTION/TEST METHOD: Visual inspection
label | 5da7dfee-868d-4781-88fc-453d783f87d1 |  | label | RECORD OF CONFORMITY: Up to date drawing sets and this ITP signed
label | f41c4922-b797-4f21-a270-de0a927a404d |  | label | HP*
label | 086a01da-bf12-40b3-bb3e-f7f6142c146f |  | label | RESPONSIBILITY: Project Engineer
text | 114d4389-4900-4b1a-ac1d-be47b1dd4721 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 Implementation of all measures & controls
label | 08c215c2-5ff1-45fe-9172-1ecbb47634d4 |  | label | FREQUENCY: Prior to commencing any activity
label | 95c99182-c738-4df8-9e09-34288d407837 |  | label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP.
label | eb87c6a7-8d70-4a12-b4ad-084a546d63d2 |  | label | REFERENCE DOCUMENTS: PSP, EMP, TMP, SWMS, WP
label | cd9b462b-ffed-4e6d-b8df-c0882bb689bc |  | label | INSPECTION/TEST METHOD: Visual Inspection
label | 5a8c68cc-a4e2-439d-872e-f7baa54f1234 |  | label | RECORD OF CONFORMITY: Site & Office Inspection
label | c723ab62-c1bc-4bd5-9ab5-b15d2d841429 |  | label | HP*
label | 757c291f-01c3-4455-ad1f-be8536ae2b62 |  | label | RESPONSIBILITY: Project Engineer/Site Supervisor
text | 98b1bc1f-9692-4512-b9a8-072615daffcf |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 Definition of the work area
label | 14aaad70-fa11-45c4-9a86-8d509ccc8ebd |  | label | FREQUENCY: Before commencement of activity
label | 01a47b27-60fe-4083-9115-0643f6eee282 |  | label | ACCEPTANCE CRITERIA: Work area has been cleared and surveyed (marked on site).
label | 90677655-1d13-4f8c-a987-ef7eac08f221 |  | label | ACCEPTANCE CRITERIA: Limits of excavation clearly defined.
label | 0aa952e3-bdbb-4f03-b5c3-3805fef9e07c |  | label | REFERENCE DOCUMENTS: Drawings
label | 2c67c521-4004-4bd0-bed0-dd50a7e3cc19 |  | label | INSPECTION/TEST METHOD: Visual Inspection
label | f7364379-cac4-40fe-81df-24092c9c3188 |  | label | RECORD OF CONFORMITY: Site inspection
label | fb6c83d2-29d2-4fc3-bf4e-f28754d0779f |  | label | HP*
label | d75cace3-c22f-4766-9bc9-8fbf8a264bea |  | label | RESPONSIBILITY: Foreman
text | 1488dd5b-705d-4c26-b7ef-bee03941568a |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.4 Service Locations
label | a4dd59d7-ffe7-4baf-9d99-b9412de99d40 |  | label | FREQUENCY: Prior to start
label | a8749e11-a018-4279-b26b-c9db7111a775 |  | label | ACCEPTANCE CRITERIA: Locate and mark all underground services within the works and 10m beyond;
label | 2758a802-d5d4-4ebe-bec2-6ba9f84d281c |  | label | ACCEPTANCE CRITERIA: Service Locations and Depths recorded by surveyor where required.
label | 1b18581a-75b2-495b-9c2f-80381c859012 |  | label | REFERENCE DOCUMENTS: cl 7.1.8 cl. 8.1
label | 91c5dfca-0ceb-4cc6-9499-86f3c5a0157f |  | label | INSPECTION/TEST METHOD: Verify
label | 625dea91-116b-44ad-a80f-4eb7ed3d20e1 |  | label | RECORD OF CONFORMITY: Survey Report of Service Locations & Depths
label | 22563455-7fd0-4a82-8a20-dc39619d17ae |  | label | IP/SCP
label | 8d453b1b-667b-4127-affb-5fa028f539b9 |  | label | RESPONSIBILITY: Project Engineer/Foreman/Surveyor
text | 26f7bd7e-0fce-4220-ae21-ec18752c31fc |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 Subsoil Pipes/Fittings
label | 0e6514fe-22ff-4e77-a389-9c2ff4168d62 |  | label | FREQUENCY: Prior to start
label | daafcea4-e2af-4d75-82f8-1ee00d618c1e |  | label | ACCEPTANCE CRITERIA: Approval of pipe type and manufacturer;-
label | 17391169-be98-4ea3-b65f-0185ec649dfc |  | label | ACCEPTANCE CRITERIA: DN100 Perforated Drainage PVC to be provided where Swale longitudinal grade is flatter than 2%.
label | 860fccb6-3958-422f-b159-c28626c05853 |  | label | REFERENCE DOCUMENTS: DWG 3231
label | 6c90573f-1264-429e-9c81-7f397417e189 |  | label | INSPECTION/TEST METHOD: Verify
label | 6a2d16a9-6331-4ca1-99f8-29e9a899f11c |  | label | RECORD OF CONFORMITY: Technical Data Sheet or Product Catalogue
label | 064dd13c-16b9-4346-99b8-65a22a864af7 |  | label | HP*
label | cf7917c9-7e71-4bc0-ad6d-8b7466566f4c |  | label | RESPONSIBILITY: Project Engineer
text | df5f46c7-1e11-4216-b1fd-c240c4bdf5a5 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Backfill Material
label | 9ab44c60-26b6-4205-827e-cd12b8d4457a |  | label | FREQUENCY: Prior to Start
label | 4202f1fc-c327-4619-aec6-75254c6367f2 |  | label | ACCEPTANCE CRITERIA: Summary test results for:
label | 5a4ab03f-40c7-44a3-9b4f-7a8f53ca571f |  | label | ACCEPTANCE CRITERIA: Course sand transition layer
label | a37016e4-2335-4f09-9480-35133c47903c |  | label | ACCEPTANCE CRITERIA: 5mm Gravel Screenings
label | 58297d7d-a0dc-4c9f-b44d-a55bb3b7e3f5 |  | label | ACCEPTANCE CRITERIA: Geotextile
label | 7cc6f967-3d5f-41a0-acbf-22b4a4163b9c |  | label | REFERENCE DOCUMENTS: DWG 3231, DWG 3232
label | fe767a53-d350-4ec1-b592-20d05470655e |  | label | INSPECTION/TEST METHOD: Verify
label | b860352b-be10-4912-9b3c-d3473ad21da4 |  | label | RECORD OF CONFORMITY: Test Report
label | 5c1a55cc-0328-4fb2-8569-e2e72f0d442e |  | label | HP*
label | 6b9bc8aa-ac41-4796-92cb-7b1f73fcf585 |  | label | RESPONSIBILITY: Project Engineer
text | f977d419-fd13-40c7-93b2-37e855f9a087 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3.1 Excavations
label | 529702b2-f4fc-4a87-abbd-4a7a532635c5 |  | label | FREQUENCY: Each lot
label | 4b952c80-7313-4c43-b23a-89775782e048 |  | label | ACCEPTANCE CRITERIA: In accordance to the dimensions outlined in the drawings.
label | 9f810ec8-c2f1-4502-b25c-7b519e540bf1 |  | label | REFERENCE DOCUMENTS: cl. 7.1.8 cl. 7.1.11 Drawings
label | 1ab8672b-1845-4bc3-8cd3-d05896fe07f1 |  | label | INSPECTION/TEST METHOD: Inspect & verify
label | 66a63727-cbd0-40db-94bb-f558f5319a31 |  | label | RECORD OF CONFORMITY: This ITP signed
label | 17d1adf3-980c-49a5-a40d-470ec9e6f669 |  | label | IP
label | 85a6ef29-200e-4028-924d-fb05a64ba81a |  | label | RESPONSIBILITY: Project Engineer/Foreman
text | a57a4d3f-4b47-44b0-8e99-73d7a6ed7761 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Stock Piling
label | 6cba5f28-29bb-48d0-b3b0-b7152d8d9e0f |  | label | FREQUENCY: Each stockpile
label | ff008d9a-6c5d-403f-a881-4b06d74877af |  | label | ACCEPTANCE CRITERIA: Consent from Principal Rep on location;
label | 1449b52b-8e33-49dc-9b1b-3aa1fe62af11 |  | label | ACCEPTANCE CRITERIA: Materials are stockpiled separately
label | 25f811b7-3524-465e-a421-546c07c48780 |  | label | REFERENCE DOCUMENTS: cl. 7.1.5
label | 798659e2-f009-4eac-b646-48b008c35788 |  | label | INSPECTION/TEST METHOD: Verify
label | b35142e8-5fcb-4820-b992-6e100f4125e6 |  | label | RECORD OF CONFORMITY: This ITP signed
label | 8aa25268-dd86-4fc6-8bb9-853ca9f6e0eb |  | label | IP
label | 0f194c34-1a34-4cd5-a61a-5cd4ec48d308 |  | label | RESPONSIBILITY: Foreman
text | 46f220e0-587d-454e-b201-8580bf0e0101 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Inspection Prior to Backfilling
label | 33d1ad06-803f-40a6-945c-a847ad60a5a6 |  | label | FREQUENCY: Each lot
label | 26e3805a-0972-4fc3-b73d-f80d8fcc1492 |  | label | ACCEPTANCE CRITERIA: Fulton Hogan to check and approve all pipes for the accuracy of alignment, level, grade & invert level.
label | 898c3839-8707-4bf0-ac14-7acb5f6ee59c |  | label | REFERENCE DOCUMENTS: N/A
label | d7e82e44-a8fe-4a18-bbf2-7fb079bfca4e |  | label | INSPECTION/TEST METHOD: Visual inspection
label | 9c7f2ebc-fb79-4ab2-b206-88d088950867 |  | label | RECORD OF CONFORMITY: This ITP signed
label | 3fbd662d-0fb8-4877-b70f-21d608731b43 |  | label | IP
label | 5a04be8e-44db-4033-80bb-bc0b786df796 |  | label | RESPONSIBILITY: Project Engineer
text | 537519c5-1b7d-401c-a541-127031a3bacf |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 Backfilling of Trenches
label | d4445ca1-b508-484b-86ac-3023d37617e3 |  | label | FREQUENCY: Each lot applicable
label | ccff61d7-a5cf-49dc-be04-b87496aaba05 |  | label | ACCEPTANCE CRITERIA: Trench has been backfilled to level and with the correct materials as per the drawings
label | 9fd8d919-11e9-417d-a73f-7f95bfb60c67 |  | label | REFERENCE DOCUMENTS: N/A
label | f580fa2b-526a-4d8d-aa4a-b164e7e0d628 |  | label | INSPECTION/TEST METHOD: Inspect & verify
label | 897c2e7e-a1ab-48a3-a0f7-3dfd897faf48 |  | label | RECORD OF CONFORMITY: This ITP signed
label | 4a57de7a-aa48-4390-8691-f8262b91ea98 |  | label | IP
label | 06aef09f-a8bb-4e10-b43a-7c23eaa82861 |  | label | RESPONSIBILITY: Foreman
text | 87c25ad9-956d-4e22-9f9e-18967bc81945 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 Connection To Pits
label | bdc7fc40-9362-4ca5-a749-ef74ca15d929 |  | label | FREQUENCY: Each lot applicable
label | ec975bd1-410e-4ba0-84a4-33f9ddceb55a |  | label | ACCEPTANCE CRITERIA: Holes for subsurface drains shall be 150 mm diameter and cut not broken out.
label | 6a4ca8a2-814a-4f31-a5e5-c6406c70e4b4 |  | label | ACCEPTANCE CRITERIA: Subsoil drains are to be provided where shown along all swales, refer to typical section shown on drawing CP17038-LAN- DET-Cl-3231
label | 41d1973d-a069-48da-8538-46ffb3a5d375 |  | label | REFERENCE DOCUMENTS: Cl 7.2.6 Cl 7.2.7 NAR General Notes
label | a507031d-f42e-43d1-b5fe-8726d88543e6 |  | label | INSPECTION/TEST METHOD: Verify
label | 7af1e019-12e5-4bc8-a1e9-f2ce834518d1 |  | label | RECORD OF CONFORMITY: This ITP signed
label | 8248bdbe-ef11-4e38-83a8-d69afce6605f |  | label | IP
label | 1f1e9fbb-11cb-4fb4-b431-1c4c64d49224 |  | label | RESPONSIBILITY: Project Engineer/Foreman
text | 379f1a22-36c1-4a25-9c0a-2e160d251990 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 4.1 As Built
label | ba5c2520-bacc-4cbc-8a0e-1e60da3b8a75 |  | label | FREQUENCY: Each lot
label | f645dc36-080f-40b9-8ee8-0a72fe79c319 |  | label | ACCEPTANCE CRITERIA: Lot Report submitted after completion of works detailing alignment and level
label | 89ad9cfe-d93d-407b-a1c8-5cb80c6e8396 |  | label | REFERENCE DOCUMENTS: -
label | 6ab8bbe2-96eb-44cb-bddd-2ce51d82a24c |  | label | INSPECTION/TEST METHOD: Completed Lot
label | cc7d0f3a-c93e-426c-9698-efc3fdf8ac9a |  | label | RECORD OF CONFORMITY: Aconex
label | c931bb5e-c888-4978-b96b-9c6cb7446be1 |  | label | SCP
label | c55e3589-33f1-4097-8aaf-eefc63ae6803 |  | label | RESPONSIBILITY: Project Engineer
text | a2325f6f-1637-4769-8ae3-e6aab1e976d9 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 7fe07a26-9ee9-478d-9d6e-4d79044264b7 |  | label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | bd61c903-f638-4ccc-aa48-776f198ecc9e |  | text | Print Name:
text | e591c56b-2e19-44e3-bc86-04ee5eba1ac0 |  | text | Position:
text | f33edfb1-eeec-4e75-8450-b41495a45abd |  | text | Signature:
text | 698e6654-b578-4c04-8fb0-0d9d2d131612 |  | text | Date:
checklist-flat |  |  | checklist | ITP 007 - In-Situ Pits and Misc Structures - Excavation/Preliminaries | itp |  |  |  | Yes | ITP 007 - In-Situ Pits and Misc Structures - Excavation/Preliminaries | 7347e419-1f75-4505-bd6d-f4b148a80cb4
checkpoint-status |  |  | checkpoint | 1.1 Check for correct documentation
label | 4a989391-9d7b-4f7d-96d9-83cf44c123b7 |  | label | FREQUENCY: Prior to commencing works
label | 97848c67-c70e-4dcb-8c70-fcbd619a76ea |  | label | ACCEPTANCE CRITERIA: • Current revision drawing is being used including the subcontractors copy; • Current revision to be obtained via Aconex.
label | 0a0c381b-a3ba-45b0-9275-fb52ba2ec3b1 |  | label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | 68635121-13e2-4d69-9c6a-0a57510249f6 |  | label | INSPECTION/TEST METHOD: Visual inspection
label | 1c7730db-7268-4215-9d47-ec4d541561c0 |  | label | RECORD OF CONFORMITY: This ITP signed
label | 1e6a87cc-a3a4-43ae-a55f-f1a8576397ef |  | label | HP*
label | a667093c-1383-43db-9d4c-0bddd96580bc |  | label | RESPONSIBILITY: FH Engineer
text | 550ab7ce-ad58-483d-a037-efba72f1b47a |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 Setting out for miscellaneous structures
label | b2ce488f-b84c-4a57-af04-c1a8be262fdf |  | label | FREQUENCY: Prior to Start
label | a45f7b0c-9034-4e83-8fcb-c3d8340a3d31 |  | label | ACCEPTANCE CRITERIA: Conformance with Jacobs for Construction Drawings and pipe penetrations in the correct locations.
label | 740badb7-9529-4f69-b958-79c18f47b411 |  | label | REFERENCE DOCUMENTS: Drawings
label | 5f6996f8-0230-47ff-8c5f-640387df2def |  | label | INSPECTION/TEST METHOD: Verify
label | 36e017bb-cdd0-4b66-bb3e-7fa3837feba4 |  | label | RECORD OF CONFORMITY: Survey Report
label | d252ef8f-c257-422f-a4d2-122a5404889b |  | label | SCP
label | 1f1d540b-7a7d-420e-8fb2-8d8d93bcf90a |  | label | RESPONSIBILITY: FH Engineer Surveyor
text | ea730ac0-adb1-4579-8093-58ab205b5c17 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 Materials & Source Approval
label | 231065a8-ae38-4056-9c38-54a19a28f3fe |  | label | FREQUENCY: Prior to Start
label | 8604322b-c944-4017-be01-2bdc2fa9999e |  | label | ACCEPTANCE CRITERIA: • Mix design approved; • Minimum concrete grade VR330/32.
label | 67987c65-f718-47d6-aa25-67729420f620 |  | label | REFERENCE DOCUMENTS: CP17038-LAN-DET-PM-SP-0001 cl 7.2.3(b) VicRoads Standards Sec610
label | dc2c2419-7957-4c82-878b-96f204e5994d |  | label | INSPECTION/TEST METHOD: Verify
label | 7113108f-e3c5-4f72-bf8f-230f87fc450b |  | label | RECORD OF CONFORMITY: Concrete Mix Design Certificate
label | f45bdce2-bd5c-4a37-8bea-9ae951f199ea |  | label | HP*
label | acfc7766-9328-4ba5-a295-b10ee5eec78b |  | label | RESPONSIBILITY: FH Engineer
text | c123ec7d-2370-4b52-ba72-c9a251292cfb |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 Materials & Source Approval
label | 5f9862b4-2b58-44c0-bc59-ca6d34973884 |  | label | FREQUENCY: Prior to Start
label | cc1bd31d-602b-4675-8ab2-056882981ea6 |  | label | ACCEPTANCE CRITERIA: • Covers, grates, lids and lintels as specified on drawings; • Class D cover used in landside areas; • Class G cover used in airside areas.
label | 91cb5452-1e0a-4baa-b6da-5cff1fd83320 |  | label | REFERENCE DOCUMENTS: CP17038-LAN-DET-PM-SP-0001 cl 7.2.3(c)
label | 174d5de6-c803-419a-b4f6-500b336c9daa |  | label | INSPECTION/TEST METHOD: Verify
label | 879eb049-1bb0-4eb9-98c4-094351eb0116 |  | label | RECORD OF CONFORMITY: Recipient & Inspection Check List
label | 50a16602-ce96-44f9-952e-1ac9f9eea59d |  | label | HP*
label | de24a6ae-7fbf-4c90-a91c-8bfccdfaf5d1 |  | label | RESPONSIBILITY: FH Engineer
text | ee008db4-e3fe-4933-8ce1-36e19686ef3b |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 Materials & Source Approval
label | b7e7948f-4810-460e-94f9-937de16b759b |  | label | FREQUENCY: Prior to Start
label | 25f15a58-f12e-4e39-8160-15bea2b32f34 |  | label | ACCEPTANCE CRITERIA: Step irons manufactured from steel to AS/NZS 3679.1 Grade 250 or AS/NZA 4671 Grade N500, prepared, pre-treated and hot dip galvanized with a minimum average coating thickness of 600 g/m2; With approval from Principal’s Rep, step irons may: • Manufactured from 20mm steel bar, galvanised or covered with polypropylene plastic; • Prefabricated hardened plastic type
label | ade9132c-780a-4133-ae5a-39f50fb077f4 |  | label | REFERENCE DOCUMENTS: CP17038-LAN-DET-PM-SP-0001 cl 7.2.3(d)
label | ed3ec45c-b283-4d2f-95f8-d6943a475591 |  | label | INSPECTION/TEST METHOD: Verify
label | 9c04a951-dca5-4920-a430-60925703953c |  | label | RECORD OF CONFORMITY: Recipient & Inspection Check List
label | a6550ee5-d486-47b6-9ed7-6a839e8d3e6b |  | label | HP*
label | 72d6033f-eb1a-47ed-9994-6ded0a4e994d |  | label | RESPONSIBILITY: FH Engineer
text | 7418596f-7bd7-4761-9dfa-e4923f88f200 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 Materials & Source Approval
label | 2de33ec8-d60f-408f-b129-ec09285366ee |  | label | FREQUENCY: Prior to Start
label | e20ce0ef-e80e-4b20-b841-403b6cc728e8 |  | label | ACCEPTANCE CRITERIA: Reinforcement complies with requirements of VicRoads Standards Sec611.
label | 215d552d-f19d-40af-9e58-d66e2dd9cb20 |  | label | REFERENCE DOCUMENTS: CP17038-LAN-DET-PM-SP-0001 cl 7.2.3(e)
label | f3694363-b6b1-47b4-bc70-4ec14c80d8c6 |  | label | INSPECTION/TEST METHOD: Verify
label | cab26a88-6c56-4c2c-8312-6b53d05beed8 |  | label | RECORD OF CONFORMITY: ACRS certificate
label | 5ce22295-8eec-4b36-8dc6-be3d7f775012 |  | label | HP*
label | b5497fc3-2d60-4c42-a979-8b451f4f0b77 |  | label | RESPONSIBILITY: FH Engineer
text | 2d6490a0-0027-4b7e-8cdb-f77eb96be4e1 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 Materials & Source Approval
label | 58799e7c-a89e-4f45-ba61-4d24511fc130 |  | label | FREQUENCY: Each lot
label | d19395ea-7f16-44ad-9d03-85026204fbef |  | label | ACCEPTANCE CRITERIA: Concrete for miscellaneous structures shall be as specified in drawings, typically it will be as follows (MPa/slump): • Pad footings 32/80; • Bored piers 25/80; • Raft slab 25/80; • Buried pits & trenches 40/80;
label | 74acc9e3-f85b-4865-a977-bcb4d2aa7c71 |  | label | REFERENCE DOCUMENTS: DRAWINGS - CP17038-LAN-DET-ST-3840
label | be993a6b-223c-46a4-b1c8-7f50caabd8f1 |  | label | INSPECTION/TEST METHOD: Verify
label | 2acc07c9-2fa3-43e1-a9dd-3f91f9670910 |  | label | RECORD OF CONFORMITY: Approved Mix Design
label | e0363bc4-868e-478f-9ae8-58a46456a43d |  | label | IP
label | 6ed5e9d6-aa6d-482f-b309-9c195173dd86 |  | label | RESPONSIBILITY: FH Engineer
text | 93e795c2-d771-4bf6-8b30-1adce6fc1f06 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3.1 Excavate Pits
label | f2d4ab70-7f65-4a26-8d13-78b4c6b226c2 |  | label | FREQUENCY: Each lot
label | 4ef0f435-6dc8-40f0-9f1c-9c3093c313da |  | label | ACCEPTANCE CRITERIA: Excavation to depth indicated on Drawings or as necessary to secure a satisfactory foundation.
label | feb3ed28-149c-4f59-ac9e-d3fced98f7f0 |  | label | REFERENCE DOCUMENTS: CP17038-LAN-DET-PM-SP-0001 cl 7.2.4
label | 227714f9-f36a-46e8-9663-ed89ed1ccf61 |  | label | INSPECTION/TEST METHOD: Verify
label | 3ef350ed-b558-4104-93d5-3ed9aec77a1f |  | label | RECORD OF CONFORMITY: This ITP signed
label | 8004ca0b-84d8-46b0-b58e-927d640b2ee0 |  | label | IP
label | 78e264a2-211e-44c1-805e-0af545fe90b8 |  | label | RESPONSIBILITY: FH Engineer
text | 12636de8-8de5-4b8b-9393-f299a47ae13e |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Soakage Pit (only where applicable)
label | 98e09b30-59ab-4695-b646-988440e61b39 |  | label | FREQUENCY: Each lot
label | 425eb2f5-f149-4bb5-8b31-b5b58c861cb5 |  | label | ACCEPTANCE CRITERIA: Where applicable, excavate minimum 300mm depth for the sump of the soakage pit below the invert of the pit; 50mm dia pipe constructed into soakage pit.
label | f3c4634f-bef2-4d54-8fbf-135dcdb45772 |  | label | REFERENCE DOCUMENTS: CP17038-LAN-DET-PM-SP-0001 cl 8.3.5.9 CP17038-LAN-DET-ST-3855
label | bce7d33d-f6fa-4eb1-a4ae-efd8b7d11f85 |  | label | INSPECTION/TEST METHOD: Verify
label | d93baf4c-25ce-4e95-83f6-3f3a52660831 |  | label | RECORD OF CONFORMITY: This ITP signed
label | 83e9dda3-ac6f-4b1e-9d98-03824c8c46f9 |  | label | IP
label | 23c2e7d3-9a4e-4f75-8344-ec511df377a9 |  | label | RESPONSIBILITY: FH Engineer
text | 8db8a3f3-81d9-4fea-89b3-61e59ba7cb80 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Confirm Ground - Check 100kPa Bearing Pressure
label | 2b78a8a6-0a91-4b12-bd0e-c769902e5202 |  | label | FREQUENCY: Each lot
label | c84d5b04-609a-4e7b-9e48-d21e60225678 |  | label | ACCEPTANCE CRITERIA: Completion of excavation and inspection of subgrade materials; Geotechnical engineer to sign off ground condition.
label | 38760622-90e4-4926-b14a-315baac27b54 |  | label | REFERENCE DOCUMENTS: CP17038-LAN-DET-ST-3840 (Note F1)
label | 6bd0739c-9cea-4dad-bb3a-92f7a29887a7 |  | label | INSPECTION/TEST METHOD: Verify
label | d82f90a1-56fc-4153-a2a5-922d4c8252c8 |  | label | RECORD OF CONFORMITY: Geotech Eng to confirm ground
label | cdff15c8-c863-41a3-9a28-ab2cd09d98d2 |  | label | TP
label | 0bef4c2f-611a-4cc7-820c-914bff7ae310 |  | label | RESPONSIBILITY: FH Engineer
text | 26e6d6fa-8c76-4d1a-8d5b-f9c3d2092eee |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 2c576cc1-a2c2-46f0-9cb6-58365f8c8657 |  | label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | 190f1df2-65b9-41db-904a-eeed117131f8 |  | text | Print Name:
text | 6570eb46-6c15-476e-ae52-d7b01bcbff03 |  | text | Position:
text | 90bf41c2-9cb2-41af-8ae8-529a4be63ef4 |  | text | Signature:
text | 509afdcc-e415-4f6f-b965-2c7f3bec6651 |  | text | Date:
checklist-flat |  |  | checklist | ITP 008 - In-Situ Pits and Misc Structures - Concrete Works | itp |  |  |  | Yes | ITP 008 - In-Situ Pits and Misc Structures - Concrete Works | 7ca1cca9-e73e-4cba-bcb8-a35dc806801c
checkpoint-status |  |  | checkpoint | 1.1 Check for correct documentation
label | 7351ad7c-f4ba-4977-a7cf-30520eceb6cf |  | label | FREQUENCY: Prior to commencing works
label | 9f24675c-d237-4fef-926e-68e67a83a2ad |  | label | ACCEPTANCE CRITERIA: Current revision drawing is being used including the subcontractors copy. Current revision to be obtained via Aconex.
label | 0827a2d6-145a-48c2-a4b5-df5ede990946 |  | label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | 8a158538-caa4-4009-ae65-a65ec3298a37 |  | label | INSPECTION/TEST METHOD: Visual inspection
label | 2839cfe1-e69e-4f14-bda3-43db08b16813 |  | label | RECORD OF CONFORMITY: This ITP signed
label | 694a68cf-c13c-4dca-86fe-ecce3333cab4 |  | label | HP*
label | 5a520bc0-1dab-4049-8e3f-335cc0d2c7be |  | label | RESPONSIBILITY: FH Engineer
text | 62f206a5-bee7-4a11-bfcb-989392b74ae5 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 Setting out for miscellaneous structures
label | 812aae9d-209d-4276-8e6f-794516b46501 |  | label | FREQUENCY: Prior to Start
label | f5aeff09-f30c-4aaa-b094-4e49136c093b |  | label | ACCEPTANCE CRITERIA: Conformance with JACOBS for Construction Drawings and pipe penetrations in the correct locations.
label | 9cdd8083-adf4-4650-9426-2fcafe315dd8 |  | label | REFERENCE DOCUMENTS: Drawings
label | ffc0fe87-fe54-42ec-9d5b-85871bdf0e8d |  | label | INSPECTION/TEST METHOD: Verify
label | a7f4b12c-d9df-45ad-9736-2e6cc887ae55 |  | label | RECORD OF CONFORMITY: Survey Report
label | cfab0d3a-4326-4727-8b18-99003f6cd58d |  | label | SCP
label | ce28c9ba-8227-46d1-8e9a-78bcd5a4fc86 |  | label | RESPONSIBILITY: FH Engineer Surveyor
text | 32f1a9fe-bfda-4efd-9099-82493332e60b |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 Concrete Trial
label | 8a445654-4b49-417e-a438-d42a76a30029 |  | label | FREQUENCY: Prior to Start
label | 9d70507d-2174-4b7b-85a3-68ec2bc2ee5c |  | label | ACCEPTANCE CRITERIA: The Contractor shall not proceed with full scale works until the trial has been reviewed by the Principal’s Representative.
label | 409f0deb-6c90-4df9-891f-d931d01c4747 |  | label | REFERENCE DOCUMENTS: CP17038-LAN-DET-PM-SP-0001 cl 6.7
label | af20c56d-b406-4210-a817-4b04f64a9640 |  | label | INSPECTION/TEST METHOD: Verify
label | 263b6da7-8ea7-4cea-86c7-0dc0ecd1e05e |  | label | RECORD OF CONFORMITY: Aconex
label | c57d3aaa-59b9-49d2-a37a-878739af4d03 |  | label | HP
label | 2f91a2b8-891c-492c-9641-84a0b9ed4d00 |  | label | RESPONSIBILITY: FH Engineer/ Superintendent
text | 04d26b3b-3086-4218-b52b-6cc9b13a6880 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.4 Concrete Methodology
label | 6f89eaa1-9ebf-4a21-b69e-2aa90e7765be |  | label | FREQUENCY: Prior to Placement
label | c988cd41-ee39-4248-896a-9574326486ed |  | label | ACCEPTANCE CRITERIA: Concrete shall not be placed until the proposed method of placement, spacing of planned transverse construction joints and the provision of dowels, constructed formwork, reinforcement and embedments conforming to the requirements of this specification and the drawings, has been reviewed by the Principal’s Representative. The Principal’s Representative will provide direction at this time on whether a trial section of concrete subbase and base courses is required.
label | 9476fe34-50ae-44fd-8217-671ac3c20ebd |  | label | REFERENCE DOCUMENTS: CP17038-LAN-DET-PM-SP-0001 cl 6.7
label | 03c29c31-821a-49f6-ad1f-d0ee88e7b046 |  | label | INSPECTION/TEST METHOD: Verify
label | bd2048f0-ed0a-48a8-af45-4ba8f429c414 |  | label | RECORD OF CONFORMITY: Aconex
label | 8ced9946-fd52-4dac-a924-6484e9f4e9b3 |  | label | HP
label | 66bef376-f98c-4c51-aace-d5c87c5fb76f |  | label | RESPONSIBILITY: FH Engineer/ Superintendent
text | 4efa5a71-d9a1-4406-8b02-69c9c195697c |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.5 Manual Placement of Concrete (between Fixed Forms) and Replacement Base Slabs
label | 9aa00845-5292-4033-a1f3-b01e3e5dc1ec |  | label | FREQUENCY: Prior to Placement
label | 7c758744-20fc-43db-a398-9defbd28bf2e |  | label | ACCEPTANCE CRITERIA: Concrete shall not be placed until the Principal’s Representative has reviewed the proposed method of placement, compaction, and curing of concrete.
label | a8c212b9-bfcf-4dad-bf1b-dc7a55da99b8 |  | label | REFERENCE DOCUMENTS: CP17038-LAN-DET-PM-SP-0001 cl 6.7(d)
label | 23dc8703-ac05-41c2-b3c0-ba789ff0b6da |  | label | INSPECTION/TEST METHOD: Verify
label | a6552da7-b112-4176-84ec-687dc06a1ed8 |  | label | RECORD OF CONFORMITY: Aconex
label | 1b75bd54-db62-411a-b46f-a0504cf09493 |  | label | WP
label | 7efbe7c6-e452-417c-a739-f8c26688b1a7 |  | label | RESPONSIBILITY: FH Engineer/ Superintendent
text | c7731032-8663-45c2-8c49-da2e09a28deb |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.6 Joint Sealant Material Submission
label | 4904b34f-7cdd-41de-96fb-6b2953c02797 |  | label | FREQUENCY: Prior to Joint Sealing
label | ad6afd31-ad35-4a5a-a23a-15806b3a3713 |  | label | ACCEPTANCE CRITERIA: A full technical description of the proposed sealant and method of installation recommended by its manufacturer shall be submitted for approval by the Principal’s Representative at least four weeks prior to installation.
label | 7eac714f-93c4-4141-8a41-3398fc6c95e6 |  | label | REFERENCE DOCUMENTS: CP17038-LAN-DET-PM-SP-0001 cl 6.10
label | d8843ec7-b61b-4f3d-8017-71ab2b3ae9ce |  | label | INSPECTION/TEST METHOD: Verify
label | 737dfa70-6486-45dc-8b8b-5f804c3d0704 |  | label | RECORD OF CONFORMITY: Aconex
label | 8fe2890c-f379-4557-a47a-342b1354bf67 |  | label | HP
label | 4473c6c5-a162-4af0-b57f-cf3bec00d6cb |  | label | RESPONSIBILITY: FH Engineer/ Superintendent
text | 2e34ac86-b225-4467-b1f1-a7760fecdada |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.7 Odd Shaped and Mismatched Slabs - For All Types of Base
label | 965fb899-b744-4e5e-ad2d-952043166c95 |  | label | FREQUENCY: Prior to Odd Shaped and Mismatched Slabs
label | e5a04d9e-a71d-47ea-b41a-8a5dadb2a7cd |  | label | ACCEPTANCE CRITERIA: Joint arrangements for odd shaped and mismatched slabs shall be designed by the Contractor and submitted to the Principal’s Representative for review at least four weeks prior to the work commencing.
label | 9eab3783-2366-4638-a38a-c8ad7bcf6824 |  | label | REFERENCE DOCUMENTS: CP17038-LAN-DET-PM-SP-0001 cl 6.14
label | f4f1bfea-4bab-401b-bbe4-1078493850f5 |  | label | INSPECTION/TEST METHOD: Verify
label | b44f4a9f-63f5-46af-99c8-ded0280303b5 |  | label | RECORD OF CONFORMITY: Aconex
label | cd5927b9-812f-41e8-a380-b78d6bdc4b93 |  | label | HP
label | e5c84690-bc91-4fd9-a039-168ed3a32d4d |  | label | RESPONSIBILITY: FH Engineer/ Superintendent
text | c84547d8-e4aa-4552-a6d4-3d3f1eec8c1f |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.8 Texturing of Surface
label | 6da8eec4-dd08-4df0-92a1-c52a5b51afbe |  | label | FREQUENCY: Prior to works
label | d07bb95e-607d-4a27-8c7d-96709f2153e3 |  | label | ACCEPTANCE CRITERIA: Should the Contractor wish to use an alternative method to achieve the texture depth, details of the proposed method shall be submitted to the Principal’s Representative for approval. The Principal’s Representative may require the Contractor to cast a sample test panel of size 3 m x 3 m of textured concrete prior to approval.
label | 40f1dcba-40a1-4454-bd14-3413559e4bf4 |  | label | REFERENCE DOCUMENTS: CP17038-LAN-DET-PM-SP-0001 cl 6.17
label | 0bddd47f-3d37-40a0-b656-5386a84abb2a |  | label | INSPECTION/TEST METHOD: Verify
label | 81563033-7e38-46fe-be6d-753fa37fcba0 |  | label | RECORD OF CONFORMITY: Aconex
label | a3915f63-0a6b-45a0-9655-244f888946c3 |  | label | HP
label | 51d73ad6-4a4f-4930-803b-a9861b4676c9 |  | label | RESPONSIBILITY: FH Engineer/ Superintendent
text | 512e05e8-8253-4f79-9650-5c29123d29e9 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.9 Curing and Protection
label | 9faa2592-5208-4b33-98a3-b5db6d62ed96 |  | label | FREQUENCY: Prior to use of Curing compound
label | e02ee040-0f53-416e-b7b9-538433174835 |  | label | ACCEPTANCE CRITERIA: Prior to the use of curing compounds, the Contractor shall submit to the Principal’s Representative for review not less than four weeks prior to placement of concrete.
label | 04ba2c29-be4a-4073-b5a3-c48f4d3d87fd |  | label | REFERENCE DOCUMENTS: CP17038-LAN-DET-PM-SP-0001 cl 6.18
label | d53e4203-72c3-41fb-b81c-fc6e21636b20 |  | label | INSPECTION/TEST METHOD: Verify
label | 5fdd6054-f034-44eb-ac03-b413d50747be |  | label | RECORD OF CONFORMITY: Aconex
label | ef8a35f9-db21-4e49-8bc1-fa0a122ce5e6 |  | label | HP
label | a005c9a8-186b-41a8-a2fd-885e6df21264 |  | label | RESPONSIBILITY: FH Engineer/ Superintendent
text | 792f8cf4-ffd6-4b85-96e6-5505e30a2895 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.10 Evaporative Retarding Compound
label | 835f7447-9290-4b4f-8dc0-27b7503de001 |  | label | FREQUENCY: Prior to use of Curing compound
label | e196f349-7d55-416f-be99-f1ed8db6a090 |  | label | ACCEPTANCE CRITERIA: Details of the proposed compound and its application procedure shall be submitted to the Principal’s Representative for review not less than four weeks prior to the commencement of concreting works.
label | 340004f2-23f7-4cce-8631-ea389a3e6519 |  | label | REFERENCE DOCUMENTS: CP17038-LAN-DET-PM-SP-0001 cl 6.18
label | b0302fb3-a491-4d4c-a229-a7e5736e6d3c |  | label | INSPECTION/TEST METHOD: Verify
label | 954cc624-a33f-42ba-b018-c269334aab1f |  | label | RECORD OF CONFORMITY: Aconex
label | cb183b58-682c-4e7a-8373-6267dd5132f9 |  | label | HP
label | f06b0a31-7111-43b3-ad04-ce9195ee317d |  | label | RESPONSIBILITY: FH Engineer/ Superintendent
text | eb496141-251c-46ed-9993-53f6e59f2910 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.11 Concrete Base Course
label | a032e102-f52e-4cf7-a08b-a224f453c403 |  | label | FREQUENCY: Prior to use of Curing compound
label | 6f9cd46e-3d24-429d-9258-3783f76cd3db |  | label | ACCEPTANCE CRITERIA: With the exception of concrete saws and coring machines and personnel the concrete base course shall not be trafficked until the in situ compressive strength has reached at least 20 MPa based on concrete cylinder testing or at least 17 MPa based on core testing. Construction equipment and personnel may traffic the base when the base in situ compressive strength is at least 20 MPa based on concrete cylinder testing or at least 17 MPa based on core testing and provided that all sealing of joints has been completed. Other loadings shall not be applied onto the base course concrete until the in situ compressive strength is at least 30 MPa based on concrete cylinder testing or at least 26 MPa based on core testing. Backfill material shall not be placed against the edge of the base until the in situ compressive strength is at least 20 MPa and provided that all sealing of joints has been completed.
label | a19e8d57-221c-4a8b-a665-424115f4e639 |  | label | REFERENCE DOCUMENTS: CP17038-LAN-DET-PM-SP-0001 cl 6.19(c)
label | 1dd52ee7-9db8-46b7-bf82-7d644d27ec5f |  | label | INSPECTION/TEST METHOD: Verify
label | e33c754f-f164-4923-8db1-1bab64c91ea1 |  | label | RECORD OF CONFORMITY: Aconex
label | 7c5ce4bc-40a1-4084-9733-4efd29972944 |  | label | HP*
label | b0cc8e31-02e0-4183-bd44-037cb6bd9539 |  | label | RESPONSIBILITY: FH Engineer/ Superintendent
text | e7f63664-c67e-4063-9a46-3bc9769cd9d2 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 Formwork
label | 2fc511df-ebce-48e0-9636-11637652f264 |  | label | FREQUENCY: Each lot
label | 1e2c45f2-a9b9-4193-a219-51b44b8c2357 |  | label | ACCEPTANCE CRITERIA: Formwork shall conform to shapes, lines, levels and dimensions as shown or indicated on the Drawings.
label | 13033e8c-aeb9-48e1-a403-ddd83fe093e4 |  | label | REFERENCE DOCUMENTS: Drawings
label | 4ba7f15e-4182-49b1-8d22-e4b7980b19c6 |  | label | INSPECTION/TEST METHOD: Verify
label | 100eb8f5-f9de-4e00-b1ff-85411da004c9 |  | label | RECORD OF CONFORMITY: This ITP signed
label | 44fba006-f54f-4f15-9285-666872d8b7e5 |  | label | IP
label | 5e9dd56f-44ca-47f4-87f6-be76a3263a09 |  | label | RESPONSIBILITY: FH Engineer/ Surveyor
text | 25af8f25-9476-481c-a6d8-5933b9c84a2d |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3.1 Steel Fixing
label | d080f0a1-6d16-4a3e-a5da-7275ce80738f |  | label | FREQUENCY: Each lot
label | f96bb6e5-5619-4a08-9401-134d6862daf8 |  | label | ACCEPTANCE CRITERIA: Reinforcing Steel bent and placed in accordance with AS 4671. Reinforcing bars supported on plastic/concrete chairs spaced no greater than 60 bar diameters. Mesh supported on plastic/concrete chairs spaced at 750 maximum centres. Adequate cover to reinforcement
label | 85867c3b-2383-46e2-90c2-fab20bedc8c5 |  | label | REFERENCE DOCUMENTS: CP17038-LAN-DET-ST-3841
label | 4b44e985-1240-40b7-8d61-ecce6f14bec3 |  | label | INSPECTION/TEST METHOD: Verify
label | e1960168-ac60-46a8-b218-7a0a0787c097 |  | label | RECORD OF CONFORMITY: This ITP signed
label | 120eda3b-cf16-40db-9dc5-e1a4bfcb4dfe |  | label | IP
label | 65c83f9b-8f17-4198-9504-e41bd9c94ed3 |  | label | RESPONSIBILITY: FH Engineer
text | 96977d1d-15ab-4cf0-b562-6c7cdd81b526 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 4.1 Pre-Pour Inspection
label | 51980bb6-46ab-4c20-9a98-e76e32e35e21 |  | label | FREQUENCY: Prior to concrete pour
label | d78a17c9-4cc9-4e26-b2a9-a5a9426d15aa |  | label | ACCEPTANCE CRITERIA: Performed final Pre-pour inspection Fulton Hogan to notify Superintendent 24 hours in advance to pour concrete to enable the formwork and reinforcement to be inspected and approved. CL 005A – Pre-pour Checklist completed .
label | f9bbb12e-8142-4b7c-a702-a59065105de5 |  | label | REFERENCE DOCUMENTS: WP 008
label | a0bb2ef1-607e-4486-a9ad-2e49660e7dea |  | label | INSPECTION/TEST METHOD: Inspection
label | 10b9e207-7ea7-4c2a-9dd8-a16c749101b2 |  | label | RECORD OF CONFORMITY: CL011A
label | 18e00355-0b6b-458e-a05c-d894b329af5f |  | label | HP*/WP
label | bf9c7587-fcc7-4fdb-934f-a5fd02f03ef1 |  | label | RESPONSIBILITY: FH Engineer/ Superintendent
text | ce04264f-f8a4-43b8-814d-1f36c84f49cc |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 5.1 Pour In-Situ Pits
label | b2810de7-ef6c-4fff-a5da-a4c7d018f31c |  | label | FREQUENCY: Each lot
label | e3ecd533-2250-488a-acc3-b7005d8f8dc7 |  | label | ACCEPTANCE CRITERIA: Hydrotite installed at construction joints including wrapped around pipes/conduits prior to concrete placement. Pits constructed at the locations and to the dimensions and details shown on the drawings using specified concrete mix. Concrete Testing – Pits: For each pour 1 slump (nominated slump +/- 10mm) & 3 cylinders to be cast per test. Concrete placed within in 90mins from batching; Concrete does not fall from a height of more than 1.5m.
label | 23d43601-d12f-4c7f-8cbc-1c59daa35660 |  | label | REFERENCE DOCUMENTS: CP17038-LAN-DET-ST-3858 WP 008
label | 167c9b90-0ad8-4ac1-a42f-a615aa71d4cb |  | label | INSPECTION/TEST METHOD: Visual inspection Inspection Test reports attached
label | 2378dbcc-e1ff-435b-a310-bd19fc235ecb |  | label | RECORD OF CONFORMITY: This ITP signed Concrete pour record sheet CL006B Delivery Docket
label | 6e1bd160-0e46-4aa0-9d7a-d5e7244797e3 |  | label | IP HP* TP HP*
label | 18314faa-b1d0-47c9-8bd4-9923d3248aa1 |  | label | RESPONSIBILITY: FH Engineer
text | e929c8d1-0b70-489e-96b2-75cb28b243d6 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Concrete Traceability
label | d438280f-ce12-4ad7-8521-637fcbd0c954 |  | label | FREQUENCY: Each lot
label | af5de237-4a9e-403f-9176-6f0a9cbedbdb |  | label | ACCEPTANCE CRITERIA: All concrete delivery information recorded on CL 009B – Concrete Pour record sheet.
label | 50910caf-c055-4d2e-a733-72cacbc51b9a |  | label | REFERENCE DOCUMENTS: CL 009B
label | ddfafbeb-2933-44ef-92bc-5b005e989046 |  | label | INSPECTION/TEST METHOD: Record
label | bc473b46-c282-4627-b328-cc51a36b96e6 |  | label | RECORD OF CONFORMITY: CL009B
label | f6d40c2c-e7fd-459d-b611-fa4148640ab1 |  | label | IP
label | 11d5dff5-e48b-41a8-ba6e-134cd0e3035a |  | label | RESPONSIBILITY: FH Engineer
text | 4991cfae-c200-468b-bbfb-8fcf7e18cb03 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Finishing & Cutting
label | ee60c1c0-f8bf-4fd7-81fc-8104cdb6e0d6 |  | label | FREQUENCY: Each lot
label | 081453dd-5d5d-4e00-9fa3-dd7d788dc69c |  | label | ACCEPTANCE CRITERIA: Concrete vibrated to ensure compaction and air voids removed; Screed finish on exposed surfaces; Concrete protected against loss of moisture and rapid temperature changes using curing compound or wet hessian.
label | c5e7bc0e-47a5-4e4c-b189-7796ab3236ee |  | label | REFERENCE DOCUMENTS: WP 008
label | bb877f26-9a13-4476-8048-40ee4bb93455 |  | label | INSPECTION/TEST METHOD: Verify
label | 3864d061-5001-40cc-a182-b4532bf92d59 |  | label | RECORD OF CONFORMITY: This Signed ITP
label | 9fce67cd-6ed4-47bd-bfb6-271cd0133c90 |  | label | IP
label | d78a90f3-d066-411f-a503-e407705414d4 |  | label | RESPONSIBILITY: FH Engineer
text | d65fcd7f-71ab-42cd-9e3b-8927af131c5c |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Joint Sealing
label | 851f045e-7bc7-4597-a8b6-5d3bc2341635 |  | label | FREQUENCY: Each lot
label | 8fc9df50-a076-4e1c-afe0-5bbcc5c7495c |  | label | ACCEPTANCE CRITERIA: Joint sealant shall be allowed on the finished base concrete until the in situ strength of the concrete is at least 60% of the target 28 day compressive strength
label | 2b70cf62-42c5-40df-aff1-c438a6d07226 |  | label | REFERENCE DOCUMENTS: CP17038-LAN-DET-PM-SP-0001 cl 6.18 (a) CP17038-LAN-DET-Cl-3314
label | cf6e24e8-4523-4525-933e-fe6247730e9f |  | label | INSPECTION/TEST METHOD: Verify
label | 73c73b03-4893-435d-9d54-977a2e3cae67 |  | label | RECORD OF CONFORMITY: This Signed ITP
label | 71e02dee-1729-49c9-b1ee-83a3cbabf87b |  | label | IP
label | f586ac1c-ff47-4757-b946-34b01fd8a056 |  | label | RESPONSIBILITY: FH Engineer
text | 21b69eb8-2e51-428b-a5e9-3c58c8a463a6 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 6.1 Removal of Formworks
label | 8c160096-cb44-4cc8-80e0-a147aa3899d2 |  | label | FREQUENCY: Each lot
label | 18c3fc20-e69b-44b6-aa44-fc00d3641892 |  | label | ACCEPTANCE CRITERIA: Forms remain and maintained firmly in place until the concrete has attained the necessary strength to support its own weight.
label | abbeee66-3a0e-47da-8134-81a97d09da43 |  | label | REFERENCE DOCUMENTS: WP 008
label | 0f83f01e-18ad-4eb2-8d3c-067b49fa4ee8 |  | label | INSPECTION/TEST METHOD: Verify
label | a4f24b0e-6160-4667-83d9-8e9143de879a |  | label | RECORD OF CONFORMITY: This Signed ITP
label | 271e1679-8134-4a91-b3d3-c5f4c049fe34 |  | label | IP
label | d2ff2c8e-8cd6-4246-b650-8894d23e9ead |  | label | RESPONSIBILITY: FH Engineer
text | 7b7dbf5a-25af-48fe-b297-77840bb79b33 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Backfill
label | c2158e9d-109f-4a79-9b0a-6c992b33f1f0 |  | label | FREQUENCY: Each lot
label | 5a96751a-c0b4-4397-8223-c4e461c20528 |  | label | ACCEPTANCE CRITERIA: No backfilling against in situ concrete structures within 7 days of concrete placement. Backfill material placed and compacted to refusal in layers not exceeding 300mm loose thickness.
label | 964a08c1-0b1e-4c54-99ad-9aa9b0857217 |  | label | REFERENCE DOCUMENTS: CP17038-LAN-DET-PM-SP-0001 cl 7.2.5
label | 97bd136a-071b-4fab-97a5-e2b945f503eb |  | label | INSPECTION/TEST METHOD: Verify
label | 06d7355d-235f-45ce-ba0b-4b4a139b6c7c |  | label | RECORD OF CONFORMITY: This ITP signed
label | 5cb0fb35-2096-4a98-be5e-8f6c0ba34646 |  | label | IP
label | 906667c5-1ed6-4f01-8139-e4b425fae427 |  | label | RESPONSIBILITY: FH Engineer
text | 46e8b23c-5822-4630-9165-9a24f249181a |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Post Pour Checklist
label | a484ca1e-485c-49f2-935a-17e1769c7754 |  | label | FREQUENCY: Each Concrete Pour
label | 36dc9d38-a951-4b18-8f65-b8523fab41b8 |  | label | ACCEPTANCE CRITERIA: CL 005B – Post-pour Checklist completed and signed by Fulton Hogan.
label | f966c472-137f-46fe-a97a-4c621d5e6550 |  | label | REFERENCE DOCUMENTS: WP 008
label | 69159f8c-1337-436a-8ff6-19373715af39 |  | label | INSPECTION/TEST METHOD: Verify
label | 42068e6b-ef04-44db-a3d2-f27a1fbc7cc9 |  | label | RECORD OF CONFORMITY: CL 005B
label | 3b0ba907-979a-4808-b560-33e6b7856d96 |  | label | IP
label | 14c3df71-df28-4241-a45e-c6cea1b46aea |  | label | RESPONSIBILITY: FH Engineer
text | 10d9975e-f708-465d-802e-e10b55117e9a |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 753cc83d-e9bc-4ee3-b40c-5aaad6f300d8 |  | label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | 4c6d3ab1-397a-4e52-9e4b-aac3f646f444 |  | text | Print Name:
text | 3b78aef8-1e24-4cd7-876e-989f537087b4 |  | text | Position:
text | f7d27929-2853-4ae5-813f-9a224115b0e0 |  | text | Signature:
text | 5f925d27-6317-42c1-944b-1453f67485da |  | text | Date:
checklist-flat |  |  | checklist | ITP 015 - Existing Underground Service Protection |  |  |  |  | Yes | ITP 015 - Existing Underground Service Protection | 9dbc25ff-bcce-44ca-85d0-b0a0a2fe6e44
checkpoint-status |  |  | checkpoint | 1.1 Check for Correct Documentation
label | 80a1ce71-4db8-4b78-bec4-edf19fad34ed |  | label | FREQUENCY: Prior to commencing activity
label | 2e155d3d-d902-4a17-81ee-141ede20c6fd |  | label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | 3275d71e-d160-4ea3-873a-fb6251abcedc |  | label | Using the correct and complete set of drawings
label | e343eb4f-9802-491b-9fea-5516840d1df9 |  | label | All drawings are the latest revision
label | d9163ff6-7c20-46a4-bdf8-531c3f0403b1 |  | label | REFERENCE DOCUMENTS: Drawings /Aconex Register
label | 247465f3-88c8-4248-bda9-31fc5393f545 |  | label | INSPECTION/TEST METHOD: Visual Inspection
label | f83b48fd-6bee-464f-be1f-9f59edfbe4e0 |  | label | RECORD OF CONFORMITY: Drawings and drawing registers
label | 6d6e909f-cad0-4ddb-b75a-002c7f1197cf |  | label | HP*
label | 3af945d6-2630-4b33-95c5-ba68d4b145b5 |  | label | RESPONSIBILITY: Project Engineer
text | 2ee5c4a3-069c-4521-92f4-88dc4c463042 |  | text | Date Completed:
holdpoint |  |  | holdpoint | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 1.2 Implementation of all measures and controls
label | cdd8d8ff-5fc3-4afd-bd61-7051a72ec8c5 |  | label | FREQUENCY: Prior to commencing activity
label | fd0eef70-0465-438a-8108-e11d78ca4669 |  | label | ACCEPTANCE CRITERIA: All necessary measures and controls being implemented, that is PSP, EMP, TMP, SWMS & WP
label | 69eb9e68-0a25-44a7-9f8d-0b4d2980c34a |  | label | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | 3374b135-5f4a-488b-a3e1-6c2c3aa3dd0d |  | label | INSPECTION/TEST METHOD: Visual Inspection
label | 4cdb4394-4f13-42e3-8964-c6a9f1bdda89 |  | label | RECORD OF CONFORMITY: This ITP signed
label | 80975bb2-520a-4c10-bc25-1b1647a3413d |  | label | HP*
label | faa08f4c-d2c4-4b8c-8359-7a525c238cf3 |  | label | RESPONSIBILITY: Project Engineer
text | 9725c18f-945f-4105-b275-fe2ba3431e04 |  | text | Date Completed:
holdpoint |  |  | holdpoint | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 1.3 Concrete Material Compliance
label | c910587f-f64b-4304-b034-e9d4a8efb953 |  | label | FREQUENCY: Prior to commencing activity
label | 3e99ffad-b7ef-43d9-843e-d54b7987165f |  | label | ACCEPTANCE CRITERIA: Cement for use in concrete encasement shall be 20MPa Portland Cement Type GP complying with AS 3972
label | da4d1e87-c00e-4e57-9028-ad6a9907e716 |  | label | REFERENCE DOCUMENTS: CP14038-AIR-DET-PMSP-0002 / cl. 12.3.4 / cl. 9.3.1.10
label | e9f57f14-2e81-4f21-9a66-9cb2bb810fa5 |  | label | INSPECTION/TEST METHOD: Verify
label | 0af36717-d847-49d9-ade2-c8c0f6b3d01e |  | label | RECORD OF CONFORMITY: Mix Design Approval
label | 3dd1bb47-14fe-4945-ae45-75437ddc5244 |  | label | HP
label | 640869d8-a901-4313-bc6d-933c6cb4f88d |  | label | RESPONSIBILITY: Project Engineer /Principal’s Representative
text | b74fff45-6081-45c9-86ae-5f7ffdbe903d |  | text | Date Completed:
holdpoint |  |  | holdpoint | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 1.4 Steel Reinforcement Material Compliance
label | 54a2d49e-06e4-46a4-bf31-4c31c8eb85c1 |  | label | FREQUENCY: Prior to commencing activity
label | 2e9600e5-d5b6-45cc-a0ae-fb99694c2181 |  | label | ACCEPTANCE CRITERIA: Welded wire fabric shall be SL92 mesh as per drawings
label | e6816484-2bf9-46e2-b127-2ffdf56bc186 |  | label | REFERENCE DOCUMENTS: CP14038- AIR-DET-CI- 0387
label | 4790d5f2-cdd4-4e28-9b29-2202f382ab0d |  | label | INSPECTION/TEST METHOD: Verify
label | 71e623f8-aba9-4ace-ac14-4955c64e9484 |  | label | RECORD OF CONFORMITY: Material Conformance Certificate
label | 0dc2dd66-2abb-4868-84c2-7f3db5fc1fb9 |  | label | HP*
label | abaec05b-52d5-42c1-9966-17d7915dd6de |  | label | RESPONSIBILITY: Project Engineer
text | 2952570e-7c80-4886-b9bf-da9bbb1a98ae |  | text | Date Completed:
holdpoint |  |  | holdpoint | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 1.5 Service Identification
label | 517f6ce7-d005-4715-99ca-19cb4ae6b205 |  | label | FREQUENCY: Prior to commencing activity
label | 0f7f7bde-4a54-47e2-a2db-06d8291bdc6a |  | label | ACCEPTANCE CRITERIA: All existing services’ locations must be confirmed prior to commencing work.
label | f860f559-d07f-4f05-b2c9-901a4bdd104c |  | label | Contractor to obtain excavation permit from APAM.
label | 17a94a5b-773f-4994-9b3e-c504b975ea2b |  | label | REFERENCE DOCUMENTS: CP14038-AIR-DET-PMSP-0002 / cl. 9.1.1
label | ecfe8e47-0de2-4570-8128-88c9235d816d |  | label | INSPECTION/TEST METHOD: Verify
label | ef2ac28b-4186-4568-b168-2c50783a2073 |  | label | RECORD OF CONFORMITY: APAM Excavation Permit
label | 762da8d3-dbd5-48b3-b30d-a23acc98586e |  | label | HP*
label | afa3115f-25fa-47b9-936e-9c912c64b9c6 |  | label | RESPONSIBILITY: Project Engineer
text | b348be21-1e2d-4f0f-9736-26e90880f693 |  | text | Date Completed:
holdpoint |  |  | holdpoint | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 1.6 Method of Treatment
label | ff3d4e0a-aea8-42f2-a287-4fa46599a018 |  | label | FREQUENCY: Prior to commencing activity
label | 009144a5-3c8f-4303-b150-e59bcca2bd3f |  | label | ACCEPTANCE CRITERIA: The method of treatment for existing services to be protected shall be included in the demolition work plan submitted to the Principal’s Representative
label | 4e41302c-2202-4fc3-a0db-16ca3b17dcf8 |  | label | REFERENCE DOCUMENTS: CP14038-AIR-DET-PMSP-0002/ cl. 2.2
label | a6be341e-efdc-43b7-927d-5c3136de0bf6 |  | label | INSPECTION/TEST METHOD: Verify
label | c6642c1d-681d-4c47-ab84-89d5020f0a8d |  | label | RECORD OF CONFORMITY: Demolition Work Plan
label | 5e87935e-2d17-41ab-b2df-66bd4c738e88 |  | label | HP
label | 3d48a83c-ca10-42d9-abe5-3bd03fcfc234 |  | label | RESPONSIBILITY: Project Engineer /Principal’s Representative
text | 9f1325da-f4ea-4572-9e35-a9a4e7b88651 |  | text | Date Completed:
holdpoint |  |  | holdpoint | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 2.1 Excavation
label | 07ab5a2c-2d73-463d-88e4-553fb5c3646c |  | label | FREQUENCY: Each Lot
label | 6bd44278-57fc-4c3d-80a9-c37fb09bf288 |  | label | ACCEPTANCE CRITERIA: Only excavation methods approved by the Principal’s Representative (as per Demolition Work Plan) will be used.
label | 513eccd0-00d1-47b0-bcf4-c44ead3e28cf |  | label | REFERENCE DOCUMENTS: CP14038-AIR-DET-CI0010
label | aff321f2-617d-4759-a1f0-72288c31c32c |  | label | INSPECTION/TEST METHOD: Verify
label | 7f75bb4d-d8ca-477c-a1bd-49195dff49d5 |  | label | RECORD OF CONFORMITY: This ITP signed
label | 1b6c1e2f-7408-4061-b9b9-bf36cdbe1bf5 |  | label | IP
label | f2f9bf28-07e3-4c4b-b6f1-435367459b23 |  | label | RESPONSIBILITY: Project Engineer /Foreman
text | 689da524-a2a6-4143-9843-bd76c7c630d5 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Survey Record
label | 7eea23d5-a48b-41d2-8a00-e8176bdc4a04 |  | label | FREQUENCY: Each Lot
label | d793e5fe-9f44-45b9-bc9b-86690226fec5 |  | label | ACCEPTANCE CRITERIA: Where existing services are to be retained, a surveyor shall record the position of proven service, including depth and cover to each surface.
label | c9d435ff-e7fb-496c-87b3-a383001c9899 |  | label | REFERENCE DOCUMENTS: FH QMP Section 6.3
label | 6bbe1bbd-849c-4b7c-8cf0-bad08e266370 |  | label | INSPECTION/TEST METHOD: Verify
label | 8f2fe6c1-8dc6-4eca-a861-293c8621c51f |  | label | RECORD OF CONFORMITY: Survey Record
label | 850774ce-f132-4020-a71a-ed0616500c40 |  | label | IP
label | f67d7294-7a3c-47c4-95ad-dc8e0835b5a1 |  | label | RESPONSIBILITY: Project Engineer /Foreman
text | 3fa15c6b-bcd2-4b32-ba64-217eac4d305d |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Protection of existing services crossing trenches
label | 4bb17537-e4a4-489e-92b7-9eec03f6c9dd |  | label | FREQUENCY: Each Lot
label | 14b02348-8d17-4652-a947-ff60d4b915b3 |  | label | ACCEPTANCE CRITERIA: Where existing services are to be retained, careful actions must be taken to ensure that no damage is caused to the service
label | e6418505-7664-4b48-8b78-eb38c7291ef8 |  | label | Services are to be carefully exposed, supported and protected whilst excavation works and other activities under and around the service are being carried out.
label | e086437f-df9b-4f25-a611-610377d77c1d |  | label | Any backfilling that is required under the existing service must be properly compacted.
label | 68db724b-e5b1-4271-ba12-6cfdeb6e508c |  | label | REFERENCE DOCUMENTS: CP14038-AIDET-PM-SP002-C-Cl 9.3.1.7
label | 4320a143-5f3e-4a9e-8912-ae5d5a99e1f1 |  | label | INSPECTION/TEST METHOD: Visual Inspection
label | 3d3f67f5-0a25-4aba-be94-0f8b0c78cc58 |  | label | RECORD OF CONFORMITY: This ITP signed
label | 288f076e-2eea-49e5-a2bf-45c528f3b644 |  | label | IP
label | 200a29a4-bf34-40dc-91b3-7cc1f186788a |  | label | RESPONSIBILITY: Project Engineer
text | 38907e0b-3bc3-41e7-9dd1-c30f71956100 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Placement of Reinforcement
label | 4cfc1342-a5b3-4deb-9255-68237482c05c |  | label | FREQUENCY: Each Lot
label | b7871fd2-37bf-4c26-ba8f-ecff99dedd11 |  | label | ACCEPTANCE CRITERIA: SL92 mesh shall be placed all around the service to be protected as specified on the Drawings.
label | 8a89eb82-62fd-4d80-9bec-91b4a455dd18 |  | label | Steel reinforcement shall have a minimum cover of 60mm
label | 4586e058-4fba-4e76-b35e-05fa7be17f61 |  | label | Minimum lap length shall be 150mm.
label | a064d085-3e96-4ece-b94a-6b2f4a87335b |  | label | Spacers and supports shall be either proprietary or purpose-made using 20MPa concrete.
label | 25cc86bc-269f-4e49-a50c-23e1f7e4ca81 |  | label | REFERENCE DOCUMENTS: CP14038-AIR-DET-CI0387 / CP14038-AIR-DET-PMSP-0002 / cl. 12.3.7
label | 2e0cb908-1989-4401-8175-d9a971aa561a |  | label | INSPECTION/TEST METHOD: Verify
label | e7be031d-d566-4084-a903-e39d4daf4c77 |  | label | RECORD OF CONFORMITY: This ITP signed
label | 347b930a-1536-43b3-ba51-496c749e6542 |  | label | IP
label | a69e8462-8563-4f5c-84f1-de15375970dd |  | label | RESPONSIBILITY: Project Engineer /Foreman
text | de1afbda-bb69-4408-9d89-03f9e5015142 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 Concrete Encasing
label | 12525d33-c6c7-466c-a930-20737ce7230b |  | label | FREQUENCY: Each Lot
label | fad7c232-ac2a-4650-bdfd-919ef489e9d9 |  | label | ACCEPTANCE CRITERIA: 20MPa concrete shall be used for the concrete encasement.
label | 52f98064-b916-4d66-a2a2-e6f509b57d5a |  | label | For existing services banks containing ducts up to 150mm in diameter, ensure minimum thickness of 100mm of concrete from surface of individual conduits.
label | bf7f0efa-ebcf-4b81-8377-bc2c56cd3989 |  | label | For existing pipes up to 675mm in diameter, ensure minimum thickness of 150mm of concrete from surface of pipe
label | 8500bf39-cd81-4b9e-83ea-965cf30a7589 |  | label | Concrete shall be placed within 90 minutes from batch time.
label | a7c97f8b-d66e-4b6a-a2eb-690bb47f041a |  | label | Temperature of concrete shall be not less than 10C and no more than 30C.
label | e4a7cfeb-f8d7-4184-860a-ddf43097406b |  | label | REFERENCE DOCUMENTS: CP14038-AIR-DET-PMSP-0002 / cl. 9.3.1.9 / CP14038-AIR-DET-CI0387
label | 2edbfc7f-f4ff-4e14-999c-e1bd04ff756d |  | label | INSPECTION/TEST METHOD: Verify
label | ab0a32be-0b8c-46b1-a614-3857d4664596 |  | label | RECORD OF CONFORMITY: This ITP signed
label | 978f5872-dfc9-404c-a5b8-d7ecfb701e9e |  | label | IP
label | 957cd289-28f1-4c4e-91f8-ff13a1d7f5f2 |  | label | RESPONSIBILITY: Project Engineer /Foreman
text | 256e7190-c003-4b16-bf95-a4cc3fbbb15d |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 Concrete Compaction
label | 8d2c75ff-01b1-448a-9a13-d15120732e51 |  | label | FREQUENCY: Each Lot
label | 5014c661-9e3d-40f2-9b43-fa8c51eebbbc |  | label | ACCEPTANCE CRITERIA: Concrete shall not be placed at a rate which will prevent adequate compaction and the layer shall not exceed 300mm thickness before vibration.
label | de9e634e-768c-49ad-bd0d-83047a5df4dc |  | label | Internal vibrators shall not impinge on the outer surface of conduits/pipes during vibration of concrete.
label | 380bdd53-b7f6-430c-9265-afeb61534270 |  | label | REFERENCE DOCUMENTS: CP14038-AIR-DET-PMSP-0002 / cl. 12.4.8 & 12.4.9
label | 26cf8687-7b84-4a7d-876a-f8664dabfc8f |  | label | INSPECTION/TEST METHOD: Visual Inspection
label | c3af1b0c-a183-41f4-8651-0687182f33d7 |  | label | RECORD OF CONFORMITY: This ITP signed
label | fb951ff0-570e-4f68-9917-88f2d1f10e42 |  | label | IP
label | 0b18772c-72e8-4345-abc1-3c131f94f5e6 |  | label | RESPONSIBILITY: Project Engineer /Foreman
text | 377e0887-123c-4c2f-8daf-a88f9898be3b |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.7 Orange Detectable Warning Tape
label | 0c9bed9e-3e2a-4c48-92dd-9f23df3063ce |  | label | FREQUENCY: Each Lot
label | b66213dd-9b21-4ca5-b84b-4672ad535d23 |  | label | ACCEPTANCE CRITERIA: Orange detectable warning tape incorporating a magnetic strip shall be installed with at least 300mm cover to the top of concrete encasement.
label | 56a5c917-fc6a-4090-8dbb-aae18c7cbf71 |  | label | REFERENCE DOCUMENTS: CP14038- AIR-DET-CI- 0387
label | abc0d651-ec19-44af-9f09-b96643302416 |  | label | INSPECTION/TEST METHOD: Visual Inspection
label | 489127d9-ab41-4d3a-b75e-c66d919d2ce5 |  | label | RECORD OF CONFORMITY: This ITP signed
label | 475c6c85-6963-4c46-96b4-7553809ca74b |  | label | IP
label | 4d21dacc-497e-4fa2-82c5-31374b50e039 |  | label | RESPONSIBILITY: Project Engineer /Foreman
text | 2c7bfa58-359b-4c3b-924c-553c255c2071 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 7497bfaf-2df9-494e-9240-d5aa4fea5741 |  | label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | 82364b22-c81d-410b-a38b-b8da00ab711c |  | text | Print Name:
text | edf7020f-8e49-4530-b29b-ce44395f7dff |  | text | Position:
text | eef29986-77c2-47cd-9b25-887b53ae1cf3 |  | text | Signature:
text | 71783f62-d804-4713-8270-accb0a23d278 |  | text | Date:
checklist-sectioned |  |  | checklist | ITP 027 - Electrical & Communication Conduit (Aurecon) - Rev 0 | itp |  |  |  | Yes | ITP 027 - Electrical & Communication Conduit (Aurecon) - Rev 0 | a5812ac7-eb30-48f2-b17e-7b40b3af246d
checkpoint-group |  |  | section | ITP 027 - Electrical & Communication Conduit (Aurecon) - Rev 0
checkpoint-status |  |  | checkpoint | 1.1 Materials
label | d9ce4573-6fe1-44e7-b35b-2d16ec51dbc7 |  | label | FREQUENCY: Prior to Commencing works
label | fe79e46b-bbd8-469c-ab39-ba126cb40a9c |  | label | ACCEPTANCE CRITERIA: Ensure that the correct materials are being used as per drawings and specifications; Ensure PVC conduits match diameter required.
label | 963c155a-f8e6-475a-82cb-4f72ec0d5f90 |  | label | REFERENCE DOCUMENTS: Drawings/ Specification 500287-HV-SPEC-02
label | 5b108964-2dec-4d42-bc82-c8730df0a6a2 |  | label | INSPECTION/TEST METHOD: Verify
label | c8fd9a9f-658c-410f-be17-116f794b5cb1 |  | label | RECORD OF CONFORMITY: This ITP Signed
label | 2e67f190-53a8-4d27-838c-5bfc0c73072a |  | label | HP*
label | f05d0526-f44a-4a18-9431-709fcdcd3b7c |  | label | RESPONSIBILITY: Project Engineer
text | 2b03a5e8-18af-494a-9d6c-bc64a6a51f78 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 Setting Out for Conduits
label | 26c08001-c948-4867-a7c5-9db690a23a21 |  | label | FREQUENCY: Prior to Commencing works
label | 6b4a9172-c96c-41b5-a322-e03f714aa6f0 |  | label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | 87dfd127-f86d-48df-b11d-2bca1d25aed8 |  | label | Using the correct and complete set of drawings;
label | fabe3832-c024-42b6-a029-53151e3c484f |  | label | All drawings are the latest revision.
label | 3d10504e-d427-43d4-b24b-0a302af52aba |  | label | REFERENCE DOCUMENTS: Drawings/ Aconex
label | a2d1cda9-df06-442d-b1ce-69cf5824362c |  | label | INSPECTION/TEST METHOD: Verify
label | 0b30358e-710e-4026-be71-855f9ddc5db6 |  | label | RECORD OF CONFORMITY: Signed ITP
label | 34ab79c5-7dae-453a-bc17-5e3a44740a75 |  | label | HP*
label | 128e11cd-db49-436a-b32f-c8392bfe1b9e |  | label | RESPONSIBILITY: Project Engineer
text | 5e71acc4-6798-438a-9a57-4ec8b3bee51f |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 Existing Service Location
label | 341569ea-93a3-4012-8dea-8f6923263830 |  | label | FREQUENCY: Prior to Commencing works
label | 73d9ae6d-cb18-40df-b34f-21e35d9a8785 |  | label | ACCEPTANCE CRITERIA: Location of services to be found and marked on the ground within the works;
label | 8ba3bacf-59f6-4f7c-a5f8-f7728dc6b77f |  | label | Services located within the works area to be exposed.
label | 54c68378-51fa-4ca5-a150-2b41e4436702 |  | label | REFERENCE DOCUMENTS: DBYD/ Drawings
label | 18ae9343-c4be-49cd-95c3-802aa7f64cec |  | label | INSPECTION/TEST METHOD: Verify
label | fe2ab46e-61b9-4663-9977-c011b325ae6b |  | label | RECORD OF CONFORMITY: Melbourne Airport Excavation Permit
label | d3712b42-cd36-4730-bda2-02aa2067c276 |  | label | IP
label | 61f8b9f6-4c41-4299-879d-28892b1cc4d0 |  | label | RESPONSIBILITY: Project Engineer
text | 104bde2c-612e-4f08-9343-1d1ccd61403b |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3.1 Excavate Trenches for Conduits
label | 4b367cc0-2165-4d76-80c8-187ef0a41494 |  | label | FREQUENCY: Each Lot
label | 00b9b8ba-7595-4581-afcd-adcd64ca15e6 |  | label | ACCEPTANCE CRITERIA: Depth and width of trench shall be excavated to the requirements specified on the Drawings for each Section.
label | 1eb36da9-9ac1-4d90-9455-c1ca2b0a74a6 |  | label | Excavations deeper than 3.0m shall be undertaken under the guidance of the Contractor's Geotech Engineer.
label | 18e0e82d-c5d2-466f-941b-efdda3e37647 |  | label | REFERENCE DOCUMENTS: Drawings 500287-HV-SPEC-02
label | e8ac9355-5bec-421a-8afa-b67b5b5ef348 |  | label | INSPECTION/TEST METHOD: Verify
label | 64694792-2e69-48d4-898d-e56e165d3862 |  | label | RECORD OF CONFORMITY: Signed ITP
label | 0c186fe7-6f98-490d-9a22-50b08cdeb3da |  | label | IP
label | be64ce6f-100f-4955-88d3-cf4326ead838 |  | label | RESPONSIBILITY: Project Engineer
text | 9bc965fc-0e45-47cc-8265-2cb56f85dc5e |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Laying and Jointing of Conduits
label | 0ae0f930-1a61-40e3-975a-d6780bf26e12 |  | label | FREQUENCY: Each Lot
label | 4bc2b5fd-e37a-4e6c-addd-3a81040c8e0c |  | label | ACCEPTANCE CRITERIA: SCATA Conduit to bypass electrical Pits;
label | e6c63467-2c1d-4096-bfdf-7a630189c83a |  | label | Electrical conduit to bypass SCATA pits;
label | 7911f55a-a47c-4e25-a29c-747699abeb6d |  | label | REFERENCE DOCUMENTS: 500287-HV-SPEC-02 Drawings
label | 08eb14c8-22aa-4e6b-9e3b-a745a9ac636e |  | label | INSPECTION/TEST METHOD: Verify
label | c53441b9-cb80-4782-b9dc-1e7a521f3fc0 |  | label | RECORD OF CONFORMITY: Signed ITP
label | 1c69d503-3663-4e0f-8d27-363573bbda61 |  | label | IP
label | f8c13b1c-ce79-4e4c-bd94-76f528c955d0 |  | label | RESPONSIBILITY: Project Engineer / Foreman
text | 7e7ab2c7-dfc8-4ed9-ba7a-f388ddf7ac3a |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Conduit Layout
label | 7bc3a873-e9ea-44fa-8d23-136ee98898ac |  | label | FREQUENCY: Each Lot
label | 330dab15-0c62-4f29-be6a-5516bd898c14 |  | label | ACCEPTANCE CRITERIA: Conduit arrangement to suit trench detail;
label | 84cdc063-0e1f-424c-af5e-73f246b61f78 |  | label | Conduit to slope towards pit for drainage purposes;
label | 9138ae7e-ca33-4b2b-9cf0-ccbaff954b05 |  | label | Quantity of conduits to be confirmed and entered w/ each lot.
label | 9e3bbe86-a3ce-4ae5-9524-6a4a338ebc8d |  | label | REFERENCE DOCUMENTS: 500287-HV-SPEC-02 VicRoads Section 706-Installation of Utility Infrastructure
label | 5260b3d0-f269-48b2-a3e4-8ddfb06dfc8f |  | label | INSPECTION/TEST METHOD: Verify
label | b8f3c009-874d-4f46-88d0-00061cd240a8 |  | label | RECORD OF CONFORMITY: Signed ITP
label | 9f6b7457-9147-422c-8c07-bcad4fc149df |  | label | IP
label | 169f5d19-a350-4829-a493-372bb8179b23 |  | label | RESPONSIBILITY: Project Engineer/ Foreman
text | fca41c8e-6282-4ffa-ae25-d794f37c33de |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 Conduit Pre-Pour
label | 6bb1e2af-ceb6-4f89-b854-91a0072ca662 |  | label | FREQUENCY: Prior to Backfill
label | 8d7ce733-cc08-4bdb-a4e1-b13844f026d6 |  | label | ACCEPTANCE CRITERIA: Layout is to be inspected prior to the commencement of concrete encasement &/or backfilling the conduit.
label | 94b18061-074f-46ab-b236-990d15c6221a |  | label | REFERENCE DOCUMENTS: Drawings
label | 3c25c116-3160-484a-afa5-4330660606c6 |  | label | INSPECTION/TEST METHOD: Verify
label | edbd254f-f2ea-442f-8331-374ef6a9c724 |  | label | RECORD OF CONFORMITY: Visual Inspection / Signed ITP
label | 36455640-d08e-40e2-8602-0c7c00f1c027 |  | label | IP
label | ada1b182-2850-46ba-b345-5e58ff6f5171 |  | label | RESPONSIBILITY: Project Engineer / Foreman
text | 1496f6b1-369e-4385-8088-9357aa8fa3b7 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 Backfilling Conduits
label | 7d174364-522c-4013-9339-67db272550bf |  | label | FREQUENCY: Each Lot
label | b3456a40-de22-4636-bbc8-ca0d35371c7f |  | label | ACCEPTANCE CRITERIA: Non Aircraft Pavement Areas
label | af7fe61b-7258-4ce4-af6f-c0a724e69bd6 |  | label | Backfill shall be 650mm to top of conduits. Use the approved backfill
label | 22f734c3-94a1-4d2e-8e97-0554b422de2d |  | label | Installation of ‘Marker Tape’ both Electrical & Communication shall be minimum 300mm from surface level as per drawings
label | ca1b6cab-3781-42ea-96f5-5c72f064c609 |  | label | REFERENCE DOCUMENTS: 500287-HV-SPEC-02
label | 0331ee09-c7ed-4e02-9bb4-ad3480745d89 |  | label | INSPECTION/TEST METHOD: Verify
label | e248bc24-dc8d-4a12-ac96-5c115d595c09 |  | label | RECORD OF CONFORMITY: Visual Inspection / Signed ITP
label | b3d5bc7e-6ad5-4fee-a589-85c5914b97f4 |  | label | IP
label | 55dfe53d-9ddd-4ec4-a71d-be32685222d6 |  | label | RESPONSIBILITY: Project Engineer / Foreman
text | c51b2434-ddec-491f-a04f-edb25efb434a |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3.6 Conduit Draw Cord
label | ea6c280d-02b2-4453-841b-94668eb75318 |  | label | FREQUENCY: Each Lot
label | 314cbdbf-3a8e-4339-b297-d1aae44fbb2d |  | label | ACCEPTANCE CRITERIA: All electrical conduits shall be fitted with draw cord.
label | 326c86c8-54bf-47d2-9adb-9914d2c99107 |  | label | REFERENCE DOCUMENTS: 500287-HV-SPEC-02
label | 118383de-b0ec-4c36-881a-eba3e54fdd75 |  | label | INSPECTION/TEST METHOD: Visual
label | da0f3e86-b1bc-41e7-b2f8-1fba8ed951c8 |  | label | RECORD OF CONFORMITY: Signed ITP
label | 8934da95-a717-4827-bc1e-89f653a1df31 |  | label | IP
label | a1a08b65-8bd3-48dc-b3f9-b07732056aed |  | label | RESPONSIBILITY: Project Engineer / Foreman
text | 9bb5cc04-e76c-45cf-8c63-0ffc7dcda0bf |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 4.1 As Built Survey
label | 81b50b9d-919c-4c30-9949-fd0b7d031705 |  | label | FREQUENCY: Prior to Backfilling Each Lot
label | 5f97039d-4039-4dac-a0c9-b978d4a41942 |  | label | ACCEPTANCE CRITERIA: Surveyor to pick up completed conduit runs before backfill with survey report to be submitted with ITP.
label | 11e9e8c3-511d-4c56-b103-2bd01cd8f2ea |  | label | REFERENCE DOCUMENTS: FH PMS Section 5.1
label | fc84c0cb-ae4a-47c6-981e-6bdbbdb11457 |  | label | INSPECTION/TEST METHOD: Verify / Inspection
label | 193f1115-9fe7-432f-929c-034903964f56 |  | label | RECORD OF CONFORMITY: Survey Report
label | a1b22470-2b3d-4a85-965d-ea3b69d939b2 |  | label | SCP / IP
label | 327310b9-c4f4-4bd9-9337-27d54977092d |  | label | RESPONSIBILITY: Project Engineer / Surveyor
text | 251892ce-e33d-4370-866e-f97c22fdda77 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | fcef85f4-c742-49a7-89af-1328feada580 |  | label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 57ed2ff8-fda3-4254-b242-495c2d8115ed |  | text | Print Name:
text | 1fd2050a-c694-4bdd-a7b8-142c0b05ffac |  | text | Position:
text | cfa5a655-6e71-4262-a2d4-0dee437d595f |  | text | Date:
checklist-flat |  |  | checklist | ITP-002 - Demolition of Existing Concrete Pavement, Pits, Pipes, Duct Banks, & Electrical Infrastructure Civil | itp |  |  |  | Yes | ITP 002 - Demolition of Existing Concrete Pavement, Pits, Pipes, Duct Banks & Electrical Infrastructure | b2e98fa3-cbc4-4a00-8d8c-8e0b7e3eab7b
checkpoint-status |  |  | checkpoint | 1.1 Check for correct documentation
label | 9c30dad8-2fb0-4979-a7af-3471f4ee4318 |  | label | FREQUENCY: Prior to commencing any activity
label | 47c54fc7-7a60-4e64-96f6-1bf391afcf95 |  | label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are: - using the correct and complete set of drawings - all drawings are the latest revision
label | 548c23f1-6a8b-4113-8a13-08800f8e8bc3 |  | label | REFERENCE DOCUMENTS: Drawings & drawing registers
label | a844bcd2-1ffc-4c46-b12b-1af9ecde025b |  | label | INSPECTION/TEST METHOD: Visual inspection
label | 460c2cde-316b-451d-959a-cb495c6821d6 |  | label | RECORD OF CONFORMITY: Up to date drawing sets and this ITP signed
label | 9b1ee971-8c87-494f-aaca-b8b9db149506 |  | label | HP*
label | 27a32680-1545-4cfb-8a7d-959b145efa86 |  | label | RESPONSIBILITY: Project Engineer
text | 9d0f3807-6373-48db-91b7-8281e3f0e963 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 Demolition Work Plan
label | c8744c12-f9f7-459a-b818-37621a51566a |  | label | FREQUENCY: Prior to start
label | 414904eb-9e5b-4dc8-ad30-837ce583bb51 |  | label | ACCEPTANCE CRITERIA: Prepare a Demolition Work Procedure and have it checked and approved.
label | 2ff57f9f-670b-482f-a63b-0d66430f2341 |  | label | REFERENCE DOCUMENTS: Demolition Work Plan
label | e3cf0eb1-0180-4480-a06a-f22498db5056 |  | label | INSPECTION/TEST METHOD: Verify
label | f1a2a03c-803b-4d4c-99cc-248cc29415b7 |  | label | RECORD OF CONFORMITY: This ITP signed
label | ad4477f5-576a-456c-8119-0f9b386b0638 |  | label | HP*
label | 4a074b72-c990-4837-8a57-1d894e0d62b1 |  | label | RESPONSIBILITY: Project Engineer/Principals Rep
text | c2199f9b-dd30-4bcc-9f45-5f2a121b9f72 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 Dilapidation Report
label | 69c2e2ef-ec76-4b5a-8fd8-723fc6134f12 |  | label | FREQUENCY: Prior to start
label | f313a6ac-2039-4631-b8f2-2c2effef94e2 |  | label | ACCEPTANCE CRITERIA: Dilapidation report submitted to Principals Representative for approval prior to works commencing.
label | 757bbb75-054c-497f-98c0-f094f461e3e8 |  | label | REFERENCE DOCUMENTS: Dilapidation Report
label | e67a13ad-5397-4580-9a0a-dae51ed94a14 |  | label | INSPECTION/TEST METHOD: Verify
label | cd9bf939-03a9-4089-adc4-59d469134bf1 |  | label | RECORD OF CONFORMITY: This ITP signed
label | befa698a-3ed3-4972-8d43-a67481ebe662 |  | label | HP*
label | 20a0c517-d711-4d4c-95de-337142558425 |  | label | RESPONSIBILITY: Project Engineer
text | 57c28bd1-8890-4c1b-bfb8-dad35a870631 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.4 Service Identification
label | fe6aed40-ee63-4441-b769-f1763a8b7089 |  | label | FREQUENCY: Prior to start
label | ffdb6c9c-f5cb-42b8-b6f2-f22ddb505bf2 |  | label | ACCEPTANCE CRITERIA: Contractor to obtain existing service information from Melbourne Airport (APAM) prior to commencing works. FH to investigate the accuracy of the plans & locate and expose/prove existing services via non-destructive methods. Obtain Excavation Permit from Melbourne Airport.
label | ef3b1f67-d9b4-415d-901a-432b8c5ffdf5 |  | label | REFERENCE DOCUMENTS: WP0002
label | 815b80b6-029a-466b-af6b-c0a8db521720 |  | label | INSPECTION/TEST METHOD: Excavation Permit
label | 04e3951a-61bc-4fe9-8e62-db53f8c3fb25 |  | label | RECORD OF CONFORMITY: This ITP signed
label | 5337bf28-a8d4-4cb4-b566-e63e23611849 |  | label | HP*
label | 8b842456-a275-4a54-8fa7-1d6ba8408a2d |  | label | RESPONSIBILITY: Project Engineer
text | b7cf2099-b4d4-45f7-bcc6-8f935d3d2e93 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.5 Implementation of all measures & controls
label | 0a697b18-55e9-4f10-bab7-0595314f2b61 |  | label | FREQUENCY: Prior to works
label | aca224f8-fab6-40cf-bb67-22b446d7a3dc |  | label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS and WP
label | af7c0270-d146-49cf-ab08-28ec0a2c8318 |  | label | REFERENCE DOCUMENTS: PSP, EMP, TMP, SWMS, WP
label | f473f621-9ba5-4c44-b43a-23381885fc26 |  | label | INSPECTION/TEST METHOD: Visual inspection
label | e3cb14b6-8c2e-43b8-9dc9-ba0a7cecc74c |  | label | RECORD OF CONFORMITY: This ITP signed
label | f7c4721b-9322-4619-b411-6a342faeca83 |  | label | HP*
label | 7c6c5254-1385-40ce-901f-4ca17cc091ec |  | label | RESPONSIBILITY: Project Engineer
text | b41b07a3-55af-4784-b7be-134fbc65d68d |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 Saw Cutting
label | f2c854ae-4409-45df-bfa7-72e95d19ae02 |  | label | FREQUENCY: Each lot
label | 6cfc2aec-8900-419d-b916-7ab5db464a72 |  | label | ACCEPTANCE CRITERIA: Cut locations / extents to be clearly set out by surveyor and checked by FH prior to saw cutting. Removal of slabs to only proceed once twin saw cuts (full depth) have been completed to reduce likelihood of damage.
label | 8bdefc32-9940-483e-8a8b-6dc2d2898abd |  | label | REFERENCE DOCUMENTS: Drawings & drawing registers
label | 42e1f5c5-e98b-41c3-a443-071c4f0f589d |  | label | INSPECTION/TEST METHOD: Verify
label | 207f07c5-8b85-49f2-b231-8db0dbf6b75f |  | label | RECORD OF CONFORMITY: This ITP signed
label | d8017be4-a8e7-4a7a-937c-234e387d9e1b |  | label | IP
label | 276160ca-03cc-4901-9bc0-c2630020544c |  | label | RESPONSIBILITY: Project Engineer/Foreman
text | ebff2114-b827-4f05-ace8-ad5e45e1bdd9 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Disposal of Material
label | 1e2125b6-9bfe-4654-bfbd-7260d9aafa36 |  | label | FREQUENCY: Each lot
label | 8608ce22-53e9-4f8b-ab6f-e78212a65c84 |  | label | ACCEPTANCE CRITERIA: Surplus material, debris and demolished material will be sorted into: - Hazardous Materials (notify APAM) - Non-Hazardous Materials; - Clean fill; - Crushed Clean Fill; - Salvageable Materials. - Contaminated materials Attention drawn to Principals Representative of suspected hazardous materials. These shall be disposed of and transported to a licensed disposal facility.
label | 4bbd9851-b6fa-4bd8-9fca-b7be78f4eccd |  | label | REFERENCE DOCUMENTS: CP17038-LAN-DET-PM-SP-0001 2.4.3.1 2.4.3.3
label | a0b622fc-2f71-40fd-a18b-23c7c4e0bbe1 |  | label | INSPECTION/TEST METHOD: Verify
label | ce143ab5-e980-4878-bdf1-fd055cdfa3f5 |  | label | RECORD OF CONFORMITY: This ITP signed/Dockets
label | 0e12eb6d-cd68-4564-9092-2df7d5de3d10 |  | label | IP
label | a948794e-cfa8-4faa-902b-07f5c862c2ff |  | label | RESPONSIBILITY: Project Engineer/Foreman
text | e966e7a5-e90d-496c-b561-61f0199952f0 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Plant & Equipment
label | 2cd53ee1-b4e0-414c-beca-95baceafa9cd |  | label | FREQUENCY: Each lot
label | 761d1916-3d6f-43e1-88ca-96ace54752b2 |  | label | ACCEPTANCE CRITERIA: Plant and equipment shall be appropriate for the task, inducted to site and checked prior to commencing work
label | 795f8bd9-09cc-4777-9d61-f7f7f08e3ec7 |  | label | REFERENCE DOCUMENTS: CP17038-LAN-DET-PM-SP-0001 8.3.1
label | ed498bc7-0e9e-4f56-be64-5a23508b84a2 |  | label | INSPECTION/TEST METHOD: Visual inspection
label | a74df776-8ac6-485b-97b5-2badf2d03d56 |  | label | RECORD OF CONFORMITY: This ITP signed
label | 6204e46f-ba3e-4e6c-8af8-3338f6e3200d |  | label | IP
label | 2dac0bc1-dbc0-4375-bc80-2bbf5bfc6662 |  | label | RESPONSIBILITY: Project Engineer/Foreman
text | 5ef62ef3-b234-44c5-8764-daf496206e8d |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Site Cleanliness and Housing Keeping
label | f6d1508a-cd23-48f2-8850-00f6573709fd |  | label | FREQUENCY: Each lot
label | 08f41fde-1015-405c-b8d3-2ae6955edce4 |  | label | ACCEPTANCE CRITERIA: Site will be kept clean and a good standard of housekeeping will be maintained with voids and cavities backfilled and compacted Existing haul roads and pavements are to be kept clean (progressively)
label | b7b31d59-c879-43a8-b889-5cfa10105453 |  | label | REFERENCE DOCUMENTS: CP17038-LAN-DET-PM-SP-0001 2.3.2
label | 84aacec0-e321-4ae1-bd60-31927bc51f78 |  | label | INSPECTION/TEST METHOD: Verify
label | 9d8bfda6-978c-44bf-9e75-179227c40428 |  | label | RECORD OF CONFORMITY: This ITP signed
label | d1b8fc6d-3945-48c9-8115-32bc82461e8b |  | label | IP
label | 4a17af5b-14b7-4a81-916f-586078a5f5f1 |  | label | RESPONSIBILITY: Project Engineer/Foreman
text | f8be4fbc-e2cd-4238-b787-ba88d74a15d0 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 817c4c6c-cb79-4e20-8907-196952cc5220 |  | label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | a21e9f79-f270-4904-ba9c-8b8a471e80c6 |  | text | Name:
text | fa611295-eca9-4605-bf0c-f005e1a51762 |  | text | Position:
text | 2663222f-9291-41c9-912a-74fe5e0ed013 |  | text | Signature:
text | 64fa620e-e368-467c-a773-d4c598751567 |  | text | Date:
checklist-flat |  |  | checklist | ITP 004 - Stormwater Drainage | itp |  |  |  | Yes | ITP 004 - Stormwater Drainage | bf7ca02a-9925-4d01-9a18-cdd1667b919c
checkpoint-status |  |  | checkpoint | 1.1 Check for correct documentation
label | c8dbb0c0-0df2-437c-8d54-317786c7d151 |  | label | FREQUENCY: Prior to commencing any activity
label | 67827efe-93f6-4443-ad58-f5862a900402 |  | label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision
label | de448081-56fb-4ba3-86e0-ef619176a4f1 |  | label | REFERENCE DOCUMENTS: Drawings and Aconex Register
label | 2e30f9d2-6399-4f97-bf4f-d22f0a93235d |  | label | INSPECTION/TEST METHOD: Visual inspection
label | 2b060339-2b5f-4c5b-a125-e39abb9aa813 |  | label | RECORD OF CONFORMITY: Up to date drawing sets and this ITP signed
label | 63039d68-d195-4ada-b395-8d3029f4d6a8 |  | label | HP*
label | 4bf45191-6bf6-41f1-a329-b69ad443b8eb |  | label | RESPONSIBILITY: Project Engineer
text | ef44ee1e-746a-45b6-94b7-b07bf1f6a842 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 Implementation of all measures and controls
label | 25652c0a-264f-4aef-b67c-0e4a39b8d130 |  | label | FREQUENCY: Prior to commencing any activity
label | e90f9589-340b-4d40-8d07-134c4db9c05c |  | label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | 339b427d-94a3-4def-bead-0da3241ab75c |  | label | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | 72285cf4-ec37-4d08-84ae-129e8394f071 |  | label | INSPECTION/TEST METHOD: Visual Inspection
label | fa4bec94-f30f-4c6c-9413-17d32d8116d1 |  | label | RECORD OF CONFORMITY: Site and Office Inspection
label | 30d5a290-b23c-46a8-87bd-543570b2043d |  | label | HP*
label | 7be66fc7-e907-4743-a216-3c2c26aac84c |  | label | RESPONSIBILITY: Project Engineer/ Site Supervisor
text | 3a7a2cc5-3c02-4a56-b434-c73cea8be7b0 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 Definition of the work area (survey)
label | efff0324-5d35-4053-8274-cf3dcb4f4738 |  | label | FREQUENCY: Before commenceme nt of activity
label | b73b0966-879b-4299-9968-0b7693cf290a |  | label | ACCEPTANCE CRITERIA: Work area has been cleared and surveyed (marked on site). Limits of excavation clearly defined. Confirm position of all culverts with the Principal’s Representative
label | e4c846be-43cc-4781-a45f-3391525fc926 |  | label | REFERENCE DOCUMENTS: Drawings CP17038-LAN- DET-PM-SP- 0001
label | 934aee49-ec47-4b7c-bf64-652ef5936e83 |  | label | INSPECTION/TEST METHOD: Visual Inspection
label | d02ce47f-6b27-4920-aeba-6fb5d09444aa |  | label | RECORD OF CONFORMITY: Site Inspection
label | e235a95c-313e-4d24-84df-f7486633960a |  | label | HP*
label | d3afba54-7f81-4f91-895d-c4157d4c455f |  | label | RESPONSIBILITY: Site Supervisor/ Surveyor
text | e06ab53e-68ad-433e-a385-86c53ecd7fcd |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.4 Service Locations
label | 54d4500c-4f36-45e2-b1fe-c9248bfcbfd9 |  | label | FREQUENCY: Prior to start
label | 810dc03a-9d56-40fd-97d9-d14c7f9b9d5b |  | label | ACCEPTANCE CRITERIA: Locate services and mark on the ground within the works, and 10m beyond the boundary of works where applicable.
label | 9758ff5a-ab2f-44c3-8603-9c50ffc47acd |  | label | REFERENCE DOCUMENTS: CP17038-AIR- DET-PM-SP- 0001 cl.8.1
label | c7cfd7cc-8102-4966-8b1f-f6f0aad1cecd |  | label | Cables marked with paint lines and “buried cable” flags installed along cable routes.
label | b9834040-54c4-49d6-b2a7-be1d06699249 |  | label | Services located within the works area to be exposed using approved location methods, in the presence of the Principal’s Representative where required.
label | dc37d51a-acb0-4fd7-bb39-ccb50cd82811 |  | label | Service Locations and Depths recorded by Surveyor where required
label | ab9d6c38-d733-4997-8595-f9624914df24 |  | label | Ensure no mechanical excavation within 3m of Fuel Lines
label | 81ddbeab-98c0-4153-8761-12ee6ee2d568 |  | label | INSPECTION/TEST METHOD: Verify
label | 86e6ebe8-d93f-4585-8349-7e5dbcc8a8fe |  | label | RECORD OF CONFORMITY: Survey Report of Service Locations and Depths
label | e71f1650-42dd-40ff-8ace-e621a83287a8 |  | label | IP / SCP
label | 9b33ed74-2e2c-4d68-b5b0-d954bd32d42e |  | label | RESPONSIBILITY: Project Engineer Project Engineer / Foreman / Surveyor
text | 7d18f174-2fbe-46db-a7d5-ea8dc41636ab |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.5 Excavation Permit
label | c090985d-7aa4-4f8a-8733-9d2ab9856a05 |  | label | FREQUENCY: Prior to start
label | 904bac24-da44-498e-a93b-50e10c4a7529 |  | label | ACCEPTANCE CRITERIA: Excavation Permit issued by APAM obtained prior to any excavation on site.
label | 545518d9-622a-44b2-815b-b7db0e8cef7a |  | label | REFERENCE DOCUMENTS: CP17038-AIR- DET-PM-SP- 0001 cl.8.4.3
label | 8c47d5f9-b378-485e-ae37-1f65ff6c2b72 |  | label | INSPECTION/TEST METHOD: Obtain off Melbourne Airport
label | 891c941e-1e6b-42e0-a28f-6d380779f40f |  | label | RECORD OF CONFORMITY: Proof of permit and this ITP signed
label | 337a72ca-485c-4795-8d60-aec288e472e3 |  | label | HP*
label | 907a4ac6-99a4-416c-b391-6f107dbdf11e |  | label | RESPONSIBILITY: Project Engineer
text | 55306d10-6fb4-4d05-8ad7-0f51b8511e89 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 Pipe Material
label | ab8f711e-0216-4c82-b275-ab0e7d528d34 |  | label | FREQUENCY: Prior to commencement of works
label | 35d488f1-16af-4f78-bb84-5cbb518fc4f2 |  | label | ACCEPTANCE CRITERIA: Pipe Type shall be rubber ring jointed class 4 reinforced concrete pipe. Socket and spigot type.
label | 4b3788b5-e442-42b0-90da-7847d5330d79 |  | label | REFERENCE DOCUMENTS: CP17038-AIR- DET-PM-SP- 0001 cl.7.1.9
label | bc9047c0-e8fd-4121-b32d-0763a403395c |  | label | INSPECTION/TEST METHOD: Verify
label | 14b95670-d7a3-4cb5-b5b0-8214e9fdcdad |  | label | RECORD OF CONFORMITY: Delivery docket or Technical data sheet
label | 2a85e3c7-7c0c-4d6d-83d8-d61734302603 |  | label | HP*
label | 191b8a81-3e7e-4aa0-bd30-1f86ed43d062 |  | label | RESPONSIBILITY: Project Engineer
text | ba7cb5a2-76d6-4a37-8efe-747c35bcba48 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Bedding Material
label | a1a75d29-1c90-4bdc-a117-50c7a184d17d |  | label | FREQUENCY: Each Lot
label | 23816cf9-140c-44f2-af03-31f9955fdec3 |  | label | ACCEPTANCE CRITERIA: Bedding is select fill 20mm class 2 FCR, Bedding and backfill material requirements and a Plasticity Index of 20 max. Material shall be free from perishable matter and lumps
label | f5e403ce-a4c8-43b7-a874-1207566263f4 |  | label | REFERENCE DOCUMENTS: CP17038-AIR- DET-PM-SP- 0001 cl.7.1.3c CP17038-AIR- DET-PM-SP- 0001- Table 701.041
label | ac1ce611-8dd5-454d-966c-3d408e53ff88 |  | label | INSPECTION/TEST METHOD: Verify
label | 0834d9be-4ae7-45c7-8481-c5c241e3a831 |  | label | RECORD OF CONFORMITY: Delivery Docker or This ITP signed
label | e88120c9-fb63-4414-a487-ddcb3991991b |  | label | IP
label | b923ffd7-4183-45d4-b515-a17192de8678 |  | label | RESPONSIBILITY: Project Engineer
text | af1b644d-ddfb-4f99-b694-820b60b46586 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Encasement Material
label | ecd9d6b7-f2b4-4f4c-8564-2a69ce9ad3e5 |  | label | FREQUENCY: Each Lot
label | 45d4383e-d38c-4f8c-ab59-cac460242e2f |  | label | ACCEPTANCE CRITERIA: Encasement Material is 5Mpa lean mix concrete
label | 765af417-2318-46b0-8e70-7aad8a7ebef4 |  | label | REFERENCE DOCUMENTS: CP17038-AIR- DET-PM-SP- 0001 cl.8.2.3.3
label | 85db1b78-979d-4270-b300-109549bf9d0a |  | label | INSPECTION/TEST METHOD: Verify
label | dce4f3df-d153-4b52-915c-54922353aa85 |  | label | RECORD OF CONFORMITY: Delivery Docket or This ITP Signed
label | f77b19e2-7ce9-4156-ad49-f160ea24a0f4 |  | label | IP/TP
label | d823444c-51c5-48df-8abe-0bf43b58267a |  | label | RESPONSIBILITY: Project Engineer
text | d6cfab55-d94c-40df-8a13-e6036161f6fe |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Backfill Material
label | 69b0b968-08ec-41bc-a3f9-c5e4bc1e8ee3 |  | label | FREQUENCY: Each Lot
label | 852beaff-979c-499e-aec9-5397eaceeedd |  | label | ACCEPTANCE CRITERIA: Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform to the requirements of Table 701.041 and Table 701.042.
label | 19d4a114-2e71-4668-adfc-258269bc9476 |  | label | Material to be used for selected backfilling shall be class 2 FCR.
label | 06b97c7c-620d-4e4f-a04e-9b9d3539f06d |  | label | Material to be used for ordinary backfill shall be the best excavated material available on site, shall be free from perishable matter and shall conform to the requirements of Table 701.041.
label | 11448ed4-c2e3-4f8d-853d-8819403e6fd4 |  | label | REFERENCE DOCUMENTS: CP17038-AIR- DET-PM-SP- 0001 cl.7.1.3c Table 701.041 & Table 701.042
label | fc34edab-5b7b-461b-b903-0ec3d1634220 |  | label | INSPECTION/TEST METHOD: Delivery Docket
label | c717d28b-80e9-4a36-913e-8546c2be9b2a |  | label | RECORD OF CONFORMITY: Delivery Docket or This ITP Signed
label | 0f755d1b-4d73-4b90-92b0-3f63ff136cdc |  | label | IP/TP
label | 903e2635-d01d-486f-90d2-8c84e74f0313 |  | label | RESPONSIBILITY: Project Engineer
text | 49cdee69-625c-49d4-8c13-0d7f2d5e3e03 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3.1 Excavation
label | b4d85cc1-a282-4176-a2cb-3ff022bec578 |  | label | FREQUENCY: Each Lot
label | 631def0f-c1c8-4f2c-b104-52fe22eba4bd |  | label | ACCEPTANCE CRITERIA: In accordance with the drawings.
label | a12069cd-9cd0-4e71-89e8-c9985c09af6f |  | label | Culvert Excavation depth shall include depth required to achieve specified bedding depth.
label | 2dba1729-33bf-4cad-8119-4a5bcaa492e6 |  | label | Width of trench shall be nominal pipe diameter + min. 300mm and max. 600mm horizontal clearance to trench wall.
label | 9cadb01d-84ad-4662-8f7e-2e35765f4d03 |  | label | Trench sides adequately shored (where deeper than 1.5m) or benched.
label | 0acff7de-16f9-4ee7-9c33-33bbd8e618d2 |  | label | Rock encountered in trench shall be removed to a depth of 75mm from bottom of pipe, any resulting depression to be filled with 20mm class 2-compacted crushed rock.
label | 214d07ac-28c4-4ebb-baad-5a4936d06756 |  | label | REFERENCE DOCUMENTS: CP17038-AIR- DET-PM-SP- 0001 cl.7.1.8
label | b55b4492-b309-4fac-b5b5-60fe805b4dbd |  | label | INSPECTION/TEST METHOD: Verify
label | ca71c1cf-6517-4bde-b57f-1a1539db9436 |  | label | RECORD OF CONFORMITY: This ITP Signed
label | defc9b6c-b2b6-422a-b5bb-94db7b22130f |  | label | IP
label | 0ccb2176-a4da-4db2-9dab-35538bd1a30b |  | label | RESPONSIBILITY: Project Engineer / Foreman
text | 688e774f-3fb1-4c07-afb1-9eb24d918a16 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Stockpiling Material
label | cf4fce32-c5ba-434b-ba2e-d5dea9c7ab90 |  | label | FREQUENCY: Each Lot
label | 1cc71c2e-43c9-4f0f-b59c-c1756ad750b8 |  | label | ACCEPTANCE CRITERIA: Material shall not be stockpiled or stored on any airside areas without consent of the Principal’s Representative.
label | b9a4024d-7585-4d49-bcb4-a3af38825249 |  | label | REFERENCE DOCUMENTS: CP17038-AIR- DET-PM-SP- 0001 cl.7.1.5
label | a51dcf2e-a09f-413a-a590-e37a6e3f6153 |  | label | INSPECTION/TEST METHOD: Verify
label | b67013ea-a286-4efb-bc83-5f30518a272f |  | label | RECORD OF CONFORMITY: This ITP Signed
label | ca010fb8-bc5f-4e18-8e57-283788b6d46e |  | label | IP
label | 8b618181-537d-4d35-9617-6b8ff5178f07 |  | label | RESPONSIBILITY: Project Engineer / Foreman
text | 5f8ef2d1-34a1-4a32-be03-9379845f2035 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Drainage During Works
label | b565506d-c312-4d57-bc55-2723000fd47e |  | label | FREQUENCY: Each Lot
label | c3961b36-a0ff-499d-8f9b-2c01e9a488c3 |  | label | ACCEPTANCE CRITERIA: Ensure no water is discharged inside taxiway or runway strips, or on aircraft movement areas.
label | 3c132bfe-13a4-46d7-8d1c-a723ba5007fb |  | label | Provide safe discharge of seepage and stormwater and keep trenches and excavations dewatered during the process of construction
label | 8f594901-631f-47fa-a05b-4925b62c2d02 |  | label | Ensure temporary flow diversion is in place prior to obstructing any waterway.
label | 8386ffa9-cd18-4390-b5d2-fbca98777550 |  | label | Obtain written approval from Principal’s representative prior to obstructing or diverting waterways
label | 70139ce4-208f-4d16-a1f0-219e48ef2b06 |  | label | REFERENCE DOCUMENTS: CP17038-AID- DET-PM-SP- 0001 cl. 7.1.6
label | b1ae7ac8-390d-414b-8ae2-0f827b1b1a72 |  | label | INSPECTION/TEST METHOD: Inspect
label | ec0c6a9b-2bdc-4ce6-8c4f-770fc19f22da |  | label | RECORD OF CONFORMITY: This ITP Signed
label | 4a4836bb-e326-4c73-bdf8-691ab40c46e5 |  | label | IP
label | 0150c591-47fb-48a1-8077-c2893cf07639 |  | label | RESPONSIBILITY: Project Engineer / Foreman.
text | 3b29a562-e0e0-4d59-b74c-f5802c659bfb |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 Bedding of pipes
label | 66813162-059c-40fc-b7b4-464953e080ce |  | label | FREQUENCY: Each Lot
label | 1889dafb-d115-4b8d-b33a-0c96d1850c8c |  | label | ACCEPTANCE CRITERIA: Bedding material will be evenly graded 20mm class 2 FCR as per specification and drainage detail drawing.
label | d153fc83-b1cb-4ff3-8ce7-c35da733da05 |  | label | Bedding material shall be place across full width of trench or if non trench condition, to a width of 0.8m greater than diameter of culvert.
label | b49b6f13-cea2-40db-91ef-6222816cf1f7 |  | label | Compacted bedding depth shall satisfy: D<1500mm:100mm, D>1500mm:150mm and support each pipe along entire length.
label | 2edd6222-7712-4207-bd7e-21230f092221 |  | label | Bedding material shall be compacted to a mean density ratio of not less than 85%
label | 3ca9c15c-a5a9-487c-b45b-ead983f2032f |  | label | Testing for bedding to be conducted in lots as described within the Works Specification, undertaking testing for an absolute minimum of 20% of these lots.
label | 6d83bebb-571a-4194-9681-e1c58e75c5c2 |  | label | REFERENCE DOCUMENTS: CP17038-AIR- DET-PM-SP- 0001 cl7.1.9
label | c45631c1-5d26-4d19-b980-4ad1e9fcb36d |  | label | FHPL-RFI- 000249
label | 59bc98f2-01ea-4478-9b21-5bac7746ac52 |  | label | FHPL-RFI- 000249
label | 09789997-7ac7-4b08-b912-e583202738c1 |  | label | INSPECTION/TEST METHOD: Verify & Visual Inspection
label | 2cf69a3b-6e47-4743-93b5-5e9638673b85 |  | label | RECORD OF CONFORMITY: Delivery Docket and This ITP signed
label | 4f1b63ba-3ef3-4c12-96ab-e59d919ebe42 |  | label | IP
label | 9d262c3f-0a00-45d8-a887-d137e3261a6a |  | label | RESPONSIBILITY: Project Engineer
text | 4d5300c0-e3aa-4eac-95ac-f15385fcef88 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 Laying and Jointing of Pipes
label | 3b0e06bd-e687-49da-b65f-e762f3a5c1fa |  | label | FREQUENCY: Each lot
label | ddc56386-acaf-4dd2-bb64-02e0a22bea6a |  | label | ACCEPTANCE CRITERIA: All pipes shall be laid on an evenly graded bed of 20 mm nominal size Class 2 FCR compacted in accordance with the relevant Australian Standards. Bedding material shall be provided and placed for the full width of the trench or, where the culvert is to be placed without trenching, to a width 0.8 m greater than the overall width of the culvert.
label | cdad2185-9d0d-4e68-a16b-2f7306fdaa05 |  | label | Rebate and socket ends of pipe sections shall be placed facing upstream and be fully entered.
label | 40fb6c98-0f1c-48c9-9162-f267809694df |  | label | All concrete pipes unless otherwise stated on the drawings shall be spigot and socket type with rubber ring joints. Deviation at the joints used in such pipes shall not exceed the manufacture's specification. Pipes above this size may be flush jointed with external bands.
label | 0a2c4cc7-b19a-446f-a0c9-02765afc2143 |  | label | REFERENCE DOCUMENTS: CP17038-AIR- DET-PM-SP- 0001 cl7.1.9
label | d3ba784e-aee9-43aa-a8fc-01266318c72a |  | label | INSPECTION/TEST METHOD: Inspect & Verify
label | 412c2543-8691-4588-bc89-a0d05d995e6b |  | label | RECORD OF CONFORMITY: This ITP Signed
label | 89825299-91db-4594-8092-3675ac7ba7fa |  | label | IP
label | 01e28db1-e288-4705-99f4-efd9aa4e1aa9 |  | label | RESPONSIBILITY: Project Engineer
text | 80a56e17-ea74-4760-9a2c-849d8add678c |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3.6 Cutting of Pipes
label | c079ff19-7e40-442f-b1fb-ac280d11c8ea |  | label | FREQUENCY: Each lot (if applicable)
label | c959eef4-dc95-4a15-a267-e246fabc6de7 |  | label | ACCEPTANCE CRITERIA: Where necessary to cut pipes to length or to create penetrations, pipes shall be cut using electric saw, jagged edges removed and bevel cut edges of pipes in accordance with manufacturer’s specifications. Any exposed rebar to be coated with an approved epoxy.
label | c62be391-ad37-4001-b196-38cc4866674a |  | label | REFERENCE DOCUMENTS: CP17038-AIR- DET-PM-SP- 0001-8.2.3.5
label | d60ec594-306c-4ec8-a3c4-b40487770aa2 |  | label | INSPECTION/TEST METHOD: Verify
label | f11f72ba-a0cf-4efe-81d9-882b3f41a8b4 |  | label | RECORD OF CONFORMITY: This ITP Signed
label | 102f5daf-2014-4c2f-a3bb-0d96dc4719d4 |  | label | IP
label | a5200252-8a40-44be-b691-8f74f13c4817 |  | label | RESPONSIBILITY: Project Engineer
text | 211fe948-a641-414e-8182-008673ff99cb |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3.8 Backfilling of trenches
label | d199908b-786d-401d-a73f-81ebd607d38f |  | label | FREQUENCY: Each Lot
label | e1ff63c2-60b0-4235-8b73-4bd75aeaaf2e |  | label | ACCEPTANCE CRITERIA: Ensure floatation of the pipe does not occur at any stage, restrain if required. Backfill placed on both sides of pipe equally. Concrete backfill to be vibrated to fill all voids. Where non trenching conditions apply, selected backfill material shall be placed for the full width of the previously placed bedding material and to a height equal to the lower of 300mm above top of pipe or design subgrade level. Ordinary backfill consisting of the best available excavated material may be used to support selected backfill material.
label | 08ceb657-5de4-4438-8165-ca0f0532e568 |  | label | REFERENCE DOCUMENTS: CP17038-AIR- DET-PM-SP- 0001 cl.7.1.10
label | 3f07d15c-cc22-44e6-9435-59eba35fbc04 |  | label | INSPECTION/TEST METHOD: Inspect and Verify
label | 4b9963ee-c3a1-4db4-9132-62d7a630517b |  | label | RECORD OF CONFORMITY: This ITP Signed
label | 4f4070f2-2344-4635-9fe4-e05ae8818e49 |  | label | IP
label | 082be5e3-8338-423a-aece-038cad847bd4 |  | label | RESPONSIBILITY: Project Engineer/ Foreman
text | 4b15ad01-6270-414e-9603-2f86887f979c |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3.9 Compaction of fill
label | bed01a52-34bc-48e9-8ab0-b7eb08017471 |  | label | FREQUENCY: Each Lot
label | 99199b8b-9e8c-44f6-a163-e2c727763366 |  | label | ACCEPTANCE CRITERIA: Bedding and backfill material shall be placed in layers not exceeding 150mm loose thickness. Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer. Backfill Material size <40mm shall be compacted to a mean value of density ratio of not less than 97% Backfill Material size >40mm shall be compacted using a grading, mixing, watering and rolling procedure.
label | 7fa32561-9de9-4fe8-a355-27e76b00db16 |  | label | REFERENCE DOCUMENTS: CP17038-AIR- DET-PM-SP- 0001 cl.7.1.11
label | 1a62e284-7ecf-48ab-889d-af2e2295973d |  | label | INSPECTION/TEST METHOD: Inspect and Verify
label | c1d683a5-6cf4-48ec-88e3-3da73f79b1a9 |  | label | RECORD OF CONFORMITY: This ITP Signed
label | e7acb66a-3857-4a3f-8a19-64dc2eb4c2e0 |  | label | IP
label | 0f5de9d0-7b76-40ed-acbc-dfdcaa0ff09f |  | label | RESPONSIBILITY: Project Engineer / Foreman
text | 2d738a9b-c86e-4ed0-8fc3-d13c8b974aea |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 4.1 Inspection of Pipes
label | 2fef8c1f-662c-4616-8412-b93caba847da |  | label | FREQUENCY: Prior to constructing pavement
label | 3ebc4a58-adf1-4fda-b31d-f0fad65636d0 |  | label | ACCEPTANCE CRITERIA:
label | 92cf9c20-ee0c-4f34-a427-faf2acd20287 |  | label | REFERENCE DOCUMENTS: Complete CCTV inspection of all newly constructed drainage pipes by FH in the presence of Principal’s Representative.
label | 864acdfd-2079-4601-88ab-2af47f2b6519 |  | label | INSPECTION/TEST METHOD: Verify
label | 8502f391-a3eb-42bc-8c31-c946f038888b |  | label | RECORD OF CONFORMITY: Aconex Corresponden ce
label | 837955e3-66e0-42a1-aca3-146af5930f45 |  | label | IP
label | b3fe6416-c28c-40fd-9299-e48db2780f1b |  | label | RESPONSIBILITY: Project Engineer
text | d29d01ae-1439-4059-b6bc-6c370631840d |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Inspection of Pipes
label | 1764f057-01cf-40a7-90a7-1687d294d243 |  | label | FREQUENCY: Prior to construction of asphalt and concrete layers
label | 3eaa8942-ba43-45dc-a4e1-bb71fb643467 |  | label | ACCEPTANCE CRITERIA: Independent CCTV testing of all drainage lines is to be undertaken and submitted to the Principal's Representative as per the Works Specification.
label | 7614a1f8-1d37-4937-962b-fdcaa4e5a3d5 |  | label | REFERENCE DOCUMENTS: CP17038-AIR- DET-PM-SP- 0001 cl.7.1.13
label | c3e8c480-7852-4ada-8f1c-866ece7aa129 |  | label | INSPECTION/TEST METHOD: Verify
label | 3c52225d-2de3-4b3d-910d-7d4abe7189db |  | label | RECORD OF CONFORMITY: Aconex Corresponden ce
label | a6a9b955-2f2a-43d2-81a4-9b3d0656f7ec |  | label | HP
label | cef0d4f2-bdb3-4b13-abfa-be7a6a26abfa |  | label | RESPONSIBILITY: Principal’s Representative Project Engineer
text | 8a19f890-cec4-4432-9856-44cd90930d4f |  | text | Date Completed:
holdpoint |  |  | holdpoint | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 4.3 Repairs to Damaged Pipes and Box Culverts
label | 17e16626-aa4f-462b-a379-5a5f2471a64f |  | label | FREQUENCY: Prior to Completion
label | 68369ce2-ba4b-4508-91b2-a073d43b2882 |  | label | ACCEPTANCE CRITERIA: Details shall be submitted to the Principal’s representative of the proposed rectification treatments including manufacturer’s product specifications and warranties, the area and thickness of repair treatment, detailed repair procedures, and inspection and test plans.
label | 45a36911-9267-4721-88a5-ca3568899fb8 |  | label | REFERENCE DOCUMENTS: VR Section 701.24(Jan 2015)
label | e3ac58f4-cbd1-4355-b3fe-ea27ed5e15c7 |  | label | INSPECTION/TEST METHOD: Verify
label | 8e7be758-9557-4992-afee-0529b2b334e1 |  | label | RECORD OF CONFORMITY: Aconex Corresponden ce
label | 3d44dd70-8c58-497f-b6e5-9cd8421a56c8 |  | label | HP
label | bfe02bf1-0858-4060-8011-63795209ab82 |  | label | RESPONSIBILITY: Principal’s Representative Project Engineer
text | 9bd6aa7b-5a2a-45b4-9673-f3d6774bba4a |  | text | Date Completed:
holdpoint |  |  | holdpoint | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 4.4 Records
label | c0596c7c-114b-4355-b50b-05e3f7f5c82f |  | label | FREQUENCY: After Practical Completion
label | 2a90913c-deff-4dc1-b520-fbe8293aa95b |  | label | ACCEPTANCE CRITERIA: Levels and alignments recorded in as built report.
label | 60ba8735-b686-4c51-9d78-90998ac841b6 |  | label | REFERENCE DOCUMENTS:
label | 19f6598e-4832-414b-8db9-3fa6032ee56a |  | label | INSPECTION/TEST METHOD: Verify
label | 07266989-4f61-431e-a09c-96294a00081a |  | label | RECORD OF CONFORMITY: Aconex Corresponden ce
label | aa4828d8-774e-41a6-ae67-f8cb32874415 |  | label | IP
label | 0b0ef48f-3fb1-4932-8a75-169b5a8b74f4 |  | label | RESPONSIBILITY: Project Engineer
text | 69d78650-b346-43a2-95ea-1de9577b565a |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 1df03028-233a-4808-a77e-46e4584d9542 |  | label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 76d39671-f058-441f-bab1-54f2735179fd |  | text | Print Name:
text | 406fae19-8e58-4cab-9698-e98e2a2b6e0d |  | text | Position:
text | 18975b20-96a3-4088-876a-7a5c1c7d3ca9 |  | text | Date:
checklist-flat |  |  | checklist | Lot - | itp |  |  |  | Yes | ITP-025 Track Drains | c2f4446e-ee9e-459a-a025-a3c6b16215e4
checkpoint-status |  |  | checkpoint | 1.1 Check for correct documentation
label | aac74f24-8208-49e2-949e-5f8890835e15 |  | label | Prior to Commencing any Activity
label | 2c4a8252-a34a-4878-b1e3-cf258f9e83a7 |  | label | "Drainage design satisfies requirements of all relevant catchment and drainage authorities, a copy of all drainage work approvals are to be forwaded to the superintendent "
label | f34a4cd3-6d82-4e29-91e1-78bd03945a41 |  | label | Drawings and drawing registers Visual inspection
label | b9fd45ff-17b1-44aa-90c7-9abc314788a6 |  | label | This ITP signed off
label | 54ca8e1b-29a1-46de-90db-a1c7d038d774 |  | label | HP*
checkpoint-status |  |  | checkpoint | 1.2 Implementation of all measures and controls
label | 653cc047-f26b-4cae-8653-f06fea8f668e |  | label | Prior to Commencing any Activity
label | 435b1925-f2b2-4b5c-b01d-73b21b31299c |  | label | All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | 92ba0523-502c-4618-a15f-ff56f12c4143 |  | label | PSP, EMP, TMP, JSEA, SWMS, WP Visual Inspection
label | 3cf5e8ee-e9bb-40df-8197-8305e518097a |  | label | This ITP signed off
label | eb884b8b-2122-41f4-8011-4d382604dd0e |  | label | HP*
checkpoint-status |  |  | checkpoint | 1.3 Approval of drainage design
label | d48cfb29-5772-4e6b-a934-fe90f0d87239 |  | label | Prior to commencing any activity
label | ab52e561-0860-4dac-b8de-e6d6f8228cb2 |  | label | "Drainage design satisfies requirements of all relevant catchment and drainage authorities, a copy of all drainage work approvals are to be forwaded to the superintendent "
label | ca37e1ae-3f4a-479d-8f9e-477207b08071 |  | label | Plan Aprroved for Construction Visual inspection
label | 4bd559b9-0f66-4552-bf43-396522ea89f4 |  | label | This ITP Signed Off
holdpoint |  |  | holdpoint | Hold Point Sign Off
checkpoint-status |  |  | checkpoint | 1.4 Materials Check
label | 14579821-5566-442b-b1ff-da94de612fd7 |  | label | Prior to commencing any activity
label | 41584a77-0dd5-465a-8a9c-50fccf5ee2aa |  | label | "Ensure drainage pipes are of correct classification and are without damage Check triangle drains are of adequate quality, and are design according Ri57A rail profile"
label | 5d064a9f-501c-43b5-9021-d2d1c9cebe94 |  | label | "VRIOGS 005.2 cl 10.1 TS 9021A" Visual inspection
label | 477860b0-2bcd-4053-925b-2d608d7a266d |  | label | This ITP Signed Off
label | 53eac027-f57c-4560-8368-ae11c7b34af8 |  | label | HP*
holdpoint |  |  | holdpoint | Test Report Request
checkpoint-status |  |  | checkpoint | 1.5 Excavation Permit
label | d9152562-a5b7-4953-9c13-694a58dce8aa |  | label | Prior to commencing any activity
label | 03263237-0636-49ac-a32f-88e1f135542b |  | label | "Ensure that excavation permit has been approved, detailing tasks and associated risks Depth of trenches shall be taken into consideration, >1.5m requires a worksafe permit"
label | ac59320d-04fb-427f-8d5b-a1843deee680 |  | label | Fulton Hogan Procedure Visual inspection
label | 0635ee99-f9b1-4b92-8653-5402ef2ae4c3 |  | label | This ITP signed off
label | 8144ab7b-9b9b-49ee-b8ba-212a12af69d7 |  | label | HP*
checkpoint-status |  |  | checkpoint | 2.1 Set out drainage
label | 129d8de5-1854-42f0-9f29-358bc3aa7ab1 |  | label | Prior to commencing any activity
label | 5b96f67c-9d3c-44d2-82b1-b58d584e805e |  | label | "The position of all drainage lines are to be confirmed with the superintendent Track drain locations are to be identified"
label | db0d7bcc-fcd4-49c5-8442-d07bd61a7dd9 |  | label | Design Drawings and Register Visual inspection
label | 605461ac-efca-49f7-8c09-b781e2d6d543 |  | label | This ITP signed off
label | 068caa46-2949-42ef-abed-0e8d42fd128d |  | label | HP*
checkpoint-status |  |  | checkpoint | 2.2 Excavation (pipes)
label | 5c16ee54-cae1-4cab-aec0-bbf045972c85 |  | label | Each Trench
label | be39a37c-3baf-4d3a-9612-bd2cb9533232 |  | label | " Trenching to allow for minimum clearance depth of 100mm below UPVC pipe, and 15mm from bottom of rail to surface of pipe Track drains usually have invert for pipes at 400mm depth, with floor of pit 10mm deeper. "
label | ce7c0d32-b1bc-4ce4-8421-dd8927339876 |  | label | "STD 9021 VRIOGS 005.2 Pt4 cl 10.1" Visual Inspection
label | 6e659089-6fc8-4bff-bd53-7a1084e02716 |  | label | This ITP Signed Off
label | 1e8acf20-e14b-496e-b2af-2149783db1a8 |  | label | IP
checkpoint-status |  |  | checkpoint | 2.3 Bedding
label | 4d073e36-abac-43a4-bb4c-771f1a5eb0da |  | label | Each Lot
label | a7594d12-6b6d-4ced-be2c-707614475f6b |  | label | Class 2 crush rock shall be compacted to refusal of 100mm minimum thickness
label | 2d17bc65-f9cc-4fda-b268-ce9d7bef41d5 |  | label | STD T9021A Visual inspection
label | 40cc8b1f-9ccd-4bc0-b005-f48bc321d9f5 |  | label | This ITP signed off
label | 78bda7c4-2323-4972-b28b-4aa86642eff4 |  | label | WP
checkpoint-status |  |  | checkpoint | 2.4 Joining
label | ac63f00b-6898-442a-904a-4795fb9777c6 |  | label | Each Lot
label | a9961aa3-b9e4-4f9e-97da-a9adfd836633 |  | label | UPVC pipes shall be joined using appropriate plumbing adhesive
label | 660cd06e-5309-4147-87f1-99cd86220ade |  | label | VRIOGS 005.2 Verify
label | e406b1d7-71eb-4f4b-a716-6ca1e8e3e6bd |  | label | This ITP signed off
label | 79b5c959-d05a-4bb4-8e44-855f1abd7db8 |  | label | WP
checkpoint-status |  |  | checkpoint | 2.5 Approval of installation
label | 226cf36f-4db4-408b-82ce-5df147c47af4 |  | label | Each Lot
label | b502c949-480e-4fe1-b08c-2f1cda203402 |  | label | Each drainage line shall be inspected and position noted before placement of any backfill or concrete
label | 2fbf68d6-be47-4d4c-9dc7-9d0857b21e91 |  | label | "VRIOGS 005.2 Pt 4 cl 3.4.1" Verify
label | 1069fe94-8b9b-4e99-a161-d86d73a94ba5 |  | label | This ITP signed off
holdpoint |  |  | holdpoint | Hold Point Sign Off
checkpoint-status |  |  | checkpoint | 2.6 Track Drain Installation
label | 5f7fc3df-b010-4e2c-b653-7479aba54678 |  | label | Each lot
label | 12600838-2eb8-48a0-8654-a29439e3e54d |  | label | Track drains shall be welded to designated positions, and cleaned of all weld splatter . Weld shall be sealed after installation
label | b067dc5f-3a1a-493a-9f03-3be08c085098 |  | label | STD T9021A Visual inspection
label | ad4b3095-eec6-4329-b7c1-faef11c7e845 |  | label | This ITP signed off
label | 0c7da17a-7518-4b97-b504-cfdf4bfd7b34 |  | label | IP
checkpoint-status |  |  | checkpoint | 2.7 Concrete Pour
label | 91ed13c3-a138-429e-9bb3-7ab3d7e8235c |  | label | Each Lot
label | 414f19d7-31ab-4639-afa7-8e6ed4611659 |  | label | Ensure correct heights of sub grade, as to allow for minimum thickness 150mm concrete, to be poured in same period as track slab
label | 2fdf532e-a3c9-43d6-9bc9-3a3ef9207da6 |  | label | STD T9021A Visual inspection
label | b46f4881-3bd9-4795-a30e-49b1f0046c00 |  | label | This ITP Signed off
label | e36862e1-e760-40c0-bc9e-acdf42d79f10 |  | label | IP
checkpoint-status |  |  | checkpoint | Final Inspection
label | 1550596f-d6cb-47bf-97fb-716670a112cc |  | label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | b9756d11-c1d2-4bdc-a4f4-b1b4a8f80769 |  | text | Name:
text | 27234743-dc2c-49e1-9620-b812b90aa25c |  | text | Position:
text | 27ff3c92-87e2-470f-95b3-5a83ca9e64be |  | text | Signature:
text | 07380a3c-99d8-4c49-962b-8c14cf258e85 |  | text | Date:
checklist-flat |  |  | checklist | ITP 016 - Kerbing Works | itp |  |  |  | Yes | ITP 016 - Kerbing Works | c660d06d-c096-4dda-95ae-5543db7956cf
checkpoint-status |  |  | checkpoint | 1.1 Check for correct documentation
label | a63e0008-aab2-4086-aa6f-49a85c406ec1 |  | label | FREQUENCY: Prior to commencing works
label | 697ca51a-01ea-4d16-9210-cd9e5d9a0759 |  | label | ACCEPTANCE CRITERIA: Current revision drawing is being used including the subcontractors copy. Current revision to be obtained via Aconex.
label | 7558f4af-83db-4439-a4cd-2f010f6664c7 |  | label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | b3ff6558-8cd9-4018-aa09-510e32c01073 |  | label | INSPECTION/TEST METHOD: Visual inspection
label | aee515d3-dffb-4942-8a49-d6d06b3422b5 |  | label | RECORD OF CONFORMITY: This ITP signed
label | bb22b41e-fc06-4152-a866-bae26c703401 |  | label | HP*
label | a22d837a-a329-4fa5-b845-043f10316c02 |  | label | RESPONSIBILITY: FH Engineer
text | c6897617-3e70-411c-ab6d-4b9dae90941a |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 Setting out for miscellaneous structures
label | 30ce0dd8-1541-44e1-9c18-0ef6ef81d8c8 |  | label | FREQUENCY: Prior to Start
label | c95e6b8f-a41e-496b-bb74-17f2903065ea |  | label | ACCEPTANCE CRITERIA: Set out in accordance with JACOBS Construction Drawings.
label | 060fc8e0-5735-43f9-a560-eabef4102881 |  | label | REFERENCE DOCUMENTS: Drawings
label | 1ea742c3-09da-4460-92f2-c9f75b018044 |  | label | INSPECTION/TEST METHOD: Verify
label | b33ea8bf-e4c7-4fcb-b59f-3ae59829e62d |  | label | RECORD OF CONFORMITY: Survey Report
label | 0fbed60b-7042-4a23-8fa2-0b0eb3b0d4cb |  | label | SCP
label | 58015630-2c03-4600-86e8-145337160080 |  | label | RESPONSIBILITY: FH Engineer, Surveyor
text | 5b17e23f-f801-4e12-9905-33709f56eb0f |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 Supply and Ordering
label | c36e5ba1-3afb-4c4b-bcc5-101f5f47f9b7 |  | label | FREQUENCY: Prior to Placement
label | 1526c1ce-b926-4a56-8364-054b0ef3b941 |  | label | ACCEPTANCE CRITERIA: Machine placed concrete – in accordance with the prescription ordering requirements specified in AS1379, and with a maximum aggregate size not exceeding 20mm, in accordance with AS 2758.1
label | b0b02f51-8d86-4c5d-9c74-4029727c6472 |  | label | REFERENCE DOCUMENTS: AS 2876, Section 4.3.2(b)
label | 937c2c4e-0902-42f7-a1d7-2fcf4f6afe8c |  | label | INSPECTION/TEST METHOD: Verify
label | e814713b-6df6-4b64-aad7-c345028f6eb5 |  | label | RECORD OF CONFORMITY: Dockets
label | bc6a497d-266f-4731-9ac2-0a3d4f103d8f |  | label | IP
label | eb82547e-5eff-4fe8-8c93-555df9851bbe |  | label | RESPONSIBILITY: FH Engineer
text | 95b05576-e764-46c8-a4a1-02cc45e5276f |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3.1 Bedding Material Requirements
label | 37e150d6-e362-4214-b024-345c3db35100 |  | label | FREQUENCY: Prior to placement
label | a830014a-b9ab-410e-8160-0308dc908ff9 |  | label | ACCEPTANCE CRITERIA: Where the Kerb and channel are not placed on the extended pavement subbase, the bedding material shall consist of adequately compacted material in accordance with the requirements specified by the authority responsible for the road pavement construction. The minimum compacted thickness of bedding layer shall be 7mm and shall extend at least 150mm beyond the back of kerb.
label | 2fbe8114-360e-478d-b513-dd242f68483a |  | label | REFERENCE DOCUMENTS: AS 2876, Section 8.3
label | 193d1d60-3aa0-44e8-995e-f73090e375bc |  | label | INSPECTION/TEST METHOD: Verify
label | e172844f-0556-440d-a998-6c290a029fb6 |  | label | RECORD OF CONFORMITY: Test Report
label | 2eecc5f8-2a42-4766-9f62-16fbe501c080 |  | label | IP
label | 3e12a284-e717-4107-895f-ba756ee14cba |  | label | RESPONSIBILITY: FH Engineer
text | b53429d5-91ee-4544-8da7-898938fd5e6f |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 4.1 Tolerances
label | 3dd7bc9f-2e16-456b-a34d-3399d586dc4a |  | label | FREQUENCY: Prior to Works
label | c37e87ff-4e14-4211-9ad9-7b18ac42727c |  | label | ACCEPTANCE CRITERIA: The finished concrete shall not vary from horizontal alignment or level by more than 100m at any point. The finished work shall not deviate at any point more than 5mm under a straight edge 3m long. Deviation on vertical curves shall not exceed 5mm in 3m from the true vertical curve. Profile dimensions shall not different by more than 5mm except that the overall width shall not differ by more than 15mm.
label | 278ee300-4287-4dcf-bb8f-ea5f5e742eb4 |  | label | REFERENCE DOCUMENTS: AS 2876, Section 9 (a), (b) & ©
label | 57ddb15f-2d04-4a19-97c2-db1979ff6d94 |  | label | INSPECTION/TEST METHOD: Verify
label | 451b72e6-73c7-4400-84c9-1eadafa57f2c |  | label | RECORD OF CONFORMITY: Survey
label | 92441298-4eb0-4f4d-a482-e144a2c4a13c |  | label | IP
label | 0ca86a25-f5c5-4d8f-b0cf-eaeb40747d31 |  | label | RESPONSIBILITY: FH Engineer/ Surveyor
text | bda72dc6-6c08-4cce-8cdf-bb545d2de85d |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 5.1 Finishing
label | ce34cd17-4a08-46cb-8e21-9284cd349fb6 |  | label | FREQUENCY: Prior to use of Curing compound
label | 43eaf28f-7570-4454-8207-b555e297234b |  | label | ACCEPTANCE CRITERIA: Contractor to ensure all concrete surfaces shall be finished by appropriate method to achieve specified dimensions, falls, tolerances, or similar details relating to the shape and uniformity of the surface and texture of the surface
label | 6568a131-cebf-450a-bb77-e80a109a9d4f |  | label | REFERENCE DOCUMENTS: AS 2876 – Appendix A
label | 7dbe8b8f-58ec-49c2-9c98-9560c7d55131 |  | label | INSPECTION/TEST METHOD: Verify
label | ca40b9f5-1b19-461e-be43-93e35cc148d1 |  | label | IP
label | 77ec6daa-848c-42c2-bf1c-1c5a8941372e |  | label | RESPONSIBILITY: FH Engineer/ Principal’s Representative
text | 097bf663-ce44-497c-b09e-1e18e40f4b46 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Spacing
label | eb3e7e82-8c4e-44bb-8a00-98c490058696 |  | label | FREQUENCY: Each Lot
label | 94d09a86-e1b7-41e9-9384-fdf54d62c383 |  | label | ACCEPTANCE CRITERIA: Shrinkage control joints shall be formed at 2.5m spacing
label | 623fbe06-5545-4964-92f2-4058c6f48f63 |  | label | REFERENCE DOCUMENTS: AS 2876 – Section 11.2.1
label | 12fcdcfc-7045-403b-a46f-d222a7b9287f |  | label | INSPECTION/TEST METHOD: Verify
label | d235d1d5-a91e-439e-b733-5b336ed27400 |  | label | RECORD OF CONFORMITY: This ITP signed
label | bb13e465-47bc-4299-bbca-598cb7c5380d |  | label | IP
label | cc8c4a0c-9e24-4af9-925f-ccf4d715972c |  | label | RESPONSIBILITY: FH Engineer/Surveyor
text | 5c61b84e-2b17-4a1f-9b62-291c748fb082 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | b18960c1-9ad6-46c6-99c7-3e31c67be621 |  | label | On behalf of Fulton Hogan, it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 45229960-0aca-449d-85de-852fd85a04b2 |  | text | Print Name:
text | af3a4585-6f2e-4c04-81f5-2798add43684 |  | text | Position:
text | da02915f-b01a-4382-b53a-3ddc7fe80171 |  | text | Date:
holdpoint |  |  | holdpoint | Add Signature / Request Sign Off
checklist-flat |  |  | checklist | ITP 010 - Placement of Unbound Flexible Pavement | itp |  |  |  | Yes | ITP 010 - Placement of Unbound Flexible Pavement | c6b6b0c6-9c1a-47b3-b1fa-b00fea4be08d
checkpoint-status |  |  | checkpoint | 1.1 The current revision drawings are being used including subcontractors’ copy
label | 924dd866-d4fb-4419-bfaa-71fb3b0c517a |  | label | FREQUENCY: Prior to commencing works
label | 9f140bb8-d1f2-4396-8137-1be1ec962770 |  | label | ACCEPTANCE CRITERIA: Current revision drawing (via Aconex) is being used including the subcontractors’ copy.
label | 1862ab94-c93b-4ea9-a166-8e28e86d322b |  | label | REFERENCE DOCUMENTS: Aconex
label | 99876fd2-e686-49ab-973f-8b938231800e |  | label | INSPECTION/TEST METHOD: Visual Inspection
label | deeb4c70-6b88-4247-9a83-57bb9a7fba02 |  | label | RECORD OF CONFORMITY: This ITP signed
label | c599b1df-eee0-448a-8e68-84f7908142dd |  | label | IP
label | eaedf88b-8857-4d7a-8366-09c152fa15be |  | label | RESPONSIBILITY: Project Engineer
text | c313451c-dac7-48fc-9d26-3eeb02b73640 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 Material classification
label | 57ef3f49-0112-4aac-8412-2322cae8e2db |  | label | FREQUENCY: Prior to commencing works
label | 5ee5af9e-fa01-4143-b9e9-b74f2b464cbb |  | label | ACCEPTANCE CRITERIA: Mixes registered by VicRoads as ‘General’ may be used in the construction of roadworks. Mixes registered as ‘Conditional’ may be used provided the conditions are complied with. Mixes registered as ‘Experimental’ shall only be used with the written permission of the Principal’s Representative.
label | c78f0fc7-06ce-4c8b-8082-a1a2354e3c12 |  | label | REFERENCE DOCUMENTS: CP17038-LAN-DET- PM-SP-0001 Cl.3.3 VR Section 812 VR Section 820
label | d1458603-64ad-41af-b9d2-39ea86967e1f |  | label | INSPECTION/TEST METHOD: Verify
label | 4f285799-2dd2-418c-ae9f-599f6acfff53 |  | label | RECORD OF CONFORMITY: Aconex Notification
label | 0eb83236-309c-4093-a2ba-ce0f79ac3317 |  | label | AP
label | aa21b590-65c2-438a-a6ac-017b72296260 |  | label | RESPONSIBILITY: Project Engineer /Principal’s Representative
text | 8d5fcf27-0cc8-45c5-a91e-36935b272a69 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 Implementation of all measures and controls
label | 9ab379b6-00a2-4407-ade9-0b51e6f715fd |  | label | FREQUENCY: Prior to commencing any activity
label | 3907a5cb-8008-436f-a851-e14babc58fd3 |  | label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP`
label | ce5e1e23-e6dd-44b9-8680-29d9d9bdc4ac |  | label | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | 3f90eefe-fa78-4a34-b223-37439082c751 |  | label | INSPECTION/TEST METHOD: Visual Inspection
label | 2fe62e45-adf2-4467-ac75-ff05d0b01e2c |  | label | RECORD OF CONFORMITY: This ITP signed
label | 258673af-8db6-4118-a299-451dd46efc95 |  | label | HP*
label | 504c965e-4723-403e-8c9d-315c0ce64414 |  | label | RESPONSIBILITY: Project Engineer/ Site Supervisor
text | f62bc401-5b49-4d48-af4e-7f9b116b4503 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.4 Plant and Equipment
label | 4ca85538-d4fb-40b7-86ba-777c981294bf |  | label | FREQUENCY: Prior to placing FCR
label | 8c00f194-7900-4cf0-9bb7-a7d450f0e2c3 |  | label | ACCEPTANCE CRITERIA: Plant and equipment used in the Works are appropriate to achieve specification requirements
label | 4bf32ecc-c116-4f4d-9b51-9cdcebc56fa2 |  | label | REFERENCE DOCUMENTS: N/A
label | 734ed5e4-5efb-470a-a7d8-f0cc91d1d7d1 |  | label | INSPECTION/TEST METHOD: Visual Inspection
label | 2bb47640-d60f-42e1-b067-e4b948d574d2 |  | label | RECORD OF CONFORMITY: This ITP signed
label | 0ec5737a-ca1f-4e06-b023-78edb654425f |  | label | IP
label | 7ebbdc01-ffc8-43db-8fba-7fd76bc21564 |  | label | RESPONSIBILITY: Project Engineer
text | 9cc32d6a-607e-4314-a9d2-cb448237edf1 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 The commencement of construction of base and subbase
label | aae6e54c-216a-4c75-9607-1f5476aaa482 |  | label | FREQUENCY: Prior to placing subbase
label | 0dac1841-03d4-4ac1-9e32-bbae6d93e4d1 |  | label | ACCEPTANCE CRITERIA: Underlying ITP signed off Identifying and removing soft areas to a minimum of 300mm depth. Underlying layer shall be clean of all foreign matter. The edges of previously placed materials shall be watered. Proof roll underlying layer prior to commencing
label | 2f5f5d41-e3b7-4d89-a171-b00f378ab17e |  | label | REFERENCE DOCUMENTS: Cl 2.6.1 or Vicroads Section204
label | 5a54171f-2e87-437b-84f4-ff9f0f397f25 |  | label | INSPECTION/TEST METHOD: Verify
label | 55841282-09ee-4a81-9c99-6c7f08b9ffef |  | label | RECORD OF CONFORMITY: This ITP signed
label | 082dfaea-7418-4f96-a8c6-a8d3a637ce0f |  | label | IP HP*
label | c8dc48bf-2c34-4b03-b35f-70dfdf83af4a |  | label | RESPONSIBILITY: Project Engineer /Principal’s Representative
text | d9acf6bf-876d-49d3-8287-64149d39ef97 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Place and compaction of base and subbase
label | f7b141da-d89f-408e-9764-7e5a889b15da |  | label | FREQUENCY: Each Lot
label | 92a1a007-a2e6-4c4f-bece-dae784907adc |  | label | ACCEPTANCE CRITERIA: Material during compaction shall have a moisture content of not less than 85% of optimum; Pavement base layer does not exceed 150mm and Subbase layer does not exceed 200mm; Underlying layers are not disturbed during placing, compacting and trimming;
label | 6c7e28b4-6989-4df5-853a-6b5bc8a58977 |  | label | REFERENCE DOCUMENTS: CP17038- LAN-DET- PM-SP-0001 cl. 3.8(a) and (b)
label | 35140593-d1fb-44d5-9c75-f90c92ecb8b5 |  | label | INSPECTION/TEST METHOD: Verify & Visual Inspection
label | 113b99a1-33ab-4b24-888f-a6925a5ca446 |  | label | RECORD OF CONFORMITY: This ITP signed
label | 5526985e-e12c-4406-91a6-e9a6690ecce6 |  | label | IP
label | 73980352-e50d-4c8b-aa7b-cb931a577a50 |  | label | RESPONSIBILITY: Project Engineer
text | c787df4e-a7a3-49fc-bf84-e001823df512 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Conformity with Drawing
label | 2d3d2556-ba5f-418b-ad4a-cb298284bf97 |  | label | FREQUENCY: Each Lot
label | 6d0c40b8-1c4f-4d4c-ab8e-993d41d3b481 |  | label | ACCEPTANCE CRITERIA: Width of each side of the pavement shall not be less than the specified offset width or more than 50 mm outside the specified offset width when measured at right angles from the centre line or design line. Where pavement is to be constructed to the lip level of kerb and channel, it shall be constructed flush with the lip of the channel or not more than 5 mm above. Any material that has been compacted and then trimmed from the compacted surface to conform to the correct level or thickness as shown on the drawings shall not be re-used in the pavement construction without the approval of the Principal’s Representative.
label | 1f4e3f31-11b9-46e6-aec1-ea662c2399c7 |  | label | REFERENCE DOCUMENTS: CP17038- LAN-DET- PM-SP-0001 Cl 3.6
label | b37ddcbd-fb42-423d-9abb-0e91c63ba564 |  | label | INSPECTION/TEST METHOD: Verify
label | adb692aa-7cc0-46f1-91c1-28a3e0a88e06 |  | label | RECORD OF CONFORMITY: This ITP signed
label | a1b8c7bc-7ce7-4689-8163-39e51b68cad2 |  | label | IP
label | a8a8200f-70e4-4a29-8a19-29e23b2fcb90 |  | label | RESPONSIBILITY: Project Engineer
text | 92961263-cbf2-45ef-8b11-1f6c6def607e |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Jointing
label | 5cb34c79-f413-4057-976c-d52dbf87811d |  | label | FREQUENCY: Each Lot
label | 60772433-1bc6-4d05-9f75-1dae10c06a32 |  | label | ACCEPTANCE CRITERIA: Transverse Joints are offset from one layer to the next not less than 2m. Longitudinal joints shall be offset from one layer to the next by not less than 150 mm. Longitudinal joints shall be located within 300 mm of the planned position of traffic lanes lines or within 300 mm of the centre of a traffic lane.
label | a2033e26-e3d1-44e3-9b19-73c552280484 |  | label | REFERENCE DOCUMENTS: CP17038- LAN-DET- PM-SP-0001 Cl3.7
label | a619f17b-aa15-49d5-a772-2ac4e371731f |  | label | INSPECTION/TEST METHOD: Verify
label | 696b77af-8c37-4fbe-84ab-fc56fd3258e7 |  | label | RECORD OF CONFORMITY: This ITP signed
label | 5ba93826-cca2-4876-b066-76af9e730fa0 |  | label | IP
label | 4356839b-7d98-4438-b403-c0239d29458f |  | label | RESPONSIBILITY: Project Engineer
text | 5e6f5396-98d5-409d-9df0-60de9140ab20 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 Test Roll
label | fd0713d6-2524-4dbf-a201-9461d6c66519 |  | label | FREQUENCY: Each Lot
label | bcef6111-27bb-4b5e-b2db-4051a1c17463 |  | label | ACCEPTANCE CRITERIA: WITNESS POINT: Principal Rep present during all test rolling.
label | f210ac27-8d86-4f04-8324-1c372067b3ba |  | label | Test rolling requirement shall be without visible deformation or springing
label | f74f54f5-247b-4bb7-b602-cb9b86e974f3 |  | label | Ensure clearly signed on Test Roll Record or Plan
label | a11f77cb-768e-426a-9a17-89537723a988 |  | label | REFERENCE DOCUMENTS: VicRoads Section 173 CP17038- LAN-DET- PM-SP-0001 Cl. 3.8(b)(iv)
label | d604bdb2-4292-4d02-9b51-28fab1ac657d |  | label | INSPECTION/TEST METHOD: Visual Inspection
label | 05d1cf1f-7fd7-4643-a592-af37622dadb5 |  | label | RECORD OF CONFORMITY: This ITP signed
label | cb72c997-d28f-4ad3-874a-e3c709245cff |  | label | HP
label | 0fade274-83c6-4f4c-bc89-0a0f542c77a7 |  | label | RESPONSIBILITY: Project Engineer / Principal’s Representative
text | 9f7dc28a-8038-40eb-880d-12473d1a8c80 |  | text | Date Completed:
holdpoint |  |  | holdpoint | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 2.6 Compaction Testing
label | f81ca7f6-496b-455b-97d8-a0ec98934038 |  | label | FREQUENCY: Each Lot until 3 consecutive comply – Then reduce to 1 per 2 lots
label | f6887b6c-95ca-471c-98b2-d978fb3f20e0 |  | label | ACCEPTANCE CRITERIA: Material during compaction has a moisture content >85% OMC and maintained until test rolling completed.
label | 01966988-d09a-4d1a-940b-814fcfb2cd26 |  | label | Compaction Scale B: Lower Subbase layers = CDR% modified (six tests): >97%
label | 11cb15cd-6352-49e9-a6e2-bfda0398537f |  | label | Compaction Scale B: Upper Subbase layers = CDR% modified (six tests): >97%
label | 488a5cc4-149e-4a1a-9ab3-58f5ed0b555c |  | label | Compaction Scale B: Base Layer directly beneath bituminous surfacing = CDR% modified (six tests): >98%
label | 1b4c604f-0e19-44e2-80ac-155263c59ab9 |  | label | Compaction Scale B: Other Base Layers = CDR% modified (six tests): >98%
label | 1b949629-b1a6-48aa-b4a8-7294047b55f8 |  | label | REFERENCE DOCUMENTS: CP17038-LAN-DET- PM-SP-0001 cl. 3.8 & cl. 3.10 & cl. 3.11(b) Table: 304.081 304.082 304.111
label | cc347038-fd36-4585-bf94-f332d299ef38 |  | label | INSPECTION/TEST METHOD: Testing
label | 7ce25a13-3dbe-4c53-a3b5-db7cb72a96e1 |  | label | RECORD OF CONFORMITY: Test Report
label | 7723e351-6573-4704-bd46-fcbb19219520 |  | label | TP
label | b82699c8-355b-4f80-b75f-a00a263341d6 |  | label | RESPONSIBILITY: Project Engineer
text | 4b26c844-b2e5-496c-8d7e-650035e51770 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.7 Post Compaction Testing
label | 6db373d9-5c28-42ac-bc2e-436c199b856b |  | label | FREQUENCY: Refer to table 304.111 for various minimum frequency or testing for Grading and PL
label | cd72d3f6-1e10-49d9-ad2f-b0aca90b67d0 |  | label | ACCEPTANCE CRITERIA: Scale B requirements: Grading, PI
label | cdffd4f0-e26a-475d-9a3f-6c028a2a5344 |  | label | REFERENCE DOCUMENTS: CP17038- LAN-DET- PM-SP-0001 cl. 3.8 Table 304.101 304.102
label | efec1c78-3136-4d55-b88d-57cf4dcd0d9d |  | label | INSPECTION/TEST METHOD: Testing
label | f5846202-efff-432a-8616-cb75b0ca0f65 |  | label | RECORD OF CONFORMITY: Test Report
label | 84542046-ae64-4f51-8552-48a5ef7433bc |  | label | TP
label | f2ba8d94-2281-4f3f-8d44-590a8eea560c |  | label | RESPONSIBILITY: Project Engineer
text | 850cb0f0-2cd0-40cb-9f30-5b45684d7aaf |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.8 Conformance and Tolerances
label | c725c10e-25c8-4765-b856-b623fff29d3e |  | label | FREQUENCY: Top of each pavement course
label | 6cbe9755-0c70-4175-bc64-31eabf9e8ef6 |  | label | ACCEPTANCE CRITERIA: Pavement course (base, upper subbase, or lower subbase) width and surface level conform with drawings. Scale B surface level is measured. Mean value and standard deviation complies with table 304.062.
label | 17fa2ee6-19f6-4a6d-93f9-ade3e60d9051 |  | label | Min. number of level measurements per lot = 40 for Scale B. No point on the surface of any pavement layer shall vary by more than 8 mm from a 3 m straight edge, or 10 mm from a 6 m straight edge, placed in any direction. Refer to CP17038-LAN-DET-PM- SP-0001 cl. 3.6c for details of thickness tolerances.
label | 0df6b709-9f2c-4a7e-806f-9c87315bc1fc |  | label | REFERENCE DOCUMENTS: CP17038- LAN-DET- PM-SP-0001 cl. 3.6
label | 1e772b90-ee5e-46af-8882-8e4e68c48f84 |  | label | VicRoads 304.06
label | 370d346b-bcbc-4321-866c-ecd719f2be4f |  | label | Table 304.062 304.064
label | edafddbe-a805-4b60-83d3-1f6b328f75c9 |  | label | INSPECTION/TEST METHOD: Survey
label | 62750989-7cff-4b54-be0c-8adad66cc263 |  | label | RECORD OF CONFORMITY: Survey Conformance Report
label | 6920f259-4e03-4622-a6cd-c7d2b3a32478 |  | label | SCP
label | 7b5d0b73-a206-4674-af51-89cd734927c8 |  | label | RESPONSIBILITY: Project Engineer
text | b217ebb2-aa22-4eba-90f4-91ba8f1095f8 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.9 Preparation of Granular Pavements for Bituminous Surfacing
label | 5bf777d1-625e-4e22-ab1f-449a63a69117 |  | label | FREQUENCY: Base’s finished surface
label | 8f62648e-17a3-4c53-a989-8b2cfa4936c7 |  | label | ACCEPTANCE CRITERIA: The Contractor shall prepare for bituminous surfacing the lengths, widths and areas specified or shown on the drawings for bituminous surfacing plus an additional 0.3 m on sides where there is no concrete edging. The surface of the shoulders and verges shall be matched to the finished surface of the prepared pavement.
label | f64c2d57-becd-4438-9230-9daa3b2e8dbb |  | label | REFERENCE DOCUMENTS: CP17038- LAN-DET- PM-SP-0001 cl. 3.12
label | a4e5f39b-3de0-4f95-96e4-d119bcea9f2c |  | label | INSPECTION/TEST METHOD: Verify & Visual Inspection
label | aa036db3-554c-4571-a9fa-9338f75084c3 |  | label | RECORD OF CONFORMITY: This ITP Signed
label | 18a41aee-f54c-4e4d-a6fb-c5ea2a226443 |  | label | IP
label | df9be9ac-b9bb-4583-bfa0-227be2a9c577 |  | label | RESPONSIBILITY: Inspection point
text | 348d1e48-7bc6-4a3c-bec4-25b57862f292 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | cc892c05-4725-4738-ae07-1803443fed74 |  | label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 57c183be-bc09-435f-b36b-b6254009c508 |  | text | Print Name:
text | 5425aeb6-91f9-4d31-90f8-48f2aa748378 |  | text | Position:
text | 4a882cba-4119-4379-9362-23472d84b275 |  | text | Date:
checklist-flat |  |  | checklist | ITP-011 Cement Treated Crushed Rock | itp |  |  |  | Yes | ITP 011 - Cement Treated Crushed Rock Placement | c90d2533-3a5c-4f27-af89-b2c0eb738b02
checkpoint-status |  |  | checkpoint | 1.1 The current revision drawings are being used including subcontractors copy
label | 628f79f7-fd16-4ca5-82fa-fa1ddecc900e |  | label | FREQUENCY: Prior to start
label | dbb76c87-eb1b-4b0d-87d3-b4241ff07dae |  | label | ACCEPTANCE CRITERIA: Current revision drawing (via Aconex) is being used including the subcontractors’ copy.
label | 0e296700-20be-4997-b9ba-e834a2430153 |  | label | REFERENCE DOCUMENTS: Aconex
label | c38a2634-2fc0-4333-b635-0a43f0182636 |  | label | INSPECTION/TEST METHOD: Visual inspection
label | df265627-a187-4bef-8888-76ea71fad091 |  | label | RECORD OF CONFORMITY: This ITP signed
label | 6167dffa-a9d8-4995-9378-5800f1691bf6 |  | label | IP
label | a80da318-92a7-4158-95d0-195be70eab63 |  | label | RESPONSIBILITY: Project Engineer
text | 4f9529c1-6e1e-4610-a996-421d4af71fc1 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 Material Conformance
label | 1a3b4bfb-88b4-4958-8424-e9cc32432223 |  | label | FREQUENCY: Each lot
label | 297ef035-fd4c-4852-9b10-7e6b5106dc65 |  | label | ACCEPTANCE CRITERIA: Cement treated crushed rock shall use Portland and blended cement and shall be GP Type. Water added to the crushed rock products either onsite or in PMWMCR shall be clean and substantially free from detrimental impurities such as oils, salts, acids, alkalis and vegetable substances. The contractor shall carry out testing in accordance with the minimum test frequency specified in table 815.141. Material source to be in accordance with VR CoP RC500.00. Mix Registration in accordance with VR CoP RC500.02.
label | c6e61084-0b62-4517-bc61-87a25931919f |  | label | REFERENCE DOCUMENTS: VR SS Sec 815.07, 815.08, 815.10 Table 815.141
label | 866daf06-ac9e-463a-84d4-7ea4e18bdd03 |  | label | INSPECTION/TEST METHOD: Verify
label | f53079fa-7e87-4a20-a2c9-62ad58a70aaf |  | label | RECORD OF CONFORMITY: Aconex Approval
label | 84c24200-1440-4cd8-9962-5d5b06355661 |  | label | HP*
label | fe172660-6293-49c3-8047-d69206f33513 |  | label | RESPONSIBILITY: Fulton Hogan
text | 1a681919-e56a-4fc5-84b5-86ef67b0393c |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 Process Control
label | aa7ab755-6f21-4855-b91d-a954d0469204 |  | label | FREQUENCY: Prior to commencing works
label | 938dac0c-ba8d-4f92-aa06-43a711dae33d |  | label | ACCEPTANCE CRITERIA: Production and process program have been undertaken and satisfactory to specification requirements.
label | c092ee99-7b91-415f-b03a-a0d17cabd72d |  | label | REFERENCE DOCUMENTS: N/A
label | 7d208979-803d-455e-93ed-74904a87944b |  | label | INSPECTION/TEST METHOD: Verify
label | 4e4baa9b-0164-481f-b5a0-8953d28e47a0 |  | label | RECORD OF CONFORMITY: Aconex Approval
label | 3314d32e-234d-4cf6-a2dd-dc88bd08c1ce |  | label | HP*
label | e2cc6484-f648-442c-8397-a4e481455737 |  | label | RESPONSIBILITY: Project Engineer/Principals Rep
text | afad64d0-4250-42eb-aec1-d417cae3221c |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.4 Implementation of all measures & controls
label | 2f56863f-c41e-4bbf-95f0-98cedd4a09c0 |  | label | FREQUENCY: Prior to commencing works
label | 7e7a401c-05a1-47fc-a429-6b12af37ef86 |  | label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP.
label | bd3f8842-31f8-4425-b925-4a23275de930 |  | label | REFERENCE DOCUMENTS: PSP, EMP, TMP, SWMS, WP
label | 0bd160bf-0e91-490d-9680-4977e97ea5bd |  | label | INSPECTION/TEST METHOD: Visual inspection
label | 55887f16-c586-4730-9384-89c392c83bc2 |  | label | RECORD OF CONFORMITY: Site & Office Inspection
label | d98875ee-08a1-4076-99c3-6b87a183d8c2 |  | label | HP*
label | 7bc0dd60-26b8-4195-be0d-56b156150ff3 |  | label | RESPONSIBILITY: Project Engineer/Site Supervisor
text | f26cea18-bf45-48b6-816e-08edf7f80d64 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.5 Plant & Equipment
label | bf128e81-ee49-4807-a6a5-bb1f22987e70 |  | label | FREQUENCY: Prior to placing FCR
label | 315ad210-4ee2-4a23-9ea0-3390de9d5fad |  | label | ACCEPTANCE CRITERIA: Plant and equipment used in the Works are appropriate to achieve specification requirements.
label | 7f681f57-89c8-4d29-81b9-3a55baf9ea14 |  | label | REFERENCE DOCUMENTS: N/A
label | 9d49240b-c6bc-484c-be50-50278d410934 |  | label | INSPECTION/TEST METHOD: Visual Inspection
label | 47cbde42-2b53-4a1d-85c2-53cd78d67b2f |  | label | RECORD OF CONFORMITY: This ITP signed
label | 4f6bfd3f-8a85-401a-bf60-7999a43cf92f |  | label | IP
label | f5f22e8f-0594-4a7d-bd0e-ae62d8e4e7fc |  | label | RESPONSIBILITY: Project Engineer
text | e7470687-5c24-452b-b189-9b80445ff303 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 The commencement of construction of cement treated crushed rock
label | c61a6e71-bb20-4f71-bfc1-172bced7035d |  | label | FREQUENCY: Prior to placing CTCR
label | e6531eba-2a0f-4058-b80b-3f2523415d4a |  | label | ACCEPTANCE CRITERIA: Ensure the planned CTCR lot can achieve the specification requirements prior to commencement.
label | 333e61db-4312-4b5c-8a2e-25771dcb6cdd |  | label | REFERENCE DOCUMENTS: N/A
label | ea3affd4-406f-432a-a4c3-025e25861a66 |  | label | INSPECTION/TEST METHOD: Verify
label | ebd18b22-1ed6-40d1-94fb-96eb12d6e729 |  | label | RECORD OF CONFORMITY: This ITP signed
label | ce14dcb8-fa32-457a-ab10-8a44debf4c6c |  | label | HP*
label | 82df7b19-f696-47f8-b6fc-ca3197827028 |  | label | RESPONSIBILITY: Project Engineer
text | 46647fec-78e2-4994-90ef-668e78c8d491 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Place, spread, and compact CTCR
label | e4d230d6-7bae-41a0-93d2-8a87882b08b5 |  | label | FREQUENCY: Each lot
label | 1af478ac-2a1f-4761-b36b-6ea68bac3e8d |  | label | ACCEPTANCE CRITERIA: - CTCR placed, spread, compacted and trimmed within the allowable working time. (working time from VR Sec306 - table 306.091); - The compacted layer thickness is controlled between 100mm and 180mm; - Except for the purpose of curing, no water was added to cementations treated material; - Delivery dockets are available for inspection.
label | bab9fef0-c106-4671-b53d-f5c48e34b844 |  | label | REFERENCE DOCUMENTS: VR Sec306 – Table 306.09 VR Sec306 – Table 306.091
label | 5c9e168d-6341-48a7-8aaa-5a43310d6e44 |  | label | INSPECTION/TEST METHOD: Visual Inspection
label | 455754fc-61ed-435f-808a-bb7b32977004 |  | label | RECORD OF CONFORMITY: This ITP signed
label | de52bd7a-e4ef-422d-992a-e07471e2bf6a |  | label | IP
label | 126e5de5-dc96-4186-b605-48e4e292d7ec |  | label | RESPONSIBILITY: Fulton Hogan
text | 72b74903-dae8-48da-90be-47ea47b51c01 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Construction Jointing
label | d163be36-d66b-4e48-8e31-1f9adab09163 |  | label | FREQUENCY: Each lot
label | 7b673beb-32dd-465b-8f9c-1c6dd228a998 |  | label | ACCEPTANCE CRITERIA: - Transverse joints are offset 2m from one layer to next; - Longitudinal joints are offset 150mm from one layer to the next; - Longitudinal joints are located within 300mm of the planned position of traffic lane lines, or within 300mm of centre of traffic lane, or off running lanes where pavement is built through a centre median.
label | ecab6c1b-d2a9-4805-9a72-05018e94206a |  | label | REFERENCE DOCUMENTS: VR Sec306 306.08
label | 416c6aa6-86a1-4faa-b4ae-7a53cd95aa5d |  | label | INSPECTION/TEST METHOD: Verify
label | 0f175223-1b83-4888-b6c1-3df81ae88ca2 |  | label | RECORD OF CONFORMITY: This ITP signed
label | 22209f3c-045a-44ce-bf78-9b3103970053 |  | label | IP
label | 7ae2e39c-0180-4354-85a5-813b2b781000 |  | label | RESPONSIBILITY: Fulton Hogan
text | a7b3c7d7-205d-4964-b8f0-b2cc41ae212b |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 Test Compaction/Rolling
label | 73ab6a82-3f09-4d08-82c6-f3ad55cfc03e |  | label | FREQUENCY: Each lot
label | 0b71b652-3859-472e-94a6-aff5dc159268 |  | label | ACCEPTANCE CRITERIA: Scale A testing requirements:0 - Calculation of characteristic density ratio on modified compactive effort. Not less than 96% (if less than 96% then read and follow 306.09 (b) there may be opportunity to assess pavement design with Principal’s Representative); - 6 tests per lot. Moisture content at time of spreading and compactions is within +0.5% and –1.0% of modified optimum moisture content. Test rolling may be carried out in accordance with the requirements of Section 173 on the cementitious treated pavement subbase layer within the maximum allowable working time for the relevant binder and time of year as specified in Table 306.091.
label | 13c3679a-0044-49df-969b-8b76188e1c6d |  | label | REFERENCE DOCUMENTS: VR Sec306 306.09 VR Sec306 306.05 VR Sec306 306.10 VR Sec173
label | 99a31e86-d4b0-44d5-a936-6345371e74fb |  | label | INSPECTION/TEST METHOD: NATA onsite testing
label | 7397714f-7950-45ea-ac73-f821f8ef9490 |  | label | RECORD OF CONFORMITY: NATA test reports
label | 9a9215d2-b5ef-4201-b034-d051ec601150 |  | label | TP
label | 9f95539e-1d95-48af-8091-c75d9c4f38e8 |  | label | RESPONSIBILITY: Fulton Hogan
text | 5b32411e-519b-4d42-b920-6381fe73c198 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Curing & Protection of Compacted Layers
label | 3303f09e-9aa7-480b-a09f-597ba09fe5a6 |  | label | FREQUENCY: Each Lot for Design modulus of 500MPa
label | 6d403eed-2936-4299-a9e8-313c57f0c758 |  | label | ACCEPTANCE CRITERIA: - No construction traffic used compacted layers within the first 24 hours; - Surface was kept moist for 7 days unless covered by succeeding layer or approved curing membrane.
label | fd03234e-0bfb-484f-9ca7-2362256face7 |  | label | REFERENCE DOCUMENTS: VR Sec306 – Table 306.11
label | 4dff0252-46fb-4f3b-8825-a568b2b87d5d |  | label | INSPECTION/TEST METHOD: Verify
label | a3c9b656-752a-4296-8979-4ef833655331 |  | label | RECORD OF CONFORMITY: This ITP signed
label | 357bb055-8f50-43da-81d1-dc31b83e5c76 |  | label | HP*
label | af3a999e-c000-46af-9461-c7d8438f47d0 |  | label | RESPONSIBILITY: Fulton Hogan
text | e492783a-0958-4d96-8860-1f2ab54d9623 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Conformance with drawings
label | 8929ab75-5f48-4df0-9193-cd655795ebe7 |  | label | FREQUENCY: Top of pavement course
label | 17bf4e76-093c-44ea-bf8f-9ba37c142a36 |  | label | ACCEPTANCE CRITERIA: Scale A tolerances at top of pavement course (i.e. top of CTCR). Refer to VR Sec306 – Table 306.034 fir level tolerances at the surface of subgrade or subbase. Refer to VR Sec306 – Cl306.10 for test rolling. • No point on prepared surface lies more than 8mm below 3m straight edge or 10mm from a 6m straight edge; • Mean range and standards deviation meets following requirements (table 306.032) Scale A Cementitious Treated Subbase x¯ range (mm) +4 to -8 Max S (mm) 8
label | 73ff34fe-8dfb-4330-a0f6-c1df25962cd7 |  | label | REFERENCE DOCUMENTS: VR Sec306 – 306.03 VR Sec306 – 306.032
label | 770f30f5-4e82-43c0-8ce5-f9d9f99c7f25 |  | label | INSPECTION/TEST METHOD: Survey Check
label | 75952acc-b221-4bf8-8afa-cc4aa323e554 |  | label | RECORD OF CONFORMITY: Survey Conformance Documents
label | 52547355-01dc-46d3-a127-24bafcfae265 |  | label | SCP
label | 5feb9e44-ce86-4741-bc97-c487c671109e |  | label | RESPONSIBILITY: Fulton Hogan
text | 1c404f5b-eaa0-406d-82fb-b55d361d8add |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | c7057a4c-b192-4b71-8bf1-83873f5648e9 |  | label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | 661b4d43-4c6f-4442-bc83-41006fe830df |  | text | Print Name:
text | 5de36083-0110-4ad0-80bb-4664d2fd03bd |  | text | Position:
text | e7b88b31-97ab-41f5-a6f8-d86ce959dc35 |  | text | Signature:
text | 13671ab0-e54d-4d95-a8a2-38e1390052df |  | text | Date:
checklist-flat |  |  | checklist | ITP 026 - Precast Pit Installation | itp |  |  |  | Yes | ITP 026 - Precast Pit Installation | caef01a0-6a46-46fe-8d8a-c3b0750835c3
checkpoint-status |  |  | checkpoint | 1.1 The current revision drawings are being used including subcontractors copy.
label | 0acd0a38-3811-4362-8d7e-d8ce465539d5 |  | label | FREQUENCY: Prior to commencing works
label | dc9667cd-feb4-405e-9ba6-b3861fc97b55 |  | label | ACCEPTANCE CRITERIA: Current revision drawing is being used including the subcontractors copy. Current revision to be obtained via Aconex.
label | f2a07e18-8569-4849-9799-14ed4481a42d |  | label | REFERENCE DOCUMENTS: Drawings and drawing registers & RFi Responses
label | d4395383-4a1f-47eb-9bdd-060d78caaf53 |  | label | INSPECTION/TEST METHOD: Visual inspection
label | a0c1b211-ad23-44e5-a648-2c2663146206 |  | label | RECORD OF CONFORMITY: Up to date drawing sets and this ITP signed
label | 07182a9a-f847-4b52-8c46-a5b74fa24a6e |  | label | HP*
label | 85d8c841-e000-45c7-8562-d291eddb3d46 |  | label | RESPONSIBILITY: FH Engineer
text | e1d9896c-2aa5-4877-bbbd-3c9edac16e53 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 Setting out for miscellaneous structures
label | f02db0bb-2620-43ff-9543-b878b68a4faa |  | label | FREQUENCY: Prior to Start
label | 19be1e35-4923-4aba-bb6c-628800d853e3 |  | label | ACCEPTANCE CRITERIA: Conformance with Jacobs for Construction Drawings and pipe penetrations in the correct locations.
label | 29573270-45be-4525-86a3-755013bab9ab |  | label | REFERENCE DOCUMENTS: WP 020
label | 1cfc8363-dd67-4a71-8425-64ef2dd578fd |  | label | INSPECTION/TEST METHOD: Verify
label | 4171e8ce-281b-4a09-9baa-259874057e1f |  | label | RECORD OF CONFORMITY: Asbuilts drawings
label | 63415ccb-5e5b-446b-9831-9ec84f706a8f |  | label | SCP
label | ba423a38-53ec-4eac-b595-1e84cc2a2e7f |  | label | RESPONSIBILITY: FH Engineer, Surveyor
text | 9cbba32d-9b90-41df-86f5-2e0dd8e85972 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 Materials & source Approval
label | 0cbf29c1-1168-4e8a-bcce-ebdcff019990 |  | label | FREQUENCY: Pre-commencement
label | bbd5830f-7571-4e79-acc7-9f8874097e17 |  | label | ACCEPTANCE CRITERIA: Details submitted to Principal’s Representative regarding: Test Certificates demonstrating class D load rating and compliance of the pit to AS 3600 & AS 3996
label | 95af7477-24a6-428c-a231-950f4966790f |  | label | REFERENCE DOCUMENTS: CP14038-LAN-DET-PM-SP-0001
label | bc75cdb3-363a-4125-816f-7e27a383555d |  | label | INSPECTION/TEST METHOD: Verify
label | 85e32bdc-73a7-4a67-9c05-962ad2d1664c |  | label | RECORD OF CONFORMITY: Aconex correspondence
label | 0ceec80f-84bb-4e94-899e-705a782b9069 |  | label | AP
label | 15d1aefd-a93d-4a78-9c51-f660bea48326 |  | label | RESPONSIBILITY: FH engineer and Principal’s Representative
text | 9760bc7b-e937-47bd-9544-4e5f7960a03d |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Materials & source
label | 0f2ecba6-8e70-432e-bf5c-2af9a66de911 |  | label | FREQUENCY: Each Delivery
label | 1ed3ba07-59d7-46f7-90b1-7c2a239153a0 |  | label | ACCEPTANCE CRITERIA: Pits, pit covers, grates, lids and lintels shall be as specified on drawings and installed as per manufacture’s recommendations
label | 5bee4dcd-a620-44b5-b15c-7459fe605c73 |  | label | - Date of manufacture
label | bf7109b4-5919-497e-b976-b8dd7abd6207 |  | label | - Manufacturer’s name or registered mark and location of manufacture .
label | e28c9519-34c2-4d12-bede-84bc73751a3d |  | label | - Maximum mass of unit in kg
label | 3e1dacb5-7a2d-41c7-b0f6-2f18bfe95d65 |  | label | - Batch number
label | 55fbad45-4800-415b-8893-c780a224dee2 |  | label | - Inspection status
label | b61d88b5-df1d-4fc8-9089-354b0af163b0 |  | label | REFERENCE DOCUMENTS: Drawings and drawing registers & RFi Responses
label | 902377a9-ffdc-4121-b528-1ad4fadf3730 |  | label | CP14038-LAN-DET-PM-SP-0001 – 7.2.6
label | 53a689f6-6d83-422e-93ab-8f0b07e1b56c |  | label | INSPECTION/TEST METHOD: Verify
label | 6657f0ea-cad0-4831-ada4-b71d24e2b2f6 |  | label | RECORD OF CONFORMITY: Receival
label | 670b5089-0b73-40a7-a6ac-7ba6d21dd2e9 |  | label | IP
label | 123e2a6c-88e0-4f54-8a79-ebc9013d082d |  | label | RESPONSIBILITY: FH Engineer
text | 576bf353-40d4-48de-b1b8-bf898416d311 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Acceptance Covers Frames/Grates
label | b3e53b37-87fb-4e7d-9eb6-a4ae79b4f0c4 |  | label | FREQUENCY: Prior to Start
label | b633c415-de92-4b45-a05b-7e115a66a5cc |  | label | ACCEPTANCE CRITERIA: All Pit covers shall conform to Class D-Landside standards.
label | e3afc158-dc08-42bc-8969-0075e5848cf2 |  | label | REFERENCE DOCUMENTS: CP14038-LAN-DET-PM-SP-0001 – 7.2.1 / AS3996 CL3.1
label | b711fe9f-36b4-40ce-a907-bc07acfca35e |  | label | INSPECTION/TEST METHOD: Verify
label | 399532ea-3c56-4fe1-a420-edab34fe3fbe |  | label | RECORD OF CONFORMITY: Receival inspection checklist
label | 92b35398-a69f-49da-b68f-d3a98ec25bb3 |  | label | HP*
label | c8661294-0dff-47aa-ac25-7ea1babc407f |  | label | RESPONSIBILITY: FH Engineer
text | c8af037e-be5b-4d8e-8e70-e0b102101f7e |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3.1 Excavate Pits
label | c3e560cb-b67c-408e-9fc3-4e7efb8acc40 |  | label | FREQUENCY: Each Lot
label | 38ed2724-462c-47c0-a7f7-24dc3f2292cd |  | label | ACCEPTANCE CRITERIA: Excavation depth shall be as per specified on drawings or as necessary to secure satisfactory foundation. Excavation shall provide a clearance from all external faces of the pit to each face of the excavation of not less than 400mm.
label | 0cf23ae5-707d-41c1-af1d-31e574e3dd52 |  | label | REFERENCE DOCUMENTS: CP14038-LAN-DET-PM-SP-0001 –C- 7.2.4
label | e14d4ff3-78f4-4266-90fe-3108a2cc0d20 |  | label | INSPECTION/TEST METHOD: Verify
label | 38c16fad-44e5-4228-b194-5f5a0f9f4e01 |  | label | RECORD OF CONFORMITY: This ITP signed
label | c9e8a68e-a01f-4052-906f-b25a3b13d09d |  | label | IP
label | 9dc7a698-d10d-455a-84bf-d6b5e5cd05ff |  | label | RESPONSIBILITY: FH Engineer
text | 6a67a72b-ce86-4991-87ac-0c594a186929 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Confirm Ground
label | 881dd2c8-68b2-4a20-b65b-c3fc1fd42205 |  | label | FREQUENCY: Each Lot
label | 250be7af-e8aa-431e-8652-c67ea092d5b8 |  | label | ACCEPTANCE CRITERIA: Pits shall be constructed on firm subgrade with a minimum allowable bearing capacity of 130kPa and in accordance with manufacturers instructions
label | 62242a45-6559-4a94-9562-1f529ec10a5e |  | label | REFERENCE DOCUMENTS: Manufacture Drawings, Manufacturer ITP/WP/ Installation guide
label | b45c0bb0-8939-4871-8d5a-4634cb622dfe |  | label | INSPECTION/TEST METHOD: Verify
label | 3b42a7b6-1deb-4ddc-bebf-aeb8d3d58840 |  | label | RECORD OF CONFORMITY: DCP Results attached, Test result
label | 506c07d4-5cdd-4016-94e3-62c99e1bb4c7 |  | label | HP
label | 8a811737-c339-4bd4-8da3-9df3b312934f |  | label | RESPONSIBILITY: FH Engineer, Principal’s Representative
text | 01b24ecc-19c4-4a1d-9c8c-0235c09d0d56 |  | text | Date Completed:
holdpoint |  |  | holdpoint | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 3.3 Blinding
label | 68db57a7-f7f9-4bd3-98b2-919e73252cbf |  | label | FREQUENCY: Each Lot
label | 7b821962-9907-4a52-a4d5-c579ace683b7 |  | label | ACCEPTANCE CRITERIA: Blinding to be installed in either of the following methods:
label | 27d292e5-4cd9-4391-bd50-03e5aeaab54a |  | label | - 50mm 20Mpa Concrete
label | cf08af75-d542-4d5c-9670-e1ec62233754 |  | label | - 100mm Class 3 Wet Mix Crushed Rock – Compacted to refusal using handheld mechanical aid (DPU / Wacker Plate).
label | ed575d72-a9bf-4564-86b6-0be191e911c6 |  | label | - Installed blinding layer is to be stable and level to ensure the precast pit is vertical
label | bffd1699-2811-416a-b01d-9a2d8dfc826d |  | label | REFERENCE DOCUMENTS: Drawings & Manufacturer ITP/WP/ Installation guide
label | 14c17d97-ff36-401f-ad84-6e16edcab0f4 |  | label | INSPECTION/TEST METHOD: Verify
label | ccf77faa-0959-43c3-88cd-b7d6bcd9cae6 |  | label | RECORD OF CONFORMITY: This ITP signed
label | 1ada1537-9fb6-45cf-b677-0abeac4c1418 |  | label | IP
label | c4bd08e9-bdd7-4873-8382-d7aef54d7699 |  | label | RESPONSIBILITY: FH Engineer
text | 121d74d2-3b20-4db2-a8f5-4fdd2c29b954 |  | text | Date Completed:
holdpoint |  |  | holdpoint | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 4.1 Drawing Approvals
label | ef74e529-166c-420b-a401-2c16ca848b55 |  | label | FREQUENCY: Each Lot
label | 96d3fffa-205b-45d2-9fa3-27a010de762f |  | label | ACCEPTANCE CRITERIA: Ensure manufacturer drawings are supplied with correct dimensions and blockouts to suit all services to be installed into the pit designated in Jacobs Design Drawings
label | ad5511cb-79ea-4a08-bbbc-17e8f9d0b899 |  | label | REFERENCE DOCUMENTS: Manufacturer Drawings. Jacobs Drawings
label | fe23ca9c-cc07-49bc-a130-f6b92743ca89 |  | label | INSPECTION/TEST METHOD: Verify
label | fea8d672-195a-4f4f-b7ec-cc0b31796282 |  | label | RECORD OF CONFORMITY: This ITP signed
label | 5a6feadc-26f9-4a42-81ab-198e64239fdd |  | label | IP
label | 92300979-ab9f-44b8-9ea4-e9d731eba8d7 |  | label | RESPONSIBILITY: FH Engineer
text | 053572b5-85ce-4db4-9356-906d2b608886 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Pit Delivery
label | c421d061-5194-4a7c-8c66-d1b88b3d549a |  | label | FREQUENCY: Each Lot
label | 644f0ab6-76e9-4061-94ff-d8a807852699 |  | label | ACCEPTANCE CRITERIA: Ensure each pit component is inspected upon arrival ensuring:
label | b5cad514-7ff5-49c9-a201-67b5054877f2 |  | label | - Dimensions are as shown on manufacturer drawings
label | 0ae9c8cb-b7af-437f-be3a-bec3f45f02f2 |  | label | - All blockouts in correct positions and to dimensions.
label | e9b59def-04cd-452c-b34d-e90225818c4a |  | label | - No damage to any pit component to the satisfaction of FH Engineer
label | 57687320-3dea-4e97-be2f-662048a972e3 |  | label | - No modifications to the pits are to be made without written approval from manufacturer
label | 929f3b1f-4cf1-4842-a854-ebe8481139fc |  | label | INSPECTION/TEST METHOD: Visual Inspection
label | e931f2ab-4d6d-4941-becf-73ef7ecff7b0 |  | label | RECORD OF CONFORMITY: This ITP Signed
label | 1df1d860-a0a3-4609-98f9-fb17c8ab8c5d |  | label | HP*
label | 465cd1f7-a2a3-46d1-8c85-f44c6e1b6c26 |  | label | RESPONSIBILITY: FH Engineer
text | b4fe96d1-8114-4eb5-b1ef-6141e4092cbc |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 5.1 Positioning Pit Components
label | 23b95115-4448-406a-b5ae-86c7560fe0bf |  | label | FREQUENCY: Each Lot
label | 359a1168-69c4-4b3c-b4f7-500bcf11bc59 |  | label | ACCEPTANCE CRITERIA: Precast Pit installed as per survey set out points marked on blinding layer
label | e3554b38-ffff-4a48-9fb4-dab63aebfbc8 |  | label | REFERENCE DOCUMENTS: Survey
label | 99dfd0ed-156b-473e-9fbb-48f4f138bbfb |  | label | INSPECTION/TEST METHOD: Verify
label | 0528f4f6-9fba-4753-8639-1c60d5c411a5 |  | label | RECORD OF CONFORMITY: This ITP Signed
label | 44dbf29e-524b-4642-b577-498094d23286 |  | label | HP*
label | 0986b639-2be7-4adc-a127-a9dd3afea94d |  | label | RESPONSIBILITY: Surveyor
text | 2f15021d-84c5-4b44-9d50-b0bfc98cd6d6 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Lid Encasement Slab Installation
label | c5ba6f07-a657-4866-93c1-e76ed5115e1b |  | label | FREQUENCY: Each Lot
label | d1a94bd8-f573-49e2-823f-5c00c571bea9 |  | label | ACCEPTANCE CRITERIA: Seal Pit Wall and Lid encasement slab using mastic type sealant ensuring no gaps remain. Any encasement slab on a slope is to be checked by the surveyor and achieved using packers and infilled using non-shrink grout – Conbextra C or equivalent.
label | 208d851f-190c-47ea-9716-f9cb44946dd5 |  | label | REFERENCE DOCUMENTS: Manufacturer Guide
label | d39b1461-5308-4ab9-802f-537224e2e6cd |  | label | INSPECTION/TEST METHOD: Visual Inspection
label | 89090737-4ff5-4550-83d1-8193a4c7f518 |  | label | RECORD OF CONFORMITY: This ITP Signed
label | 27396038-0d9d-4e62-91b2-196763b0ca6a |  | label | IP
label | e77f9671-ff35-4a99-bb0d-ac2836e0b817 |  | label | RESPONSIBILITY: FH Engineer
text | 1b6ee9bf-bb78-422d-bb3d-9fed7835b062 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | 9.3 Quality Report
label | 229c274b-f679-4762-9f4d-22d820680721 |  | label | FREQUENCY: Each Lot
label | fd22639b-c0fa-4951-bb71-cb74ab6a181a |  | label | ACCEPTANCE CRITERIA: Submit to Principal’s Representative via Aconex report detailing the results of all quality control and testing
label | c2d787d4-096c-45e7-8faa-074d534e7748 |  | label | REFERENCE DOCUMENTS: CP14038-LAN-DET-PM-SP-0001-
label | 54957e70-f30a-4e67-9ba4-3225527c767d |  | label | INSPECTION/TEST METHOD: Verify
label | 21539396-b6e9-4424-8ee0-1f3ea9a49d59 |  | label | RECORD OF CONFORMITY: Aconex correspondence
label | 1bf00bff-ceba-41a8-a2ee-c40f48555c00 |  | label | HP*
label | 5745cc80-a68c-4b30-8666-6f32d5601bc8 |  | label | RESPONSIBILITY: FH Engineer
text | f5782843-8b28-408f-8be0-755083afeb34 |  | text | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 021804d9-f872-4d3a-be46-dbb3f243c714 |  | label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | d343a72e-be23-48b4-ba0b-ec183d275bab |  | text | Print Name:
text | 32fdf1dd-02cf-4330-9dcb-760186902284 |  | text | Position:
text | 6ddee1fd-fec0-4d63-924a-bad8df59597e |  | text | Date: