## MATRICES
Area | Lot No | Lot Description | Lot Status | Lot Closed On | ACTUAL Lot Closed On | Lot Created On | ACTUAL Lot Created On | Lot Opened On | Work Commenced On | Work Completed On | Work Completed On | Lot Type | From and To Chainage | Construction Element | Activity | Design Package No | Traffic Direction | Engineer Responsible | comments | Print Name: | Date: | Lot verified By | Is the relevant NCR attached to the Lot?
Area 1 | ITP-001-A1-LOT-001 | ITP-001-A1-LOT-001 - 11 Trees - Median Ch 24640 to Ch 25040 | [7 empty] | pass | [9 empty] | Khulood Hwayyis | 2021-10-20
Area 1 | ITP-001-A1-LOT-002 | ITP-001-A1-LOT-002 - Memorial park & Hume Hwy Center Median | CLOSED | 2021-11-09 |  | 2021-10-18 |  | 2021-10-25 | 2021-10-26 | 2021-10-26 |  | EAL- Earthworks Lot | Zone 1 - Memorial Park and Hume Hwy Tree Removal | EART - Earthwork | CLGR - Clearing and Grubbing | 1145-ACM-CVR-DPK-0001 | ME - Median | Qassim Al-Montafjy |  | Omar El-Khub | 2021-11-09 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-001-A1-LOT-003 | ITP-001-A1-LOT-003 - 9 Trees - Zone 3 - Westbound Ch 15000 to Ch 14700 | CLOSED | 2022-01-27 |  | 2022-01-11 |  | 2022-01-11 | 2022-01-12 | 2022-01-14 |  | EAL- Earthworks Lot | 15000 - 14700 |  | CLGR - Clearing and Grubbing | 1145-ACM-CVR-DPK-0001 | WB - Westbound | James Moran | 9 x trees - Zone 3 | James Moran | 2022-01-27 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-001-A1-LOT-004 | ITP-001-A1-LOT-004 - 64 Trees - Zone 4 - Westbound Ch 14400 to Ch 13880 |  | 2022-01-27 |  | 2022-01-13 |  | 2022-01-14 | 2022-01-14 | 2022-02-21 |  |  | 14500 - 13900 |  | CLGR - Clearing and Grubbing | 1145-ACM-CVR-DPK-0001 | WB - Westbound | James Moran | 64 Trees - Zone 4 (Golf course) | James Moran | 2022-01-27
Area 1 | ITP-001-A1-LOT-005 | ITP-001-A1-LOT-005 - 1 Tree - Zone 1 - Hume Hwy South Center Median - Ch70139 - Ch70272 | CLOSED | 2022-03-30 |  | 2022-01-25 |  | 2022-01-25 | 2022-02-11 | 2022-02-12 |  | CIL-Civil Lot | CH70139 to CH70272 | EART - Earthwork | CLGR - Clearing and Grubbing | 1145-ACM-CVR-DPK-0001 | ME - Median | Qassim Al-Montafjy | 1 Tree - Zone 1 - at Hume south Island and is removed due to the drainage design change. | Qassim Al-Montafjy | 2022-02-11 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-001-A1-LOT-006 | ITP-001-A1-LOT-006 - 4Trees - Zone 4 - Golf Course - CH13800 - CH13600 | CLOSED | 2022-03-09 |  | 2022-02-09 |  | 2022-02-10 | 2022-02-11 | 2022-02-11 |  | EAL- Earthworks Lot | CH13800 to CH13600 | EART - Earthwork | CLGR - Clearing and Grubbing | 1145-ACM-CVR-DPK-0001 |  | Khulood Hwayyis | 4 trees to be removed | Khulood Hwayyis | 2022-02-11 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-001-A1-LOT-007 | ITP-001-A1-LOT-007 - 2 Trees - Zone 1 - Craigieburn - Hardy Ave - Ch16085 - Ch16110 | CLOSED | 2022-03-30 |  | 2022-02-10 |  | 2022-02-10 | 2022-02-11 | 2022-02-11 |  | CIL-Civil Lot | Ch16085 to ch16110 | EART - Earthwork | CLGR - Clearing and Grubbing | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Qassim Al-Montafjy | 2 Trees removed at Zone 1 Hardy Ave. | Qassim Al-Montafjy | 2022-02-11 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-001-A1-LOT-008 | ITP-001-A1-LOT-008 - 3 Trees - Zone 2 - Craigieburn Road- West Bound - Ch16060 - Ch16080 | CLOSED | 2022-03-30 |  | 2022-02-10 |  | 2022-02-10 | 2022-02-11 | 2022-02-11 |  | CIL-Civil Lot | Ch16060 to Ch16080 | EART - Earthwork | CLGR - Clearing and Grubbing | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Qassim Al-Montafjy | Only 2 trees removed out of 3 as the 3rd is not exist. | Qassim Al-Montafjy | 2022-02-11 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-001-A1-LOT-010 | ITP-001-A1-LOT-010 - Topsoil Strip - Zone 4 - Westbound Ch13600 - Ch14400 | CLOSED | 2022-03-09 |  | 2022-02-16 |  | 2022-02-17 | 2022-02-18 | 2022-03-01 |  | EAL- Earthworks Lot | Ch13600 to Ch14400 | EART - Earthwork | CLGR - Clearing and Grubbing | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Khulood Hwayyis | 150mm topsoil strip | Khulood Hwayyis | 2022-03-01 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-001-A1-LOT-011 | ITP-001-A1-LOT-011 - Clearing & Grubbing - eastbound zone 3 CH25370 -Dalys | CLOSED | 2022-04-11 |  | 2022-03-30 |  | 2022-03-30 | 2022-03-30 | 2022-03-30 |  | EAL- Earthworks Lot | 25370 | EART - Earthwork | CLGR - Clearing and Grubbing | 1145-ACM-CVR-DPK-0001 | EB - Eastbound | Simon colosimo |  | Simon Colosimo | 2022-04-05 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-001-A1-LOT-012 | ITP-001-A1-LOT-012 - 24 Trees TBR & 1 trim - Zone 3- CH14760 - CH15080 | CLOSED | 2022-04-11 |  | 2022-04-04 |  | 2022-04-06 | 2022-04-06 | 2022-04-08 |  | EAL- Earthworks Lot | CH14760 - CH15080 | EART - Earthwork | CLGR - Clearing and Grubbing | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Khulood Hwayyis | 24 Trees to be removed and 1 tree to be trimmed | Khulood Hwayyis | 2022-04-11 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-001-A1-LOT-013 | ITP-001-A1-LOT-013 - Z3 Topsoil Stripping - BTW Bridgewater Rd and the access to the sporting club - Ch14400 to Ch15080 | CLOSED | 2022-06-09 |  | 2022-04-28 |  | 2022-04-28 | 2022-05-03 | 2022-06-03 |  | EAL- Earthworks Lot | Ch14400 to Ch15080 | EART - Earthwork | CLGR - Clearing and Grubbing | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Khulood Hwayyis | Topsoil stripping - Zone 3 - BTW Bridgewater rd and Access to sporting club | Khulood Hwayyis | 2022-06-06 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-001-A1-LOT-014 | ITP-001-A1-LOT-014 - Tree Removal - Rayfield trees | CLOSED | 2022-04-09 |  | 2022-04-05 |  | 2022-04-05 | 2022-04-06 | 2022-04-06 |  | EAL- Earthworks Lot | 25500 | EART - Earthwork | CLGR - Clearing and Grubbing | 1145-ACM-CVR-DPK-0001 | EB - Eastbound | Simon Colosimo |  | Simon Colosimo | 2022-04-05 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-001-A1-LOT-015 | ITP-001-A1-LOT-015 - Tree Removal B/W Newbold Ave to Bridgewater Rd |  |  |  | 2022-05-16 |  | 2022-05-16 | 17/0522 |  |  | CIL-Civil Lot | 15200 to 15680 | EART - Earthwork | CLGR - Clearing and Grubbing | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Abdullah Abdullah
Area 1 | ITP-001-A1-LOT-016 | ITP-001-A1-LOT-016- Trees Removal Zone 1,2 & 4 - 17 Trees |  |  |  | 2022-06-20 |  | 2022-06-20 | 2000-06-22 |  |  | CIL-Civil Lot | 16140 to 16300 |  | CLGR - Clearing and Grubbing | 1145-ACM-CVP-DPK-0001 |  | Qassim AL-Montafjy | -Corner of walters 39, 40 -Cimberwood 560, 566 -Balyang 1116, 1182, 1183, 1184, 1185, 1186, 1187, 1188, 1189, 1190, 1191, 1194, 1195 | Qassim Al-Montafjy
Area 1 | ITP-006-A1-LOT-001 | ITP-006-A1-LOT-001- Memorial Park East - CH26130 - CH26160 - NB | CLOSED | 2022-04-06 |  | 2021-11-17 |  | 17/11/21 | 2021-11-17 | pass |  | EAL- Earthworks Lot | CH 26130 to CH 26160 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | EB - Eastbound | Qassim Al-Montafjy | This lot was affected by asbestos and as well as design issue | Babak Rudd | 2022-04-06 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-006-A1-LOT-002 | ITP-006-A1-LOT-002 - Memorial Park East - CH26130- CH26160 - NB | CLOSED | 2022-04-06 |  | 2021-12-01 |  | 2021-12-01 | 2021-12-01 | not applicable |  | EAL- Earthworks Lot | CH26130 to CH26180 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | EB - Eastbound | Qassim Al-Montafjy | This lot is affected by asbestos | Babak Rudd | 2022-04-06 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-006-A1-LOT-003 | ITP-006-A1-LOT-003 - Memorial Park East - CH26180 - CH26220 - NB | CLOSED | 2022-04-06 |  | 2021-12-02 |  | 2021-12-02 | 2021-12-02 | not applicable |  | EAL- Earthworks Lot | CH26180 to CH26225 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | EB - Eastbound | Qassim Al-Montafjy | This lot is for compaction tests only and is affected by asbestos as well as design challenge. | Babak Rudd | 2022-04-06 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-006-A1-LOT-004 | ITP-006-A1-LOT-004 - Hume Hwy North Median - CH70330 - CH70400 - NB | CLOSED | 2022-04-06 |  | 2021-11-30 |  | 2021-11-30 | 2021-11-30 | not applicable |  | EAL- Earthworks Lot | CH70330 to CH70400 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | NB - Northbound | Qassim Al-Montafjy | This lot is affected by asbestos |  |  | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-006-A1-LOT-005 | ITP-006-A1-LOT-005 - Hume Hwy North Median - CH70330 - CH70400 - NB | CLOSED | 2022-04-06 |  | 2021-12-08 |  | 2021-12-08 | 2021-12-08 | not applicable |  | EAL- Earthworks Lot | CH70330 - CH70400 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | NB - Northbound | Qassim Al-Montafijy | 200mm typeB material placement | Babak Rudd | 2022-04-06 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-006-A1-LOT-006 | ITP-006-A1-LOT-006 - Hume Hwy North Median - CH70400 - CH70445 - NB | CLOSED | 2022-04-06 |  | 2021-12-12 |  | 2021-12-12 | 2021-12-12 | not applicable |  | EAL- Earthworks Lot | CH70400 - CH70445 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | NB - Northbound | QASSIM AL- MONTAFJY, KHULOOD HWAYYIS | REVIEW THE CUT FLOOR LAYER AND 97% COMPACTION TEST | Babak Rudd | 2022-04-06 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-006-A1-LOT-007 | ITP-006-A1-LOT-007 - Hume Hwy North Median - CH70485- CH70506 - SB | CLOSED | 2022-04-06 |  | 2021-12-15 |  | 2021-12-15 | 2021-12-15 | not applicable |  | EAL- Earthworks Lot | CH70485 To CH70506 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | SB - Southbound | Qassim Al-Montafjy |  | Babak Rudd | 2022-04-06 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-006-A1-LOT-008 | ITP-006-A1-LOT-008 - Hume Hwy South Median- NB - CH70190- CH70280 Cut Floor | CLOSED | 2022-05-06 |  | 2022-02-07 |  | 2022-02-07 | 2022-02-08 | pass |  | EAL- Earthworks Lot | CH70190 to CH70280 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | NB - Northbound | Qassim Al-Montafjy | This lot is for undertake a compaction test at 1175mm/Cut Floor | Babak Rudd | 2022-05-06 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-006-A1-LOT-009 | ITP-006-A1-LOT-009 - Hume Hwy South Median - NB - CH70190- CH70280 Layer 1 | CLOSED | 2022-06-16 |  | 2022-02-07 |  | 2022-02-07 | 08/02/2022 | pass | 2022-02-15 | EAL- Earthworks Lot | 70190 to 70280 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | NB - Northbound | Qassim Al-Montafjy | Placing 1st layer of Type B ( in situ ) | Qassim Al-Montafjy | 2022-06-15 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-006-A1-LOT-010 | ITP-006-A1-LOT-010 - Hume Hwy South Median- NB - CH70190- CH70280 Layer 2 | CLOSED | 2022-06-16 |  | 2022-02-08 |  | 2022-02-08 | 2022-02-09 | pass | 2022-02-15 | EAL- Earthworks Lot | CH70190 to CH70280 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | NB - Northbound | Qassim Al-Montafjy | Subgrade preparation | Qassim Al-M0ntafjy | 2022-06-15 | Babak Rudd-Project Quality Manager | YES
Area 1 | ITP-006-A1-LOT-011 | ITP-006-A1-LOT-011 - Golf Course East - WB - CH14250-CH14090 | CLOSED | 2022-04-28 |  | 2022-03-11 |  | 2022-03-16 | 2022-03-16 | pass |  | EAL- Earthworks Lot | 14090 - 14250 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | EB - Eastbound | James Moran | Proof Roll and Compaction Test of Subgrade for placement of Type A | James Moran | 2022-04-20 | Babak Rudd-Project Quality Manager
Area 1 | ITP-006-A1-LOT-012 | ITP-006-A1-LOT-012 - Hume Hwy North Median - CH70330 - CH70400 - NB- 400mm below Subgrade | CLOSED | 2022-05-06 |  | 2022-03-29 |  | 2022-03-29 | 2022-03-30 | pass |  | EAL- Earthworks Lot | 70330 to 70400 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | NB - Northbound | Qassim Al-Montafjy | This lot is made to undertake a compaction test at 1175mm and prepare for 1st layer of Type B | Babak Rudd | 2022-05-06 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-006-A1-LOT-013 | ITP-006-A1-LOT-013 - Hume Hwy North Median - CH70330 - CH70400 - NB - 400 below subgrade |  |  |  | 2022-03-30 |  | 2022-03-30 | 2022-03-31 | not started |  |  | 70330 to 70400 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | NB - Northbound | Qassim Al-montafjy | Placing Type B in situ material first lift @975mm
Area 1 | ITP-006-A1-LOT-014 | ITP-006-A1-LOT-014 - Golf Course West - WB - CH13860-CH13700 | CLOSED | 2022-04-28 |  | 2022-03-30 |  | 2022-03-21 | 2022-03-21 | pass |  | CIL-Civil Lot | 13850 - 13640 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | WB - Westbound | James Moran | Golf Course West - Sub grade preparation for 1st lift of Type A capping - Zone 4 WB carriageway | James Moran | 2022-04-20 | Babak Rudd-Project Quality Manager
Area 1 | ITP-006-A1-LOT-015 | ITP-006-A1-LOT-015- Hume Hwy North Median - CH70310 - CH70400 - SB - Bottom of Subgrade | CLOSED | 2022-06-03 |  | 2022-03-30 |  | 2022-03-30 | 2022-03-30 | pass | 2022-05-03 | EAL- Earthworks Lot | 70330 to 70400 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | SB - Southbound | Qassim Al-Montafjy | cut off below the subgrade to 975mm depth for rectification and this lot,as per design,is omitted of Type B . | Qassim Al-Montafjy | 2022-05-30 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-006-A1-LOT-016 | ITP-006-A1-LOT-016 - Golf Course East - WB - CH14040-CH14090 | CLOSED | 2022-05-06 |  | 2022-04-07 |  | 2022-04-12 | 2022-04-12 | pass |  | EAL- Earthworks Lot | CH14060 to CH14090 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Khulood Hwayyis | Cutfloor compaction test | Khulood Hwayyis | 2022-05-04 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-006-A1-LOT-017 | ITP-006-A1-LOT-017 - Golf Course East - WB - CH14250-CH14306 | CLOSED | 2022-06-03 |  | 2022-04-07 |  | 2022-04-12 | 2022-04-12 | pass | 2022-05-25 | CIL-Civil Lot | CH14250 to CH14306 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Khulood Hwayyis | Compaction test for the subgrade surface | Khulood Hwayyis | 2022-05-12 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-006-A1-LOT-018 | ITP-006-A1-LOT-018- Hume Hwy North Median - CH70330 - CH70400 - NB - Subgrade | CLOSED | 2022-06-16 |  | 2022-04-12 |  | 2022-04-12 | 2022-04-12 | pass | 2022-05-13 | EAL- Earthworks Lot | 70330 ti 70400 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | NB - Northbound | Qassim Al-Montafjy | Placing 2nd Layer of Type B | Qassim Al-Montafjy | 2022-06-15 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-006-A1-LOT-019 | ITP-006-A1-LOT-019 - Golf Course East - WB - CH14040-CH14090 - lift 1 | CLOSED | 2022-05-06 |  | 2022-04-13 |  | 2022-04-13 | 2022-04-13 | pass |  | EAL- Earthworks Lot | CH14040-CH14090 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Khulood Hwayyis | Review the cut floor and place the 1st lift of Type B | Khulood Hwayyis | 2022-05-04 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-006-A1-LOT-020 | ITP-006-A1-LOT-020 - Golf Course East - WB - CH14040-CH14090 - lift 2 | CLOSED | 2022-05-19 |  | 2022-04-13 |  | 2022-04-13 | 2022-04-13 | pass |  | EAL- Earthworks Lot | CH14040 to CH14090 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Khulood Hwayyis | Proof roll the 1st lift of type B and review the Area to place the second lift | Khulood Hwayyis | 2022-05-18 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-006-A1-LOT-021 | ITP-006-A1-LOT-021 - Hume Hwy North Median - CH70310 - CH70330 - NB - 200 below Subgrade | CLOSED | 2022-06-07 |  | 2022-04-27 |  | 2022-04-27 | 2022-04-27 | pass | 2022-04-27 | EAL- Earthworks Lot | CH70310 - CH70330 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | NB - Northbound | Qassim Al-Montafjy | The lot is located between the bull nose and the High Voltage service | Qassim Al-Montafjy | 30/05/202 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-006-A1-LOT-022 | ITP-006-A1-LOT-022 - Hume Hwy North Median - CH70310 - CH70330 - NB - Subgrade | CLOSED | 2022-06-07 |  | 2022-04-27 |  | 2022-04-27 | 2022-04-28 | pass | 2022-04-28 | EAL- Earthworks Lot | 70310 to 70330 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | NB - Northbound | Qassim Al-Montafjy |  | Qassim al-Montafjy | 2022-06-03 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-006-A1-LOT-023 | ITP-006-A1-LOT-023- Hume Hwy North Median - CH70310 - CH70326 - SB - Subgrade | CLOSED | 2022-06-29 |  | 2022-05-05 |  | 2022-05-05 | 2022-05-05 | pass | 2022-05-12 | EAL- Earthworks Lot | 70310 to 70326 |  | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | SB - Southbound | Qassim Al-Montafjy | This located above the HV services which is required to place Stab sand as per MRPV Superintendent request | Qassim Al- Montafjy | 2022-06-24 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-006-A1-LOT-024 | ITP-006-A1-LOT-024- Hume Hwy North Median - CH70400 - CH70460 - SB - Bottom of Subgrade | CLOSED | 2022-06-07 |  | 2022-05-10 |  | 2022-05-10 | 2022-05-10 | pass | 2022-05-10 | EAL- Earthworks Lot | 70400 to 70460 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | SB - Southbound | Qassim Al-Montafjy |  | Qassim Al-Montafjy | 2022-05-30 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-006-A1-LOT-025 | ITP-006-A1-LOT-025- Golf Course West- Ch 13865 to Ch 13900 - Subgrade prep | CLOSED | 2022-06-03 |  | 2022-05-10 |  | 2022-05-10 | 2022-05-10 | pass | 2022-05-20 | EAL- Earthworks Lot | CH13865 to CH13900 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Subgrade prep and compaction test |  | Khulood Hwayyis | 2022-06-02 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-006-A1-LOT-026 | ITP-006-A1-LOT-026- Hume Hwy North Median - CH70326 - CH70460 - SB - Subgrade | CLOSED | 2022-06-22 |  | 2022-05-11 |  | 2022-05-11 | 2022-05-11 | pass | 2022-05-11 | EAL- Earthworks Lot | CH70326 - CH70460 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | SB - Southbound | Qassim Al-Montafjy |  | Qassim al-Montafjy | 2022-06-22 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-006-A1-LOT-027 | ITP-006-A1-LOT-027- Golf Course East- Ch 13960 to Ch 14040 - 400 below subgrade | pass | pass | 2022-06-29 | 2022-05-24 |  | 2022-05-24 | 2022-05-24 | pass |  | EAL - Earthworks Lot | pass | EART - Earthwork | TYPB - Type B | 1145-C200-FUL-QAC-ITP-0006 | WB - Westbound | Khulood Hwayyis and James Moran | 400 below subgrade prep and place 1st lift of type B 765m2 | pass | pass | pass | pass
Area 1 | ITP-006-A1-LOT-028 | ITP-006-A1-LOT-028- Golf Course East- Ch 13960 to Ch 14040 - 200 below subgrade | pass | pass | 2022-06-20 | 2022-05-24 |  | 2022-05-24 | 2022-05-24 | pass |  | EAL - Earthworks Lot | pass | EART - Earthwork | TYPB - Type B | 1145-C200-FUL-QAC-ITP-0006 | WB - Westbound | Khulood Hwayyis and James Moran | Placing the 2nd lift of type B material, 200mm below subgrade | pass | pass | pass | pass
Area 1 | ITP-006-A1-LOT-029 | ITP-006-A1-LOT-029- Golf Course West- Ch 13865 to Ch 13900 - Subgrade prep | pass | pass | 2022-06-15 | 2022-05-26 |  | 2022-05-26 | 2022-05-26 | pass |  | EAL - Earthworks Lot | pass | EART - Earthwork | TYPB - Type B | 1145-C200-FUL-QAC-ITP-0006 | WB - Westbound | James Moran | Doing a second proof roll of subgrade due to rain event | pass | pass | pass | pass
Area 1 | ITP-006-A1-LOT-030 | ITP-006-A1-LOT-030- Golf Course West- Ch 13940 to Ch 14040 - Subgrade prep | pass | pass | 2022-06-21 | 2022-05-26 |  | 2022-05-26 | 2022-05-26 | pass |  | EAL - Earthworks Lot | pass | EART - Earthwork | TYPB - Type B | 1145-C200-FUL-QAC-ITP-0006 | WB - Westbound | James Moran | Proof Roll of Subgrade | pass | pass | pass | pass
Area 1 | ITP-006-A1-LOT-031 | ITP-006-A1-LOT-031 - Zone 3 - WB - Ch14625 to Ch14660 - Onhold | not started | not started |  | 2022-06-02 |  |  | 2022-06-02 |  |  | EAL - Earthworks Lot | wip | EART - Earthwork | TYPB - Type B | 1145-C200-FUL-QAC-ITP-0006 | WB - Westbound | Khulood Hwayyis | Rip and Re compact the sungrade at 820mm |  |  | not started | not started
Area 1 | ITP-006-A1-LOT-032 | ITP-006-A1-LOT-032- Hume Hwy North Median - CH70460- CH70490 - SB- Entry - Bottom Of Subgrade | CLOSED | 2022-06-07 |  | 2022-05-17 |  | 2022-05-17 | 2022-05-17 |  |  | EAL- Earthworks Lot | 70460 to 70490 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | SB - Southbound | Qassim Al-Montafjy | This Lot is for undertaking only compaction test | Qassim Al-Montafjy | 2022-05-30 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-006-A1-LOT-033 | ITP-006-A1-LOT-033- Hume Hwy North Median - CH70460 - CH70490 - SB- Entry - 400 below subgrade | CLOSED | 2022-06-14 |  | 2022-05-19 |  | 2022-05-18 | 2022-05-19 | pass | 2022-05-19 | EAL- Earthworks Lot | 70465 to 70490 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | SB - Southbound | Qassim Al-Montafjy |  | Qassim Al-Montafjy | 2022-06-09 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-006-A1-LOT-034 | ITP-006-A1-LOT-034- Hume Hwy North Median - CH70460- CH70490 - SB- Entry - 200mm below Subgrade/ Cut floor | CLOSED | 2022-06-14 |  | 2022-05-18 |  | 2022-05-18 | 2022-05-18 | pass | 2022-05-19 | EAL- Earthworks Lot | 70460 to 70490 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | SB - Southbound | Qassim Al-Montafjy |  | Qassim Al-Montafjy | 2022-06-09 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-006-A1-LOT-035 | ITP-006-A1-LOT-035- Hume Hwy North Median - CH70460- CH70490 - SB- Entry - Subgrade | CLOSED | 2022-06-21 |  | 2022-05-19 |  | 2022-05-19 | 2022-05-19 | pass | 2022-05-19 | EAL- Earthworks Lot | 70460 to 70490 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | SB - Southbound | Qassim Al-Montafjy |  | Qassim Al-Montafjy | 2022-06-17 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-006-A1-LOT-036 | ITP-006-A1-LOT-036 - Hume Hwy North Median - CH70400 - CH70435 - NB - Type Pavement 6 - Egress- Subgrade | not started | not started |  | 2022-05-24 |  | 2022-05-24 | 2022-05-24 | not started |  | EAL - Earthworks Lot | pass | EART - Earthwork | TYPB - Type B | 1145-C200-FUL-QAC-ITP-0006 | NB - Northbound | Qassim Al-Montafjy | This lot is for undertaking a compaction Test for Subgrade layer of Pavement Type 6 | not started | not started | not started | not started
Area 1 | ITP-006-A1-LOT-038 | ITP-006-A1-LOT-038- Memorial Park East - CH16145 - CH16220 - 600mm below cut floor | not started | not started |  | 2022-06-29 |  | 2022-06-29 | 2022-06-29 |  |  | EAL - Earthworks Lot | wip | EART - Earthwork | TYPB - Type B | 1145-ACM-CVP-DPK-0001 | EB - Eastbound | Qassim Al-Montafjy |  |  |  | not started | not started
Area 1 | ITP-006-A1-LOT-039 | ITP-006-A1-LOT-039- Hume Hwy North- Bullnose - CH16366 - CH16380 - 200mm below Subgrade | not started | not started |  | 2022-06-30 |  | 2022-06-30 | 2022-06-30 |  |  | EAL - Earthworks Lot | wip | EART - Earthwork | TYPB - Type B | 1145-ACM-CVP-DPK-0001 | ME - Median | Qassim Al-Montafjy |  |  |  | not started | not started
Area 1 | ITP-006-A1-LOT-040 | ITP-006-A1-LOT-040- Hume Hwy South - Bullnose - CH16366 - CH16380 - 200mm below Subgrade | not started | not started |  | 2022-06-30 |  | 2022-06-30 | 2022-06-30 |  |  | EAL - Earthworks Lot | wip | EART - Earthwork | TYPB - Type B | 1145-ACM-CVP-DPK-0001 | ME - Median | Qasssim Al-Montafjy | This work Done as per RFI dispensation of TYPE B first Layer and Placing CTCR as 2nd of Type B |  |  | not started | not started
Area 1 | ITP-006-A1-LOT-041 | ITP-006-A1-LOT-041- Memorial Park East - CH16145 - CH16220 - 300mm below Subgrade | not started | not started | [8 empty] | not started | [8 empty] | not started | not started
Area 1 | ITP-007-A1-LOT-001 | ITP-007-A1-LOT-001 - Memorial Park - CH26130- CH26225 - NB | CLOSED | 2022-04-06 |  | 2021-12-03 |  | 2021-12-03 | 2021-12-01 | not applicable |  | CIL-Civil Lot | CH26130- CH26225 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | EB - Eastbound | Qassim AL-MONTAFJY | This lot is affected by asbestos | Babak Rudd | 2022-04-06 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-007-A1-LOT-002 | ITP-007-A1-LOT-002 - Hume Hwy North Median - CH70330 - CH70400 - NB | CLOSED | 2022-04-06 |  | 2021-12-09 |  | 2021-12-09 | 2021-12-10 | not applicable |  | EAL- Earthworks Lot | CH70330-CH70400 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | NB - Northbound | Qassim Al-Montafjy | Lot affaced by asbestos | Babak Rudd | 2022-04-06 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-007-A1-LOT-003 | ITP-007-A1-LOT-003 - Hume Hwy North Median - CH70330 - CH70400 - NB | CLOSED | 2022-04-06 |  | 2021-12-10 |  | 2021-12-10 | 2021-12-10 | not applicable |  | EAL- Earthworks Lot | CH70330-CH70400 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | NB - Northbound | Qassim Al-Montafjy | This lot affected by asbestos | Babak Rudd | 2022-04-06 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-007-A1-LOT-004 | ITP-007-A1-LOT-004 - Hume Hwy North Median - CH70400 - CH70445 - NB | CLOSED | 2022-04-06 |  | 2021-12-13 |  | 2021-12-13 | 2021-12-13 | not applicable |  | EAL- Earthworks Lot | CH70400 - CH70445 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | NB - Northbound | QASSIM AL-MONTAFJY, KHULOOD HWAYYIS | PLACE THE FIRST 130mm OF TYPE A MATERIAL | Babak Rudd | 2022-04-06 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-007-A1-LOT-005 | ITP-007-A1-LOT-005 - Hume Hwy North Median - CH70400 - CH70445 - NB | CLOSED | 2022-04-06 |  | 2021-12-13 |  | 2021-12-13 | 13/12/2021 | not applicable |  | EAL- Earthworks Lot | CH70400 - CH70445 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | NB - Northbound | QASSIM AL-MONTAFJY, KHULOOD HWAYYIS | PLACEMENT OF THE SECOND 130mm TYPE A MATERIAL | Babak Rudd | 2022-04-06 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-007-A1-LOT-006 | ITP-007-A1-LOT-006 - Hume Hwy North Median - CH70485 - CH70506 - SB - Layer 1 | CLOSED | 2022-04-06 |  | 2021-12-15 |  | 2021-12-15 | 2021-12-15 | not applicable |  | EAL- Earthworks Lot | CH70485 To CH70506 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | SB - Southbound | Qassim Al-Montafjy | This lot affected by abestos | Babak Rudd | 2022-04-06 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-007-A1-LOT-007 | ITP-007-A1-LOT-007 - Hume Hwy North Median - CH70485 - CH70506 - SB | CLOSED | 2022-04-06 |  | 2021-12-15 |  | 2021-12-15 | 2021-12-15 | not applicable |  | EAL- Earthworks Lot | CH70485 TO CH70506 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | SB - Southbound | Qassim Al-Montafjy | The area is closed to the Gate 1.2 | Babak Rudd | 2022-04-06 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-007-A1-LOT-008 | ITP-007-A1-LOT-008 - Hume Hwy South Median - CH70190 - CH70280 - NB - Layer 1 | CLOSED | 2022-06-29 |  | 2022-02-14 |  | 14/02/2022 | 2022-02-14 | 2022-02-17 |  | EAL- Earthworks Lot | 70190 to 70280 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | NB - Northbound | Qassim Al-Montafjy | Placing the 1st layer of Type A | Qassim Al-Montafjy | 2022-06-24 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-007-A1-LOT-009 | ITP-007-A1-LOT-009 - Hume Hwy South Median - CH70190 - CH70280 - NB - Layer 2 |  |  |  | 2022-02-14 |  | 2022-02-14 | 2022-02-15 |  |  | EAL- Earthworks Lot | 70190 to 70280 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | NB - Northbound | Qassim Al-Montafjy | Placing 2nd Layer of Type A | Qassim Al-Montafjy
Area 1 | ITP-007-A1-LOT-010 | ITP-007-A1-LOT-010 - Golf Course East - WB - CH14250-CH14090 - Lift 1 |  |  |  | 2022-03-21 |  | 2022-03-21 | 2022-03-21 | 2022-05-11 |  | EAL- Earthworks Lot | CH14090-CH14250 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Khulood Hwayyis | Place 150mm (first lift) of Type A Material | Khulood Hwayyis | 2022-05-30
Area 1 | ITP-007-A1-LOT-011 | ITP-007-A1-LOT-011 - Golf Course East - WB - CH14250-CH14090 - Lift 2 |  |  |  | 2022-03-22 |  | 2022-03-22 | 2022-03-22 |  |  | EAL- Earthworks Lot | CH14090-CH14250 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | WB - Westbound | James Moran | Place 150mm (second lift) of Type A Material
Area 1 | ITP-007-A1-LOT-012 | ITP-007-A1-LOT-012 - Golf Course West - WB - CH13860-CH13700 - Lift 1 |  |  |  | 2022-03-30 |  | 2022-03-31 | 2022-04-01 |  |  | CIL-Civil Lot | 13860 - 13640 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | WB - Westbound | James Moran | Golf Course West - Type A Capping
Area 1 | ITP-007-A1-LOT-013 | ITP-007-A1-LOT-013 - Golf Course West - WB - CH13860-CH13700 - Lift 2 |  |  |  | 2022-04-02 |  | 2022-04-02 | 2022-04-02 |  |  | EAL- Earthworks Lot | 13860 - 13700 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | WB - Westbound | James Moran | Place Type A Day 2
Area 1 | ITP-007-A1-LOT-015 | ITP-007-A1-LOT-015 - Hume Hwy North Median - CH70330 - CH70400 - NB - Layer 2 |  |  |  | 2022-04-08 |  | 2022-04-08 | 2022-04-08 | 2022-05-17 |  |  | 70330 to 70400 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | NB - Northbound | Qassim Al-Montafjy | Placing Type A @ 260mm as a one Layer | Qassim Al-Montafjy | 2022-06-16
Area 1 | ITP-007-A1-LOT-018 | ITP-007-A1-LOT-018 - Golf Course East - WB - CH14250-CH14306 - lift 1 |  |  |  | 12.04.2022 |  | 12.04.2022 | 12.04.2022 |  |  | EAL- Earthworks Lot | CH14250-CH14306 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | WB - Westbound | James Moran |  | Khulood Hwayyis | 2022-05-24
Area 1 | ITP-007-A1-LOT-020 | ITP-007-A1-LOT-020 - Golf Course East - WB - CH14250-CH14306 - lift 2 |  |  |  | 2022-04-13 |  | 2022-04-13 | 2022-04-13 |  |  | EAL- Earthworks Lot | CH14250 to CH14306 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Khulood Hwayyis | Review the area and place the 2nd lift of Capping
Area 1 | ITP-007-A1-LOT-022 | ITP-007-A1-LOT-022 - Hume Hwy North Median - CH70310 - CH70330 - NB - Layer 1 | CLOSED | 2022-06-07 |  | 2022-04-28 |  | 2022-04-28 | 2022-04-28 | 2022-04-28 |  | EAL- Earthworks Lot | 70310 to 70330 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | NB - Northbound | Qassim Al-Montafjy | This lot is located between bull nos and High Voltage | Qassim Al-Montafjy | 2022-06-03 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-007-A1-LOT-023 | ITP-007-A1-LOT-023 - Hume Hwy North Median - CH70310 - CH70330 - NB - Layer 2 | CLOSED | 2022-06-22 |  | 2022-04-28 |  | 2022-04-28 | 2022-04-28 | 2022-03-30 |  | EAL- Earthworks Lot | 70310 to 70330 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | NB - Northbound | Qassim Al-Montafjy |  | Qassim Al-Montafjy | 2022-06-16 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-007-A1-LOT-024 | ITP-007-A1-LOT-024 - Golf Course West - Ch13865 to Ch13900 - 1st lift Capping |  |  |  | 2022-05-10 |  | 2022-05-26 | 2022-05-26 |  |  | EAL- Earthworks Lot | Ch13865 to Ch13900 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | WB - Westbound | James Moran | Review the subgrade and place 1st lift of Capping
Area 1 | ITP-007-A1-LOT-025 | ITP-007-A1-LOT-025 - Hume Hwy North Median - CH70400 - CH70460 - SB - Type A Layer 1 | CLOSED | 2022-06-16 |  | 2022-05-11 |  | 2022-05-11 | 2022-05-11 | 2022-05-12 |  | EAL- Earthworks Lot | CH70382 - CH70460 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | SB - Southbound | Qassim Al-Montafjy |  | Qassim Al-Montafjy | 2022-06-01 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-007-A1-LOT-026 | ITP-007-A1-LOT-026 - Hume Hwy North Median - CH70326 - CH70400 - SB - Type A Layer 1 | CLOSED | 2022-06-21 |  | 125/05/2022 |  | 2022-05-12 | 2022-05-12 | 2022-05-14 |  | EAL- Earthworks Lot | 70310 to 70400 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | SB - Southbound | Qassim Al- Montafjy | Placing Type A @ 260mm as a one layer | Qassim Al-Montafjy | 2022-06-16 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-007-A1-LOT-027 | ITP-007-A1-LOT-027- Hume Hwy North Median - CH70460 - CH70490 - SB- Entry - Type A Layer 1 | CLOSED | 2022-06-16 |  | 2022-05-20 |  | 2022-05-20 | 2022-05-20 | 2022-05-20 |  | EAL- Earthworks Lot | CH70460 - CH70490 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | SB - Southbound | Qassim Al-Montafjy |  | Qassim Al-Montafjy | 2022-06-15 | Babak Rudd-Project Quality Manager | N/A
Area 1 | ITP-007-A1-LOT-028 | ITP-007-A1-LOT-028- Hume Hwy North- Bullnose - CH16366 - CH16380 - Type A - Layer 1 | not started | not started |  | 2022-07-08 |  | 2022-07-08 | 2022-07-08 |  |  | EAL - Earthworks Lot | CH16366 to CH16380 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVP-DPK-0001 | ME - Median | Qassim Al-Montafjy |  |  |  | not started | not started
Area 1 | ITP-007-A1-LOT-029 | ITP-007-A1-LOT-029- Hume Hwy South - Bullnose - CH16366 - CH16380 - Type A -Layer 1 | not started | not started |  | 2022-07-08 |  | 2022-07-08 | 2022-07-08 |  |  | EAL - Earthworks Lot | CH16366 to CH16380 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | ME - Median | Qassim Al-Montafjy |  |  |  | not started | not started
Area 1 | ITP-009-A1-LOT-003 | ITP-009-A1-LOT-003 - Golf Course East - CH14250-CH14165 - WB | not started | not started |  | 2022-03-22 |  | 2022-03-30 | 2022-03-30 |  |  | EAL- Earthworks Lot | CH14165 to CH14250 | PAVI - Paving | PAVI - Unbound Pavements | 1145-C200-FUL-QAC-0009 | WB - Westbound | Khulood Hwayyis | Place 150mm of Class 4 Crushed rock |  |  | not started | not started
Area 1 | ITP-009-A1-LOT-004 | ITP-009-A1-LOT-004 - Golf Course East - CH14165-CH14090 - WB | not started | not started |  | 2022-04-02 |  | 2022-04-02 | 2022-04-02 |  |  | EAL- Earthworks Lot | CH14090 to CH14165 | PAVI - Paving | PAVI - Unbound Pavements | 1145-C200-FUL-QAC-0009 | WB - Westbound | Khulood Hwayyis | Place 150mm of CL4 |  |  | not started | not started
Area 1 | ITP-009-A1-LOT-005 | ITP-009-A1-LOT-005 - Hume Hwy North Median - CH70310 - CH70400 - NB - CL4 | not started | not started | [17 empty] | not started | not started
Area 1 | ITP-009-A1-LOT-006 | ITP-009-A1-LOT-006 - Hume Hwy North Median - CH70310 - CH70460 - SB - CL4 | not started | not started | [17 empty] | not started | not started
Area 1 | ITP-009-A1-LOT-007 | ITP-009-A1-LOT-007 - Hume Hwy North Median - CH70460 - CH70490 - SB - Entry- CL4 | not started | not started | [17 empty] | not started | not started
Area 1 | ITP-009-A1-LOT-008 | ITP-009-A1-LOT-008 - Hume Hwy South Median - CH70140 - CH70190 - NB - Type 6 Pavement | not started | not started | [17 empty] | not started | not started
Area 1 | ITP-010-A1-LOT-001 | ITP-010-A1-LOT-001 - Hume Hwy North - Ch 70320 - Ch 70460- SB - Double Sides | not started | not started |  | 2022-06-29 |  | 2022-06-29 | 29/06/200 |  |  | DRL- Drainage Lot | 70320 to 70452 |  | SUBS Subsoil Drainage ÃŠ | 1145-ACM-CVD-DPK-0002 | SB - Southbound | Qassim Al-Montafjy |  |  |  | not started | not started
Area 1 | ITP-010-A1-LOT-002 | ITP-010-A1-LOT-002 - Hume Hwy South - Ch 70140 - Ch 70204 - NB - Double sides | not started | not started |  | 2022-06-29 |  | 2022-06-29 | 2022-06-29 |  |  | CIL-Civil Lot | CH70140 to CH70204 |  | SUBS Subsoil Drainage ÃŠ | 1145-ACM-CVD-DPK-0002 | NB - Northbound | Qassim Al-Montafjy |  |  |  | not started | not started
Area 1 | ITP-010-A1-LOT-003 | ITP-010-A1-LOT-003 - Hume Hwy North - Ch 70315 - Ch 70386 - NB -Double sides | not started | not started |  | 2022-07-04 |  | 2022-07-04 | 2022-07-04 |  |  | DRL- Drainage Lot | CH70315 to CH70386 | STOR - Stormwater | SUBS Subsoil Drainage ÃŠ | 1145-ACM-CVD-DPK-0002 | NB - Northbound | Qassim Al-Montafjy |  |  |  | not started | not started
Area 1 | ITP-010-A1-LOT-004 | ITP-010-A1-LOT-004- Hume Hwy North - Ch 70386 - Ch 70436 - NB- One side | not started | not started | [17 empty] | not started | not started
Area 1 | ITP-010-A1-LOT-005 | ITP-010-A1-LOT-005- Hume Hwy North - Ch 70460- Ch 70490 - SB- West side | not started | not started |  | 2022-07-06 |  | 2022-07-06 | 2022-07-06 |  |  | DRL- Drainage Lot | CH70460 to CH70490 | STOR - Stormwater | SUBS Subsoil Drainage ÃŠ | 1145-ACM-CVD-DPK-0002 | SB - Southbound | Qassim Al-Montafjy |  |  |  | not started | not started
Area 1 | ITP-017-A1-LOT-001 | ITP-017-A1-LOT-001 - Stormwater Drainage - Pit 1002 to Pit 1001 - Hume Hwy southbound Xing - Z1 | wip | wip |  | 2022-01-30 |  | 2022-01-30 | 2022-01-30 |  |  | DRL- Drainage Lot |  | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | SB - Southbound | Omar El-Khub | PROBLEM LOT. Lot Status: OPEN, Verified by: Name, Date: date. Over 60 days due to waiting for CCTV Report. |  |  | wip | wip
Area 1 | ITP-017-A1-LOT-002 | ITP-017-A1-LOT-002 - Stormwater Drainage - Pit 1014 to Pit 1015 | wip | wip |  | 2022-02-28 |  | 2022-02-28 | 2022-02-28 |  |  | DRL- Drainage Lot | 70205 to 70210 | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ |  | NB - Northbound | Qassim Al-Montafjy | Over 60 days due to waiting for CCTV Report |  |  | wip | wip
Area 1 | ITP-017-A1-LOT-003 | ITP-017-A1-LOT-003 - Stormwater Drainage - Pit 1015 to Pit 1016 | wip | wip |  | 2022-02-28 |  | 28/02/20222 | 2022-02-28 |  |  | DRL- Drainage Lot | 70197 to 70104 | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | NB - Northbound | Qassim Al-Montafjy | Over 60 days due to waiting for CCTV Report |  |  | wip | wip
Area 1 | ITP-017-A1-LOT-004 | ITP-017-A1-LOT-004 - Stormwater Drainage - Pit 1016 to Pit 1017 | wip | wip |  | 2022-02-28 |  | 2022-02-28 | 2022-02-28 |  |  | DRL- Drainage Lot | 70194 to 70197 | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | NB - Northbound | Qassim Al-Montafjy | Over 60 days due to waiting for CCTV Report |  |  | wip | wip
Area 1 | ITP-017-A1-LOT-005 | ITP-017-A1-LOT-005 - Stormwater Drainage - Pit 1017 to Pit 1018 | wip | wip |  | 2022-02-28 |  | 2022-02-28 | 2022-02-28 |  |  | DRL- Drainage Lot | 70187 to 70194 | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | NB - Northbound | Qassim Al- Montafjy | Over 60 days due to waiting for CCTV Report |  |  | wip | wip
Area 1 | ITP-017-A1-LOT-006 | ITP-017-A1-LOT-006 - Stormwater Drainage - Pit 1018 to Pit 1019 | wip | wip |  | 2022-02-28 |  | 2022-02-28 | 28/02/2022` |  |  | DRL- Drainage Lot | 70175 to 70187 | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | NB - Northbound | Qassim Al-Montafjy | Over 60 days due to waiting for CCTV Report |  |  | wip | wip
Area 1 | ITP-017-A1-LOT-007 | ITP-017-A1-LOT-007 - Stormwater Drainage - Pit 1019 to Pit 1020 | wip | wip |  | 2022-02-28 |  | 28/02/20222 | 2022-02-28 |  |  | DRL- Drainage Lot | 70140 to 70150 | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | NB - Northbound | Qassim Al- Montafjy | Over 60 days due to waiting for CCTV Report |  |  | wip | wip
Area 1 | ITP-017-A1-LOT-008 | ITP-017-A1-LOT-008 - Stormwater Drainage - Pit 1020 to Pit 1021 | wip | wip |  | 2022-02-28 |  | 2022-02-28 | 2022-02-28 |  |  | DRL- Drainage Lot | 70137 to 70157 | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | NB - Northbound | Qassim Al _montntafjy | Over 60 days due to waiting for CCTV Report |  |  | wip | wip
Area 1 | ITP-017-A1-LOT-009 | ITP-017-A1-LOT-009 - Stormwater Drainage - Pit 1021 to Pit 1022 | wip | wip |  | 2022-02-28 |  | 2022-02-28 | 2022-03-23 |  |  | DRL- Drainage Lot | 70116 to 70130 | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | NB - Northbound | Qassim Al-Montafjy | Over 60 days due to waiting for CCTV Report |  |  | wip | wip
Area 1 | ITP-017-A1-LOT-010 | ITP-017-A1-LOT-010 - Stormwater Drainage - Pit 1002 to Pit 1003 | not started | not started |  | 2022-03-10 |  | 2022-03-10 | 2022-03-18 |  |  | DRL- Drainage Lot | 70320 to 70450 | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 |  | Qassim Al-montafjy | Install Drainage Line between pit 1002 and 1003 at Hume North Median. Over 60 days due to waiting for CCTV Report. |  |  | not started | not started
Area 1 | ITP-017-A1-LOT-011 | ITP-017-A1-LOT-011 - Stormwater Drainage - Pit 1002 to Pit 1007 | not started | not started |  | 2022-03-10 |  | 2022-03-10 |  |  |  |  | 70320 to 70450 | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 |  | Qassim al-Montafjy |  |  |  | not started | not started
Area 1 | ITP-017-A1-LOT-012 | ITP-017-A1-LOT-012 - Stormwater Drainage - Pit 1003 to Pit 1004 | wip | wip |  | 2022-03-10 |  | 2022-03-10 | 2022-03-18 |  |  | DRL- Drainage Lot | 70320 to 70450 | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 |  | Qassim Al-Montafjy | Over 60 days due to waiting for CCTV Report |  |  | wip | wip
Area 1 | ITP-017-A1-LOT-013 | ITP-017-A1-LOT-013 - Stormwater Drainage - Pit 1003 to Pit 1006 |  |  |  | 2022-03-10 |  | 2022-03-10 |  |  |  | DRL- Drainage Lot | 70320 to 70450 | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 |  | Qassim Al-Montafjy
Area 1 | ITP-017-A1-LOT-014 | ITP-017-A1-LOT-014 - Stormwater Drainage - Pit 1004 to Pit 1005 | not started | not started |  | 2022-03-10 |  | 2022-03-10 | 2022-03-18 |  |  | DRL- Drainage Lot | 70320 to 70450 | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 |  | Qassim Al-Montafjy | Install Drainage Line between pit 1004 and 1005 at Hume North Median. Over 60 days due to waiting for CCTV Report. |  |  | not started | not started
Area 1 | ITP-017-A1-LOT-015 | ITP-017-A1-LOT-015 - Stormwater Drainage - Pit 1007 to Pit 1008 | not started | not started |  | 2022-03-10 |  | 2022-03-10 |  |  |  | DRL- Drainage Lot | 70320 to 70450 | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 |  | Qassim Al-Montafjy |  |  |  | not started | not started
Area 1 | ITP-017-A1-LOT-016 | ITP-017-A1-LOT-016 - Stormwater Drainage - Pit 1007 to Pit 1009 | not started | not started | [7 empty] | DRL- Drainage Lot |  | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | [5 empty] | not started | not started
Area 1 | ITP-017-A1-LOT-017 | ITP-017-A1-LOT-017 - Stormwater Drainage - Pit 1009 to Pit 1010 | not started | not started |  | 2022-03-10 |  | 2022-03-10 |  |  |  | DRL- Drainage Lot | 70320 to 70450 | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 |  | Qassim Al-Montafjy |  |  |  | not started | not started
Area 1 | ITP-017-A1-LOT-018 | ITP-017-A1-LOT-018 - Stormwater Drainage - Head wall 1000 to Pit 1001 | not started | not started |  | 2022-03-22 |  | 2022-03-22 | 2022-03-22 |  |  | DRL- Drainage Lot | At the rear of Hume compound | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | SB - Southbound | Qassim Al-Montafjy | Install Pit 1001 and stormwater pipe. Over 60 days due to waiting for CCTV Report. |  |  | not started | not started
Area 1 | ITP-017-A1-LOT-019 | ITP-017-A1-LOT-019 - Stormwater Drainage - Pit 226 to Pit 227 | not started | not started |  | 2022-04-05 |  | 2022-04-06 | 2022-04-06 | 2022-04-12 |  | DRL- Drainage Lot | 13865 - 13842 | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | WB - Westbound | James Moran | Drainage - Golf Course West- Zone 4. Over 60 days due to waiting for CCTV Report. | James Moran | 2022-06-10 | not started | not started
Area 1 | ITP-017-A1-LOT-020 | ITP-017-A1-LOT-020 - Stormwater Drainage - Pit 227 to Pit 228 | not started | not started |  | 2022-04-06 |  | 2022-04-06 | 2022-04-06 | 2022-04-13 |  | DRL- Drainage Lot | 13842 - 13815 | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | WB - Westbound | James Moran | Golf Course West - Zone 4. Over 60 days due to waiting for CCTV Report. | James Moran | 2022-06-10 | not started | not started
Area 1 | ITP-017-A1-LOT-021 | ITP-017-A1-LOT-021 - Stormwater Drainage - Pit 228 to Pit 230 | not started | not started |  | 2022-04-06 |  | 2022-04-06 | 2022-04-06 | 2022-04-14 |  | DRL- Drainage Lot | 13815 - 13797 | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | WB - Westbound | James Moran | Golf Course West - Zone 4. Over 60 days due to waiting for CCTV Report. | James Moran | 2022-06-10 | not started | not started
Area 1 | ITP-017-A1-LOT-022 | ITP-017-A1-LOT-022 - Stormwater Drainage - Pit 230 to Pit 231 | not started | not started |  | 2022-04-06 |  | 2022-04-06 | 2022-04-06 | 2022-05-04 |  | DRL- Drainage Lot | 13797 - 13770 | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | WB - Westbound | James Moran | Golf Course West - Zone 4. Over 60 days due to waiting for CCTV Report. | James Moran | 2022-06-10 | not started | not started
Area 1 | ITP-017-A1-LOT-023 | ITP-017-A1-LOT-023 - Stormwater Drainage - Pit 231 to Pit 232 | not started | not started |  | 2022-04-06 |  | 2022-04-06 | 2022-04-06 | 2022-05-06 |  | DRL- Drainage Lot | 13770 - 13745 | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | WB - Westbound | James Moran | Golf Course West - Zone 4. Over 60 days due to waiting for CCTV Report. | James Moran | 2022-06-10 | not started | not started
Area 1 | ITP-017-A1-LOT-024 | ITP-017-A1-LOT-024 - Stormwater Drainage - Pit 232 to Pit 233 | not started | not started |  | 2022-04-07 |  | 2022-04-07 | 2022-04-07 | 2022-05-10 |  | DRL- Drainage Lot | 13745 - 13730 | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | WB - Westbound | James Moran | Golf Course West - Zone 4. Over 60 days due to waiting for CCTV Report. | James Moran | 2022-06-10 | not started | not started
Area 1 | ITP-017-A1-LOT-025 | ITP-017-A1-LOT-025 - Stormwater Drainage - Pit 233 to Pit 234 | not started | not started |  | 2022-04-07 |  | 2022-04-07 | 2022-04-07 | 2022-05-10 |  | DRL- Drainage Lot | 13730 - 13705 | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | WB - Westbound | James Moran | Golf Course West - Zone 4. Over 60 days due to waiting for CCTV Report. | James Moran | 2022-06-10 | not started | not started
Area 1 | ITP-017-A1-LOT-026 | ITP-017-A1-LOT-026 - RCBC - Hume South Median - Pit 1011 to Pit 1012 | not started | not started |  | 2022-07-04 |  | 2022-07-04 | 2022-07-04 |  |  | DRL- Drainage Lot | CH70269 to CH70278 |  | STOR - DRAP Drainage ÃŠÃŠ | 1145-ACM-CVD-DPK-0002 | NB - Northbound | QassimAl-Montafjy |  |  |  | not started | not started
Area 1 | ITP-065-A1-LOT-001 | ITP-065-A1-LOT-001 - WRSB Anchor Block Pour - Hume Hwy North median - Northbound and Southbound | not started | not started |  | 2022-02-07 |  | 2021-11-19 | 2021-11-19 |  |  | CIL-Civil Lot | CH70300 - CH70500 | SAFE | SAFE - Safety Barrier | 1145-C200-FUL-QAC-0065 | ME - Median | Omar El-Khub |  |  |  | not started | not started
Area 2 | ITP-001-A2-LOT-001 | ITP-001-A2-LOT-001 - 9 Trees WB CH10780-CH10940 | [7 empty] | pass | [9 empty] | Georgie Brady | 2021-10-25
Area 2 | ITP-001-A2-LOT-002 | ITP-001-A2-LOT-002 - 34 Trees WB CH10800-CH11050 | [7 empty] | pass | [9 empty] | Georgie Brady | 2021-10-25
Area 2 | ITP-001-A2-LOT-003 | ITP-001-A2-LOT-003 - WB CH10900-CH11300 Stripping | CLOSED | 2022-02-18 |  | 2021-10-11 |  | 2021-10-11 | 2021-10-08 | 2021-11-03 |  | EAL- Earthworks Lot | CH10900-CH11300 | EART - Earthwork | CLGR - Clearing and Grubbing | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Abed Wardak | Stripping of 150mm | Abed Wardak | 2021-12-02 | Babak Rudd-Project Quality Manager | N/A
Area 2 | ITP-001-A2-LOT-004 | ITP-001-A2-LOT-004 - WB CH10500-CH10880 Stripping | [7 empty] | pass | [9 empty] | Abed Wardak | 2021-10-18
Area 2 | ITP-001-A2-LOT-005 | ITP-001-A2-LOT-005 - 29 trees CH11500-CH11300 | CLOSED | 2022-10-12 |  | 2021-10-05 |  | 2021-10-05 | 2021-10-05 | 2021-10-12 |  | EAL- Earthworks Lot | CH11500-CH11300 | EART - Earthwork | CLGR - Clearing and Grubbing | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Georgina Brady |  | Georgie Brady | 2021-11-05 | Steve Felsinger- Area Manager | N/A
Area 2 | ITP-001-A2-LOT-006 | ITP-001-A2-LOT-006 - Mickleham North CH40350 - CH40700 | CLOSED | 2022-03-31 |  | 2022-01-14 |  | 2022-01-14 | 2022-01-17 | 2022-01-21 |  | CIL-Civil Lot | CH 40350 TO CH 40500 | EART - Earthwork | CLGR - Clearing and Grubbing | 1145-ACM-CVR-DPK-0001 | NB - Northbound | Varun Panickar |  | Varun Panickar | 2022-03-30 | Babak Rudd-Project Quality Manager | N/A
Area 2 | ITP-001-A2-LOT-007 | ITP-001-A2-LOT-007 - Debonair - Vantage Stripping | CLOSED | 2022-02-18 |  | 2021-10-28 |  | 2021-10-28 | 2021-10-28 | 2021-11-08 |  | EAL- Earthworks Lot | CH11320-CH11700 | EART - Earthwork | CLGR - Clearing and Grubbing | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Abed Wardak | Stripping 150mm | Abed Wardak | 2021-12-02 | Babak Rudd-Project Quality Manager | N/A
Area 2 | ITP-001-A2-LOT-008 | ITP-001-A2-LOT-008 - 48 trees CH10100-CH10240 | CLOSED | 2022-02-18 |  | 2021-11-23 |  | 2021-11-23 | 2021-11-23 | 2021-12-17 |  | EAL- Earthworks Lot | CH10100-10240 | EART - Earthwork | CLGR - Clearing and Grubbing | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Georgie Brady | Tree clearing and pruning in property 755 | Varun Panickar | 2022-02-17 | Babak Rudd-Project Quality Manager | N/A
Area 2 | ITP-001-A2-LOT-009 | ITP-001-A2-LOT-009 - CH60140-CH60310 Stripping | CLOSED | 2022-02-18 |  | 2021-11-25 |  | 2021-11-25 | 2021-11-25 | 2021-11-26 |  | EAL- Earthworks Lot | CH60140-CH60310 | EART - Earthwork | CLGR - Clearing and Grubbing | 1145-ACM-CVR-DPK-0001 | SB - Southbound | Georgie Brady | Stripping of topsoil for haul rd | Varun Panickar | 2022-02-17 | Babak Rudd-Project Quality Manager | N/A
Area 2 | ITP-001-A2-LOT-010 | ITP-001-A2-LOT-010 - 129 trees CH10235-CH10500 | CLOSED | 2022-02-18 |  | 2021-11-25 |  | 2021-11-25 | 2021-11-25 | 2021-12-02 |  | EAL- Earthworks Lot | CH10235-CH10500 | EART - Earthwork | CLGR - Clearing and Grubbing | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Georgie Brady | Trees in property 1505 (total 129) | Georgina Brady | 2021-12-07 | Babak Rudd-Project Quality Manager | N/A
Area 2 | ITP-001-A2-LOT-011 | ITP-001-A2-LOT-011 - 9 Trees NB and SB CH40200-CH40600 | CLOSED | 2022-02-18 |  | 2022-01-10 |  | 2022-01-10 | 2022-01-12 | 2022-01-14 |  | EAL- Earthworks Lot | 40200-40600 | EART - Earthwork | CLGR - Clearing and Grubbing | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Georgie Brady | 9 x trees Mickleham Rd | Georgina Brady | 2022-01-17 | Babak Rudd-Project Quality Manager | N/A
Area 2 | ITP-001-A2-LOT-012 | ITP-001-A2-LOT-012 - WB CH10650-CH10500 Stripping |  |  |  | 2022-01-19 |  | 2022-01-19 | 2022-01-19 |  |  | EAL- Earthworks Lot | CH10650 to CH10500 | EART - Earthwork | CLGR - Clearing and Grubbing | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Jonathon Rock | Stripping top soil
Area 2 | ITP-001-A2-LOT-013 | ITP-001-A2-LOT-013 - WB CH10100 - CH10290 Stripping | CLOSED | 2022-02-18 |  | 2022-01-17 |  | 2022-01-17 | 2022-01-17 | 2022-02-10 |  | EAL- Earthworks Lot | CH10100 TO CH10290 | EART - Earthwork | CLGR - Clearing and Grubbing | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Varun Panickar | Top soil stripping | Varun Panickar | 2022-02-14 | Babak Rudd-Project Quality Manager | NO
Area 2 | ITP-001-A2-LOT-014 | ITP-001-A2-LOT-014 - WB CH10370 - CH10490 Stripping | CLOSED | 2022-02-18 |  | 2022-01-20 |  | 2022-01-20 | 2022-01-22 | 2022-02-12 |  | EAL- Earthworks Lot | CH10370 to CH10490 | EART - Earthwork | CLGR - Clearing and Grubbing | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Varun Panickar | Top Soil Stripping | Varun Panickar | 2022-02-15 | Babak Rudd-Project Quality Manager | N/A
Area 2 | ITP-001-A2-LOT-016 | ITP-001-A2-LOT-016 - Mickleham South 30000-30200 | CLOSED | 2022-03-31 |  | 2022-01-11 |  | 2022-01-11 | 2022-01-11 | 2022-01-20 |  | CIL-Civil Lot | 30000-30200 | EART - Earthwork | CLGR - Clearing and Grubbing | 1145-ACM-CVR-DPK-0001 | SB - Southbound | Aadish Pudasaini |  | Aadish Pudasaini | 2022-02-22 | Babak Rudd-Project Quality Manager | N/A
Area 2 | ITP-001-A2-LOT-017 | ITP-001-A2-LOT-017 - Mickleham South CH30200 - CH30400 | CLOSED | 2022-03-31 |  | 2022-01-11 |  | 2022-01-11 | 2022-01-11 | 2022-02-11 |  | CIL-Civil Lot | CH 30200 to CH 30400 | EART - Earthwork | CLGR - Clearing and Grubbing | 1145-ACM-CVR-DPK-0001 | SB - Southbound | Aadish Pudasaini |  | Varun Panickar | 2022-03-30 | Babak Rudd-Project Quality Manager | N/A
Area 2 | ITP-001-A2-LOT-019 | ITP-001-A2-LOT-019 - 2 trees CH11050 - CH11100 |  |  |  | 2022-04-06 |  | 2022-04-06 | 2022-04-06 |  |  |  | 11050 - 111000 | [5 empty] | ID 1634 and 1626
Area 2 | ITP-001-A2-LOT-021 | ITP-001-A2-LOT-021 - Zone 5 â€“ Aitken Blvd - SB - CH60540-CH60340 |  |  |  | 2022-05-24 |  | 2022-05-24 | 2022-05-24 |  |  | EAL- Earthworks Lot | CH60530 to CH60320 | EART - Earthwork | CLGR - Clearing and Grubbing | 1145-ACM-CVR-DPK-0001 | SB - Southbound | Abed Wardak | Stripping Topsoil 150mm
Area 2 | ITP-001-A2-LOT-022 | ITP-001-A2-LOT-022 - Desc - tree removal opposite Champion Pde |  |  |  | 2022-05-26 |  |  | 2022-06-20 |  |  | UTL- Utility Lot | CH12280-12320 | EART - Earthwork | CLGR - Clearing and Grubbing | 1145-ACM-CVR-DPK-0001 | EB - Eastbound | Simon Colosimo
Area 2 | ITP-001-A2-LOT-023 | ITP-001-A2-LOT-023 - Zone 7 - North East Corner Mick Rd - CH20533-CH20800 EB |  |  |  | 2022-06-08 |  | 2022-06-08 | 2022-06-09 |  |  | CIL-Civil Lot | CH20533-CH20800 | EART - Earthwork | CLGR - Clearing and Grubbing |  | EB - Eastbound | Jonathon Rock | Stripping top soil
Area 2 | ITP-001-A2-LOT-024 | ITP-001-A2-LOT-024 - Zone 6 & 7 - Champion, Debonair & Mickleham Rd. |  |  |  | 2022-06-21 |  | 2022-06-21 | 2022-06-22 | 2022-06-22 |  | CIL-Civil Lot | multiple chainages | EART - Earthwork | CLGR - Clearing and Grubbing | 1145-ACM-CVD-DPK-0002 | EB - Eastbound | Simon Colosimo | Trees opposite champion pde NO's 1486, 1255, 1256 Trees at Debonair Pde No's 1588, 1595, 1594, 1604 trim only | Simon Colosimo | 2022-06-22
Area 2 | ITP-001-A2-LOT-025 | ITP-001-A2-LOT-025 - Aitken Blvd to waterview blvd & Aitken creek bridge
Area 2 | ITP-001-A2-LOT-026 | ITP-001-A2-LOT-026 - Zone 5 â€“ Aitken Blvd - SB - CH60930-CH60860
Area 2 | ITP-006-A2-LOT-001 | ITP-006-A2-LOT-001 - Zone 7 East Gate 7.2-7.3 - CH10660-CH10850-WB | CLOSED |  |  | 2021-11-05 |  | 2021-11-05 | 2021-11-05 | not started |  | EAL- Earthworks Lot | CH10660-CH10850 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Georgie Brady | Subgrade |  |  | Babak Rudd-Project Quality Manager | NO
Area 2 | ITP-006-A2-LOT-002 | ITP-006-A2-LOT-002 - Zone 7 East Gate 7.1-7.2 - CH10900-CH11220-WB | OUTSTANDING |  |  | 2021-11-30 |  | 2021-11-30 | 2021-11-23 | not started |  | EAL- Earthworks Lot | CH10900-CH11220 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Abed Wardak, Georgie Brady | Gate 7.2 - 7.1 |  |  | Babak Rudd-Project Quality Manager | N/A
Area 2 | ITP-006-A2-LOT-003 | ITP-006-A2-LOT-003 - Zone 7 East Gate 7.4 - CH11680-CH11480-WB | CLOSED |  |  | 2021-12-10 |  | 2021-12-10 | 2021-12-10 | not started |  | EAL- Earthworks Lot | CH11680-11480 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Georgie Brady | Vantage to Nobility Rd |  |  | Babak Rudd-Project Quality Manager | N/A
Area 2 | ITP-006-A2-LOT-004 | ITP-006-A2-LOT-004 - Zone 7 East Gate 7.2 - CH10850-CH10900-WB |  |  |  | 2022-01-11 |  | 2022-01-11 | 2022-01-13 | not started |  | EAL- Earthworks Lot | Ch10850-10900 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Jonathon Rock; Abed Wardak | Gate 7.2 the "Plug"
Area 2 | ITP-006-A2-LOT-005 | ITP-006-A2-LOT-005 - Mickleham North CH30520 - CH30750 | CLOSED | 2022-05-10 |  | 2022-01-20 |  | 2022-01-20 | 2022-01-20 | pass |  | EAL- Earthworks Lot | CH30520-CH30750 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | NB - Northbound | Varun Panickar | Asbestos Affected Subgrade | Varun Panickar | 2022-05-05 | Babak Rudd-Project Quality Manager | N/A
Area 2 | ITP-006-A2-LOT-006 | ITP-006-A2-LOT-006 - Mickleham South CH30120-CH30234 Cut | CLOSED | 2022-05-13 |  | 2022-01-21 |  | 2022-01-21 | 2022-01-21 | pass |  | EAL- Earthworks Lot | CH30120-CH30234 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | NB - Northbound | Varun Panickar | Cut Floor | Varun Panickar | 2022-05-05 | Babak Rudd-Project Quality Manager | N/A
Area 2 | ITP-006-A2-LOT-007 | ITP-006-A2-LOT-007 - Mickleham South CH30120-CH30234 Lift 1 | CLOSED | 2022-05-13 |  | 2022-01-21 |  | 2022-01-21 | 2022-01-21 | pass |  | EAL- Earthworks Lot | CH30120-CH30234 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | NB - Northbound | Varun Panickar | Lift 1 | Varun Panickar | 2022-05-13 | Babak Rudd-Project Quality Manager | N/A
Area 2 | ITP-006-A2-LOT-008 | ITP-006-A2-LOT-008 - Mickleham South CH30120-CH30234 Lift 2 | CLOSED | 2022-05-13 |  | 2022-01-21 |  | 2022-01-21 | 2022-01-21 | pass |  | EAL- Earthworks Lot | CH30070-CH30234 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | NB - Northbound | Varun Panickar | Lift 2 | Varun Panichar | 2022-05-05 | Babak Rudd-Project Quality Manager | N/A
Area 2 | ITP-006-A2-LOT-009 | ITP-006-A2-LOT-009 - Mickleham South CH30020 - CH30316 | CLOSED | 2022-06-21 |  | 2022-02-15 |  | 2022-02-15 | 2022-02-15 | pass | 2022-02-20 | EAL- Earthworks Lot | CH30020 - CH30316 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | NB - Northbound | Varun Panickar |  | Varun Panickar | 2022-06-20 | Babak Rudd-Project Quality Manager | N/A
Area 2 | ITP-006-A2-LOT-013 | ITP-006-A2-LOT-013 - Mickleham South CH30020 - CH30120 | CLOSED | 2022-05-13 |  | 2022-02-19 |  | 2022-02-19 | 2022-02-19 | pass |  | EAL- Earthworks Lot | CH30020 - CH30120 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | SB - Southbound | Varun Panickar |  | Varun Ranickar | 2022-05-05 | Babak Rudd-Project Quality Manager | N/A
Area 2 | ITP-006-A2-LOT-015 | ITP-006-A2-LOT-015 - Zone 7 East Gate 7.3 to Mickleham - CH10550-CH10650-WB |  |  |  | 2022-02-15 |  | 2022-02-21 | 2022-02-15 | not started |  | EAL- Earthworks Lot | CH10550 to CH10650 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Abed Wardak
Area 2 | ITP-006-A2-LOT-017 | ITP-006-A2-LOT-017 - Mickleham South CH30152 - CH30316 | CLOSED | 2022-05-23 |  | 2022-02-22 |  | 2022-02-22 | 2022-02-22 | pass |  | CIL-Civil Lot | CH30152 - CH30316 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | NB - Northbound | Varun Panickar |  | Varun Panickar | 2022-05-10 | Babak Rudd-Project Quality Manager | N/A
Area 2 | ITP-006-A2-LOT-018 | ITP-006-A2-LOT-018 - Mickleham North CH30520 - CH30665 | CLOSED | 2022-05-24 |  | 2022-02-22 |  | 2022-02-22 | 2022-02-22 | pass |  | CIL-Civil Lot | CH30520 - CH30665 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | SB - Southbound | Varun Panickar | Re-test on Asbestos removal area | Varun Panickar | 2022-05-10 | Babak Rudd-Project Quality Manager | N/A
Area 2 | ITP-006-A2-LOT-019 | ITP-006-A2-LOT-019 - Mickleham North (NB) CH30520 - CH30800 | CLOSED | 2022-06-21 |  | 2022-02-21 |  | 2022-02-21 | 2022-02-21 | pass | 2022-02-24 | CIL-Civil Lot | CH30520 - CH30800 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | NB - Northbound | Varun Panickar |  | Varun Panickar | 2022-06-20 | Babak Rudd-Project Quality Manager | N/A
Area 2 | ITP-006-A2-LOT-020 | ITP-006-A2-LOT-020 - Zone 7 East Gate 7.2-7.3 - CH10580-CH10850-WB |  |  |  | 2022-02-24 |  | 2022-02-24 | 2022-02-24 | not started |  | EAL- Earthworks Lot | CH10580-CH10850 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Abed Wardak | Re-test of area post ACM removal during Mickleham Occo Works
Area 2 | ITP-006-A2-LOT-023 | ITP-006-A2-LOT-023 - Mickleham North CH10520 - CH10550 | CLOSED | 2022-06-14 |  | 2022-03-01 |  | 2022-03-01 | 2022-03-01 | pass | 2022-03-11 | CIL-Civil Lot | CH10520 - CH10550 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | EB - Eastbound | Varun Panickar | Intersection - Soft spot rectification Layer 1 | Varun Panickar | 2022-05-30 | Babak Rudd-Project Quality Manager | YES
Area 2 | ITP-006-A2-LOT-024 | ITP-006-A2-LOT-024 - Mickleham North CH10520 - CH10550 | CLOSED | 2022-06-14 |  | 2022-03-01 |  | 2022-03-01 | 2022-03-01 | pass | 2022-03-11 | CIL-Civil Lot | CH10520 - CH10550 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | EB - Eastbound | Varun Panickar | Layer 3 | Varun Panickar | 2022-05-30 | Babak Rudd-Project Quality Manager | YES
Area 2 | ITP-006-A2-LOT-025 | ITP-006-A2-LOT-025 - Mickleham North CH10520 - CH10550 L5 SG | pass | pass | 2022-06-14 | 2022-03-10 |  | 2022-03-10 | 2022-03-10 | 2022-03-11 |  | EAL - Earthworks Lot | pass | EART - Earthwork | TYPB - Type B | 1145-ACM-CVD-DPK-0003 | EB - Eastbound | Varun Panickar |  | Varun Panickar | 2022-06-03 | pass | pass
Area 2 | ITP-006-A2-LOT-027 | ITP-006-A2-LOT-027 - Zone 7 West Craigieburn Rd - CH10035-CH10185-EB |  |  |  | 2022-03-03 |  | 2022-03-03 | 2022-02-25 | not started |  | EAL- Earthworks Lot | CH10035 - CH10185 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | EB - Eastbound | Abed Wardak
Area 2 | ITP-006-A2-LOT-028 | ITP-006-A2-LOT-028 - Zone 7 East (North Half GSM) - CH10610-CH10700-WB |  |  |  | 2022-02-03 |  | 2022-02-03 | 2022-02-03 | not started |  | EAL- Earthworks Lot | CH10550 to CH10700 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Abed Wardak
Area 2 | ITP-006-A2-LOT-029 | ITP-006-A2-LOT-029 - Zone 7 West (Slither) - CH10035-CH10135 - Layer 1 |  |  |  | 2022-03-08 |  | 2022-03-09 | 2022-03-09 | not started |  | EAL- Earthworks Lot | CH10000 - CH10135 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Brighton Sarabia
Area 2 | ITP-006-A2-LOT-030 | ITP-006-A2-LOT-030 - Zone 7 West (Slither) - CH10035-CH10135 - Layer 2 |  |  |  | 2022-03-08 |  | 2022-03-09 | 2022-03-09 | not started |  | EAL- Earthworks Lot | CH10035 - CH10135 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | NB - Northbound | Brighton Sarabia
Area 2 | ITP-006-A2-LOT-031 | ITP-006-A2-LOT-031 - Mickleham South (NB) CH30316 - CH30400 | CLOSED | 2022-05-13 |  | 2022-03-09 |  | 2022-03-09 | 2022-03-09 | pass |  |  | CH30316 - CH30400 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | SB - Southbound | Varun Panickar |  | Varun Panickar | 2022-05-05 | Babak Rudd-Project Quality Manager | N/A
Area 2 | ITP-006-A2-LOT-032 | ITP-006-A2-LOT-032 - Mickleham North NB CH30470 - CH30500 Cut floor | CLOSED | 2022-06-03 |  | 2022-03-10 |  | 2022-03-10 | 2022-03-10 | pass | 2022-03-11 | CIL-Civil Lot | CH 30470- CH 30500 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | NB - Northbound | Varun Panickar | Cut Floor | Varun Panickar | 2022-05-25 | Babak Rudd-Project Quality Manager | N/A
Area 2 | ITP-006-A2-LOT-033 | ITP-006-A2-LOT-033 - Mickleham North NB CH30470 - CH30500 Layer 1 | pass | pass | 2022-06-03 | 2022-03-10 |  | 2022-03-10 | 2022-03-10 | 2022-03-11 |  | EAL - Earthworks Lot | pass | EART - Earthwork | TYPB - Type B | 1145-C200-FUL-QAC-ITP-0006 | NB - Northbound | Varun Panickar |  | Varun Panickar | 2022-05-25 | pass | pass
Area 2 | ITP-006-A2-LOT-034 | ITP-006-A2-LOT-034 - Mickleham South CH30316 - CH30400 | CLOSED | 2022-05-13 |  | 2022-03-11 |  | 2022-03-11 | 2022-03-11 | pass |  | EAL- Earthworks Lot | CH30316 - CH304000 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | NB - Northbound | Varun Panickar |  | Varun Panickar | 2022-05-05 | Babak Rudd-Project Quality Manager | N/A
Area 2 | ITP-006-A2-LOT-035 | ITP-006-A2-LOT-035 - Mickleham Intersection CH30400 - CH30420 | pass | pass | 2022-06-01 | 2022-03-10 |  | 2022-03-10 | 2022-03-10 | 2022-03-10 |  | EAL - Earthworks Lot | pass | EART - Earthwork | TYPB - Type B | 1145-C200-FUL-QAC-ITP-0006 | SB - Southbound | Varun Panickar |  | Varun Panickar | 2022-05-25 | pass | pass
Area 2 | ITP-006-A2-LOT-036 | ITP-006-A2-LOT-036 - Mickleham Intersection CH30400 - CH30420 | CLOSED | 2022-06-01 |  | 2022-03-09 |  | 2022-03-09 | 2022-03-10 | pass | 2022-03-10 |  | CH30400 - CH30420 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | SB - Southbound | Varun Panickar | Layer 2 | Varun Panickar | 2022-05-25 | Babak Rudd-Project Quality Manager | N/A
Area 2 | ITP-006-A2-LOT-037 | ITP-006-A2-LOT-037 - Mickleham Intersection CH30400 - CH30420 | pass | pass | 2022-06-01 | 2022-03-10 |  | 2022-03-10 | 2022-03-10 | 2022-03-10 |  | EAL - Earthworks Lot | pass | EART - Earthwork | TYPB - Type B | 1145-C200-FUL-QAC-ITP-0006 | SB - Southbound | Varun Panickar |  | Varun Panickar | 2022-05-25 | pass | pass
Area 2 | ITP-006-A2-LOT-038 | ITP-006-A2-LOT-038 - Mickleham Intersection CH30400 - CH30420 | CLOSED | 2022-06-01 |  | 2022-03-09 |  | 2022-03-09 | 2022-03-10 | pass | 2022-03-10 | CIL-Civil Lot | CH30400 - CH30420 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | SB - Southbound | Varun Panickar | Layer 4 | Varun Panickar | 2022-05-25 | Babak Rudd-Project Quality Manager | N/A
Area 2 | ITP-006-A2-LOT-039 | ITP-006-A2-LOT-039 - Mickleham Intersection CH30400 - CH30420 | CLOSED | 2022-06-21 |  | 2022-03-09 |  | 2022-03-09 | 2022-03-10 | pass | 2022-03-11 | CIL-Civil Lot | CH 30400 -CH30420 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | SB - Southbound | Varun Panickar | Layer 5 | Varun Panickar | 2022-05-25 | Babak Rudd-Project Quality Manager | N/A
Area 2 | ITP-006-A2-LOT-040 | ITP-006-A2-LOT-040 - Mickleham North (SB) CH30420 - CH30520 | CLOSED | 2022-05-13 |  | 2022-03-12 |  | 2022-03-12 | 2022-03-12 | pass |  | EAL- Earthworks Lot | CH30420 - CH30520 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | SB - Southbound | Varun Panickar |  | Varun Panickar | 2022-05-05 | Babak Rudd-Project Quality Manager | N/A
Area 2 | ITP-006-A2-LOT-042 | ITP-006-A2-LOT-042 - Mickleham North (NB) CH30450 - CH30520 | CLOSED | 2022-05-13 |  | 2022-03-12 |  | 2022-03-12 | 2022-03-12 | pass |  | EAL- Earthworks Lot | CH30450 - CH30520 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | NB - Northbound | Varun Panickar |  | Varun Panickar | 2022-05-04 | Babak Rudd-Project Quality Manager | N/A
Area 2 | ITP-006-A2-LOT-043 | ITP-006-A2-LOT-043 - Mickleham Intersection CH30400 - CH30430 | CLOSED | 2022-05-13 |  | 2022-03-18 |  | 2022-03-18 | 2022-03-18 | pass |  | EAL- Earthworks Lot | CH30400 - CH30430 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | ME - Median | Varun Panickar |  | Varun Panickar | 2022-05-04 | Babak Rudd-Project Quality Manager | N/A
Area 2 | ITP-006-A2-LOT-045 | ITP-006-A2-LOT-045 - Mickleham Intersection NE CH20500 - CH20550 | CLOSED | 2022-05-27 |  | 2022-03-18 |  | 2022-03-18 | 2022-03-18 | pass | 2022-04-15 | CIL-Civil Lot | CH20500 - CH20550 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | SB - Southbound | Varun Panickar |  | Varun Panickar | 2022-05-20 | Babak Rudd-Project Quality Manager | N/A
Area 2 | ITP-006-A2-LOT-046 | ITP-006-A2-LOT-046 - Mickleham North CH40750 - CH40780 | CLOSED | 2022-05-27 |  | 2022-03-20 |  | 2022-03-20 | 2022-03-20 | pass | 2022-04-15 | CIL-Civil Lot | CH40750 - CH40780 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | SB - Southbound | Varun Panickar |  | Varun Panickar | 2022-05-15 | Babak Rudd-Project Quality Manager | N/A
Area 2 | ITP-006-A2-LOT-047 | ITP-006-A2-LOT-047 - Mickleham South CH29980 - CH30015 | CLOSED | 2022-05-27 |  | 2022-03-20 |  | 2022-03-20 | 2022-03-20 | pass | 2022-04-13 | CIL-Civil Lot | CH29980 - CH30015 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | SB - Southbound | Varun Panickar | Pavement Type 6 | Varun Panickar | 2022-05-20 | Babak Rudd-Project Quality Manager | N/A
Area 2 | ITP-006-A2-LOT-048 | ITP-006-A2-LOT-048 - Mickleham Intersection CH10520 - CH10600 | CLOSED | 2022-05-13 |  | 2022-03-23 |  | 2022-03-23 | 2022-03-24 | pass |  | EAL- Earthworks Lot | CH10520 - CH10600 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Varun Panickar | No Mans Land - SE slip lane + West bound lane | Varun Panickar | 2022-05-04 | Babak Rudd-Project Quality Manager | N/A
Area 2 | ITP-006-A2-LOT-050 | ITP-006-A2-LOT-050 - Zone 7 West Dam - CH10300 to 10350 - Layer 1 |  |  |  | 2022-03-24 |  | 2022-03-24 | 2022-03-24 | not started |  | EAL- Earthworks Lot | 10300-10350 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Brighton Sarabia | Dam Backfill - Layer 1
Area 2 | ITP-006-A2-LOT-052 | ITP-006-A2-LOT-052 - Zone 7 West Dam - CH10300 to 10350 - Layer 2 |  |  |  | 2022-03-25 |  | 2022-03-25 | 2022-03-25 | not started |  | EAL- Earthworks Lot | 10300-10350 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Brighton Sarabia | Dam Backfill - Layer 2
Area 2 | ITP-006-A2-LOT-053 | ITP-006-A2-LOT-053 - Zone 7 West Dam - CH10300 to 10350 - Layer 3 |  |  |  | 2022-03-29 |  | 2022-03-29 | 2022-03-29 | not started |  | EAL- Earthworks Lot | 10300-10350 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Brighton Sarabia | Dam Backfill - Layer 3
Area 2 | ITP-006-A2-LOT-054 | ITP-006-A2-LOT-054 - Zone 7 East Gate 7.1-7.2 (Post ACM) - CH10840-CH11140-WB | [7 empty] | not started
Area 2 | ITP-006-A2-LOT-055 | ITP-006-A2-LOT-055 - Zone 7 West Dam - CH10300 to 10350 - 400mm Below Subgrade (Top of Layer 4) |  |  |  | 2022-03-30 |  | 2022-03-30 | 2022-03-30 | not started |  | EAL- Earthworks Lot | 10300-10350 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Brighton Sarabia | Cut Fill - 400mm Below Subgrade
Area 2 | ITP-006-A2-LOT-056 | ITP-006-A2-LOT-056 - Type B layer 1m below FSL | not started | not started |  | 4/04/2022 |  | 4/04/2022 | 2022-06-24 |  |  | EAL - Earthworks Lot | wip | EART - Earthwork | TYPB - Type B |  | WB - Westbound | Brighton/Michael |  |  |  | not started | not started
Area 2 | ITP-006-A2-LOT-057 | ITP-006-A2-LOT-057 - Zone 7 East (GSM Capping Shift) - CH10780-CH10850-WB |  |  |  | 2022-03-12 |  | 2022-03-12 | 2022-03-10 | not started |  | EAL- Earthworks Lot | CH10780-CH10850 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Abed Wardak | Subgrade
Area 2 | ITP-006-A2-LOT-058 | ITP-006-A2-LOT-058 - Zone 7 East SUP - CH10850 to CH10730 |  |  |  | 2022-03-22 |  | 2022-03-22 | 2022-03-22 | not started
Area 2 | ITP-006-A2-LOT-059 | ITP-006-A2-LOT-059 - Zone 7 East SUP - CH10730 to CH10680 |  |  |  | 2022-03-24 |  | 2022-03-24 | 2022-03-24 | not started |  | CIL-Civil Lot | 10730 - 10680 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Jonathan rock
Area 2 | ITP-006-A2-LOT-060 | ITP-006-A2-LOT-060 - Zone 7 East SUP - CH10600 to CH10630 |  |  |  | 2022-03-24 |  |  |  | not started
Area 2 | ITP-006-A2-LOT-061 | ITP-006-A2-LOT-061 - Zone 7 East SUP - CH10600 to CH10730 |  |  |  | 2022-03-25 |  | 2022-03-25 | 2022-03-25 | not started |  |  | 10600 to 10730
Area 2 | ITP-006-A2-LOT-062 | ITP-006-A2-LOT-062 - Zone 7 West Olive Grove to Tennis Court - CH10190 to 10410 - Subgrade Level |  |  |  | 2022-04-08 |  | 2022-04-12 | 2022-04-12 | not started |  | EAL- Earthworks Lot | 10300-10350 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Brighton Sarabia | Dam Subgrade Level
Area 2 | ITP-006-A2-LOT-062 | ITP-006-A2-LOT-062 - Zone 7 West Dam to Tennis Court - CH10290 to CH10460 - Subgrade Level | not started | not started |  | 2022-05-26 |  | 2022-05-26 | 2022-05-26 |  |  | EAL - Earthworks Lot | pass | EART - Earthwork | TYPB - Type B | 1145-C200-FUL-QAC-ITP-0006 | WB - Westbound | Brighton Sarabia |  |  |  | not started | not started
Area 2 | ITP-006-A2-LOT-063 | ITP-006-A2-LOT-063 - Zone 7 West Dam - CH10300 to 10350 - 200mm Below Subgrade |  |  |  | 2022-04-08 |  | 2022-04-08 | 2022-04-08 | not started |  | EAL- Earthworks Lot | 10300-10350 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Brighton Sarabia | Cut Fill - 200mm Below Subgrade
Area 2 | ITP-006-A2-LOT-064 | ITP-006-A2-LOT-064 - Zone 7 East Nobility Rd to Gate 7.5 - CH11360 to CH11490 - WB |  |  |  | 2022-04-12 |  | 2022-04-12 | 2022-04-11 | not started |  | EAL- Earthworks Lot | CH11360 to CH11490 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Abed Wardak
Area 2 | ITP-006-A2-LOT-065 | ITP-006-A2-LOT-065 - Zone 7 West Tennis Court - CH10350-10410 - Cut Fill (400mm Below Subgrade) |  |  |  | 2022-05-11 |  | 2022-05-11 | 2022-05-11 | not started |  | EAL- Earthworks Lot | CH 10350-10410 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Brighton Sarabia
Area 2 | ITP-006-A2-LOT-066 | ITP-006-A2-LOT-066 - Zone 7 West Tennis Court - CH10350-10410 - Cut Fill (200mm Below Subgrade) |  |  |  | 2022-05-11 |  | 2022-05-11 | 2022-05-11 | not started |  | EAL- Earthworks Lot | CH10350-CH410 | EART - Earthwork | TYPB - Type B | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Brighton Sarabia
Area 2 | ITP-006-A2-LOT-067 | ITP-006-A2-LOT-067 - Zone 7 West - CH10420-10470 - Rectification Works @ 400mm below Subgrade | not started | not started |  | 2022-05-25 |  | 2022-05-25 | 2022-05-25 |  |  | EAL - Earthworks Lot | pass | EART - Earthwork | TYPB - Type B | 1145-C200-FUL-QAC-ITP-0006 | WB - Westbound | Brighton Sarabia |  |  |  | not started | not started
Area 2 | ITP-006-A2-LOT-068 | ITP-006-A2-LOT-068 - Zone 7 West - CH10420-104270 - Rectification Works @ 200mm below Subgrade | not started | not started |  | 2022-05-25 |  | 2022-05-25 |  |  |  | EAL - Earthworks Lot | pass | EART - Earthwork | TYPB - Type B | 1145-C200-FUL-QAC-ITP-0006 | WB - Westbound | Brighton Sarabia |  |  |  | not started | not started
Area 2 | ITP-006-A2-LOT-069 | ITP-006-A2-LOT-069 - Zone 7 West - CH10420-104270 - Rectification Works @ 600mm below Subgrade | not started | not started |  | 2022-05-25 |  | 2022-05-25 | 2022-05-25 |  |  | EAL - Earthworks Lot | pass | EART - Earthwork | TYPB - Type B | 1145-C200-FUL-QAC-ITP-0006 | WB - Westbound | Brighton Sarabia |  |  |  | not started | not started
Area 2 | ITP-006-A2-LOT-072 | ITP-006-A2-LOT-072 - Zone 7 SUP - CH10550 to CH10650 - Subgrade Level | not started | not started |  | 2022-06-09 |  | 2022-06-09 | 2022-06-09 |  |  | EAL - Earthworks Lot | wip | EART - Earthwork | TYPB - Type B |  | WB - Westbound | Jonathon Rock | SUP subgrade |  |  | not started | not started
Area 2 | ITP-006-A2-LOT-073 | ITP-006-A2-LOT-073 - SUP Subgrade Prep - NW Mickleham Intersection | not started | not started | [8 empty] | not started | [8 empty] | not started | not started
Area 2 | ITP-006-A2-LOT-074 | ITP-006-A2-LOT-074 - SUP Cut Floor Level - NE Mickleham Intersection | not started | not started |  | 2022-06-14 |  | 2022-06-20 | 2022-06-20 |  |  | EAL - Earthworks Lot | pass | EART - Earthwork | TYPB - Type B |  |  | Michael Schibeci | first 200mm installed |  |  | not started | not started
Area 2 | ITP-006-A2-LOT-079 | ITP-006-A2-LOT-079 - SUP subgrade Layer 4 - 200mm installation - Mick NE | not started | not started |  | 2022-06-23 |  | 2022-06-23 | 2022-06-24 |  |  | EAL - Earthworks Lot | wip | EART - Earthwork | TYPB - Type B |  | SB - Southbound | Michael Schibeci |  |  |  | not started | not started
Area 2 | ITP-006-A2-LOT-080 | ITP-006-A2-LOT-080 - Type B layer 800m below FSL | not started | not started |  | 2022-06-24 |  | 2022-06-24 | 2022-06-25 |  |  | EAL - Earthworks Lot | wip | EART - Earthwork | TYPB - Type B |  | NB - Northbound | Michael Schibeci |  |  |  | not started | not started
Area 2 | ITP-006-A2-LOT-081 | ITP-006-A2-LOT-081 - SUP subgrade Layer 5 - 200mm installation - Mick NE | not started | not started |  | 2022-06-24 |  | 2022-06-24 | 2022-06-25 |  |  | EAL - Earthworks Lot | wip | EART - Earthwork | TYPB - Type B |  | SB - Southbound | Michael Schibeci | Layer 5 |  |  | not started | not started
Area 2 | ITP-006-A2-LOT-082 | ITP-006-A2-LOT-082 - Zone 7 West Jo's Property | not started | not started |  | 2022-06-24 |  | 2022-06-24 | 2022-06-28 |  |  | EAL - Earthworks Lot | wip | EART - Earthwork | TYPB - Type B |  | WB - Westbound | Michael Schibeci |  |  |  | not started | not started
Area 2 | ITP-006-A2-LOT-083 | ITP-006-A2-LOT-083 - Zone 7 West SW CH 10450 - CH 10490 Cut + 200 | not started | not started |  | 2022-06-24 |  | 2022-06-24 | 2022-06-24 |  |  | EAL - Earthworks Lot | pass | EART - Earthwork | TYPB - Type B | 1145-ACM-CVD-DPK-0004 | WB - Westbound | Varun Panickar |  |  |  | not started | not started
Area 2 | ITP-006-A2-LOT-084 | ITP-006-A2-LOT-084 - Zone 7 West SW CH 10450 - CH 10490 SG top | not started | not started | [8 empty] | not started | [8 empty] | not started | not started
Area 2 | ITP-006-A2-LOT-085 | ITP-006-A2-LOT-085 - SUP subgrade Layer 6 - 200mm installation - Mick NE | not started | not started |  | 2022-06-27 |  | 2022-06-27 | 2022-06-28 |  |  | EAL - Earthworks Lot | wip | EART - Earthwork | TYPB - Type B |  | SB - Southbound | Michael Schibeci | Layer 6 |  |  | not started | not started
Area 2 | ITP-006-A2-LOT-086 | ITP-006-A2-LOT-086 - Type B layer 600m below FSL dam | not started | not started |  | 2022-06-27 |  | 2022-06-27 | 2022-06-28 |  |  | EAL - Earthworks Lot | wip | EART - Earthwork | TYPB - Type B |  | NB - Northbound | Michael Schibeci |  |  |  | not started | not started
Area 2 | ITP-006-A2-LOT-087 | ITP-006-A2-LOT-087 - SUP subgrade Layer 7 - 200mm installation - Mick NE | not started | not started | [8 empty] | not started | [8 empty] | not started | not started
Area 2 | ITP-006-A2-LOT-088 | ITP-006-A2-LOT-088 - Zone 7 East - Debonair Cut Floor and Layer 1 - CH11220 to CH11300 | not started | not started |  | 2022-06-29 |  | 2022-06-29 | 2022-06-29 |  |  |  | pass |  |  |  |  | Jonathon Rock |  |  |  | not started | not started
Area 2 | ITP-006-A2-LOT-089 | ITP-006-A2-LOT-089 - Mickleham Intersection SW - Slip Lane Tie In - CH30370-30390 | not started | not started | [8 empty] | not started | [8 empty] | not started | not started
Area 2 | ITP-006-A2-LOT-090 | ITP-006-A2-LOT-090 - Mickleham Rd North (Northbound) SUP Subgrade - CH30465-30695 | not started | not started | [8 empty] | not started | [8 empty] | not started | not started
Area 2 | ITP-006-A2-LOT-091 | ITP-006-A2-LOT-091 - Zone 7 East - Layer 2 - CH11220 to CH11300 | not started | not started |  | 2022-07-01 |  | 2022-07-01 | 2022-07-01 |  |  |  | wip | [8 empty] | not started | not started
Area 2 | ITP-006-A2-LOT-093 | ITP-006-A2-LOT-093 - Type B Layer 400mm below FSL Dam - Zone 7 West (CH10300-10350) | not started | not started | [8 empty] | not started | [8 empty] | not started | not started
Area 2 | ITP-006-A2-LOT-094 | ITP-006-A2-LOT-094 - Type B Layer 200mm below FSL Dam - Zone 7 West (CH10300-10350) | not started | not started | [8 empty] | not started | [8 empty] | not started | not started
Area 2 | ITP-006-A2-LOT-095 | ITP-006-A2-LOT-095 - Zone 7 East - Layer 3 - CH11220 to CH11300 | not started | not started |  | 2022-07-02 |  | 2022-07-02 | 2022-07-04 |  |  | EAL - Earthworks Lot | wip | EART - Earthwork | TYPB - Type B |  |  | Jonathon Rock |  |  |  | not started | not started
Area 2 | ITP-006-A2-LOT-097 | ITP-006-A2-LOT-097 - Zone 7 East Debonair - Cut Floor & Layer 1 - CH11300 to CH11320 | not started | not started |  | 2022-07-04 |  | 2022-07-04 | 2022-07-04 |  |  |  | pass | [8 empty] | not started | not started
Area 2 | ITP-006-A2-LOT-098 | ITP-006-A2-LOT-098 - Zone 7 East Debonair - Layer 2 - CH11300 to CH11320 | not started | not started |  | 2022-07-05 |  | 2022-07-05 | 2022-07-06 |  |  |  | wip | EART - Earthwork |  |  |  | JRock |  |  |  | not started | not started
Area 2 | ITP-006-A2-LOT-099 | ITP-006-A2-LOT-099 - Zone 7 East Debonair - Layer 3 - CH11300 to CH11320 | not started | not started | [8 empty] | not started | [8 empty] | not started | not started
Area 2 | ITP-006-A2-LOT-100 | ITP-006-A2-LOT-100 - Zone 7 West - 755 Driveway Wedge - CH10135-CH10180 - Cut Floor Level | not started | not started | [8 empty] | not started | [8 empty] | not started | not started
Area 2 | ITP-006-A2-LOT-101 | ITP-006-A2-LOT-101 - Zone 7 East - Layer 0 - CH11360 to CH11390 | not started | not started | [8 empty] | not started | [8 empty] | not started | not started
Area 2 | ITP-006-A2-LOT-102 | ITP-006-A2-LOT-102 - Zone 7 East Debonair - cut floor and layer 1 - CH11300 to CH11320 | not started | not started |  | 2022-07-07 |  | 2022-07-07 | 2022-07-07 |  |  |  | wip | [8 empty] | not started | not started
Area 2 | ITP-006-A2-LOT-103 | ITP-006-A2-LOT-103 - Zone 7 East Debonair - Layer 2 - CH11300 to CH11320 | not started | not started | [8 empty] | not started | [8 empty] | not started | not started
Area 2 | ITP-006-A2-LOT-104 | ITP-006-A2-LOT-104 - Zone 7 West - 755 Driveway Wedge - CH10135-CH10180 - Subgrade Level | not started | not started | [8 empty] | not started | [8 empty] | not started | not started
Area 2 | ITP-006-AX-LOT-075 | ITP-006-AX-LOT-075 - SUP subgrade Layer 2 - 200mm installation - Mick NE | not started | not started |  | 2022-06-20 |  | 2022-06-20 | 2022-06-20 |  |  | EAL - Earthworks Lot | pass | EART - Earthwork | TYPB - Type B |  |  | Michael Schibeci | Layer after 400mm installed (200mm tested) |  |  | not started | not started
Area 2 | ITP-006-AX-LOT-076 | ITP-006-AX-LOT-076 - SUP subgrade Layer 3 - 200mm installation - Mick NE | not started | not started |  | 2022-06-21 |  | 2022-06-22 | 2022-06-22 |  |  | EAL - Earthworks Lot | wip | EART - Earthwork | TYPB - Type B |  | SB - Southbound | Michael Schibeci |  |  |  | not started | not started
Area 2 | ITP-007-A2-LOT-001 | ITP-007-A2-LOT-001 - Zone 7 East Gate 7.1-7.2 - CH10900-CH11220-WB Layer 1 |  |  |  | 2021-11-30 |  | 2021-11-30 |  |  |  | EAL- Earthworks Lot | CH10660-CH10850 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Georgie Brady
Area 2 | ITP-007-A2-LOT-002 | ITP-007-A2-LOT-002 - Zone 7 East Gate 7.2-7.3 - CH10660-CH10850-WB Layer 1 |  |  |  | 2021-12-20 |  | 2021-12-20 | 2021-12-20 | [8 empty] | Georgie Brady
Area 2 | ITP-007-A2-LOT-003 | ITP-007-A2-LOT-003 - Zone 7 East Gate 7.1-7.2 - CH10900-CH11220-WB Layer 2
Area 2 | ITP-007-A2-LOT-004 | ITP-007-A2-LOT-004 - Zone 7 East Gate 7.2-7.3 - CH10660-CH10850-WB Layer 2
Area 2 | ITP-007-A2-LOT-005 | ITP-007-A2-LOT-005 - Zone 7 East Gate 7.2 - CH10850-CH10900-WB - Layer 1
Area 2 | ITP-007-A2-LOT-006 | ITP-007-A2-LOT-006 - Zone 7 East Gate 7.2 - CH10850-CH10900-WB - Layer 2
Area 2 | ITP-007-A2-LOT-007 | ITP-007-A2-LOT-007 - Mickleham North CH40400 - CH40700 | [10 empty] | CH40400 - CH40700
Area 2 | ITP-007-A2-LOT-008 | ITP-007-A2-LOT-008 - Mickleham South CH30000 - CH30234 L1 | CLOSED | 2022-05-16 |  | 2022-02-09 |  | 2022-02-09 | 2022-02-09 | pass |  | CIL-Civil Lot | CH30000 - CH30234 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | NB - Northbound | Aadish Pudasaini | Layer 1 | Varun Panickar | 2022-05-06 | Babak Rudd-Project Quality Manager | N/A
Area 2 | ITP-007-A2-LOT-009 | ITP-007-A2-LOT-009 - Zone 7 East Gate 7.4-Nobility Rd - CH11680-CH11480-WB - Layer 1 |  |  |  | 2022-02-11 |  | 2022-02-14 | 2022-02-08 |  |  | EAL- Earthworks Lot | CH11680 - CH11480 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Abed Wardak
Area 2 | ITP-007-A2-LOT-010 | ITP-007-A2-LOT-010 - Zone 7 East Gate 7.4-Nobility Rd - CH11680-CH11480-WB - Layer 2
Area 2 | ITP-007-A2-LOT-011 | ITP-007-A2-LOT-011 - Mickleham South CH30000 - CH30234 Layer 2 | CLOSED | 2022-06-30 |  | 2022-02-19 |  | 2022-02-19 | 2022-02-19 | 2022-02-23 |  | CIL-Civil Lot | CH30000 - CH30234 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | NB - Northbound | Varun Panickar | Layer2 | Varun Panickar | 2022-06-30 | Babak Rudd-Project Quality Manager | YES
Area 2 | ITP-007-A2-LOT-012 | ITP-007-A2-LOT-012 - Mickleham South CH30000- CH30152 Layer 1 | CLOSED | 2022-05-16 |  | 2022-02-19 |  | 2022-02-19 | 2022-02-19 | pass |  | EAL- Earthworks Lot | CH30000 - CH30152 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | SB - Southbound | Varun Panickar | Layer 1 | Varun Panickar | 2022-05-06 | Babak Rudd-Project Quality Manager | N/A
Area 2 | ITP-007-A2-LOT-013 | ITP-007-A2-LOT-013 - Mickleham South CH30234 - CH30316 Layer 2 |  |  |  | 2022-02-21 |  | 2022-02-21 | 2022-02-21 | 2022-02-24 |  | CIL-Civil Lot | CH30234 - CH30316 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | NB - Northbound | Varun Panickar |  | Varun Panickar | 2022-06-30
Area 2 | ITP-007-A2-LOT-014 | ITP-007-A2-LOT-014 - Mickleham South CH30234 - CH30316 Layer 1 | CLOSED | 2022-06-30 |  | 2022-02-19 |  | 2022-02-19 | 2022-02-20 | 2022-02-24 |  | EAL- Earthworks Lot | CH30234 - CH30316 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | NB - Northbound | Varun Panickar | Lot over 60 days with overdue NCR. (1145-FUL-NCR-0010) Approved & Closed. | Varun Panickar | 2022-06-30 | Babak Rudd-Project Quality Manager | YES
Area 2 | ITP-007-A2-LOT-015 | ITP-007-A2-LOT-015 - Mickleham South CH30152 - CH30316 Layer 1 | CLOSED | 2022-06-30 |  | 2022-02-22 |  | 2022-02-22 | 2022-02-23 | 2022-02-25 |  | EAL- Earthworks Lot | CH30152 - CH30316 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | SB - Southbound | Varun Panickar | Lot over 60 days with overdue NCR. (1145-FUL-NCR-0010) Approved & Closed. | Varun Panickar | 2022-06-30 | Babak Rudd-Project Quality Manager | YES
Area 2 | ITP-007-A2-LOT-016 | ITP-007-A2-LOT-016 - Mickleham South CH30152 - CH30316 Layer 2 | CLOSED | 2022-06-30 |  | 2022-02-22 |  | 2022-02-22 | 2022-02-22 | 2022-02-25 |  | EAL- Earthworks Lot | CH30152 - CH30316 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | NB - Northbound | Varun Panickar | Lot over 60 days with overdue NCR. (1145-FUL-NCR-0010) Approved & Closed. | Varun Panickar | 2022-06-30 | Babak Rudd-Project Quality Manager | YES
Area 2 | ITP-007-A2-LOT-017 | ITP-007-A2-LOT-017 - Mickleham North (SB) CH30520 - CH30665 Layer 1 | CLOSED | 2022-06-30 |  | 2022-02-24 |  | 2022-02-24 | 2022-02-24 | 2022-02-26 |  | EAL- Earthworks Lot | CH30520 - CH30665 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | SB - Southbound | Varun Panickar | Lot over 60 days with overdue NCR. (1145-FUL-NCR-0010) Approved & Closed. | Varun Panickar | 2022-06-30 | Babak Rudd-Project Quality Manager | YES
Area 2 | ITP-007-A2-LOT-018 | ITP-007-A2-LOT-018 - Mickleham North (SB) CH30520 - CH30665 Layer 2 | CLOSED | 2022-06-30 |  | 2022-02-24 |  | 2022-02-24 | 2022-02-24 | 2022-03-05 |  | CIL-Civil Lot | CH30520 - CH30665 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | SB - Southbound | Varun Panickar | Lot over 60 days with overdue NCR. (1145-FUL-NCR-0010) Approved & Closed. | Varun Panickar | 2022-05-30 | Babak Rudd-Project Quality Manager | YES
Area 2 | ITP-007-A2-LOT-019 | ITP-007-A2-LOT-019 - Zone 7 East Gate 7.3 to Mickleham - CH10550-CH10850-WB - Layer 1 |  |  |  | 2022-02-25 |  | 2022-02-25 | 2022-02-25 |  |  | EAL- Earthworks Lot | CH10550-CH10850-WB | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Varun Panickar
Area 2 | ITP-007-A2-LOT-020 | ITP-007-A2-LOT-020 - Mickleham North (NB) CH30520 - CH30665 Layer 1 | CLOSED | 2022-06-30 |  | 2022-02-25 |  | 2022-02-25 | 2022-02-25 | 2022-02-28 |  | EAL- Earthworks Lot | CH30520 - CH30665 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | NB - Northbound | Varun Panickar | Lot over 60 days with overdue NCR. (1145-FUL-NCR-0010) Approved & Closed. | Varun Panickar | 2022-06-30 | Babak Rudd-Project Quality Manager | YES
Area 2 | ITP-007-A2-LOT-021 | ITP-007-A2-LOT-021 - Zone 7 East Gate 7.3 to Mickleham - CH10550-CH10650-WB - Layer 2
Area 2 | ITP-007-A2-LOT-022 | ITP-007-A2-LOT-022 - Mickleham North (NB) CH30520 - CH30665 Layer 2 | CLOSED | 2022-06-30 |  | 2022-02-25 |  | 2022-03-02 | 2022-03-02 | 2022-03-04 |  | EAL- Earthworks Lot | CH30520 - CH30665 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | NB - Northbound | Varun Panickar | Lot over 60 days with overdue NCR. (1145-FUL-NCR-0010) Approved & Closed. | Varun Panickar | 2022-06-30 | Babak Rudd-Project Quality Manager | YES
Area 2 | ITP-007-A2-LOT-023 | ITP-007-A2-LOT-023 - Mickleham North (NB) CH30665 - CH30800 Layer 1 | CLOSED | 2022-06-30 |  | 2022-02-25 |  | 2022-02-25 | 2022-02-25 | 2022-03-07 |  | EAL- Earthworks Lot | CH30665 - CH30800 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | NB - Northbound | Varun Panickar | Lot over 60 days with overdue NCR. (1145-FUL-NCR-0010) Approved & Closed. | Varun Panickar | 2022-06-30 | Babak Rudd-Project Quality Manager | YES
Area 2 | ITP-007-A2-LOT-024 | ITP-007-A2-LOT-024 - Mickleham North (NB) CH30665 - CH30800 Layer 2 | CLOSED | 2022-06-30 |  | 2022-02-26 |  | 2022-02-26 | 2022-03-03 | 2022-03-05 |  | EAL- Earthworks Lot | CH30665 - CH30800 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | NB - Northbound | Varun Panickar | Lot over 60 days with overdue NCR. (1145-FUL-NCR-0010) Approved & Closed. | Varun Panickar | 2022-06-30 | Babak Rudd-Project Quality Manager | YES
Area 2 | ITP-007-A2-LOT-025 | ITP-007-A2-LOT-025 - Zone 7 West Occo Works - CH10035-CH10185-EB - Layer 1
Area 2 | ITP-007-A2-LOT-026 | ITP-007-A2-LOT-026 - Zone 7 West Occo Works - CH10035-CH10185-EB - Layer 2
Area 2 | ITP-007-A2-LOT-027 | ITP-007-A2-LOT-027 - Zone 7 East Gate 7.3 to Mickleham - CH10650-CH10850-WB - Layer 2
Area 2 | ITP-007-A2-LOT-028 | ITP-007-A2-LOT-028 - Zone 7 East (North Half GSM) - CH10610-CH10700 - Layer 1
Area 2 | ITP-007-A2-LOT-029 | ITP-007-A2-LOT-029 - Zone 7 East (North Half GSM) - CH10610-CH10700 - Layer 2
Area 2 | ITP-007-A2-LOT-030 | ITP-007-A2-LOT-030 - Zone 7 West (Slither) - CH10000-CH10135 - Layer 1
Area 2 | ITP-007-A2-LOT-031 | ITP-007-A2-LOT-031 - Zone 7 West (Slither) - CH10035-CH10135 - Layer 2
Area 2 | ITP-007-A2-LOT-032 | ITP-007-A2-LOT-032 - Mickleham South (SB) CH30316 - CH30400 Layer 1 | CLOSED | 2022-06-30 |  | 2022-03-10 |  | 2022-03-10 | 2022-03-11 | 2022-03-10 |  | EAL- Earthworks Lot | CH30316 - CH30370 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | SB - Southbound | Varun Panickar | Lot over 60 days with overdue NCR. (1145-FUL-NCR-0010) Approved & Closed. | Varun Panickar | 2022-06-30 | Babak Rudd-Project Quality Manager | YES
Area 2 | ITP-007-A2-LOT-033 | ITP-007-A2-LOT-033 - Mickleham South (SB) CH30316 - CH30400 Layer 2 | CLOSED | 2022-06-30 |  | 2022-03-10 |  | 2022-03-10 | 2022-03-10 | 2022-03-15 |  | EAL- Earthworks Lot | CH30316 - CH30400 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | SB - Southbound | Varun Panickar | Lot over 60 days with overdue NCR. (1145-FUL-NCR-0010) Approved & Closed. | Varun Panickar | 2022-06-30 | Babak Rudd-Project Quality Manager | YES
Area 2 | ITP-007-A2-LOT-034 | ITP-007-A2-LOT-034 - Mickleham South (NB) CH30316 - CH30400 Layer 1 | CLOSED | 2022-06-30 |  | 2022-03-10 |  | 2022-03-10 | 2022-03-10 | 2022-03-13 |  | EAL- Earthworks Lot | CH30316 - CH30400 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | NB - Northbound | Varun Panickar | Lot over 60 days with overdue NCR. (1145-FUL-NCR-0010) Approved & Closed. | Varun Panickar | 2022-06-30 | Babak Rudd-Project Quality Manager | YES
Area 2 | ITP-007-A2-LOT-035 | ITP-007-A2-LOT-035 - Mickleham South (NB) CH30316 - CH30400 Layer 2 | CLOSED | 2022-06-30 |  | 2022-03-11 |  | 2022-03-11 | 2022-03-11 | 2022-03-15 |  | CIL-Civil Lot | CH30316 - CH30400 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | NB - Northbound | Varun Panickar | Lot over 60 days with overdue NCR. (1145-FUL-NCR-0010) Approved & Closed. | Varun Panickar | 2022-06-30 | Babak Rudd-Project Quality Manager | YES
Area 2 | ITP-007-A2-LOT-036 | ITP-007-A2-LOT-036 - Mickleham North (NB) CH30450 - CH30520 Layer 1 | CLOSED | 2022-06-30 |  | 2022-03-12 |  | 2022-03-12 | 2022-03-12 | 2022-03-15 |  | EAL- Earthworks Lot | CH30450 - CH30520 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | NB - Northbound | Varun Panickar | Lot over 60 days with overdue NCR. (1145-FUL-NCR-0010) Approved & Closed. | Varun Panickar | 2022-06-30 | Babak Rudd-Project Quality Manager | YES
Area 2 | ITP-007-A2-LOT-037 | ITP-007-A2-LOT-037 - Mickleham North (NB) CH30450 - CH30520 Layer 2 | CLOSED | 2022-06-30 |  | 2022-03-12 |  | 2022-03-12 | 2022-03-12 | 2022-03-12 |  | EAL- Earthworks Lot | CH30450-CH30520 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | NB - Northbound | Varun Panickar | Lot over 60 days with overdue NCR. (1145-FUL-NCR-0010) Approved & Closed. | Varun Panickar | 2022-06-30 | Babak Rudd-Project Quality Manager | YES
Area 2 | ITP-007-A2-LOT-040 | ITP-007-A2-LOT-040 - Mickleham North (SB) CH30470 - CH30520 Layer 1 | CLOSED | 2022-06-30 |  | 2022-03-12 |  | 2022-03-12 | 2022-03-12 | 2022-03-12 |  | CIL-Civil Lot | CH30470 - CH30520 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | SB - Southbound | Varun Panickar | Lot over 60 days with overdue NCR. (1145-FUL-NCR-0010) Approved & Closed. | Varun Panickar | 2022-06-30 | Babak Rudd-Project Quality Manager | YES
Area 2 | ITP-007-A2-LOT-041 | ITP-007-A2-LOT-041 - Mickleham North (SB) CH30470 - CH30520 Layer 2 | CLOSED | 2022-06-30 |  | 2022-03-12 |  | 2022-03-12 | 2022-03-12 | 2022-03-12 |  | EAL- Earthworks Lot | CH30470 - CH30520 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | SB - Southbound | Varun Panickar | Lot over 60 days with overdue NCR. (1145-FUL-NCR-0010) Approved & Closed. | Varun Panickar | 2022-06-30 | Babak Rudd-Project Quality Manager | YES
Area 2 | ITP-007-A2-LOT-044 | ITP-007-A2-LOT-044 - Mickleham North (SB) CH30430 - CH30470 Layer 1 | CLOSED | 2022-06-30 |  | 2022-03-18 |  | 2022-03-18 | 2022-03-18 | 2022-03-18 |  | EAL- Earthworks Lot | CH30430 - CH30470 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | SB - Southbound | Varun Panickar | Lot over 60 days with overdue NCR. (1145-FUL-NCR-0010) Approved & Closed. | Varun Panickar | 2022-06-30 | Babak Rudd-Project Quality Manager | YES
Area 2 | ITP-007-A2-LOT-045 | ITP-007-A2-LOT-045 - Mickleham North (SB) CH30430 - CH30470 Layer 2 | CLOSED | 2022-06-30 |  | 2022-03-18 |  | 2022-03-18 | 2022-03-19 | 2022-03-19 |  | EAL- Earthworks Lot | CH30430 - CH30470 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | SB - Southbound | Varun Packinar | Lot over 60 days with overdue NCR. (1145-FUL-NCR-0010) Approved & Closed. | Varun Panickar | 2022-06-30 | Babak Rudd-Project Quality Manager | YES
Area 2 | ITP-007-A2-LOT-046 | ITP-007-A2-LOT-046 - Mickleham Intersection CH30400 - CH30430 Layer 1 | CLOSED | 2022-06-30 |  | 2022-03-21 |  | 2022-03-21 | 2022-03-21 | 2022-03-21 |  | EAL- Earthworks Lot | CH30400 - CH30430 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | ME - Median | Varun Panickar | Similar to Lot 042 | Varun Panickar | 2022-06-30 | Babak Rudd-Project Quality Manager | YES
Area 2 | ITP-007-A2-LOT-047 | ITP-007-A2-LOT-047 - Mickleham Intersection CH30400 - CH30430 Layer 2 | CLOSED | 2022-06-30 |  | 2022-03-21 |  | 2022-03-21 | 2022-03-21 | 2022-03-21 |  | EAL- Earthworks Lot | CH30400 - CH30430 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | ME - Median | Varun Panickar | Similar to Lot 043 | Varun Panickar | 2022-06-30 | Babak Rudd-Project Quality Manager | YES
Area 2 | ITP-007-A2-LOT-048 | ITP-007-A2-LOT-048 - Mickleham Intersection (Eastern Tie End) CH10550 - CH10600 Layer 1 | CLOSED | 2022-05-16 |  | 2022-03-23 |  | 2022-03-23 | 2022-03-23 | pass |  | CIL-Civil Lot | CH10550 - CH10600 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Varun Panickar |  | Varun Panickar |  | Babak Rudd-Project Quality Manager | N/A
Area 2 | ITP-007-A2-LOT-049 | ITP-007-A2-LOT-049 - Mickleham Intersection (Eastern Tie End) CH10550 - CH10600 Layer 2 | CLOSED | 2022-06-30 |  | 2022-03-23 |  | 2022-03-23 | 2022-03-23 | 2022-03-25 |  | CIL-Civil Lot | CH10550 - CH10600 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Varun Panickar | Lot over 60 days with overdue NCR. (1145-FUL-NCR-0010) Approved & Closed. | Varun Panickar | 2022-06-30 | Babak Rudd-Project Quality Manager | YES
Area 2 | ITP-007-A2-LOT-050 | ITP-007-A2-LOT-050 - Mickleham North NW Slip Lane CH10470 - CH10490 Layer 2 | CLOSED | 2022-05-27 |  | 2022-03-28 |  | 2022-03-28 | 2022-03-28 | pass | 2022-04-28 | CIL-Civil Lot | CH10470 - CH10490 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | NB - Northbound | Varun Panickar |  | Varun Panickar | 2022-05-25 | Babak Rudd-Project Quality Manager | N/A
Area 2 | ITP-007-A2-LOT-051 | ITP-007-A2-LOT-051 - Mickleham North NW Slip Lane CH10470 - CH10490 Layer 1 | CLOSED | 2022-05-27 |  | 2022-03-28 |  | 2022-03-28 | 2022-03-28 | pass | 2022-05-05 | CIL-Civil Lot | CH10470 - CH10490 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | NB - Northbound | Varun Panickar |  | Varun Panickar | 2022-05-25 | Babak Rudd-Project Quality Manager | N/A
Area 2 | ITP-007-A2-LOT-052 | ITP-007-A2-LOT-052 - Zone 7 East Gate 7.1-7.2 (Post ACM) - CH10840-CH11140 - Layer 1 - WB |  |  |  | 2022-03-31 |  | 2022-03-31 | 2022-03-31 |  |  | EAL- Earthworks Lot | CH10840 to CH11140 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Abed Wardak
Area 2 | ITP-007-A2-LOT-053 | ITP-007-A2-LOT-053 - Zone 7 East Gate 7.1-7.2 (Post ACM) - CH10900-CH11190 - Layer 2 - WB |  |  |  | 2022-03-31 |  | 2022-04-01 | 2022-04-01 |  |  | EAL- Earthworks Lot | CH10900 to CH11180 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Abed Wardak | Boreal type a
Area 2 | ITP-007-A2-LOT-055 | ITP-007-A2-LOT-055 - Zone 7 East (Post Drainage Install) - CH10550-CH10750 - Layer 2
Area 2 | ITP-007-A2-LOT-056 | ITP-007-A2-LOT-056 - Zone 7 East - CH10780-CH10850 - Layer 1 |  |  |  | 2022-03-15 |  | 2022-03-15 | 2022-03-15 |  |  |  | 10780 to 10850 | [5 empty] | Class 4 RPI
Area 2 | ITP-007-A2-LOT-057 | ITP-007-A2-LOT-057 - Zone 7 East - CH10780-CH10850 - Layer 2 |  |  |  | 2022-03-16 |  | 2022-03-16 | 2022-03-16 |  |  |  | 10780 to 10850 | [5 empty] | RPI class 4
Area 2 | ITP-007-A2-LOT-058 | ITP-007-A2-LOT-058 - Zone 7 East - Nobility Rd to Gate 7.5 - CH11480-CH11400 - WB - Layer 1 |  |  |  | 2022-05-05 |  | 2022-05-05 | 2022-05-05 |  |  | EAL- Earthworks Lot | CH11490-CH11360 | EART - Earthwork | TACAP - Type A Capping | 1145-ACM-CVR-DPK-0001 | WB - Westbound | Abed Wardak
Area 2 | ITP-007-A2-LOT-059 | ITP-007-A2-LOT-059 - Zone 7 East - Nobility Rd to Gate 7.5 - CH11480-CH11400 - WB - Layer 2
Area 2 | ITP-007-A2-LOT-060 | ITP-007-A2-LOT-060 - Zone 7 West Dam to East of 1505 Driveway - CH10290 to CH10460 - WB - Layer 1 | not started | not started |  | 2022-05-26 |  | 2022-05-27 | 2022-05-27 |  |  | EAL - Earthworks Lot | CH10290-10460 | EART - Earthwork | TACAP - Type A Capping | 1145-C200-FUL-QAC-ITP-0007 | WB - Westbound | Brighton Sarabia |  |  |  | not started | not started
Area 2 | ITP-007-A2-LOT-061 | ITP-007-A2-LOT-061 - Zone 7 West Dam to Gate 7.7 - CH10290 to CH10400 - WB - Layer 2 | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-007-A2-LOT-062 | ITP-007-A2-LOT-062 - Zone 7 East - 7.1-7.2 - CH10920-CH10850 - WB - Layer 2 | not started | not started |  | 2022-05-27 |  | 2022-05-27 | 2022-05-27 |  |  |  | CH10920-10850 |  |  |  |  | Will |  |  |  | not started | not started
Area 2 | ITP-007-A2-LOT-063 | ITP-007-A2-LOT-063 - Zone 7 West, East of 755 Driveway - CH10180 to CH10350 - WB - Layer 1 | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-007-A2-LOT-064 | ITP-007-A2-LOT-064 - Zone 7 West, SW Intersection - CH10450 to CH10490 - WB - Layer 1 | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-007-A2-LOT-065 | ITP-007-A2-LOT-065 - Zone 7 West, Dam SUP - CH10300 to CH10350 - WB - Layer 1 | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-007-A2-LOT-066 | ITP-007-A2-LOT-066 - Zone 7 West, Slip Lane of SW Intersection - CH30370 to CH30395 - NB - Layer 1 | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-007-A2-LOT-067 | ITP-007-A2-LOT-067 - Zone 7 West, East of 755 Driveway - CH10180 to CH10350 - WB - Layer 2 | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-007-A2-LOT-068 | ITP-007-A2-LOT-068 - Zone 7 West, SW Intersection - CH10450 to CH10495 - WB - Layer 2 | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-007-A2-LOT-070 | ITP-007-A2-LOT-070 - Zone 7 East - Layer 1 Capping - CH11220 to CH11300 | not started | not started |  | 2022-07-04 |  | 2022-07-04 | 2022-07-05 |  |  | EAL - Earthworks Lot | 11220-11300 | [8 empty] | not started | not started
Area 2 | ITP-007-A2-LOT-071 | ITP-007-A2-LOT-071 - Zone 7 East - Layer 2 Capping - CH11220 to CH11300 | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-009-A2-LOT 032 | ITP-009-A2-LOT 032-Zone 7 East CH10950-CH11190 | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-009-A2-LOT 033 | ITP-009-A2-LOT 033-Zone 7 East CH10920-CH10950 | not started | not started | [5 empty] | not started | [9 empty] | not started | not started | not started | not started
Area 2 | ITP-009-A2-LOT 034 | ITP-009-A2-LOT 034-Zone 7 East CH10920-CH10850 | not started | not started | [5 empty] | not started | [9 empty] | not started | not started | not started | not started
Area 2 | ITP-009-A2-LOT 036 | ITP-009-A2-LOT 036-Zone 7 East CH11220-CH11300 | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-009-A2-LOT-002 | ITP-009-A2-LOT-002 - Mickleham South (NB) CH30020-30234 | pass | pass | 2022-05-27 | 2022-02-11 |  | 2022-02-11 | 2022-02-11 | pass | 2022-02-20 | EAL- Earthworks Lot | CH30020-30234 | PAVI - Paving | PAVI - Unbound Pavements | 1145-C200-FUL-QAC-0009 | NB - Northbound | Varun Panickar |  | pass | pass | pass | pass
Area 2 | ITP-009-A2-LOT-003 | ITP-009-A2-LOT-003 - Mickleham South (SB) CH30020-CH30152 | pass | pass | etc. | 2022-02-22 |  | 2022-02-22 | 2022-02-23 | pass | 2022-02-24 | EAL- Earthworks Lot | CH30020-CH30152 | PAVI - Paving | PAVI - Unbound Pavements | 1145-C200-FUL-QAC-0009 | SB - Southbound | Varun Panickar |  | pass | pass | pass | pass
Area 2 | ITP-009-A2-LOT-004 | ITP-009-A2-LOT-004 - Mickleham South (NB) CH30234-Ch30316 | pass | pass | etc. | 2022-02-22 |  | 2022-02-22 | 2022-02-23 | pass | 2022-02-25 | EAL- Earthworks Lot | CH30234-Ch30316 | PAVI - Paving | PAVI - Unbound Pavements | 1145-C200-FUL-QAC-0009 | NB - Northbound | Varun Panickar |  | pass | pass | pass | pass
Area 2 | ITP-009-A2-LOT-005 | ITP-009-A2-LOT-005 - Mickleham South (SB) CH30152-CH30316 | pass | pass | etc. | 2022-02-24 |  | 2022-02-24 | 2022-02-24 | pass | 2022-02-25 | EAL- Earthworks Lot | CH30152-CH30316 | PAVI - Paving | PAVI - Unbound Pavements | 1145-C200-FUL-QAC-0009 | SB - Southbound | Varun Panickar |  | pass | pass | pass | pass
Area 2 | ITP-009-A2-LOT-006 | ITP-009-A2-LOT-006 - Mickleham North (NB) CH30520-CH30665 | pass | pass |  | 2022-03-02 |  | 2022-03-02 | 2022-03-02 | pass | 2022-03-20 | CIL-Civil Lot | CH30520-CH30665 | PAVI - Paving | PAVI - Unbound Pavements | 1145-C200-FUL-QAC-0009 | NB - Northbound | Varun Panickar |  | pass | pass | pass | pass
Area 2 | ITP-009-A2-LOT-007 | ITP-009-A2-LOT-007 - Mickleham North (SB) CH30520-CH30665 | pass | pass |  | 2022-03-03 |  | 2022-03-03 | 2022-03-04 | pass | 2022-03-12 | CIL-Civil Lot | CH30520-CH30665 | PAVI - Paving | PAVI - Unbound Pavements | 1145-C200-FUL-QAC-0009 | SB - Southbound | Varun Panickar |  | pass | pass | pass | pass
Area 2 | ITP-009-A2-LOT-008 | ITP-009-A2-LOT-008 - Mickleham North (SB+NB) CH30665-CH30800 | pass | pass |  | 2022-03-03 |  | 2022-03-03 | 2022-03-03 | pass | 2022-02-25 | CIL-Civil Lot | CH30665-CH30800 | PAVI - Paving | PAVI - Unbound Pavements | 1145-C200-FUL-QAC-0009 | NB - Northbound | Varun Panickar |  | pass | pass | pass | pass
Area 2 | ITP-009-A2-LOT-009 | ITP-009-A2-LOT-009 - Zone 7 West - Occo Works (CH10040 - 10175) | not started | not started |  | 2022-03-10 |  | 2022-03-10 | 2022-03-10 | not started |  |  | CH10000-10135 | PAVI - Paving | PAVI - Unbound Pavements | 1145-C200-FUL-QAC-0009 | EB - Eastbound | Brighton Sarabia |  | not started | not started | not started | not started
Area 2 | ITP-009-A2-LOT-010 | ITP-009-A2-LOT-010 - Mickleham South (NB+SB) CH30316-CH30400 | pass | pass |  | 2022-03-12 |  | 2022-03-12 | 2022-03-12 | pass | 2022-03-23 | CIL-Civil Lot | CH30316-CH30400 | PAVI - Paving | PAVI - Unbound Pavements | 1145-C200-FUL-QAC-0009 | SB - Southbound | Varun Panickar |  | pass | pass | pass | pass
Area 2 | ITP-009-A2-LOT-011 | ITP-009-A2-LOT-011 - Mickleham North (NB) CH30430-CH30520 | pass | pass |  | 2022-03-14 |  | 2022-03-14 | 2022-03-15 | pass | 2022-03-17 | CIL-Civil Lot | CH30430-CH30520 | PAVI - Paving | PAVI - Unbound Pavements | 1145-C200-FUL-QAC-0009 | NB - Northbound | Varun Panickar |  | pass | pass | pass | pass
Area 2 | ITP-009-A2-LOT-013 | ITP-009-A2-LOT-013 - Zone 7 East (Gate 7.3-CH10650) (Class 4 Placement) | not started | not started | [5 empty] | not started | [9 empty] | not started | not started | not started | not started
Area 2 | ITP-009-A2-LOT-015 | ITP-009-A2-LOT-015 - Mickleham North (SB) CH30435-CH30455 | pass | pass |  | 2022-03-18 |  | 2022-03-18 | 2022-03-21 | pass | 2022-03-18 | CIL-Civil Lot | CH30430-CH30450 | PAVI - Paving | PAVI - Unbound Pavements | 1145-C200-FUL-QAC-0009 | SB - Southbound | Varun Panickar |  | pass | pass | pass | pass
Area 2 | ITP-009-A2-LOT-017 | ITP-009-A2-LOT-017 - Mickleham North (Type 6) CH30785-CH30820 | pass | pass |  | 2022-03-25 |  | 2022-03-25 | 2022-03-25 | pass | 2022-03-28 | CIL-Civil Lot | CH30785-CH30820 | PAVI - Paving | PAVI - Unbound Pavements | 1145-C200-FUL-QAC-0009 | NB - Northbound | Varun Panickar |  | pass | pass | pass | pass
Area 2 | ITP-009-A2-LOT-018 | ITP-009-A2-LOT-018 - Mickleham South (Type 6) CH29980-CH30030 | pass | pass |  | 2022-03-25 |  | 2022-03-25 | 2022-03-25 | pass | 2022-03-28 | CIL-Civil Lot | CH29980-CH30030 | PAVI - Paving | PAVI - Unbound Pavements | 1145-C200-FUL-QAC-0009 | SB - Southbound | Varun Panickar |  | pass | pass | pass | pass
Area 2 | ITP-009-A2-LOT-021 | ITP-009-A2-LOT-021 - Mickleham North (SB) CH30450-CH30520 | pass | pass |  | 2022-03-15 |  | 2022-03-15 | 2022-03-15 | pass | 2022-03-25 | CIL-Civil Lot | CH30450-CH30520 | PAVI - Paving | PAVI - Unbound Pavements | 1145-C200-FUL-QAC-0009 | SB - Southbound | Varun Panickar |  | pass | pass | pass | pass
Area 2 | ITP-009-A2-LOT-022 | ITP-009-A2-LOT-022 - Mickleham Rd Intersection (EB) CH30400-CH30430 | pass | pass |  | 2022-03-22 |  | 2022-03-22 | 2022-03-22 | pass | 2022-03-24 | CIL-Civil Lot | CH 30400 - CH 30430 | PAVI - Paving | PAVI - Unbound Pavements | 1145-C200-FUL-QAC-0009 |  | Varun Panickar |  | pass | pass | pass | pass
Area 2 | ITP-009-A2-LOT-024 | ITP-009-A2-LOT-024 - Mickleham Intersection (SE Lane +Slip Lane) CH10550-CH10600 | pass | pass |  | 2022-03-23 |  | 2022-03-23 | 2022-03-28 | pass | 2022-03-28 | CIL-Civil Lot | CH10550-CH10600 | PAVI - Paving | PAVI - Unbound Pavements | 1145-C200-FUL-QAC-0009 | WB - Westbound | Varun Panickar |  | pass | pass | pass | pass
Area 2 | ITP-009-A2-LOT-025 | ITP-009-A2-LOT-025 - Mickleham Intersection NE (North- Eastern Slip Lane) CH20540-CH20560 | pass | pass |  | 2022-03-28 |  | 2022-03-28 | 2022-03-28 | pass | 2022-03-28 | CIL-Civil Lot | CH20540-CH20560 | PAVI - Paving | PAVI - Unbound Pavements | 1145-C200-FUL-QAC-0009 | SB - Southbound | Varun Panickar |  | pass | pass | pass | pass
Area 2 | ITP-009-A2-LOT-026 | ITP-009-A2-LOT-026 - Mickleham Intersection NW (North-Western Slip Lane) CH20470-CH20490 | pass | pass |  | 2022-03-28 |  | 2022-03-28 | 2022-03-28 | pass | 2022-03-28 | CIL-Civil Lot | CH20470-CH20490 | PAVI - Paving | PAVI - Unbound Pavements | 1145-C200-FUL-QAC-0009 | NB - Northbound | Varun Panickar |  | pass | pass | pass | pass
Area 2 | ITP-009-A2-LOT-027 | ITP-009-A2-LOT-027 - Zone 7 East - Occo Works (CH10580 - CH10650) | not started | not started |  | 2022-03-13 |  | 2022-03-13 | 2022-03-13 | not started |  | EAL- Earthworks Lot | 10580 10650 | PAVI - Paving | PAVI - Unbound Pavements | 1145-C200-FUL-QAC-0009 | WB - Westbound | Omar El-Khub | RPI class 4 | not started | not started | not started | not started
Area 2 | ITP-009-A2-LOT-028 | ITP-009-A2-LOT-028 - Zone 7 East - Occo Works (CH10650 - CH10870) | not started | not started |  | 2022-03-16 |  | 2022-03-16 | 2022-03-16 | not started |  | CIL-Civil Lot | 10650 to 10820 | PAVI - Paving | PAVI - Unbound Pavements | 1145-C200-FUL-QAC-0009 | EB - Eastbound | Jonathon rock | Holcim class 4 | not started | not started | not started | not started
Area 2 | ITP-009-A2-LOT-029 | ITP-009-A2-LOT-029 - Zone 7 West - Occo Works (CH10035 - 10050) | not started | not started | [5 empty] | not started | [9 empty] | not started | not started | not started | not started
Area 2 | ITP-009-A2-LOT-030 | ITP-009-A2-LOT-030 - Zone 7 West - Occo Works (CH10000 - 10035) | not started | not started | [5 empty] | not started | [9 empty] | not started | not started | not started | not started
Area 2 | ITP-009-A2-LOT-031 | ITP-009-A2-LOT-031 - Zone 7 West - Occo Works (CH10000 - 10040) | not started | not started | [5 empty] | not started | [9 empty] | not started | not started | not started | not started
Area 2 | ITP-009-A2-LOT-035 | ITP-009-A2-LOT-035 - Zone 7 West CH10180-10400 | not started | not started | [5 empty] | not started | [9 empty] | not started | not started | not started | not started
Area 2 | ITP-010-A2-LOT-001 | ITP-010-A2-LOT-001 - Mickleham South CH30070-CH30234 | not started | not started |  | 2022-02-12 |  | 2022-02-12 | 2022-02-12 |  |  | DRL- Drainage Lot | CH30070-CH30234 | STOR - Stormwater | SUBS Subsoil Drainage ÃŠ | 1145-C200-FUL-QAC-0010 | NB - Northbound | Varun Panickar |  |  |  | not started | not started
Area 2 | ITP-010-A2-LOT-002 | ITP-010-A2-LOT-002 - Mickleham South CH30234-CH30316 | not started | not started |  | 2022-02-25 |  | 2022-02-25 | 2022-02-25 |  |  | DRL- Drainage Lot | CH30234-CH30316 | STOR - Stormwater | SUBS Subsoil Drainage ÃŠ | 1145-C200-FUL-QAC-0010 | NB - Northbound | Varun Panickar |  |  |  | not started | not started
Area 2 | ITP-010-A2-LOT-003 | ITP-010-A2-LOT-003 - Mickleham North Southbound ( CH 30520- 30785) | not started | not started |  | 2022-03-04 |  | 2022-03-04 | 2022-03-04 |  |  | DRL- Drainage Lot | CH30520-CH30785 | STOR - Stormwater | SUBS Subsoil Drainage ÃŠ | 1145-C200-FUL-QAC-0010 | SB - Southbound | Ahmad El Wazer |  |  |  | not started | not started
Area 2 | ITP-010-A2-LOT-004 | ITP-010-A2-LOT-004 - Mickleham North ( CH 30520- CH 30785 ) NB | not started | not started |  | 2022-03-04 |  | 2022-03-04 | 2022-03-04 |  |  | DRL- Drainage Lot | CH30520 - CH30665 | STOR - Stormwater | SUBS Subsoil Drainage ÃŠ | 1145-C200-FUL-QAC-0010 | NB - Northbound | Varun Panickar |  |  |  | not started | not started
Area 2 | ITP-010-A2-LOT-005 | ITP-010-A2-LOT-005 - Mickleham South CH30316-CH30370 | not started | not started |  | 2022-03-12 |  | 2022-03-12 | 2022-03-12 |  |  | DRL- Drainage Lot | CH30316-CH30370 | STOR - Stormwater | SUBS Subsoil Drainage ÃŠ | 1145-C200-FUL-QAC-0010 | NB - Northbound | Varun Panickar |  |  |  | not started | not started
Area 2 | ITP-010-A2-LOT-006 | ITP-010-A2-LOT-006 - Mickleham South (CH30316-CH30370) | not started | not started |  | 2022-03-15 |  | 2022-03-15 | 2022-03-15 |  |  | DRL- Drainage Lot | CH30316-CH30370 | STOR - Stormwater | SUBS Subsoil Drainage ÃŠ | 1145-C200-FUL-QAC-0010 | SB - Southbound | Varun Panickar |  |  |  | not started | not started
Area 2 | ITP-010-A2-LOT-007 | ITP-010-A2-LOT-007 - Zone 7 West of mick Rd ( CH 20070- CH 20175 ) | not started | not started |  | 2022-03-12 |  | 2022-03-12 | 2022-03-12 |  |  |  | 20070 to 20170 | STOR - Stormwater | SUBS Subsoil Drainage ÃŠ | 1145-C200-FUL-QAC-0010 | EB - Eastbound | Jonathon |  |  |  | not started | not started
Area 2 | ITP-010-A2-LOT-008 | ITP-010-A2-LOT-008 - Zone 7 East (CH 10500 - CH 10850 ) - NOT USED | not started | not started |  | 2022-03-03 |  | 2022-03-03 | 2022-03-03 |  |  | DRL- Drainage Lot |  | STOR - Stormwater | SUBS Subsoil Drainage ÃŠ | 1145-C200-FUL-QAC-0010 | WB - Westbound | Omar El-Khub |  |  |  | not started | not started
Area 2 | ITP-010-A2-LOT-009 | ITP-010-A2-LOT-009 - Zone 7 East (CH 10600- CH 10780) | not started | not started |  | 2022-03-15 |  | 2022-03-15 | 2022-03-15 |  |  | DRL- Drainage Lot | 10600 to 10780 | [8 empty] | not started | not started
Area 2 | ITP-010-A2-LOT-010 | ITP-010-A2-LOT-010 - Zone 7 West (CH 10050 - 10098) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-010-A2-LOT-011 | ITP-010-A2-LOT-011 - Zone 7 East (CH 10780 - 10850) | not started | not started |  | 2022-03-18 |  | 2022-03-18 | 2022-03-18 |  |  |  | 10780 to 10850 | [8 empty] | not started | not started
Area 2 | ITP-010-A2-LOT-012 | ITP-010-A2-LOT-012 - Mickleham North - Pavement 6 (CH30785-CH30845) | not started | not started |  | 2022-03-25 |  | 2022-03-25 | 2022-03-25 |  |  | DRL- Drainage Lot | CH30785-CH30845 | STOR - Stormwater | SUBS Subsoil Drainage ÃŠ | 1145-C200-FUL-QAC-0010 | NB - Northbound | Varun Panickar |  |  |  | not started | not started
Area 2 | ITP-010-A2-LOT-013 | ITP-010-A2-LOT-013 - Mickleham Intersection - SE Traffic Island (CH10550 - CH10560) | not started | not started |  | 2022-03-28 |  | 2022-03-28 | 2022-03-28 |  |  | DRL- Drainage Lot | CH10550 - CH10560 | STOR - Stormwater | SUBS Subsoil Drainage ÃŠ | 1145-C200-FUL-QAC-0010 | EB - Eastbound | Varun Panickar |  |  |  | not started | not started
Area 2 | ITP-010-A2-LOT-014 | ITP-010-A2-LOT-014 - Zone 7 West CH10000-CH10180 | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-010-A2-LOT-015 | ITP-010-A2-LOT-015 - Mickleham North (SB) + NE Traffic Island (CH40500-CH40360) | not started | not started |  | 2022-03-20 |  | 2022-03-20 | 2022-03-20 |  |  | DRL- Drainage Lot | CH40500-CH40360 | STOR - Stormwater | SUBS Subsoil Drainage ÃŠ | 1145-C200-FUL-QAC-0010 | SB - Southbound | Varun Panickar |  |  |  | not started | not started
Area 2 | ITP-010-A2-LOT-016 | ITP-010-A2-LOT-016 - Mickleham South CH29980-CH30070 | not started | not started |  | 2022-03-26 |  | 2022-03-26 | 2022-03-26 |  |  | DRL- Drainage Lot | CH29980-CH30070 | STOR - Stormwater | SUBS Subsoil Drainage ÃŠ | 1145-C200-FUL-QAC-0010 | NB - Northbound | Varun Panickar |  |  |  | not started | not started
Area 2 | ITP-010-A2-LOT-017 | ITP-010-A2-LOT-017 - Mickleham North CH30430-CH30520 NB | not started | not started |  | 2022-03-26 |  | 2022-03-26 | 2022-03-26 |  |  | DRL- Drainage Lot | CH30430-CH30520 | STOR - Stormwater | SUBS Subsoil Drainage ÃŠ | 1145-C200-FUL-QAC-0010 | NB - Northbound | Varun Panickar |  |  |  | not started | not started
Area 2 | ITP-010-A2-LOT-018 | ITP-010-A2-LOT-018 - Mickleham Intersection CH20475-CH20500 NW Island | not started | not started |  | 2022-03-26 |  | 2022-03-26 | 2022-03-26 |  |  | DRL- Drainage Lot | CH20475-CH20500 | STOR - Stormwater | SUBS Subsoil Drainage ÃŠ | 1145-ACM-CVD-DPK-0003 | NB - Northbound | Varun Panickar |  |  |  | not started | not started
Area 2 | ITP-010-A2-LOT-019 | ITP-010-A2-LOT-019 - Zone 7 East WB - CH10850 to CH10950 | not started | not started |  | 2022-06-20 |  | 2022-06-20 | 2022-06-20 |  |  |  | 10850 to 10950 |  |  |  |  | Jonathon Rock |  |  |  | not started | not started
Area 2 | ITP-010-A2-LOT-020 | ITP-010-A2-LOT-020 - Zone 7 East WB - CH10920 to CH11020 | not started | not started |  | 2022-06-21 |  | 2022-06-21 | 2022-06-21 |  |  |  | 10920 to 11020 |  |  |  |  | Jonathon Rock |  |  |  | not started | not started
Area 2 | ITP-010-A2-LOT-021 | ITP-010-A2-LOT-021 - Zone 7 East WB - CH11070 to CH11140 | not started | not started |  | 2022-06-29 |  | 2022-06-29 | 2022-06-29 |  |  | DRL- Drainage Lot | 11070-11140 | STOR - Stormwater | SUBS Subsoil Drainage ÃŠ |  |  | Jonathon Rock |  |  |  | not started | not started
Area 2 | ITP-010-A2-LOT-022 | ITP-010-A2-LOT-022 - Zone 7 East WB - CH10880 to 11020 | not started | not started |  | 2022-06-30 |  | 2022-06-30 | 2022-06-30 |  |  |  | Ch 10880 ch 11020 |  |  |  |  | Jonathon rock |  |  |  | not started | not started
Area 2 | ITP-010-A2-LOT-023 | ITP-010-A2-LOT-023 - Zone 7 East WB - CH11020 to 11110 | not started | not started |  | 2022-07-01 |  | 2022-07-01 | 2022-07-01 |  |  | DRL- Drainage Lot | 11020-11110 | STOR - Stormwater | SUBS Subsoil Drainage ÃŠ |  | WB - Westbound |  |  |  |  | not started | not started
Area 2 | ITP-010-A2-LOT-024 | ITP-010-A2-LOT-024 - Craigieburn Rd WB - CH10910-10840 | not started | not started |  | 2022-07-02 |  | 2022-07-02 | 2022-07-02 |  |  | DRL- Drainage Lot | 10840-10910 | STOR - Stormwater | [7 empty] | not started | not started
Area 2 | ITP-010-AX-LOT-XXX | ITP-010-AX-LOT-XXX - Desc | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-011-A2-LOT-001 | ITP-011-A2-LOT-001 - Mickleham South CH30070 - CH30234 | pass | pass |  | 2022-02-14 |  | 2022-02-14 | 2022-02-14 | pass | 2022-02-17 | CIL-Civil Lot | CH30070-CH30234 | EART - Earthworks | EART - Cement Treated Crushed Rock | 1145-C200-FUL-QAC-0011 | NB - Northbound | Varun Panickar |  | Varun Panickar | 2022-05-26 | pass | pass
Area 2 | ITP-011-A2-LOT-002 | ITP-011-A2-LOT-002 - Mickleham South CH30000 - CH30200 | pass | pass |  | 2022-02-26 |  | 2022-02-26 | 2022-02-26 | pass | 2022-03-02 | CIL-Civil Lot | CH30000 - CH30200 | EART - Earthworks | EART - Cement Treated Crushed Rock | 1145-C200-FUL-QAC-0011 | NB - Northbound | Varun Panickar |  | Varun Panickar | 2022-05-26 | pass | pass
Area 2 | ITP-011-A2-LOT-003 | ITP-011-A2-LOT-003 - Mickleham South CH30234 - CH30316 | pass | pass |  | 2022-02-28 |  | 2022-02-28 | 2022-02-28 | pass | 2022-03-02 | CIL-Civil Lot | CH30234 - CH30316 | EART - Earthworks | EART - Cement Treated Crushed Rock | 1145-C200-FUL-QAC-0011 | NB - Northbound | Varun Panickar |  | Varun Panickar | 2022-05-26 | pass | pass
Area 2 | ITP-011-A2-LOT-004 | ITP-011-A2-LOT-004 - Mickleham North (Northbound) CH30520 - CH30665 | pass | pass |  | 2022-03-04 |  | 2022-03-04 | 2022-03-04 | pass | 2022-03-06 | CIL-Civil Lot | CH30520 - CH30665 | EART - Earthworks | EART - Cement Treated Crushed Rock | 1145-C200-FUL-QAC-0011 | NB - Northbound | Varun Panickar |  | Varun Panickar | 2022-05-26 | pass | pass
Area 2 | ITP-011-A2-LOT-005 | ITP-011-A2-LOT-005 - Mickleham North (Southbound) CH30520 - CH30575 | pass | pass |  | 2022-03-06 |  | 2022-03-06 | 2022-03-06 | pass | 2022-03-12 | CIL-Civil Lot | CH30520 - CH30575 | EART - Earthworks | EART - Cement Treated Crushed Rock | 1145-C200-FUL-QAC-0011 | SB - Southbound | Varun Panickar |  | Varun Panickar | 2022-05-25 | pass | pass
Area 2 | ITP-011-A2-LOT-006 | ITP-011-A2-LOT-006 - Mickleham North CH30665 - CH30820 | not started | not started |  | 2022-03-06 |  | 2022-03-06 | 2022-03-06 | pass | 2022-03-07 | CIL-Civil Lot | CH30665 - CH30820 | EART - Earthworks | EART - Cement Treated Crushed Rock | 1145-C200-FUL-QAC-0011 | NB - Northbound | Varun Panickar |  | Varun Panickar | 2022-05-31 | not started | not started
Area 2 | ITP-011-A2-LOT-007 | ITP-011-A2-LOT-007 - Mickleham North CH30575 - CH30665 | pass | pass |  | 2022-03-12 |  | 2022-03-12 | 2022-03-12 | pass | 2022-03-14 | CIL-Civil Lot | CH30575 - CH30665 | EART - Earthworks | EART - Cement Treated Crushed Rock | 1145-C200-FUL-QAC-0011 | SB - Southbound | Varun Panickar |  | Varun Panickar | 2022-05-25 | pass | pass
Area 2 | ITP-011-A2-LOT-008 | ITP-011-A2-LOT-008 - Mickleham South (NB) CH30316 - CH30400 | pass | pass |  | 2022-03-15 |  | 2022-03-15 | 2022-03-15 | pass | 2022-03-17 | CIL-Civil Lot | CH30316 - CH30400 | EART - Earthworks | EART - Cement Treated Crushed Rock | 1145-C200-FUL-QAC-0011 | NB - Northbound | Varun Panickar |  | Varun Panickar | 2022-05-25 | pass | pass
Area 2 | ITP-011-A2-LOT-012 | ITP-011-A2-LOT-012 - Mickleham South CH30316 - CH30375 | pass | pass |  | 2022-03-18 |  | 2022-03-18 | 2022-03-18 | pass | 2022-03-20 | CIL-Civil Lot | CH30316 - CH30375 | EART - Earthworks | EART - Cement Treated Crushed Rock | 1145-C200-FUL-QAC-0011 | SB - Southbound | Varun Panickar |  | Varun Panickar | 2022-05-25 | pass | pass
Area 2 | ITP-011-A2-LOT-013 | ITP-011-A2-LOT-013 - Mickleham North (Northbound) CH30430 - CH30470 | pass | pass |  | 2022-03-21 |  | 2022-03-21 | 2022-03-21 | pass | 2022-03-23 | CIL-Civil Lot | CH30430 - CH30470 | EART - Earthworks | EART - Cement Treated Crushed Rock | 1145-C200-FUL-QAC-0011 | NB - Northbound | Varun Panickar |  | Varun Panickar | 2022-05-25 | pass | pass
Area 2 | ITP-011-A2-LOT-014 | ITP-011-A2-LOT-014 - Mickleham North (Southbound) CH30400 - CH30520 | pass | pass |  | 2022-03-21 |  | 2022-03-21 | 2022-03-21 | pass | 2022-03-25 | CIL-Civil Lot | CH30400 - CH30520 | EART - Earthworks | EART - Cement Treated Crushed Rock | 1145-C200-FUL-QAC-0011 | SB - Southbound | Varun Panickar |  | Varun Panickar | 2022-05-25 | pass | pass
Area 2 | ITP-011-A2-LOT-015 | ITP-011-A2-LOT-015 - Mickleham North (Northbound) CH30470 - CH30520 | pass | pass |  | 2022-03-21 |  | 2022-03-21 | 2022-03-21 | pass | 2022-03-23 | CIL-Civil Lot | CH30470 - CH30520 | EART - Earthworks | EART - Cement Treated Crushed Rock | 1145-C200-FUL-QAC-0011 | NB - Northbound | Varun Panickar |  | Varun Panickar | 2022-05-25 | pass | pass
Area 2 | ITP-011-A2-LOT-016 | ITP-011-A2-LOT-016 - Mickleham Intersection CH30400 - CH30430 | pass | pass |  | 2022-03-22 |  | 2022-03-22 | 2022-03-22 | pass | 2022-03-27 | CIL-Civil Lot | CH30400 - CH30430 | EART - Earthworks | EART - Cement Treated Crushed Rock | 1145-C200-FUL-QAC-0011 | EB - Eastbound | Varun Panickar |  | Varun Panickar | 2022-05-25 | pass | pass
Area 2 | ITP-011-A2-LOT-017 | ITP-011-A2-LOT-017 - Zone 7 East (WB) CH10590 - CH10620 | pass | pass |  | 2022-03-28 |  | 2022-03-28 | 2022-03-28 | pass | 2022-03-30 | CIL-Civil Lot | CH10590 - CH10620 | EART - Earthworks | EART - Cement Treated Crushed Rock | 1145-C200-FUL-QAC-0011 | WB - Westbound | Varun Panickar |  | Varun Panickar | 2022-05-25 | pass | pass
Area 2 | ITP-011-A2-LOT-018 | ITP-011-A2-LOT-018 - Mickleham Intersection (SE SLIP LANE + WB CARRIAGEWAY) CH10550 - CH10590 | pass | pass |  | 2022-03-27 |  | 2022-03-27 | 2022-03-27 | pass | 2022-03-29 | CIL-Civil Lot | CH10550 - CH10590 | EART - Earthworks | EART - Cement Treated Crushed Rock | 1145-C200-FUL-QAC-0011 | WB - Westbound | Varun Panickar |  | Varun Panickar | 2022-05-25 | pass | pass
Area 2 | ITP-011-A2-LOT-019 | ITP-011-A2-LOT-019 - Mickleham Intersection (NE Slip Lane + East Bound Carriageway) CH20520 - CH20570 | pass | pass |  | 2022-03-28 |  | 2022-03-28 | 2022-03-28 | pass | 2022-03-30 | CIL-Civil Lot | CH20520 - CH20570 | EART - Earthworks | EART - Cement Treated Crushed Rock | 1145-C200-FUL-QAC-0011 | WB - Westbound | Varun Panickar |  | Varun Panickar | 2022-05-25 | pass | pass
Area 2 | ITP-011-A2-LOT-020 | ITP-011-A2-LOT-020 - Mickleham Rd Intersection NW Slip Lane CH20470 - CH20490 | pass | pass |  | 2022-03-29 |  | 2022-03-29 | 2022-03-29 | pass | 2022-03-31 | CIL-Civil Lot | CH20470 - CH20490 | EART - Earthworks | EART - Cement Treated Crushed Rock | 1145-C200-FUL-QAC-0011 | EB - Eastbound | Varun Panickar |  | Varun Panickar | 2022-05-25 | pass | pass
Area 2 | ITP-011-A2-LOT-021 | ITP-011-A2-LOT-021 - Mickleham to Debonair CH10830-CH11300 | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-012-A2-LOT-001 | ITP-012-A2-LOT-001 - Zone 7 West (CH 10050 - 10098) | not started | not started |  | 2022-03-18 |  | 2022-03-18 | 2022-03-18 |  |  | CIL-Civil Lot | CH 10000 - CH 10180 | STOR Ã Stormwater | KERC - Kerb & Channel | 1145-C200-FUL-QAC-0012 | EB - Eastbound | Omar EL-Khub |  |  |  | not started | not started
Area 2 | ITP-012-A2-LOT-002 | ITP-012-A2-LOT-002 - Zone 7 East (CH 10600 - 10850) | not started | not started |  | 2022-03-19 |  | 2022-03-19 | 2022-03-19 |  |  |  | 10600-10850 | [8 empty] | not started | not started
Area 2 | ITP-012-A2-LOT-003 | ITP-012-A2-LOT-003 - Mickleham South (NB+SB) CH30105-CH30234 | wip | wip |  | 2022-03-01 |  | 2022-03-01 | 2022-03-01 |  |  | DRL- Drainage Lot | CH30105-Ch30234 | STOR Ã Stormwater | KERC - Kerb & Channel | 1145-C200-FUL-QAC-0012 | NB - Northbound | Varun Panickar |  | Varun Panickar | 2022-05-30 | wip | wip
Area 2 | ITP-012-A2-LOT-004 | ITP-012-A2-LOT-004 - Mickleham North (Media) CH30510-CH30700 | wip | wip |  | 2022-03-16 |  | 2022-03-16 | 2022-03-16 |  |  | DRL- Drainage Lot | CH30510-Ch30700 | STOR Ã Stormwater | KERC - Kerb & Channel | 1145-C200-FUL-QAC-0012 | NB - Northbound | Varun Panickar |  |  |  | wip | wip
Area 2 | ITP-012-A2-LOT-005 | ITP-012-A2-LOT-005 - Mickleham North (SB + Verge) CH30510-CH30785 | pass | pass |  | 2022-03-17 |  | 2022-03-17 | 2022-03-22 | 2022-04-13 |  | CIL-Civil Lot | CH30520-Ch30785 | STOR Ã Stormwater | KERC - Kerb & Channel | 1145-C200-FUL-QAC-0012 | SB - Southbound | Varun Panickar |  | Varun Panickar | 2022-05-30 | pass | pass
Area 2 | ITP-012-A2-LOT-006 | ITP-012-A2-LOT-006 - Mickleham North (NB) CH30510-CH30665 | wip | wip |  | 2022-03-17 |  | 2022-03-17 | 2022-03-17 |  |  | DRL- Drainage Lot | CH30520-Ch30665 | STOR Ã Stormwater | KERC - Kerb & Channel | 1145-C200-FUL-QAC-0012 | NB - Northbound | Varun Panickar |  | Varun Panickar | 2022-05-30 | wip | wip
Area 2 | ITP-012-A2-LOT-007 | ITP-012-A2-LOT-007 - Mickleham South (NB) CH30234-CH30365 | pass | pass |  | 2022-03-17 |  | 2022-03-17 | 2022-03-17 | 2022-03-30 |  | DRL- Drainage Lot | CH30234-Ch30365 | STOR Ã Stormwater | KERC - Kerb & Channel | 1145-C200-FUL-QAC-0012 | NB - Northbound | Varun Panickar |  | Varun Panickar | 2022-05-30 | pass | pass
Area 2 | ITP-012-A2-LOT-008 | ITP-012-A2-LOT-008 - Mickleham South (Median) CH30285-CH30365 | wip | wip |  | 2022-03-17 |  | 2022-03-17 | 2022-03-17 | 2022-03-20 |  | DRL- Drainage Lot | CH30285-Ch30365 | STOR Ã Stormwater | KERC - Kerb & Channel | 1145-C200-FUL-QAC-0012 | SB - Southbound | Varun Panickar |  | Varun Panickar | 2022-05-30 | wip | wip
Area 2 | ITP-012-A2-LOT-009 | ITP-012-A2-LOT-009 - Mickleham North (SB + Verge) CH40190-CH40300 | pass | pass |  | 2022-03-19 |  | 2022-03-19 | 2022-03-19 | 2022-03-22 |  | DRL- Drainage Lot | CH40210-CH40300 | STOR Ã Stormwater | KERC - Kerb & Channel | 1145-C200-FUL-QAC-0012 | SB - Southbound | Varun Panickar |  | Varun Panickar | 2022-05-30 | pass | pass
Area 2 | ITP-012-A2-LOT-010 | ITP-012-A2-LOT-010 - Mickleham North (NB) CH30455-CH30510 | wip | wip |  | 2022-03-22 |  | 2022-03-22 | 2022-03-22 |  |  | DRL- Drainage Lot | CH30455-CH30510 | STOR Ã Stormwater | KERC - Kerb & Channel | 1145-C200-FUL-QAC-0012 | NB - Northbound | Varun Panickar |  | Varun Panickar | 2022-05-30 | wip | wip
Area 2 | ITP-012-A2-LOT-011 | ITP-012-A2-LOT-011 - Mickleham North (SB) CH30455-CH30510 | wip | wip |  | 2022-03-24 |  | 2022-03-24 | 2022-03-24 | 2022-03-24 |  | DRL- Drainage Lot | CH30455-CH30520(SB) | STOR Ã Stormwater | KERC - Kerb & Channel | 1145-C200-FUL-QAC-0012 | NB - Northbound | Varun Panickar |  | Varun Panickar | 2022-05-30 | wip | wip
Area 2 | ITP-012-A2-LOT-012 | ITP-012-A2-LOT-012 - Mickleham South(Bullnose) CH30375-CH30385 | wip | wip |  | 2022-03-25 |  | 2022-03-25 | 2022-03-25 |  |  | DRL- Drainage Lot | CH30375-CH30385 | STOR Ã Stormwater | KERC - Kerb & Channel | 1145-C200-FUL-QAC-0012 | NB - Northbound | Varun Panickar |  | Varun Panickar | 2022-05-30 | wip | wip
Area 2 | ITP-012-A2-LOT-013 | ITP-012-A2-LOT-013 - Mickleham Intersection (NB+SB+EB) Traffic Islands - CH10490-CH10550 | pass | pass |  | 2022-03-30 |  | 2022-03-30 | 2022-03-30 | 2022-03-31 |  | CIL-Civil Lot | CH10490-CH10550 | STOR Ã Stormwater | KERC - Kerb & Channel | 1145-C200-FUL-QAC-0012 | ME - Median | Varun Panickar |  | Varun Panickar | 2022-05-30 | pass | pass
Area 2 | ITP-012-A2-LOT-014 | ITP-012-A2-LOT-014 - Mickleham Intersection (SE Verge) - CH10540-CH10600 | not started | not started |  | 2022-03-31 |  | 2022-03-31 | 2022-03-31 | 2022-03-31 |  | DRL- Drainage Lot | CH10540-CH10600 | STOR Ã Stormwater | KERC - Kerb & Channel | 1145-C200-FUL-QAC-0012 | EB - Eastbound | Varun Panickar |  | Varun Panickar | 2022-06-01 | not started | not started
Area 2 | ITP-012-A2-LOT-015 | ITP-012-A2-LOT-015 - Mickleham North (NB + SB) - CH40330-CH40470 | pass | pass |  | 2022-03-31 |  | 2022-03-31 | 2022-03-31 | 2022-03-31 |  | DRL- Drainage Lot | CH40470-CH40330 | STOR Ã Stormwater | KERC - Kerb & Channel | 1145-C200-FUL-QAC-0012 | EB - Eastbound | Varun Panickar |  | Varun Panickar | 2022-05-30 | pass | pass
Area 2 | ITP-017-A2-LOT-001 | ITP-017-A2-LOT-001 - Stormwater Drainage - Pit 582 to Pit 583 - Zone 7 East Mickleham to Debonair (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-002 | ITP-017-A2-LOT-002 - Stormwater Drainage - Pit 578 to Pit 579 - Zone 7 East Mickleham to Debonair (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-003 | ITP-017-A2-LOT-003 - Stormwater Drainage - Pit 579 to Pit 580 - Zone 7 East Mickleham to Debonair (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-004 | ITP-017-A2-LOT-004 - Stormwater Drainage - Pit 580 to Pit 581A - Zone 7 East Mickleham to Debonair (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-005 | ITP-017-A2-LOT-005 - Stormwater Drainage - Pit 581A to Pit 581 - Zone 7 East Mickleham to Debonair (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-006 | ITP-017-A2-LOT-006 - Stormwater Drainage - Pit 581 to Pit 582 - Zone 7 East Mickleham to Debonair (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-007 | ITP-017-A2-LOT-007 - Stormwater Drainage - Pit 577 to Pit 578 - Zone 7 East Mickleham to Debonair (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-008 | ITP-017-A2-LOT-008 - Stormwater Drainage - Pit 583 to Pit 584 - Zone 7 East Mickleham to Debonair (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-009 | ITP-017-A2-LOT-009 - Stormwater Drainage - Pit 584 to Pit 585 - Zone 7 East Mickleham to Debonair (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-010 | ITP-017-A2-LOT-010 - Stormwater Drainage - Pit 573 to Pit 573a - Zone 7 East Mickleham to Debonair (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-011 | ITP-017-A2-LOT-011 - Stormwater Drainage - Pit 575 to Pit 576 - Zone 7 East Mickleham to Debonair (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-012 | ITP-017-A2-LOT-012 - Stormwater Drainage - Pit 576 to Pit 577 - Zone 7 East Mickleham to Debonair (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-013 | ITP-017-A2-LOT-013 - Stormwater Drainage - Pit 999 to Pit 1000 - Zone 7 West Stage 1 (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-014 | ITP-017-A2-LOT-014 - Mickleham North. ( Pit 1042-1041) | not started | not started |  | 2022-02-25 |  | 2022-02-25 | 2022-02-26 |  |  | DRL- Drainage Lot |  | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | SB - Southbound | Varun Panickar |  |  |  | not started | not started
Area 2 | ITP-017-A2-LOT-015 | ITP-017-A2-LOT-015 - Mickleham North (Pit 1041-1040) | pass | pass |  | 2022-02-25 |  | 2022-02-25 | 2022-02-26 | 2022-04-29 |  | DRL- Drainage Lot |  | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | SB - Southbound | Varun Panickar |  | Varun Panickar | 2022-06-29 | pass | pass
Area 2 | ITP-017-A2-LOT-016 | ITP-017-A2-LOT-016 - Mickleham North (Pit 1040-1039) | not started | not started |  | 2022-02-25 |  | 2022-02-25 | 2022-02-26 |  |  | DRL- Drainage Lot |  | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | SB - Southbound | Varun Panickar |  |  |  | not started | not started
Area 2 | ITP-017-A2-LOT-017 | ITP-017-A2-LOT-017 - Mickleham North ( Pit 1039-1038) | not started | not started |  | 2022-02-26 |  | 2022-02-26 | 2022-02-26 |  |  | DRL- Drainage Lot | Pit 1038 - 1039 | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | SB - Southbound | Varun Panickar |  |  |  | not started | not started
Area 2 | ITP-017-A2-LOT-018 | ITP-017-A2-LOT-018 - Mickleham North (Pit 1038-1037) | pass | pass |  | 2022-02-26 |  | 2022-02-26 | 2022-02-26 | 2022-04-30 |  | DRL- Drainage Lot | Pit 1038 -1037 | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | SB - Southbound | Varun Panickar |  | Varun Panickar | 2022-06-29 | pass | pass
Area 2 | ITP-017-A2-LOT-019 | ITP-017-A2-LOT-019 - Mickleham North (Pit 1037-1036) | pass | pass |  | 2022-02-27 |  | 2022-02-27 | 2022-02-26 | 2022-04-30 |  | DRL- Drainage Lot | Pit 1037 - 1036 | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | SB - Southbound | Varun Panickar |  | Varun Panickar | 2022-06-29 | pass | pass
Area 2 | ITP-017-A2-LOT-020 | ITP-017-A2-LOT-020 - Mickleham North (Pit 1036-1035) | not started | not started |  | 2022-02-27 |  | 2022-02-27 | 2022-02-26 |  |  | DRL- Drainage Lot |  | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | SB - Southbound | Varun Panickar |  |  |  | not started | not started
Area 2 | ITP-017-A2-LOT-021 | ITP-017-A2-LOT-021 - Mickleham North (Pit 1035-1034) | not started | not started |  | 2022-02-27 |  | 2022-02-27 | 2022-02-26 |  |  | DRL- Drainage Lot |  | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | NB - Northbound | Varun Panickar |  |  |  | not started | not started
Area 2 | ITP-017-A2-LOT-022 | ITP-017-A2-LOT-022 - Mickleham North (Pit 1034-1033) | not started | not started |  | 2022-02-28 |  | 2022-02-28 | 2022-02-26 |  |  | DRL- Drainage Lot |  | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | SB - Southbound | Varun Panickar |  |  |  | not started | not started
Area 2 | ITP-017-A2-LOT-023 | ITP-017-A2-LOT-023 - Mickleham Intersection ( Pit 1048-1047) | not started | not started |  | 2022-03-03 |  | 2022-03-03 | 2022-03-03 |  |  | DRL- Drainage Lot |  | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | SB - Southbound | Varun Packinar |  |  |  | not started | not started
Area 2 | ITP-017-A2-LOT-024 | ITP-017-A2-LOT-024 - Mickleham Intersection ( Pit 1047-1046) | not started | not started |  | 2022-03-03 |  | 2022-03-03 | 2022-03-03 |  |  | DRL- Drainage Lot |  | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | SB - Southbound | Varun Packinar |  |  |  | not started | not started
Area 2 | ITP-017-A2-LOT-025 | ITP-017-A2-LOT-025 - Mickleham Intersection ( Pit 1046-1045) | wip | wip |  | 2022-03-04 |  | 2022-03-04 | 2022-03-04 | 2022-04-30 |  | DRL- Drainage Lot | Pit 1046 - 1045 | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | SB - Southbound | Varun Packinar |  | Varun Panickar | 2022-06-29 | wip | wip
Area 2 | ITP-017-A2-LOT-026 | ITP-017-A2-LOT-026 - Mickleham Intersection ( Pit 1045-1044 ) | pass | pass |  | 2022-03-04 |  | 2022-03-04 | 2022-03-04 | 2022-04-30 |  | DRL- Drainage Lot | Pit 1044 - 1045 | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | SB - Southbound | Varun Packinar |  | Varun Panickar | 2022-06-29 | pass | pass
Area 2 | ITP-017-A2-LOT-027 | ITP-017-A2-LOT-027 - Mickleham Intersection ( Pit 1044-1043) | pass | pass |  | 2022-03-04 |  | 2022-03-04 | 2022-03-04 | 2022-04-30 |  | DRL- Drainage Lot | Pit 1044 - 1043 | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | SB - Southbound | Varun Packinar |  | Varun PAnickar | 2022-06-29 | pass | pass
Area 2 | ITP-017-A2-LOT-028 | ITP-017-A2-LOT-028 - Mickleham Intersection ( M1-M2) | not started | not started |  | 2022-03-07 |  | 2022-03-07 | 2022-03-07 |  |  | DRL- Drainage Lot |  | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | SB - Southbound | Varun Packinar |  |  |  | not started | not started
Area 2 | ITP-017-A2-LOT-029 | ITP-017-A2-LOT-029 - Mickleham Intersection ( 1049-1048) | pass | pass |  | 2022-03-07 |  | 2022-03-07 | 2022-03-09 | 2022-04-30 |  | DRL- Drainage Lot |  | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | SB - Southbound | Varun Panickar |  | Varun Panickar | 2022-06-29 | pass | pass
Area 2 | ITP-017-A2-LOT-030 | ITP-017-A2-LOT-030 - Mickleham Intersection (1049-1050) | pass | pass |  | 2022-03-07 |  | 2022-03-07 | 2022-03-10 | 2022-04-29 |  | DRL- Drainage Lot | Pit 1049 -1050 | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | SB - Southbound | Varun Panickar |  | Varun Panickar | 2022-06-29 | pass | pass
Area 2 | ITP-017-A2-LOT-031 | ITP-017-A2-LOT-031 - Mickleham Intersection (1191-1192) | not started | not started |  | 2022-03-09 |  | 2022-03-09 | 2022-03-09 |  |  | DRL- Drainage Lot |  | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | ME - Median | Varun Panickar |  |  |  | not started | not started
Area 2 | ITP-017-A2-LOT-032 | ITP-017-A2-LOT-032 - Mickleham Intersection (1192-1193) | not started | not started |  | 2022-03-09 |  | 2022-03-09 | 2022-03-09 | 2022-04-01 |  | DRL- Drainage Lot | Pit 1192 -1193 | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | ME - Median | Varun Panickar |  | Varun Panickar | 2022-06-29 | not started | not started
Area 2 | ITP-017-A2-LOT-033 | ITP-017-A2-LOT-033 - Mickleham Intersection (997-998) | not started | not started |  | 2022-03-10 |  | 2022-03-10 | [13 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-034 | ITP-017-A2-LOT-034 - Mickleham Intersection (996-997) | not started | not started |  | 2022-03-15 |  | 2022-03-15 | [13 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-037 | ITP-017-A2-LOT-037 - Mickleham Intersection SE (1193-998) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-038 | ITP-017-A2-LOT-038 - Mickleham Intersection NE (1050-994) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-039 | ITP-017-A2-LOT-039 - Mickleham Intersection (993-1088) | not started | not started |  | 2022-03-15 |  | 2022-03-15 | 2022-03-16 |  |  | DRL- Drainage Lot |  | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | NB - Northbound | Varun Panickar |  |  |  | not started | not started
Area 2 | ITP-017-A2-LOT-040 | ITP-017-A2-LOT-040 - Mickleham Intersection (Pit 1013 - pit 1014) | not started | not started |  | 2022-03-16 |  | 2022-03-16 | [13 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-041 | ITP-017-A2-LOT-041 - Mickleham Intersection NW (1014-1015) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-042 | ITP-017-A2-LOT-042 - Mickleham Intersection SE (1178-1178a) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-043 | ITP-017-A2-LOT-043 - Mickleham Intersection (1178-1177) | not started | not started |  | 2022-03-22 |  | 2022-03-22 | 2022-03-25 |  |  | DRL- Drainage Lot |  | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | NB - Northbound | Varun Panickar |  |  |  | not started | not started
Area 2 | ITP-017-A2-LOT-044 | ITP-017-A2-LOT-044 - Mickleham Intersection (1177-1066) | not started | not started |  | 2022-03-22 |  | 2022-03-22 | 2022-03-25 |  |  | DRL- Drainage Lot |  | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | ME - Median | Varun Panickar |  |  |  | not started | not started
Area 2 | ITP-017-A2-LOT-045 | ITP-017-A2-LOT-045 - Mickleham Intersection (1177-1176) | not started | not started |  | 2022-03-22 |  | 2022-03-22 | 2022-03-25 |  |  | DRL- Drainage Lot |  | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | ME - Median | Varun Panickar |  |  |  | not started | not started
Area 2 | ITP-017-A2-LOT-046 | ITP-017-A2-LOT-046 - Mickleham Intersection (1176-1015) | not started | not started |  | 2022-03-22 |  | 2022-03-22 | 2022-03-25 |  |  | DRL- Drainage Lot |  | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | ME - Median | Varun Panickar |  |  |  | not started | not started
Area 2 | ITP-017-A2-LOT-047 | ITP-017-A2-LOT-047 - Mickleham North NB (1069-1116) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-048 | ITP-017-A2-LOT-048 - Mickleham North (1096-1097) | not started | not started |  | 2022-03-22 |  | 2022-03-22 | 2022-03-25 |  |  | DRL- Drainage Lot |  | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | NB - Northbound | Varun Panickar |  |  |  | not started | not started
Area 2 | ITP-017-A2-LOT-049 | ITP-017-A2-LOT-049 - Mickleham North (1079-1080) | not started | not started |  | 2022-03-22 |  | 2022-03-22 | 2022-03-25 |  |  | DRL- Drainage Lot |  | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | NB - Northbound | Varun Panickar |  |  |  | not started | not started
Area 2 | ITP-017-A2-LOT-050 | ITP-017-A2-LOT-050 - Mickleham North (1092-1093) | not started | not started |  | 2022-03-22 |  | 2022-03-22 | 2022-03-25 |  |  | DRL- Drainage Lot |  | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | NB - Northbound | Varun Panickar |  |  |  | not started | not started
Area 2 | ITP-017-A2-LOT-051 | ITP-017-A2-LOT-051 - Mickleham North NB (1161-1162) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-052 | ITP-017-A2-LOT-052 - Mickleham Intersection (Pit 1014 - pit 1159) | not started | not started |  | 2022-03-29 |  | 2022-03-29 | 2022-03-02 |  |  | DRL- Drainage Lot |  | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | NB - Northbound | Varun Panickar |  |  |  | not started | not started
Area 2 | ITP-017-A2-LOT-054 | ITP-017-A2-LOT-054 - Stormwater Drainage - Pit 573 to Pit 573a - Zone 7 East Mickleham to Debonair (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-055 | ITP-017-A2-LOT-055 - Stormwater Drainage - Pit 573a to Pit 573b - Zone 7 East Mickleham to Debonair (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-056 | ITP-017-A2-LOT-056 - Stormwater Drainage - Pit 573b to Pit 573c - Zone 7 East Mickleham to Debonair (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-057 | ITP-017-A2-LOT-057 - Stormwater Drainage - Pit 573b to Pit 572a - Zone 7 East Mickleham to Debonair (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-058 | ITP-017-A2-LOT-058 - Stormwater Drainage - Pit 572a to Pit 572 - Zone 7 East Mickleham to Debonair (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-059 | ITP-017-A2-LOT-059 - Stormwater Drainage - Pit 572 to Pit 571 - Zone 7 East Mickleham to Debonair (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-060 | ITP-017-A2-LOT-060 - Stormwater Drainage - Pit 571 to Pit 569 - Zone 7 East Mickleham to Debonair (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-061 | ITP-017-A2-LOT-061 - Stormwater Drainage - Pit 569 to Pit 568 - Zone 7 East Mickleham to Debonair (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-062 | ITP-017-A2-LOT-062 - Stormwater Drainage - Pit 568 to Pit 567 - Zone 7 East Mickleham to Debonair (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-063 | ITP-017-A2-LOT-063 - Stormwater Drainage - Pit 567 to Pit 587a - Zone 7 East Mickleham to Debonair (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-064 | ITP-017-A2-LOT-064 - Stormwater Drainage - Pit 567 to Pit 567a - Zone 7 East Mickleham to Debonair (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-065 | ITP-017-A2-LOT-065 - Stormwater Drainage - Pit 567a to Pit 567b - Zone 7 East Mickleham to Debonair (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-066 | ITP-017-A2-LOT-066 - Stormwater Drainage - Pit 567b to Pit 567c - Zone 7 East Mickleham to Debonair (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-067 | ITP-017-A2-LOT-067 - Stormwater Drainage - Pit 567b to Pit 566a - Zone 7 East Mickleham to Debonair (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-068 | ITP-017-A2-LOT-068 - Stormwater Drainage - Pit 566a to Pit 565 - Zone 7 East Mickleham to Debonair (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-069 | ITP-017-A2-LOT-069 - Stormwater Drainage - Pit 565 to Pit 564 - Zone 7 East Mickleham to Debonair (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-070 | ITP-017-A2-LOT-070 - Stormwater Drainage - Pit 564 to Pit 563 - Zone 7 East Mickleham to Debonair (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-071 | ITP-017-A2-LOT-071 - Stormwater Drainage - Pit 563 to Pit 562 - Zone 7 East Mickleham to Debonair (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-072 | ITP-017-A2-LOT-072 - Stormwater Drainage - Pit 562 to Pit 561 - Zone 7 East Mickleham to Debonair (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-073 | ITP-017-A2-LOT-073 - Mickleham Intersection (Pit 994- pit 995) | not started | not started |  | 2022-02-17 |  | 2022-03-29 | 2022-02-17 |  |  | DRL- Drainage Lot | 20530-20540 | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | 1145-C200-FUL-QAC-0017 | EB - Eastbound | Ahmad El Wazer |  |  |  | not started | not started
Area 2 | ITP-017-A2-LOT-074 | ITP-017-A2-LOT-074 - Stormwater Drainage - Pit 557A to Pit 556 - Zone 7 East Debonair to Vantage (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-075 | ITP-017-A2-LOT-075 - Stormwater Drainage - Pit 556 to Pit 556A - Zone 7 East Debonair to Vantage (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-076 | ITP-017-A2-LOT-076 - Stormwater Drainage - Pit 556A to Pit 555 - Zone 7 East Debonair to Vantage (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-077 | ITP-017-A2-LOT-077 - Stormwater Drainage - Pit 555 to Pit 554 - Zone 7 East Debonair to Vantage (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-078 | ITP-017-A2-LOT-078 - Stormwater Drainage - Pit 554 to Pit 553 - Zone 7 East Debonair to Vantage (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-079 | ITP-017-A2-LOT-079 - Stormwater Drainage - Pit 553 to Pit 552 - Zone 7 East Debonair to Vantage (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-080 | ITP-017-A2-LOT-080 - Stormwater Drainage - Pit 552 to Pit 551 - Zone 7 East Debonair to Vantage (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-081 | ITP-017-A2-LOT-081 - Stormwater Drainage - Pit 551 to Pit 550 - Zone 7 East Debonair to Vantage (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-082 | ITP-017-A2-LOT-082 - Stormwater Drainage - Pit 550 to Pit 549 - Zone 7 East Debonair to Vantage (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-083 | ITP-017-A2-LOT-083 - Stormwater Drainage - Pit 549 to Pit 548 - Zone 7 East Debonair to Vantage (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-084 | ITP-017-A2-LOT-084 - Stormwater Drainage - Pit 548 to Pit 547 - Zone 7 East Debonair to Vantage (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-085 | ITP-017-A2-LOT-085 - Stormwater Drainage - Pit 547 to Pit 546 - Zone 7 East Debonair to Vantage (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-086 | ITP-017-A2-LOT-086 - Stormwater Drainage - Pit 546 to Pit 545 - Zone 7 East Debonair to Vantage (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-087 | ITP-017-A2-LOT-087 - Stormwater Drainage - Pit 545 to Pit 545A - Zone 7 East Debonair to Vantage (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-088 | ITP-017-A2-LOT-088 - Stormwater Drainage - Pit 545A to Pit 544 - Zone 7 East Debonair to Vantage (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-089 | ITP-017-A2-LOT-089 - Mickleham North East ( Pit 992-993) | not started | not started |  | 2022-05-05 |  | 2022-05-05 | [5 empty] | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | [6 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-090 | ITP-017-A2-LOT-090 - Mickleham North East ( Pit 993-1088) | not started | not started |  | 2022-05-05 |  | 2022-05-05 | 2022-05-05 | [12 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-091 | ITP-017-A2-LOT-091 - Mickleham North East ( Pit 1088-1087) | not started | not started |  | 2022-05-05 |  | 2022-05-05 | 2022-05-05 | [12 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-092 | ITP-017-A2-LOT-092 - Mickleham North East ( Pit 1087-1086) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-093 | ITP-017-A2-LOT-093 - Stormwater Drainage - Pit 1210 to Pit 1165 - Zone 7 West Stage 1 (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-094 | ITP-017-A2-LOT-094 - Stormwater Drainage - Pit 1165 to Pit 1166 - Zone 7 West Stage 1 (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-095 | ITP-017-A2-LOT-095 - Stormwater Drainage - Pit 1166 to Pit 1167 - Zone 7 West Stage 1 (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-096 | ITP-017-A2-LOT-096 - Stormwater Drainage - Pit 1167 to Pit 1168 - Zone 7 West Stage 1 (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-097 | ITP-017-A2-LOT-097 - Stormwater Drainage - Pit 1168 to Pit 1169 - Zone 7 West Stage 1 (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-098 | ITP-017-A2-LOT-098 - Stormwater Drainage - Pit 1169 to Pit 1170 - Zone 7 West Stage 1 (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-099 | ITP-017-A2-LOT-099 - Stormwater Drainage - Pit 1170 to Pit 1171 - Zone 7 West Stage 1 (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-100 | ITP-017-A2-LOT-100 - Stormwater Drainage - Pit 1171 to Pit 1172 - Zone 7 West Stage 1 (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-101 | ITP-017-A2-LOT-101 - Stormwater Drainage - Pit 1172 to Pit 1173 - Zone 7 West Stage 1 (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-102 | ITP-017-A2-LOT-102 - Stormwater Drainage - Pit 1173 to Pit 1174 - Zone 7 West Stage 1 (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-103 | ITP-017-A2-LOT-103 - Stormwater Drainage - Pit 1174 to Pit 1175 - Zone 7 West Stage 1 (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-104 | ITP-017-A2-LOT-104 - Stormwater Drainage - Pit 1175 to Pit 1176 - Zone 7 West Stage 1 (Westbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-105 | ITP-017-A2-LOT-105 - Mickleham South East ( Pit 998-688ac) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-106 | ITP-017-A2-LOT-106 - Mickleham South East ( Pit 688ac-688ad) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-107 | ITP-017-A2-LOT-107 - Mickleham Intersection (NE) ( Pit 995-996) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-108 | ITP-017-A2-LOT-108 - Mickleham North ( Pit 1042-1043) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-109 | ITP-017-A2-LOT-109 - Mickleham South ( Pit 1180-1181) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-110 | ITP-017-A2-LOT-110 - Mickleham South ( Pit 1184-1185) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-111 | ITP-017-A2-LOT-111 - Mickleham South ( Pit 1186-1187) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-112 | ITP-017-A2-LOT-112 - Mickleham South ( Pit 1188-1189) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-113 | ITP-017-A2-LOT-113 - Mickleham Intersection (NE) ( Pit 994-1190) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-114 | ITP-017-A2-LOT-114 - Mickleham North ( Pit 1117-1118) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-115 | ITP-017-A2-LOT-115 - Zone 7 East - Mickleham to Debonair WB - Pit 561 to 560 | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-116 | ITP-017-A2-LOT-116 - Zone 7 East - Mickleham to Debonair WB - Pit 560 to 559 | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-117 | ITP-017-A2-LOT-117 - Zone 7 East - Mickleham to Debonair WB - Pit 559 to 558 | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-118 | ITP-017-A2-LOT-118 - Debonair Intersection WB - Pit 558 to 558b | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-119 | ITP-017-A2-LOT-119 - Debonair Intersection WB - Pit 558b to 557a | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-120 | ITP-017-A2-LOT-120 - Zone 7 East - Mickleham to Debonair WB - Pit 558a to 558 | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-121 | ITP-017-A2-LOT-121 - Debonair Intersection WB - Pit 450 to 450a | not started | not started |  | 2022-06-23 |  | 2022-06-23 | 2022-06-23 |  |  | DRL- Drainage Lot | 11311-11321 | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ |  | WB - Westbound | Jonathon Rock |  |  |  | not started | not started
Area 2 | ITP-017-A2-LOT-122 | ITP-017-A2-LOT-122 - Stormwater Drainage - Pit 1176 to Pit 1177 - Zone 7 West Stage 1 (SW Intersection) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-123 | ITP-017-A2-LOT-123 - Stormwater Drainage - Pit 1177 to Pit 1178 - Zone 7 West Stage 1 (SW Intersection) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-124 | ITP-017-A2-LOT-124 - Stormwater Drainage - Pit 1177 to Pit 1066 - Zone 7 West Stage 1 (SW Intersection) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-125 | ITP-017-A2-LOT-125 - Stormwater Drainage - Pit 1176 to Pit 1015 - Zone 7 West Stage 1 (SW Intersection) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-126 | ITP-017-A2-LOT-126 - Stormwater Drainage - Pit 1049 to Pit 688ab - Zone 7 Mickleham Rd North (Southbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-127 | ITP-017-A2-LOT-127 - Stormwater Drainage - Pit 1047 to Pit 1047a - Zone 7 Mickleham Rd North (Southbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-128 | ITP-017-A2-LOT-128 - Stormwater Drainage - Pit 1045 to Pit 1163 - Zone 7 Mickleham Rd North (Southbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-129 | ITP-017-A2-LOT-129 - Stormwater Drainage - Pit 1043 to Pit 1160 - Zone 7 Mickleham Rd North (Southbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-130 | ITP-017-A2-LOT-130 - Stormwater Drainage - Pit 1041 to Pit 688aa - Zone 7 Mickleham Rd North (Southbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-131 | ITP-017-A2-LOT-131 - Stormwater Drainage - Pit 1037 to Pit 688a - Zone 7 Mickleham Rd North (Southbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-132 | ITP-017-A2-LOT-132 - Stormwater Drainage - Pit 1035 to Pit 1059 - Zone 7 Mickleham Rd North (Southbound) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-133 | ITP-017-A2-LOT-133 - Stormwater Drainage - Pit 847 to Pit 846 - Zone 7 East Debonair to Vantage (Westbound) (Superseded by 136) | not started | not started |  | 2022-07-01 |  | 2022-07-01 | 2022-07-01 |  |  | DRL- Drainage Lot | 11420-11450 | STOR - Stormwater | STOR - DRAP Drainage ÃŠÃŠ | [6 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-135 | ITP-017-A2-LOT-135 - Stormwater Drainage - Pit 558 to Pit 558C - Zone 7 East Mickleham to Debonair | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-136 | ITP-017-A2-LOT-136 - Stormwater Drainage - Pit 847 to Pit 846 - Zone 7 East Debonair to vantage | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-137 | ITP-017-A2-LOT-137 - Stormwater Drainage - Pit 846 to Pit 845A - Zone 7 East Debonair to vantage | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-138 | ITP-017-A2-LOT-138 - Stormwater Drainage - Pit 845A to Pit 845 - Zone 7 East Debonair to vantage | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-139 | ITP-017-A2-LOT-139 - Stormwater Drainage - Pit 845 to Pit 844A - Zone 7 East Debonair to vantage | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-017-A2-LOT-140 | ITP-017-A2-LOT-140 - Stormwater Drainage - Pit 844A to Pit 844 - Zone 7 East Debonair to vantage | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-026-A2-LOT-001 | ITP-026-A2-LOT-001- Mickleham South (NB) CH30000 - CH30234 |  |  |  | pass | 2022-03-25 | pass | pass |  |  | pass | pass | pass | pass | pass | pass | pass | pass
Area 2 | ITP-026-A2-LOT-002 | ITP-026-A2-LOT-002 - Mickleham South (Median) CH30120 - CH30360 |  |  |  | pass | 2022-03-26 | pass | pass |  |  | pass | pass | pass | pass | pass | pass | pass | pass
Area 2 | ITP-026-A2-LOT-003 | ITP-026-A2-LOT-003 - Mickleham South (SB) CH40050 - CH40280 |  |  |  | pass | 2022-03-26 | pass | pass |  |  | pass | pass | pass | pass | pass | pass | pass | pass
Area 2 | ITP-026-A2-LOT-004 | ITP-026-A2-LOT-004 - Mickleham South (NB) CH30234 - CH30365 |  |  |  | pass | 2022-03-27 | pass | pass |  |  | pass | pass | pass | pass | pass | pass | pass | pass
Area 2 | ITP-026-A2-LOT-005 | ITP-026-A2-LOT-005 - Mickleham North (SB) CH40640 - CH40720 |  |  |  | pass | 2022-03-27 | pass | pass |  |  | pass | pass | pass | pass | pass | pass | pass | pass
Area 2 | ITP-026-A2-LOT-006 | ITP-026-A2-LOT-006 - Mickleham North (NB) CH30615 - CH30700 |  |  |  | pass | 2022-03-27 | pass | pass |  |  | pass | pass | pass | pass | pass | pass | pass | pass
Area 2 | ITP-026-A2-LOT-007 | ITP-026-A2-LOT-007 - Mickleham North (Median) CH30433 - CH30680 |  |  |  | pass | 2022-03-28 | pass | pass |  |  | pass | pass | pass | pass | pass | pass | pass | pass
Area 2 | ITP-026-A2-LOT-008 | ITP-026-A2-LOT-008 - Mickleham North (NB) CH30450 - CH30605 |  |  |  | pass | 2022-03-28 | pass | pass |  |  | pass | pass | pass | pass | pass | pass | pass | pass
Area 2 | ITP-026-A2-LOT-009 | ITP-026-A2-LOT-009 - Mickleham North (SB) CH40490 - CH40560 |  |  |  | pass | 2022-03-29 | pass | pass |  |  | pass | pass | pass | pass | pass | pass | pass | pass
Area 2 | ITP-026-A2-LOT-010 | ITP-026-A2-LOT-010 - Zone 7 West |  |  |  | not started |  | not started | not started |  |  | not started | not started | not started | not started | not started | not started | not started | not started
Area 2 | ITP-026-A2-LOT-011 | ITP-026-A2-LOT-011 - Zone 7 East - CH10600-10820 |  |  |  | not started |  | not started | not started |  |  | not started | not started | not started | not started | not started | not started | not started | not started
Area 2 | ITP-054-A2-LOT-011 | ITP-054-A2-LOT-011 - Maintenance Strip Install - Mickleham Road North, S/Bound CH40640-40685 | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-054-A2-LOT-012 | ITP-054-A2-LOT-012 - Maintenance Strip Install - Mickleham Road North, S/Bound CH40685-40715 | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-054-A2-LOT-013 | ITP-054-A2-LOT-013 - SUP - Zone 7 East, SE Corner of Mickleham Intersection (CH10545-10620) | not started | not started |  | 2022-07-01 |  | 2022-07-01 | 2022-07-02 |  |  | CIL - Civil | 10540-10620 | PAVI - Paving | SHUP - Shared User Path |  | WB - Westbound | Brighton |  |  |  | not started | not started
Area 2 | ITP-054-A2-LOT-014 | ITP-054-A2-LOT-014 - SUP - Zone 7 East, SE Corner of Mickleham Intersection (CH10543-10551) | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-054-A2-LOT-015 | ITP-054-A2-LOT-015 - Maintenance Strip Install - Mickleham Road North, N/Bound CH30480-30605 | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-074-A2-LOT-001 | ITP-074-A2-LOT-001 - Zone 7 West - CH 10090-CH 10240 | pass | pass |  | 2021-12-01 |  | 2021-12-01 | 2021-12-01 | pass |  | CIL-Civil Lot | CH 10090 to CH 10240 | FENC - Fencing | FENC Ã Road Furniture | 1145-C200-FUL-QAC-0074 | SB - Southbound | Varun Panickar |  | pass | pass | pass | pass
Area 2 | ITP-074-A2-LOT-002 | ITP-074-A2-LOT-002 - Zone 7 West - CH 10240 - CH 10295 | pass | pass |  | 2021-12-05 |  | 2021-12-05 | 2021-12-06 | pass |  | CIL-Civil Lot | CH 10240 to CH 10295 | FENC - Fencing | FENC Ã Road Furniture | 1145-C200-FUL-QAC-0074 | SB - Southbound | Varun Panickar |  | pass | pass | pass | pass
Area 2 | ITP-074-A2-LOT-003 | ITP-074-A2-LOT-003 - Zone 7 West - CH 10360 - CH 10490 | pass | pass |  | 2021-12-06 |  | 2021-12-06 | 2021-12-07 | pass |  | CIL-Civil Lot | CH 10360 to CH 10490 | FENC - Fencing | FENC Ã Road Furniture | 1145-C200-FUL-QAC-0074 | SB - Southbound | Varun Panickar |  | pass | pass | pass | pass
Area 2 | ITP-074-A2-LOT-004 | ITP-074-A2-LOT-004 - Zone 7 West - CH 10295 - CH 10360 | not started | not started | [5 empty] | not started | [9 empty] | not started | not started | not started | not started
Area 2 | ITP-075-A2-LOT-001 | ITP-075-A2-LOT-001 - Zone 7 West Craigieburn Rd - CH10040-10175 - Base Layer | not started | not started |  | 2022-03-22 |  | 2022-03-22 | 2022-03-22 | not started |  |  | 10040-10175 | PAVI - Paving | PAVI - Asphalt Placement | 1145-C200-FUL-QAC-0075 |  | Brighton Sarabia | Traffic Direction includes Eastbound & Westbound |  |  | not started | not started
Area 2 | ITP-075-A2-LOT-002 | ITP-075-A2-LOT-002 - Zone 7 West Craigieburn Rd - CH10040-10175 - Intermediate Layer | not started | not started | [5 empty] | not started | [11 empty] | not started | not started
Area 2 | ITP-075-A2-LOT-003 | ITP-075-A2-LOT-003 - Zone 7 West Pavement 6 Area - CH10000-10040 - Base Layer | not started | not started | [5 empty] | not started | [11 empty] | not started | not started
Area 2 | ITP-075-A2-LOT-004 | ITP-075-A2-LOT-004 - Zone 7 West Pavement 6 Area - CH10000-10040 - Intermediate Layer | not started | not started | [5 empty] | not started | [11 empty] | not started | not started
Area 2 | ITP-075-A2-LOT-005 | ITP-075-A2-LOT-005 - Zone 7 East Type 1 base course - CH10650 to CH10780 | not started | not started |  | 2022-03-24 |  | 2022-03-24 | 2022-03-24 | not started |  | CIL-Civil Lot | 10650 10780 | PAVI - Paving | PAVI - Asphalt Placement | 1145-C200-FUL-QAC-0075 | WB - Westbound | Jonathan Rock |  |  |  | not started | not started
Area 2 | ITP-075-A2-LOT-006 | ITP-075-A2-LOT-006 - Zone 7 East Type 1 base course - CH10780 to ch10850 | not started | not started |  | 2022-03-24 |  | 2022-03-24 | 2022-03-24 | not started |  |  | 10780 to 10850 | [8 empty] | not started | not started
Area 2 | ITP-075-A2-LOT-007 | ITP-075-A2-LOT-007 - Zone 7 East Type 1 intermediate - CH10650 to CH10780 | not started | not started |  | 2022-03-25 |  | 2022-03-25 | 2022-03-25 | not started |  |  | 10650 to 10780 | [8 empty] | not started | not started
Area 2 | ITP-075-A2-LOT-008 | ITP-075-A2-LOT-008 - Zone 7 East Type 1 intermediate layer - CH10780 to ch10850 | not started | not started |  | 2022-03-25 |  | 2022-03-25 | 2022-03-25 | not started |  |  | 10780 to 10850 | [8 empty] | not started | not started
Area 2 | ITP-075-A2-LOT-009 | ITP-075-A2-LOT-009 - Mickleham South (SB) Layer 1 SF - CH40050-CH40240 | pass | pass |  | 2022-03-08 |  | 2022-03-08 | 2022-03-08 | pass |  | CIL-Civil Lot | CH40050-CH40240 | PAVI - Paving | PAVI - Asphalt Placement | 1145-C200-FUL-QAC-0075 | SB - Southbound | Varun Panickar |  | Varun Panickar | 2022-04-27 | pass | pass
Area 2 | ITP-075-A2-LOT-010 | ITP-075-A2-LOT-010 - Mickleham South (NB) Layer 1 SF - CH30100-CH30320 | pass | pass |  | 2022-03-09 |  | 2022-03-09 | 2022-03-09 | pass |  | CIL-Civil Lot | CH30100-CH30320 | PAVI - Paving | PAVI - Asphalt Placement | 1145-C200-FUL-QAC-0075 | NB - Northbound | Varun Panickar |  | Varun Panickar | 2022-04-27 | pass | pass
Area 2 | ITP-075-A2-LOT-011 | ITP-075-A2-LOT-011 - Mickleham South (SB) Layer 2 SI - CH30102-CH30316 | wip | wip |  | 2022-03-10 |  | 2022-03-10 | 2022-03-10 | wip |  | CIL-Civil Lot | CH30102-CH30316 | PAVI - Paving | PAVI - Asphalt Placement | 1145-C200-FUL-QAC-0075 | SB - Southbound | Varun Panickar |  | Varun Panickar | 2022-05-24 | wip | wip
Area 2 | ITP-075-A2-LOT-012 | ITP-075-A2-LOT-012 - Mickleham South Layer1 SF - CH30020-CH30100 | pass | pass |  | 2022-03-10 |  | 2022-03-10 | 2022-03-10 | pass |  | CIL-Civil Lot | CH30020-CH30100 | PAVI - Paving | PAVI - Asphalt Placement | 1145-C200-FUL-QAC-0075 | NB - Northbound | Varun Panickar |  | Varun Panickar | 2022-04-27 | pass | pass
Area 2 | ITP-075-A2-LOT-013 | ITP-075-A2-LOT-013 - Mickleham South (NB) - Layer 2 (SI) - CH30020-CH30316 | pass | pass |  | 2022-03-16 |  | 2022-03-16 | 2022-03-16 | pass | 2022-03-16 | CIL-Civil Lot | CH30020-CH30316 | PAVI - Paving | PAVI - Asphalt Placement | 1145-C200-FUL-QAC-0075 | NB - Northbound | Varun Panickar |  | Varun Panickar | 2022-05-24 | pass | pass
Area 2 | ITP-075-A2-LOT-014 | ITP-075-A2-LOT-014 - Mickleham North (SB+NB) - Layer 1 (SF) - CH40500-CH40750 | pass | pass |  | 2022-03-19 |  | 2022-03-19 | 2022-03-19 | pass |  | CIL-Civil Lot | CH40500-CH40750 | PAVI - Paving | PAVI - Asphalt Placement | 1145-C200-FUL-QAC-0075 | SB - Southbound | Varun Panickar |  | Varun Panickar | 2022-04-27 | pass | pass
Area 2 | ITP-075-A2-LOT-015 | ITP-075-A2-LOT-015 - Mickleham North (SB+NB) - Layer 2 (SI) - CH30520-CH30785 | pass | pass |  | 2022-03-22 |  | 2022-03-22 | 2022-03-22 | pass | 2022-03-22 | CIL-Civil Lot | CH30520-CH30785 | PAVI - Paving | PAVI - Asphalt Placement | 1145-C200-FUL-QAC-0075 | NB - Northbound | Varun Panickar |  | Varun Panickar | 2022-05-24 | pass | pass
Area 2 | ITP-075-A2-LOT-016 | ITP-075-A2-LOT-016 - Mickleham South - Pavement 6 Area - Layer 1 (SI) - CH29980-CH30020 | wip | wip |  | 2022-03-25 |  | 2022-03-25 | 2022-03-25 | wip | 2022-03-25 | CIL-Civil Lot | CH29980-CH30020 | PAVI - Paving | PAVI - Asphalt Placement | 1145-C200-FUL-QAC-0075 | NB - Northbound | Varun Panickar |  | Varun Panickar | 2022-04-28 | wip | wip
Area 2 | ITP-075-A2-LOT-017 | ITP-075-A2-LOT-017 - Mickleham Intersection (SB) - Layer 1 (SF) - CH40240-CH40500 | pass | pass |  | 2022-03-26 |  | 2022-03-26 | 2022-03-26 | pass |  | CIL-Civil Lot | CH40240-CH40500 | PAVI - Paving | PAVI - Asphalt Placement | 1145-C200-FUL-QAC-0075 | SB - Southbound | Varun Panickar |  | Varun Panickar | 2022-04-27 | pass | pass
Area 2 | ITP-075-A2-LOT-018 | ITP-075-A2-LOT-018 - Mickleham Intersection (NB) - Layer 1 (SF) - CH30320-CH30570 | pass | pass |  | 2022-03-26 |  | 2022-03-26 | 2022-03-26 | pass |  | CIL-Civil Lot | CH30320-CH30570 | PAVI - Paving | PAVI - Asphalt Placement | 1145-C200-FUL-QAC-0075 | NB - Northbound | Varun Packinar |  | Varun Panickar | 2022-04-27 | pass | pass
Area 2 | ITP-075-A2-LOT-019 | ITP-075-A2-LOT-019 - Mickleham Intersection (NB+SB) - Layer 2(SI) - CH30316-CH30520 | pass | pass |  | 2022-03-28 |  | 2022-03-28 | 2022-03-28 | pass | 2022-03-28 | CIL-Civil Lot | CH30316-CH30520 | PAVI - Paving | PAVI - Asphalt Placement | 1145-C200-FUL-QAC-0075 | NB - Northbound | Varun Panickar |  | Varun Panickar | 2022-05-24 | pass | pass
Area 2 | ITP-075-A2-LOT-020 | ITP-075-A2-LOT-020 - Mickleham Intersection (West going EB) - Layer 1 (SF) - CH20470-CH20490 | pass | pass |  | 2022-03-29 |  | 2022-03-29 | 2022-03-29 | pass |  | CIL-Civil Lot | CH20470-CH20490 | PAVI - Paving | PAVI - Asphalt Placement | 1145-C200-FUL-QAC-0075 | EB - Eastbound | Varun Panickar |  | Varun Panickar | 2022-04-27 | pass | pass
Area 2 | ITP-075-A2-LOT-021 | ITP-075-A2-LOT-021 - Mickleham Intersection (West Sliplane going WB) - Layer 2(SI) - CH10550-CH10570 | pass | pass |  | 2022-03-29 |  | 2022-03-29 | 2022-03-29 | pass | 2022-03-29 | CIL-Civil Lot | CH10550-CH10570 | PAVI - Paving | PAVI - Asphalt Placement | 1145-C200-FUL-QAC-0075 | WB - Westbound | Varun Panickar |  | Varun Panickar | 2022-05-25 | pass | pass
Area 2 | ITP-075-A2-LOT-022 | ITP-075-A2-LOT-022 - Mickleham South - Pavement 6 Area - Layer 2 (SI) - CH29980-CH30020 | pass | pass |  | 2022-03-30 |  | 2022-03-30 | 2022-03-30 | pass | 2022-03-30 | CIL-Civil Lot | CH29980-CH30030 | PAVI - Paving | PAVI - Asphalt Placement | 1145-C200-FUL-QAC-0075 | SB - Southbound | Varun Panickar |  | Varun Panickar | 2022-05-25 | pass | pass
Area 2 | ITP-075-A2-LOT-023 | ITP-075-A2-LOT-023 - Mickleham Intersection (SE Sliplane - WB) - Layer 1 (SF) - CH10550-CH10570 | pass | pass |  | 2022-03-29 |  | 2022-03-29 | 2022-03-29 | pass |  | CIL-Civil Lot | CH10550-CH10570 | PAVI - Paving | PAVI - Asphalt Placement | 1145-C200-FUL-QAC-0075 | WB - Westbound | Varun Panickar |  | Varun Panickar | 2022-04-27 | pass | pass
Area 2 | ITP-075-A2-LOT-024 | ITP-075-A2-LOT-024 - Mickleham South (SB) - Layer 2 (SI) - CH40210-CH40350 | pass | pass |  | 2022-03-31 |  | 2022-03-31 | 2022-03-31 | pass | 2022-04-01 | CIL-Civil Lot | CH40210-CH40350 | PAVI - Paving | PAVI - Asphalt Placement | 1145-C200-FUL-QAC-0075 | SB - Southbound | Varun Panickar |  | Varun Panickar | 2022-06-20 | pass | pass
Area 2 | ITP-075-A2-LOT-025 | ITP-075-A2-LOT-025 - Mickleham Intersection (West - EB) - Layer 2 (SI) - CH20470-CH20490 | pass | pass |  | 2022-03-29 |  | 2022-03-29 | 2022-03-29 | pass | 2022-03-29 | CIL-Civil Lot | CH20470-CH20490 | PAVI - Paving | PAVI - Asphalt Placement | 1145-C200-FUL-QAC-0075 | EB - Eastbound | Varun Panickar |  | Varun Panickar | 2022-05-25 | pass | pass
Area 2 | ITP-075-A2-LOT-026 | ITP-075-A2-LOT-026 - Mickleham Intersection (North-West sliplane) - Layer 1 (SF) - CH20470-CH20490 | pass | pass |  | 2022-04-01 |  | 2022-04-01 | 2022-04-01 | pass |  | CIL-Civil Lot | CH20470-CH20490 | PAVI - Paving | PAVI - Asphalt Placement | 1145-C200-FUL-QAC-0075 | EB - Eastbound | Varun Panickar |  | Varun Panickar | 2022-04-27 | pass | pass
Area 2 | ITP-075-A2-LOT-027 | ITP-075-A2-LOT-027 - Mickleham Intersection (EB lane) - Layer 1 (SF) - CH20515-CH20530 | pass | pass |  | 2022-04-01 |  | 2022-04-01 | 2022-04-01 | pass |  | CIL-Civil Lot | CH20515-CH20530 | PAVI - Paving | PAVI - Asphalt Placement | 1145-C200-FUL-QAC-0075 | EB - Eastbound | Varun Panickar |  | Varun Panickar | 2022-04-27 | pass | pass
Area 2 | ITP-075-A2-LOT-028 | ITP-075-A2-LOT-028 - Mickleham Intersection (WB Lane) - Layer 1 (SF) - CH10570-CH10650 | pass | pass |  | 2022-04-01 |  | 2022-04-01 | 2022-03-01 | pass |  | CIL-Civil Lot | CH10570-CH10650 | PAVI - Paving | PAVI - Asphalt Placement | 1145-C200-FUL-QAC-0075 | WB - Westbound | Varun Panickar |  | Varun Panickar | 2022-04-27 | pass | pass
Area 2 | ITP-075-A2-LOT-029 | ITP-075-A2-LOT-029 - Mickleham Intersection (North-West sliplane) - Layer 2 (SI) - CH20470-CH20490 | pass | pass |  | 2022-04-01 |  | 2022-04-01 | 2022-04-01 | pass | 2022-04-01 | CIL-Civil Lot | CH20470-CH20490 | PAVI - Paving | PAVI - Asphalt Placement | 1145-C200-FUL-QAC-0075 | EB - Eastbound | Varun Panickar |  | Varun Panickar | 2022-04-01 | pass | pass
Area 2 | ITP-075-A2-LOT-030 | ITP-075-A2-LOT-030 - Mickleham Intersection (EB lane) - Layer 2 (S1) - CH20515-CH20555 | pass | pass |  | 2022-04-05 |  | 2022-04-05 | 2022-04-01 | pass | 2022-04-01 | CIL-Civil Lot | CH20515-CH20555 | PAVI - Paving | PAVI - Asphalt Placement | 1145-C200-FUL-QAC-0075 | EB - Eastbound | Varun Panickar |  | Varun Panickar | 2022-05-25 | pass | pass
Area 2 | ITP-075-A2-LOT-031 | ITP-075-A2-LOT-031 - Mickleham Intersection (WB Lane) - Layer 2 (SI) - CH10570-CH10650 | pass | pass |  | 2022-04-05 |  | 2022-04-05 | 2022-04-01 | pass | 2022-04-20 | CIL-Civil Lot | CH10570-CH10650 | PAVI - Paving | PAVI - Asphalt Placement | 1145-C200-FUL-QAC-0075 | WB - Westbound | Varun Panickar |  | Varun Panickar | 2022-05-25 | pass | pass
Area 2 | ITP-075-A2-LOT-032 | ITP-075-A2-LOT-032 - Mickleham North - Regulation Layer (SI) - CH30785 - CH 30850 | pass | pass |  | 2022-03-30 |  | 2022-03-30 | 2022-03-30 | pass |  | CIL-Civil Lot | CH30785 - CH30850 | PAVI - Paving | PAVI - Asphalt Placement | 1145-C200-FUL-QAC-0075 | NB - Northbound | Varun Panickar |  | Varun Panickar | 2022-05-23 | pass | pass
Area 2 | ITP-075-A2-LOT-033 | ITP-075-A2-LOT-033 - Mickleham North - Layer 1 (SI) - CH30785 - CH30850 | pass | pass |  | 2022-03-30 |  | 2022-03-30 | 2022-03-30 | pass |  | CIL-Civil Lot | CH30785 - CH30850 | PAVI - Paving | PAVI - Asphalt Placement | 1145-C200-FUL-QAC-0075 | NB - Northbound | Varun Panickar |  | Varun Panickar | 2022-05-23 | pass | pass
Area 2 | ITP-075-A2-LOT-034 | ITP-075-A2-LOT-034 - Mickleham North - Layer 2 (SI) - CH30785 - CH30850 | pass | pass |  | 2022-03-30 |  | 2022-03-30 | 2022-03-30 | pass | 2022-03-31 | EAL- Earthworks Lot | CH30785 - CH30850 | PAVI - Paving | PAVI - Asphalt Placement | 1145-C200-FUL-QAC-0075 | NB - Northbound | Varun Panickar |  | Varun Panickar | 2022-06-06 | pass | pass
Area 2 | ITP-078-A2-LOT-004 | ITP-078-A2-LOT-004 - Zone 7 East Guard rail ground Beam ch10850 to CH10750, 10610 to 10630 | not started | not started |  | 2022-03-21 |  | 2022-03-21 | 2022-03-21 |  |  |  | 10850 to 10750, 10610 to 10630 | [8 empty] | not started | not started
Area 2 | ITP-078-A2-LOT-006 | ITP-078-A2-LOT-006 - Zone 7 East Guard rail ground Beam ch10750 to ch10720, 10630 to 10650 | not started | not started |  | 2022-03-22 |  | 2022-03-22 | 2022-03-22 | [12 empty] | not started | not started
Area 2 | ITP-078-A2-LOT-007 | ITP-078-A2-LOT-007 - Zone 7 East Guard rail ground Beam ch10650 to ch10750 | not started | not started |  | 2022-03-23 |  | 2022-03-23 | 2022-03-23 |  |  |  | 10650 10750 | [8 empty] | not started | not started
Area 2 | ITP-078-A2-LOT-008 | ITP-078-A2-LOT-008 (DUPLICATE) - Zone 7 East Guard rail ground Beam CH10550 to CH10650 | not started | not started |  | 2022-04-01 |  | 2022-04-01 | 2022-04-01 |  |  |  | Ch10550 to ch10650 |  |  |  |  | Jonathon Rock |  |  |  | not started | not started
Area 2 | ITP-078-A2-LOT-008 | ITP-078-A2-LOT-008 (DUPLICATE) - Zone 7 Mickleham Road - Pit 1088 Base | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-078-A2-LOT-009 | ITP-078-A2-LOT-009 - Zone 7 Mickleham Road - Pit 1088 - Walls | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-078-A2-LOT-010 | ITP-078-A2-LOT-010 - Zone 7 Mickleham Road - Pit 1088 - Soffit | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-078-A2-LOT-011 | ITP-078-A2-LOT-011 - Zone 7 Mickleham Road - Pit 1087 - Base | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-078-A2-LOT-012 | ITP-078-A2-LOT-012 - Zone 7 Mickleham Road - Pit 1087 - Walls | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-078-A2-LOT-013 | ITP-078-A2-LOT-013 - Zone 7 Mickleham Road - Pit 1087 - Soffit | not started | not started | [17 empty] | not started | not started
Area 2 | ITP-078-A2-LOT-014 | ITP-078-A2-LOT-014 - Zone 7 Mickleham Road - Pit 993 - Base Slab + Walls | pass | pass |  | 2022-03-20 |  | 2022-03-21 | 2022-03-21 | 2022-03-28 |  | DRL- Drainage Lot |  | STOR - Stormwater | IPC - Insitu Pit Construction | 1145-C200-FUL-QAC-0078 | EB - Eastbound | Varun Panickar |  | Varun Panickar | 2022-05-25 | pass | pass
Area 2 | ITP-078-A2-LOT-015 | ITP-078-A2-LOT-015 - Zone 7 Mickleham Road - Pit 993 - Haunch + Slab | pass | pass |  | 2022-03-29 |  | 2022-03-29 | 2022-03-29 | 2022-04-02 |  | DRL- Drainage Lot |  | STOR - Stormwater | IPC - Insitu Pit Construction | 1145-C200-FUL-QAC-0078 | EB - Eastbound | Varun Panickar |  | Varun Panickar | 2022-05-25 | pass | pass
Area 2 | ITP-078-A2-LOT-016 | ITP-078-A2-LOT-016 - Zone 7 Mickleham Road - Pit 994 - Base Slab + Walls | pass | pass |  | 2022-03-21 |  | 2022-03-21 | 2022-03-21 | 2022-03-28 |  | DRL- Drainage Lot |  | STOR - Stormwater | IPC - Insitu Pit Construction | 1145-C200-FUL-QAC-0078 | EB - Eastbound | Varun Panickar |  | Varun Panickar | 2022-05-25 | pass | pass
Area 2 | ITP-078-A2-LOT-017 | ITP-078-A2-LOT-017 - Zone 7 Mickleham Road - Pit 994 - Haunch + Slab | pass | pass |  | 2022-04-07 |  | 2022-04-07 | 2022-04-07 | 2022-04-15 |  | DRL- Drainage Lot |  | STOR - Stormwater | IPC - Insitu Pit Construction | 1145-C200-FUL-QAC-0078 | EB - Eastbound | Varun Panickar |  | Varun Panickar | 2022-05-25 | pass | pass
Area 2 | ITP-078-A2-LOT-018 | ITP-078-A2-LOT-018 - Zone 7 Mickleham Road - Pit 995 - Base Slab | pass | pass |  | 2022-04-07 |  | 2022-04-07 | 2022-04-08 | 2022-04-15 |  | DRL- Drainage Lot |  | STOR - Stormwater | IPC - Insitu Pit Construction | 1145-C200-FUL-QAC-0078 | EB - Eastbound | Varun Panickar |  | Varun Panickar | 2022-05-25 | pass | pass
Area 2 | ITP-078-A2-LOT-019 | ITP-078-A2-LOT-019 - Zone 7 Mickleham Road - Pit 995 - Walls | pass | pass |  | 2022-04-11 |  | 2022-04-11 | 2022-04-11 | 2022-04-19 |  | DRL- Drainage Lot |  | STOR - Stormwater | IPC - Insitu Pit Construction | 1145-C200-FUL-QAC-0078 | EB - Eastbound | Varun Panickar |  | Varun Panickar | 2022-05-25 | pass | pass
Area 2 | ITP-078-A2-LOT-020 | ITP-078-A2-LOT-020 - In-situ Drainage Headwall 992 - Base | not started | not started |  | 2022-06-21 |  | 2022-06-21 | 2022-06-22 |  |  |  | 10475 | STOR - Stormwater | IPC - Insitu Pit Construction |  | NB - Northbound | Michael Schibeci |  |  |  | not started | not started
Area 2 | ITP-078-A2-LOT-021 | ITP-078-A2-LOT-021 - In-situ Drainage Headwall 992 - Wings | not started | not started | [17 empty] | not started | not started
Utilities | ITP-040-UT-LOT-001 | ITP-040-UT-LOT-001 - G1747 Gas Protection Works - Waterview Blvd NW corner
Utilities | ITP-040-UT-LOT-002 | ITP-040-UT-LOT-002 - G1753 - North-South crossing, intersection of CRG Rd & Champion Pde
Utilities | ITP-040-UT-LOT-003 | ITP-040-UT-LOT-003- G1747 Gas Protection Works - water view NW corner
Utilities | ITP-040-UT-LOT-004 | ITP-040-UT-LOT-004 - G1730 Gas Protection Bridgewater rd intersection
Utilities | ITP-040-UT-LOT-005 | ITP-040-UT-LOT-005 - G1763 Gas Protection Debonair Pde
Utilities | ITP-040-UT-LOT-006 | ITP-040-UT-LOT-006 - G1702 Gas Protection Hardy Ave
Utilities | ITP-040-UT-LOT-007 | ITP-040-UT-LOT-007 - G1745 Gas Protection East Side of Aitken
Utilities | ITP-040-UT-LOT-008 | ITP-040-UT-LOT-008 - G1709 & G1710 Gas Protection Crossing Benston St
Utilities | ITP-040-UT-LOT-009 | ITP-040-UT-LOT-009 - G1712,G173,G1714 - Newbold Ave |  |  |  | 2022-03-08 |  | 2022-03-08 | 2022-03-08 |  |  | UTL- Utility Lot | 15716-15730 | GAS - Gas | Utility Protection Works - Gas Assets | 1145-C200-FUL-QAC-ITP-0040_00 | WB - Westbound | Abdullah Abdullah |  |  |  |  | NO
Utilities | ITP-040-UT-LOT-010 | ITP-040-UT-LOT-010 - G1718 Plumpton Ave |  |  |  | 2022-03-18 |  | 2022-03-18 | 2022-03-18 |  |  | UTL- Utility Lot | CH125630 - CH12540 | GAS - Gas | Utility Protection Works - Gas Assets | 1145-C200-FUL-QAC-ITP-0040_00 | EB - Eastbound | Abdullah Abdullah
Utilities | ITP-040-UT-LOT-011 | ITP-040-UT-LOT-011 - G1758 Highlander East
Utilities | ITP-040-UT-LOT-012 | ITP-040-UT-LOT-012 - G1757 Highlander West
Utilities | ITP-040-UT-LOT-013 | ITP-040-UT-LOT-013 - G1760 Vantage Blvd
Utilities | ITP-041-UT-LOT-001 | ITP-041-UT-LOT-001 - Private water service - East of Selwyn Area 1 (50mm)
Utilities | ITP-042-UT-LOT-001 | ITP-042-UT-LOT-001 - OF1738 - East of Bridgwater Rd - 35m
Utilities | ITP-042-UT-LOT-002 | ITP-042-UT-LOT-002 - OF1707, OF1708, OF1709, OF17115 - Between Hardy Ave & Benston St - 120m
Utilities | ITP-042-UT-LOT-003 | ITP-042-UT-LOT-003 |  |  |  | 2021-11-23 |  | 2021-11-23 | 2021-11-23 |  |  | UTL- Utility Lot | 15100 | TELE - Telecommunication | Utility Protection Works - Comms Assets | 1145-C200-FUL-QAC-ITP-0042_00 | SB - Southbound | Abdullah Abdullah
Utilities | ITP-042-UT-LOT-004 | ITP-042-UT-LOT-004 - OF1773 - East of Aitkens - 20m
Utilities | ITP-042-UT-LOT-005 | ITP-042-UT-LOT-005 - OF17108 - North-South, east side of Mickleham Rd intersection
Utilities | ITP-042-UT-LOT-006 | ITP-042-UT-LOT-006 - T1726 East - West Crossing Mickleham Rd |  |  |  | 2022-02-22 |  | 2022-02-22 | 2022-02-22 |  |  | UTL- Utility Lot | Northbound CH30700 | TELE - Telecommunication | Utility Protection Works - Comms Assets | 1145-C200-FUL-QAC-ITP-0042_00 | NB - Northbound | Abdullah Abdullah
Utilities | ITP-043-UT-LOT-001 | ITP-043-UT-LOT-001 - E1754 - North-East side of Waterview Blvd - 40m
Utilities | ITP-043-UT-LOT-002 | ITP-043-UT-LOT-002 - E1748 - North-South, east of Aitken Blvd - 25m
Utilities | ITP-043-UT-LOT-003 | ITP-043-UT-LOT-003 - E1738 - East-West crossing, west of Waterview Blvd & CRG Rd - 15m
Utilities | ITP-043-UT-LOT-004 | ITP-043-UT-LOT-004 - E1769 - East of carpark entrance Area 1 - 7m
Utilities | ITP-045-UT-LOT-001 | ITP-045-UT-LOT-001 - HUME HIGHWAY | not started | not started | [17 empty] | not started | not started
Utilities | ITP-045-UT-LOT-002 | ITP-045-UT-LOT-002 - CRAIGIEBURN ROAD/CRAIGIEBURN ROAD WEST | not started | not started | [17 empty] | not started | not started
Utilities | ITP-045-UT-LOT-003 | ITP-045-UT-LOT-003 - P.O.S BETWEEN BENSTON STREET AND HARD AVENUE | not started | not started | [17 empty] | not started | not started
Utilities | ITP-045-UT-LOT-004 | ITP-045-UT-LOT-004 - HANSON ROAD | not started | not started | [17 empty] | not started | not started
Utilities | ITP-045-UT-LOT-005 | ITP-045-UT-LOT-005 - P.O.S BETWEEN RAYFIELD AVENUE AND BELSAY PLACE | not started | not started | [17 empty] | not started | not started
Utilities | ITP-045-UT-LOT-006 | ITP-045-UT-LOT-006 - CFA STATION ACCESS | not started | not started | [17 empty] | not started | not started
Utilities | ITP-045-UT-LOT-007 | ITP-045-UT-LOT-007 - BRIDGEWATER ROAD | not started | not started | [17 empty] | not started | not started
Utilities | ITP-045-UT-LOT-008 | ITP-045-UT-LOT-008 - CIMBERWOOD DRIVE | not started | not started | [17 empty] | not started | not started
Utilities | ITP-045-UT-LOT-009 | ITP-045-UT-LOT-009 - DORCHESTER ROAD | not started | not started | [17 empty] | not started | not started
Utilities | ITP-045-UT-LOT-010 | ITP-045-UT-LOT-010 - LYGON DRIVE | not started | not started | [17 empty] | not started | not started
Utilities | ITP-045-UT-LOT-011 | ITP-045-UT-LOT-011 - MAIN STREET/BALYANG WAY | not started | not started | [17 empty] | not started | not started
Utilities | ITP-045-UT-LOT-012 | ITP-045-UT-LOT-012 - AITKEN BOULEVARD/SHOPPING CENTRE ACCESS | not started | not started | [17 empty] | not started | not started
Utilities | ITP-045-UT-LOT-013 | ITP-045-UT-LOT-013 - CRAIGIEBURN ROAD/AITKEN BOULEVARD | not started | not started | [17 empty] | not started | not started
Utilities | ITP-045-UT-LOT-014 | ITP-045-UT-LOT-014 - WATERVIEW BOULEVARD | not started | not started | [17 empty] | not started | not started
Utilities | ITP-045-UT-LOT-015 | ITP-045-UT-LOT-015 - HIGHLANDER DRIVE/VANTAGE BOULEVARD | not started | not started | [17 empty] | not started | not started
Utilities | ITP-045-UT-LOT-016 | ITP-045-UT-LOT-016 - MICKLEHAM ROAD | not started | not started |  | 2022-02-28 |  | 2022-02-28 | 2022-03-02 |  |  | UTL- Utility Lot | MICKLEHAM RD INTERSECTION | UTIL - Utility | TSIG - Traffic Signals | 1145-C200-FUL-QAC-ITP-0045 | EB - Eastbound | GARETH JACK/DION BANDIERA |  |  |  | not started | not started
Utilities | ITP-060-UT-LOT-001 | ITP-060-UT-LOT-001 - Lighting Zone 1 - Hume Hwy to Hard Ave | not started | not started | [17 empty] | not started | not started
Utilities | ITP-060-UT-LOT-002 | ITP-060-UT-LOT-002 - Lighting Zone 2 - Hardy to Rayfield Ave | not started | not started | [17 empty] | not started | not started
Utilities | ITP-060-UT-LOT-003 | ITP-060-UT-LOT-003 - Lighting Zone 3 - Rayfield to Dorchester | not started | not started | [17 empty] | not started | not started
Utilities | ITP-060-UT-LOT-004 | ITP-060-UT-LOT-004 - Lighting Zone 4 - Dorchester to Aitken Blvd | not started | not started | [17 empty] | not started | not started
Utilities | ITP-060-UT-LOT-005 | ITP-060-UT-LOT-005 - Lighting Zone 5 - Aitken Blvd | not started | not started | [17 empty] | not started | not started
Utilities | ITP-060-UT-LOT-006 | ITP-060-UT-LOT-006 - Lighting Zone 6 - Aitken Blvd to Champion | not started | not started | [17 empty] | not started | not started
Utilities | ITP-060-UT-LOT-007 | ITP-060-UT-LOT-007 - Lighting Zone 7A - Champion to Debonair | not started | not started | [17 empty] | not started | not started
Utilities | ITP-060-UT-LOT-008 | ITP-060-UT-LOT-008 - Lighting Zone 7B - Mickleham Road | not started | not started |  | 2021-12-13 |  | 2021-12-13 | 2022-02-03 |  |  | UTL- Utility Lot | Zone 7b lighting package | UTIL-Utility | UTIL - Street Lighting | 1145-C200-FUL-QAC-0060 | EB - Eastbound | Gareth Jack & Dion Bandiera |  |  |  | not started | not started
Utilities | ITP-066-A1-LOT-001 | ITP-066-A1-LOT-001 - Directional Drilling | not started | not started | [17 empty] | not started | not started
Utilities | ITP-079-UT-LOT-001 | ITP-079-UT-LOT-001 - Church Watermain | not started | not started |  | 2022-03-09 |  | 2022-03-09 | 2022-03-09 |  |  | UTL- Utility Lot | 30400-30440 | UTIL | WATE - Water | 1145-C200-FUL-QAC-ITP-0079 | NB - Northbound | ABDULLAH ABDULLAH |  |  |  | not started | not started
Utilities | ITP-079-UT-LOT-002 | ITP-079-UT-LOT-002 - Church Watermain | not started | not started | [17 empty] | not started | not started
Utilities | ITP-079-UT-LOT-003 | ITP-079-UT-LOT-003 - Church Watermain | not started | not started | [17 empty] | not started | not started
Utilities | ITP-079-UT-LOT-004 | ITP-079-UT-LOT-004 - Church Watermain | not started | not started | [17 empty] | not started | not started
Utilities | ITP-079-UT-LOT-005 | ITP-079-UT-LOT-005 - RW1712 Champion 180PE Recycled water | not started | not started |  | 2022-06-20 |  | 2022-06-20 | 2022-06-21 |  |  | UTL- Utility Lot | CH22265 | UTIL | WATE - Water | [6 empty] | not started | not started
Utilities | ITP-079-UT-LOT-006 | ITP-079-UT-LOT-006 - W1758 150mm Potable water Steel Main | not started | not started |  | 2022-06-20 |  | 2022-06-20 | 2022-06-21 |  |  | UTL- Utility Lot | 22266 | UTIL | WATE - Water |  | WB - Westbound | Abdullah Abdullah |  |  |  | not started | not started
Utilities | ITP-079-UT-LOT-007 | ITP-079-UT-LOT-007 - RW1708 Recycled water relocation Aitken Blvd to Waterview Blvd | not started | not started |  | 2022-06-28 |  | 2022-06-28 | 2022-06-28 |  |  | UTL- Utility Lot | 12833 to 13100 | UTIL | WATE - Water |  |  | Abdullah Abdullah |  |  |  | not started | not started
Utilities | ITP-079-UT-LOT-008 | ITP-079-UT-LOT-008 - RW1707 Recycled Water Relocation 280PE - Balyang | not started | not started |  | 2022-07-04 |  | 2022-07-04 | 2022-07-05 |  |  | UTL- Utility Lot | CH13364.684 to CH13700 | UTIL | WATE - Water |  | EB - Eastbound | Abdullah Abdullah |  |  |  | not started | not started

## WEBSITE
Lot No | Lot Desc
ITP-001-A1-LOT-001 | ITP-001-A1-LOT-001 - 11 Trees - Median Ch 24640 to Ch 25040
ITP-001-A1-LOT-002 | ITP-001-A1-LOT-002 - Memorial park & Hume Hwy Center Median
ITP-001-A1-LOT-003 | ITP-001-A1-LOT-003 - 9 Trees - Zone 3 - Westbound Ch 15000 to Ch 14700
ITP-001-A1-LOT-004 | ITP-001-A1-LOT-004 - 64 Trees - Zone 4 - Westbound Ch 14400 to Ch 13880
ITP-001-A1-LOT-005 | ITP-001-A1-LOT-005 - 1 Tree - Zone 1 - Hume Hwy South Center Median - Ch70139 - Ch70272
ITP-001-A1-LOT-006 | ITP-001-A1-LOT-006 - 4Trees - Zone 4 - Golf Course - CH13800 - CH13600
ITP-001-A1-LOT-007 | ITP-001-A1-LOT-007 - 2 Trees - Zone 1 - Craigieburn - Hardy Ave - Ch16085 - Ch16110
ITP-001-A1-LOT-008 | ITP-001-A1-LOT-008 - 3 Trees - Zone 2 - Craigieburn Road- West Bound - Ch16060 - Ch16080
ITP-001-A1-LOT-010 | ITP-001-A1-LOT-010 - Topsoil Strip - Zone 4 - Westbound Ch13600 - Ch14400
ITP-001-A1-LOT-011 | ITP-001-A1-LOT-011 - Clearing & Grubbing - eastbound zone 3 CH25370 -Dalys
ITP-001-A1-LOT-012 | ITP-001-A1-LOT-012 - 24 Trees TBR & 1 trim - Zone 3- CH14760 - CH15080
ITP-001-A1-LOT-013 | ITP-001-A1-LOT-013 - Z3 Topsoil Stripping - BTW Bridgewater Rd and the access to the sporting club - Ch14400 to Ch15080
ITP-001-A1-LOT-014 | ITP-001-A1-LOT-014 - Tree Removal - Rayfield trees
ITP-001-A1-LOT-015 | ITP-001-A1-LOT-015 - Tree Removal B/W Newbold Ave to Bridgewater Rd
ITP-001-A1-LOT-016 | ITP-001-A1-LOT-016- Trees Removal Zone 1,2 & 4 - 17 Trees
ITP-001-A2-LOT-001 | ITP-001-A2-LOT-001 - 9 Trees WB CH10780-CH10940
ITP-001-A2-LOT-002 | ITP-001-A2-LOT-002 - 34 Trees WB CH10800-CH11050
ITP-001-A2-LOT-003 | ITP-001-A2-LOT-003 - WB CH10900-CH11300 Stripping
ITP-001-A2-LOT-004 | ITP-001-A2-LOT-004 - WB CH10500-CH10880 Stripping
ITP-001-A2-LOT-005 | ITP-001-A2-LOT-005 - 29 trees CH11500-CH11300
ITP-001-A2-LOT-006 | ITP-001-A2-LOT-006 - Mickleham North CH40350 - CH40700
ITP-001-A2-LOT-007 | ITP-001-A2-LOT-007 - Debonair - Vantage Stripping
ITP-001-A2-LOT-008 | ITP-001-A2-LOT-008 - 48 trees CH10100-CH10240
ITP-001-A2-LOT-009 | ITP-001-A2-LOT-009 - CH60140-CH60310 Stripping
ITP-001-A2-LOT-010 | ITP-001-A2-LOT-010 - 129 trees CH10235-CH10500
ITP-001-A2-LOT-011 | ITP-001-A2-LOT-011 - 9 Trees NB and SB CH40200-CH40600
ITP-001-A2-LOT-012 | ITP-001-A2-LOT-012 - WB CH10650-CH10500 Stripping
ITP-001-A2-LOT-013 | ITP-001-A2-LOT-013 - WB CH10100 - CH10290 Stripping
ITP-001-A2-LOT-014 | ITP-001-A2-LOT-014 - WB CH10370 - CH10490 Stripping
ITP-001-A2-LOT-016 | ITP-001-A2-LOT-016 - Mickleham South 30000-30200
ITP-001-A2-LOT-017 | ITP-001-A2-LOT-017 - Mickleham South CH30200 - CH30400
ITP-001-A2-LOT-019 | ITP-001-A2-LOT-019 - 2 trees CH11050 - CH11100
ITP-001-A2-LOT-021 | ITP-001-A2-LOT-021 - Zone 5 – Aitken Blvd - SB - CH60540-CH60340
ITP-001-A2-LOT-022 | ITP-001-A2-LOT-022 - Desc - tree removal opposite Champion Pde
ITP-001-A2-LOT-023 | ITP-001-A2-LOT-023 - Zone 7 - North East Corner Mick Rd - CH20533-CH20800 EB
ITP-001-A2-LOT-024 | ITP-001-A2-LOT-024 - Zone 6 & 7 - Champion, Debonair & Mickleham Rd.
ITP-001-A2-LOT-025 | ITP-001-A2-LOT-025 - Aitken Blvd to waterview blvd & Aitken creek bridge
ITP-001-A2-LOT-026 | ITP-001-A2-LOT-026 - Zone 5 – Aitken Blvd - SB - CH60930-CH60860
ITP-006-A1-LOT-001 | ITP-006-A1-LOT-001- Memorial Park East - CH26130 - CH26160 - NB
ITP-006-A1-LOT-002 | ITP-006-A1-LOT-002 - Memorial Park East - CH26130- CH26160 - NB
ITP-006-A1-LOT-003 | ITP-006-A1-LOT-003 - Memorial Park East - CH26180 - CH26220 - NB
ITP-006-A1-LOT-004 | ITP-006-A1-LOT-004 - Hume Hwy North Median - CH70330 - CH70400 - NB
ITP-006-A1-LOT-005 | ITP-006-A1-LOT-005 - Hume Hwy North Median - CH70330 - CH70400 - NB
ITP-006-A1-LOT-006 | ITP-006-A1-LOT-006 - Hume Hwy North Median - CH70400 - CH70445 - NB
ITP-006-A1-LOT-007 | ITP-006-A1-LOT-007 - Hume Hwy North Median - CH70485- CH70506 - SB
ITP-006-A1-LOT-008 | ITP-006-A1-LOT-008 - Hume Hwy South Median- NB - CH70190- CH70280 Cut Floor
ITP-006-A1-LOT-009 | ITP-006-A1-LOT-009 - Hume Hwy South Median - NB - CH70190- CH70280 Layer 1
ITP-006-A1-LOT-010 | ITP-006-A1-LOT-010 - Hume Hwy South Median- NB - CH70190- CH70280 Layer 2
ITP-006-A1-LOT-011 | ITP-006-A1-LOT-011 - Golf Course East - WB - CH14250-CH14090
ITP-006-A1-LOT-012 | ITP-006-A1-LOT-012 - Hume Hwy North Median - CH70330 - CH70400 - NB- 400mm below Subgrade
ITP-006-A1-LOT-013 | ITP-006-A1-LOT-013 - Hume Hwy North Median - CH70330 - CH70400 - NB - 400 below subgrade
ITP-006-A1-LOT-014 | ITP-006-A1-LOT-014 - Golf Course West - WB - CH13860-CH13700
ITP-006-A1-LOT-015 | ITP-006-A1-LOT-015- Hume Hwy North Median - CH70310 - CH70400 - SB - Bottom of Subgrade
ITP-006-A1-LOT-016 | ITP-006-A1-LOT-016 - Golf Course East - WB - CH14040-CH14090
ITP-006-A1-LOT-017 | ITP-006-A1-LOT-017 - Golf Course East - WB - CH14250-CH14306
ITP-006-A1-LOT-018 | ITP-006-A1-LOT-018- Hume Hwy North Median - CH70330 - CH70400 - NB - Subgrade
ITP-006-A1-LOT-019 | ITP-006-A1-LOT-019 - Golf Course East - WB - CH14040-CH14090 - lift 1
ITP-006-A1-LOT-020 | ITP-006-A1-LOT-020 - Golf Course East - WB - CH14040-CH14090 - lift 2
ITP-006-A1-LOT-021 | ITP-006-A1-LOT-021 - Hume Hwy North Median - CH70310 - CH70330 - NB - 200 below Subgrade
ITP-006-A1-LOT-022 | ITP-006-A1-LOT-022 - Hume Hwy North Median - CH70310 - CH70330 - NB - Subgrade
ITP-006-A1-LOT-023 | ITP-006-A1-LOT-023- Hume Hwy North Median - CH70310 - CH70326 - SB - Subgrade
ITP-006-A1-LOT-024 | ITP-006-A1-LOT-024- Hume Hwy North Median - CH70400 - CH70460 - SB - Bottom of Subgrade
ITP-006-A1-LOT-025 | ITP-006-A1-LOT-025- Golf Course West- Ch 13865 to Ch 13900 - Subgrade prep
ITP-006-A1-LOT-026 | ITP-006-A1-LOT-026- Hume Hwy North Median - CH70326 - CH70460 - SB - Subgrade
ITP-006-A1-LOT-027 | ITP-006-A1-LOT-027- Golf Course East- Ch 13960 to Ch 14040 - 400 below subgrade
ITP-006-A1-LOT-028 | ITP-006-A1-LOT-028- Golf Course East- Ch 13960 to Ch 14040 - 200 below subgrade
ITP-006-A1-LOT-029 | ITP-006-A1-LOT-029- Golf Course West- Ch 13865 to Ch 13900 - Subgrade prep
ITP-006-A1-LOT-030 | ITP-006-A1-LOT-030- Golf Course West- Ch 13940 to Ch 14040 - Subgrade prep
ITP-006-A1-LOT-031 | ITP-006-A1-LOT-031 - Zone 3 - WB - Ch14625 to Ch14660 - Onhold
ITP-006-A1-LOT-032 | ITP-006-A1-LOT-032- Hume Hwy North Median - CH70460- CH70490 - SB- Entry - Bottom Of Subgrade
ITP-006-A1-LOT-033 | ITP-006-A1-LOT-033- Hume Hwy North Median - CH70460 - CH70490 - SB- Entry - 400 below subgrade
ITP-006-A1-LOT-034 | ITP-006-A1-LOT-034- Hume Hwy North Median - CH70460- CH70490 - SB- Entry - 200mm below Subgrade/ Cut floor
ITP-006-A1-LOT-035 | ITP-006-A1-LOT-035- Hume Hwy North Median - CH70460- CH70490 - SB- Entry - Subgrade
ITP-006-A1-LOT-036 | ITP-006-A1-LOT-036 - Hume Hwy North Median - CH70400 - CH70435 - NB - Type Pavement 6 - Egress- Subgrade
ITP-006-A1-LOT-038 | ITP-006-A1-LOT-038- Memorial Park East - CH16145 - CH16220 - 600mm below cut floor
ITP-006-A1-LOT-039 | ITP-006-A1-LOT-039- Hume Hwy North- Bullnose - CH16366 - CH16380 - 200mm below Subgrade
ITP-006-A1-LOT-040 | ITP-006-A1-LOT-040- Hume Hwy South - Bullnose - CH16366 - CH16380 - 200mm below Subgrade
ITP-006-A1-LOT-041 | ITP-006-A1-LOT-041- Memorial Park East - CH16145 - CH16220 - 300mm below Subgrade
ITP-006-A2-LOT-001 | ITP-006-A2-LOT-001 - Zone 7 East Gate 7.2-7.3 - CH10660-CH10850-WB
ITP-006-A2-LOT-002 | ITP-006-A2-LOT-002 - Zone 7 East Gate 7.1-7.2 - CH10900-CH11220-WB
ITP-006-A2-LOT-003 | ITP-006-A2-LOT-003 - Zone 7 East Gate 7.4 - CH11680-CH11480-WB
ITP-006-A2-LOT-004 | ITP-006-A2-LOT-004 - Zone 7 East Gate 7.2 - CH10850-CH10900-WB
ITP-006-A2-LOT-005 | ITP-006-A2-LOT-005 - Mickleham North CH30520 - CH30750
ITP-006-A2-LOT-006 | ITP-006-A2-LOT-006 - Mickleham South CH30120-CH30234 Cut
ITP-006-A2-LOT-007 | ITP-006-A2-LOT-007 - Mickleham South CH30120-CH30234 Lift 1
ITP-006-A2-LOT-008 | ITP-006-A2-LOT-008 - Mickleham South CH30120-CH30234 Lift 2
ITP-006-A2-LOT-009 | ITP-006-A2-LOT-009 - Mickleham South CH30020 - CH30316
ITP-006-A2-LOT-013 | ITP-006-A2-LOT-013 - Mickleham South CH30020 - CH30120
ITP-006-A2-LOT-015 | ITP-006-A2-LOT-015 - Zone 7 East Gate 7.3 to Mickleham - CH10550-CH10650-WB
ITP-006-A2-LOT-017 | ITP-006-A2-LOT-017 - Mickleham South CH30152 - CH30316
ITP-006-A2-LOT-018 | ITP-006-A2-LOT-018 - Mickleham North CH30520 - CH30665
ITP-006-A2-LOT-019 | ITP-006-A2-LOT-019 - Mickleham North (NB) CH30520 - CH30800
ITP-006-A2-LOT-020 | ITP-006-A2-LOT-020 - Zone 7 East Gate 7.2-7.3 - CH10580-CH10850-WB
ITP-006-A2-LOT-023 | ITP-006-A2-LOT-023 - Mickleham North CH10520 - CH10550
ITP-006-A2-LOT-024 | ITP-006-A2-LOT-024 - Mickleham North CH10520 - CH10550
ITP-006-A2-LOT-025 | ITP-006-A2-LOT-025 - Mickleham North CH10520 - CH10550 L5 SG
ITP-006-A2-LOT-027 | ITP-006-A2-LOT-027 - Zone 7 West Craigieburn Rd - CH10035-CH10185-EB
ITP-006-A2-LOT-028 | ITP-006-A2-LOT-028 - Zone 7 East (North Half GSM) - CH10610-CH10700-WB
ITP-006-A2-LOT-029 | ITP-006-A2-LOT-029 - Zone 7 West (Slither) - CH10035-CH10135 - Layer 1
ITP-006-A2-LOT-030 | ITP-006-A2-LOT-030 - Zone 7 West (Slither) - CH10035-CH10135 - Layer 2
ITP-006-A2-LOT-031 | ITP-006-A2-LOT-031 - Mickleham South (NB) CH30316 - CH30400
ITP-006-A2-LOT-032 | ITP-006-A2-LOT-032 - Mickleham North NB CH30470 - CH30500 Cut floor
ITP-006-A2-LOT-033 | ITP-006-A2-LOT-033 - Mickleham North NB CH30470 - CH30500 Layer 1
ITP-006-A2-LOT-034 | ITP-006-A2-LOT-034 - Mickleham South CH30316 - CH30400
ITP-006-A2-LOT-035 | ITP-006-A2-LOT-035 - Mickleham Intersection CH30400 - CH30420
ITP-006-A2-LOT-036 | ITP-006-A2-LOT-036 - Mickleham Intersection CH30400 - CH30420
ITP-006-A2-LOT-037 | ITP-006-A2-LOT-037 - Mickleham Intersection CH30400 - CH30420
ITP-006-A2-LOT-038 | ITP-006-A2-LOT-038 - Mickleham Intersection CH30400 - CH30420
ITP-006-A2-LOT-039 | ITP-006-A2-LOT-039 - Mickleham Intersection CH30400 - CH30420
ITP-006-A2-LOT-040 | ITP-006-A2-LOT-040 - Mickleham North (SB) CH30420 - CH30520
ITP-006-A2-LOT-042 | ITP-006-A2-LOT-042 - Mickleham North (NB) CH30450 - CH30520
ITP-006-A2-LOT-043 | ITP-006-A2-LOT-043 - Mickleham Intersection CH30400 - CH30430
ITP-006-A2-LOT-045 | ITP-006-A2-LOT-045 - Mickleham Intersection NE CH20500 - CH20550
ITP-006-A2-LOT-046 | ITP-006-A2-LOT-046 - Mickleham North CH40750 - CH40780
ITP-006-A2-LOT-047 | ITP-006-A2-LOT-047 - Mickleham South CH29980 - CH30015
ITP-006-A2-LOT-048 | ITP-006-A2-LOT-048 - Mickleham Intersection CH10520 - CH10600
ITP-006-A2-LOT-050 | ITP-006-A2-LOT-050 - Zone 7 West Dam - CH10300 to 10350 - Layer 1
ITP-006-A2-LOT-052 | ITP-006-A2-LOT-052 - Zone 7 West Dam - CH10300 to 10350 - Layer 2
ITP-006-A2-LOT-053 | ITP-006-A2-LOT-053 - Zone 7 West Dam - CH10300 to 10350 - Layer 3
ITP-006-A2-LOT-054 | ITP-006-A2-LOT-054 - Zone 7 East Gate 7.1-7.2 (Post ACM) - CH10840-CH11140-WB
ITP-006-A2-LOT-055 | ITP-006-A2-LOT-055 - Zone 7 West Dam - CH10300 to 10350 - 400mm Below Subgrade (Top of Layer 4)
ITP-006-A2-LOT-056 | ITP-006-A2-LOT-056 - Type B layer 1m below FSL
ITP-006-A2-LOT-057 | ITP-006-A2-LOT-057 - Zone 7 East (GSM Capping Shift) - CH10780-CH10850-WB
ITP-006-A2-LOT-058 | ITP-006-A2-LOT-058 - Zone 7 East SUP - CH10850 to CH10730
ITP-006-A2-LOT-059 | ITP-006-A2-LOT-059 - Zone 7 East SUP - CH10730 to CH10680
ITP-006-A2-LOT-060 | ITP-006-A2-LOT-060 - Zone 7 East SUP - CH10600 to CH10630
ITP-006-A2-LOT-061 | ITP-006-A2-LOT-061 - Zone 7 East SUP - CH10600 to CH10730
ITP-006-A2-LOT-062 | ITP-006-A2-LOT-062 - Zone 7 West Dam to Tennis Court - CH10290 to CH10460 - Subgrade Level
ITP-006-A2-LOT-062 | ITP-006-A2-LOT-062 - Zone 7 West Olive Grove to Tennis Court - CH10190 to 10410 - Subgrade Level
ITP-006-A2-LOT-063 | ITP-006-A2-LOT-063 - Zone 7 West Dam - CH10300 to 10350 - 200mm Below Subgrade
ITP-006-A2-LOT-064 | ITP-006-A2-LOT-064 - Zone 7 East Nobility Rd to Gate 7.5 - CH11360 to CH11490 - WB
ITP-006-A2-LOT-065 | ITP-006-A2-LOT-065 - Zone 7 West Tennis Court - CH10350-10410 - Cut Fill (400mm Below Subgrade)
ITP-006-A2-LOT-066 | ITP-006-A2-LOT-066 - Zone 7 West Tennis Court - CH10350-10410 - Cut Fill (200mm Below Subgrade)
ITP-006-A2-LOT-067 | ITP-006-A2-LOT-067 - Zone 7 West - CH10420-10470 - Rectification Works @ 400mm below Subgrade
ITP-006-A2-LOT-068 | ITP-006-A2-LOT-068 - Zone 7 West - CH10420-104270 - Rectification Works @ 200mm below Subgrade
ITP-006-A2-LOT-069 | ITP-006-A2-LOT-069 - Zone 7 West - CH10420-104270 - Rectification Works @ 600mm below Subgrade
ITP-006-A2-LOT-072 | ITP-006-A2-LOT-072 - Zone 7 SUP - CH10550 to CH10650 - Subgrade Level
ITP-006-A2-LOT-073 | ITP-006-A2-LOT-073 - SUP Subgrade Prep - NW Mickleham Intersection
ITP-006-A2-LOT-074 | ITP-006-A2-LOT-074 - SUP Cut Floor Level - NE Mickleham Intersection
ITP-006-A2-LOT-079 | ITP-006-A2-LOT-079 - SUP subgrade Layer 4 - 200mm installation - Mick NE
ITP-006-A2-LOT-080 | ITP-006-A2-LOT-080 - Type B layer 800m below FSL
ITP-006-A2-LOT-081 | ITP-006-A2-LOT-081 - SUP subgrade Layer 5 - 200mm installation - Mick NE
ITP-006-A2-LOT-082 | ITP-006-A2-LOT-082 - Zone 7 West Jo's Property
ITP-006-A2-LOT-083 | ITP-006-A2-LOT-083 - Zone 7 West SW CH 10450 - CH 10490 Cut + 200
ITP-006-A2-LOT-084 | ITP-006-A2-LOT-084 - Zone 7 West SW CH 10450 - CH 10490 SG top
ITP-006-A2-LOT-085 | ITP-006-A2-LOT-085 - SUP subgrade Layer 6 - 200mm installation - Mick NE
ITP-006-A2-LOT-086 | ITP-006-A2-LOT-086 - Type B layer 600m below FSL dam
ITP-006-A2-LOT-087 | ITP-006-A2-LOT-087 - SUP subgrade Layer 7 - 200mm installation - Mick NE
ITP-006-A2-LOT-088 | ITP-006-A2-LOT-088 - Zone 7 East - Debonair Cut Floor and Layer 1 - CH11220 to CH11300
ITP-006-A2-LOT-089 | ITP-006-A2-LOT-089 - Mickleham Intersection SW - Slip Lane Tie In - CH30370-30390
ITP-006-A2-LOT-090 | ITP-006-A2-LOT-090 - Mickleham Rd North (Northbound) SUP Subgrade - CH30465-30695
ITP-006-A2-LOT-091 | ITP-006-A2-LOT-091 - Zone 7 East - Layer 2 - CH11220 to CH11300
ITP-006-A2-LOT-093 | ITP-006-A2-LOT-093 - Type B Layer 400mm below FSL Dam - Zone 7 West (CH10300-10350)
ITP-006-A2-LOT-094 | ITP-006-A2-LOT-094 - Type B Layer 200mm below FSL Dam - Zone 7 West (CH10300-10350)
ITP-006-A2-LOT-095 | ITP-006-A2-LOT-095 - Zone 7 East - Layer 3 - CH11220 to CH11300
ITP-006-A2-LOT-097 | ITP-006-A2-LOT-097 - Zone 7 East Debonair - Cut Floor & Layer 1 - CH11300 to CH11320
ITP-006-A2-LOT-098 | ITP-006-A2-LOT-098 - Zone 7 East Debonair - Layer 2 - CH11300 to CH11320
ITP-006-A2-LOT-099 | ITP-006-A2-LOT-099 - Zone 7 East Debonair - Layer 3 - CH11300 to CH11320
ITP-006-A2-LOT-100 | ITP-006-A2-LOT-100 - Zone 7 West - 755 Driveway Wedge - CH10135-CH10180 - Cut Floor Level
ITP-006-A2-LOT-101 | ITP-006-A2-LOT-101 - Zone 7 East - Layer 0 - CH11360 to CH11390
ITP-006-A2-LOT-102 | ITP-006-A2-LOT-102 - Zone 7 East Debonair - cut floor and layer 1 - CH11300 to CH11320
ITP-006-A2-LOT-103 | ITP-006-A2-LOT-103 - Zone 7 East Debonair - Layer 2 - CH11300 to CH11320
ITP-006-A2-LOT-104 | ITP-006-A2-LOT-104 - Zone 7 West - 755 Driveway Wedge - CH10135-CH10180 - Subgrade Level
ITP-006-AX-LOT-075 | ITP-006-AX-LOT-075 - SUP subgrade Layer 2 - 200mm installation - Mick NE
ITP-006-AX-LOT-076 | ITP-006-AX-LOT-076 - SUP subgrade Layer 3 - 200mm installation - Mick NE
ITP-007-A1-LOT-001 | ITP-007-A1-LOT-001 - Memorial Park - CH26130- CH26225 - NB
ITP-007-A1-LOT-002 | ITP-007-A1-LOT-002 - Hume Hwy North Median - CH70330 - CH70400 - NB
ITP-007-A1-LOT-003 | ITP-007-A1-LOT-003 - Hume Hwy North Median - CH70330 - CH70400 - NB
ITP-007-A1-LOT-004 | ITP-007-A1-LOT-004 - Hume Hwy North Median - CH70400 - CH70445 - NB
ITP-007-A1-LOT-005 | ITP-007-A1-LOT-005 - Hume Hwy North Median - CH70400 - CH70445 - NB
ITP-007-A1-LOT-006 | ITP-007-A1-LOT-006 - Hume Hwy North Median - CH70485 - CH70506 - SB - Layer 1
ITP-007-A1-LOT-007 | ITP-007-A1-LOT-007 - Hume Hwy North Median - CH70485 - CH70506 - SB
ITP-007-A1-LOT-008 | ITP-007-A1-LOT-008 - Hume Hwy South Median - CH70190 - CH70280 - NB - Layer 1
ITP-007-A1-LOT-009 | ITP-007-A1-LOT-009 - Hume Hwy South Median - CH70190 - CH70280 - NB - Layer 2
ITP-007-A1-LOT-010 | ITP-007-A1-LOT-010 - Golf Course East - WB - CH14250-CH14090 - Lift 1
ITP-007-A1-LOT-011 | ITP-007-A1-LOT-011 - Golf Course East - WB - CH14250-CH14090 - Lift 2
ITP-007-A1-LOT-012 | ITP-007-A1-LOT-012 - Golf Course West - WB - CH13860-CH13700 - Lift 1
ITP-007-A1-LOT-013 | ITP-007-A1-LOT-013 - Golf Course West - WB - CH13860-CH13700 - Lift 2
ITP-007-A1-LOT-015 | ITP-007-A1-LOT-015 - Hume Hwy North Median - CH70330 - CH70400 - NB - Layer 2
ITP-007-A1-LOT-018 | ITP-007-A1-LOT-018 - Golf Course East - WB - CH14250-CH14306 - lift 1
ITP-007-A1-LOT-020 | ITP-007-A1-LOT-020 - Golf Course East - WB - CH14250-CH14306 - lift 2
ITP-007-A1-LOT-022 | ITP-007-A1-LOT-022 - Hume Hwy North Median - CH70310 - CH70330 - NB - Layer 1
ITP-007-A1-LOT-023 | ITP-007-A1-LOT-023 - Hume Hwy North Median - CH70310 - CH70330 - NB - Layer 2
ITP-007-A1-LOT-024 | ITP-007-A1-LOT-024 - Golf Course West - Ch13865 to Ch13900 - 1st lift Capping
ITP-007-A1-LOT-025 | ITP-007-A1-LOT-025 - Hume Hwy North Median - CH70400 - CH70460 - SB - Type A Layer 1
ITP-007-A1-LOT-026 | ITP-007-A1-LOT-026 - Hume Hwy North Median - CH70326 - CH70400 - SB - Type A Layer 1
ITP-007-A1-LOT-027 | ITP-007-A1-LOT-027- Hume Hwy North Median - CH70460 - CH70490 - SB- Entry - Type A Layer 1
ITP-007-A1-LOT-028 | ITP-007-A1-LOT-028- Hume Hwy North- Bullnose - CH16366 - CH16380 - Type A - Layer 1
ITP-007-A1-LOT-029 | ITP-007-A1-LOT-029- Hume Hwy South - Bullnose - CH16366 - CH16380 - Type A -Layer 1
ITP-007-A2-LOT-001 | ITP-007-A2-LOT-001 - Zone 7 East Gate 7.1-7.2 - CH10900-CH11220-WB Layer 1
ITP-007-A2-LOT-002 | ITP-007-A2-LOT-002 - Zone 7 East Gate 7.2-7.3 - CH10660-CH10850-WB Layer 1
ITP-007-A2-LOT-003 | ITP-007-A2-LOT-003 - Zone 7 East Gate 7.1-7.2 - CH10900-CH11220-WB Layer 2
ITP-007-A2-LOT-004 | ITP-007-A2-LOT-004 - Zone 7 East Gate 7.2-7.3 - CH10660-CH10850-WB Layer 2
ITP-007-A2-LOT-005 | ITP-007-A2-LOT-005 - Zone 7 East Gate 7.2 - CH10850-CH10900-WB - Layer 1
ITP-007-A2-LOT-006 | ITP-007-A2-LOT-006 - Zone 7 East Gate 7.2 - CH10850-CH10900-WB - Layer 2
ITP-007-A2-LOT-007 | ITP-007-A2-LOT-007 - Mickleham North CH40400 - CH40700
ITP-007-A2-LOT-008 | ITP-007-A2-LOT-008 - Mickleham South CH30000 - CH30234 L1
ITP-007-A2-LOT-009 | ITP-007-A2-LOT-009 - Zone 7 East Gate 7.4-Nobility Rd - CH11680-CH11480-WB - Layer 1
ITP-007-A2-LOT-010 | ITP-007-A2-LOT-010 - Zone 7 East Gate 7.4-Nobility Rd - CH11680-CH11480-WB - Layer 2
ITP-007-A2-LOT-011 | ITP-007-A2-LOT-011 - Mickleham South CH30000 - CH30234 Layer 2
ITP-007-A2-LOT-012 | ITP-007-A2-LOT-012 - Mickleham South CH30000- CH30152 Layer 1
ITP-007-A2-LOT-013 | ITP-007-A2-LOT-013 - Mickleham South CH30234 - CH30316 Layer 2
ITP-007-A2-LOT-014 | ITP-007-A2-LOT-014 - Mickleham South CH30234 - CH30316 Layer 1
ITP-007-A2-LOT-015 | ITP-007-A2-LOT-015 - Mickleham South CH30152 - CH30316 Layer 1
ITP-007-A2-LOT-016 | ITP-007-A2-LOT-016 - Mickleham South CH30152 - CH30316 Layer 2
ITP-007-A2-LOT-017 | ITP-007-A2-LOT-017 - Mickleham North (SB) CH30520 - CH30665 Layer 1
ITP-007-A2-LOT-018 | ITP-007-A2-LOT-018 - Mickleham North (SB) CH30520 - CH30665 Layer 2
ITP-007-A2-LOT-019 | ITP-007-A2-LOT-019 - Zone 7 East Gate 7.3 to Mickleham - CH10550-CH10850-WB - Layer 1
ITP-007-A2-LOT-020 | ITP-007-A2-LOT-020 - Mickleham North (NB) CH30520 - CH30665 Layer 1
ITP-007-A2-LOT-021 | ITP-007-A2-LOT-021 - Zone 7 East Gate 7.3 to Mickleham - CH10550-CH10650-WB - Layer 2
ITP-007-A2-LOT-022 | ITP-007-A2-LOT-022 - Mickleham North (NB) CH30520 - CH30665 Layer 2
ITP-007-A2-LOT-023 | ITP-007-A2-LOT-023 - Mickleham North (NB) CH30665 - CH30800 Layer 1
ITP-007-A2-LOT-024 | ITP-007-A2-LOT-024 - Mickleham North (NB) CH30665 - CH30800 Layer 2
ITP-007-A2-LOT-025 | ITP-007-A2-LOT-025 - Zone 7 West Occo Works - CH10035-CH10185-EB - Layer 1
ITP-007-A2-LOT-026 | ITP-007-A2-LOT-026 - Zone 7 West Occo Works - CH10035-CH10185-EB - Layer 2
ITP-007-A2-LOT-027 | ITP-007-A2-LOT-027 - Zone 7 East Gate 7.3 to Mickleham - CH10650-CH10850-WB - Layer 2
ITP-007-A2-LOT-028 | ITP-007-A2-LOT-028 - Zone 7 East (North Half GSM) - CH10610-CH10700 - Layer 1
ITP-007-A2-LOT-029 | ITP-007-A2-LOT-029 - Zone 7 East (North Half GSM) - CH10610-CH10700 - Layer 2
ITP-007-A2-LOT-030 | ITP-007-A2-LOT-030 - Zone 7 West (Slither) - CH10000-CH10135 - Layer 1
ITP-007-A2-LOT-031 | ITP-007-A2-LOT-031 - Zone 7 West (Slither) - CH10035-CH10135 - Layer 2
ITP-007-A2-LOT-032 | ITP-007-A2-LOT-032 - Mickleham South (SB) CH30316 - CH30400 Layer 1
ITP-007-A2-LOT-033 | ITP-007-A2-LOT-033 - Mickleham South (SB) CH30316 - CH30400 Layer 2
ITP-007-A2-LOT-034 | ITP-007-A2-LOT-034 - Mickleham South (NB) CH30316 - CH30400 Layer 1
ITP-007-A2-LOT-035 | ITP-007-A2-LOT-035 - Mickleham South (NB) CH30316 - CH30400 Layer 2
ITP-007-A2-LOT-036 | ITP-007-A2-LOT-036 - Mickleham North (NB) CH30450 - CH30520 Layer 1
ITP-007-A2-LOT-037 | ITP-007-A2-LOT-037 - Mickleham North (NB) CH30450 - CH30520 Layer 2
ITP-007-A2-LOT-040 | ITP-007-A2-LOT-040 - Mickleham North (SB) CH30470 - CH30520 Layer 1
ITP-007-A2-LOT-041 | ITP-007-A2-LOT-041 - Mickleham North (SB) CH30470 - CH30520 Layer 2
ITP-007-A2-LOT-044 | ITP-007-A2-LOT-044 - Mickleham North (SB) CH30430 - CH30470 Layer 1
ITP-007-A2-LOT-045 | ITP-007-A2-LOT-045 - Mickleham North (SB) CH30430 - CH30470 Layer 2
ITP-007-A2-LOT-046 | ITP-007-A2-LOT-046 - Mickleham Intersection CH30400 - CH30430 Layer 1
ITP-007-A2-LOT-047 | ITP-007-A2-LOT-047 - Mickleham Intersection CH30400 - CH30430 Layer 2
ITP-007-A2-LOT-048 | ITP-007-A2-LOT-048 - Mickleham Intersection (Eastern Tie End) CH10550 - CH10600 Layer 1
ITP-007-A2-LOT-049 | ITP-007-A2-LOT-049 - Mickleham Intersection (Eastern Tie End) CH10550 - CH10600 Layer 2
ITP-007-A2-LOT-050 | ITP-007-A2-LOT-050 - Mickleham North NW Slip Lane CH10470 - CH10490 Layer 2
ITP-007-A2-LOT-051 | ITP-007-A2-LOT-051 - Mickleham North NW Slip Lane CH10470 - CH10490 Layer 1
ITP-007-A2-LOT-052 | ITP-007-A2-LOT-052 - Zone 7 East Gate 7.1-7.2 (Post ACM) - CH10840-CH11140 - Layer 1 - WB
ITP-007-A2-LOT-053 | ITP-007-A2-LOT-053 - Zone 7 East Gate 7.1-7.2 (Post ACM) - CH10900-CH11190 - Layer 2 - WB
ITP-007-A2-LOT-055 | ITP-007-A2-LOT-055 - Zone 7 East (Post Drainage Install) - CH10550-CH10750 - Layer 2
ITP-007-A2-LOT-056 | ITP-007-A2-LOT-056 - Zone 7 East - CH10780-CH10850 - Layer 1
ITP-007-A2-LOT-057 | ITP-007-A2-LOT-057 - Zone 7 East - CH10780-CH10850 - Layer 2
ITP-007-A2-LOT-058 | ITP-007-A2-LOT-058 - Zone 7 East - Nobility Rd to Gate 7.5 - CH11480-CH11400 - WB - Layer 1
ITP-007-A2-LOT-059 | ITP-007-A2-LOT-059 - Zone 7 East - Nobility Rd to Gate 7.5 - CH11480-CH11400 - WB - Layer 2
ITP-007-A2-LOT-060 | ITP-007-A2-LOT-060 - Zone 7 West Dam to East of 1505 Driveway - CH10290 to CH10460 - WB - Layer 1
ITP-007-A2-LOT-061 | ITP-007-A2-LOT-061 - Zone 7 West Dam to Gate 7.7 - CH10290 to CH10400 - WB - Layer 2
ITP-007-A2-LOT-062 | ITP-007-A2-LOT-062 - Zone 7 East - 7.1-7.2 - CH10920-CH10850 - WB - Layer 2
ITP-007-A2-LOT-063 | ITP-007-A2-LOT-063 - Zone 7 West, East of 755 Driveway - CH10180 to CH10350 - WB - Layer 1
ITP-007-A2-LOT-064 | ITP-007-A2-LOT-064 - Zone 7 West, SW Intersection - CH10450 to CH10490 - WB - Layer 1
ITP-007-A2-LOT-065 | ITP-007-A2-LOT-065 - Zone 7 West, Dam SUP - CH10300 to CH10350 - WB - Layer 1
ITP-007-A2-LOT-066 | ITP-007-A2-LOT-066 - Zone 7 West, Slip Lane of SW Intersection - CH30370 to CH30395 - NB - Layer 1
ITP-007-A2-LOT-067 | ITP-007-A2-LOT-067 - Zone 7 West, East of 755 Driveway - CH10180 to CH10350 - WB - Layer 2
ITP-007-A2-LOT-068 | ITP-007-A2-LOT-068 - Zone 7 West, SW Intersection - CH10450 to CH10495 - WB - Layer 2
ITP-007-A2-LOT-070 | ITP-007-A2-LOT-070 - Zone 7 East - Layer 1 Capping - CH11220 to CH11300
ITP-007-A2-LOT-071 | ITP-007-A2-LOT-071 - Zone 7 East - Layer 2 Capping - CH11220 to CH11300
ITP-009-A1-LOT-003 | ITP-009-A1-LOT-003 - Golf Course East - CH14250-CH14165 - WB
ITP-009-A1-LOT-004 | ITP-009-A1-LOT-004 - Golf Course East - CH14165-CH14090 - WB
ITP-009-A1-LOT-005 | ITP-009-A1-LOT-005 - Hume Hwy North Median - CH70310 - CH70400 - NB - CL4
ITP-009-A1-LOT-006 | ITP-009-A1-LOT-006 - Hume Hwy North Median - CH70310 - CH70460 - SB - CL4
ITP-009-A1-LOT-007 | ITP-009-A1-LOT-007 - Hume Hwy North Median - CH70460 - CH70490 - SB - Entry- CL4
ITP-009-A1-LOT-008 | ITP-009-A1-LOT-008 - Hume Hwy South Median - CH70140 - CH70190 - NB - Type 6 Pavement
ITP-009-A2-LOT 032 | ITP-009-A2-LOT 032-Zone 7 East CH10950-CH11190
ITP-009-A2-LOT 033 | ITP-009-A2-LOT 033-Zone 7 East CH10920-CH10950
ITP-009-A2-LOT 034 | ITP-009-A2-LOT 034-Zone 7 East CH10920-CH10850
ITP-009-A2-LOT 036 | ITP-009-A2-LOT 036-Zone 7 East CH11220-CH11300
ITP-009-A2-LOT-002 | ITP-009-A2-LOT-002 - Mickleham South (NB) CH30020-30234
ITP-009-A2-LOT-003 | ITP-009-A2-LOT-003 - Mickleham South (SB) CH30020-CH30152
ITP-009-A2-LOT-004 | ITP-009-A2-LOT-004 - Mickleham South (NB) CH30234-Ch30316
ITP-009-A2-LOT-005 | ITP-009-A2-LOT-005 - Mickleham South (SB) CH30152-CH30316
ITP-009-A2-LOT-006 | ITP-009-A2-LOT-006 - Mickleham North (NB) CH30520-CH30665
ITP-009-A2-LOT-007 | ITP-009-A2-LOT-007 - Mickleham North (SB) CH30520-CH30665
ITP-009-A2-LOT-008 | ITP-009-A2-LOT-008 - Mickleham North (SB+NB) CH30665-CH30800
ITP-009-A2-LOT-009 | ITP-009-A2-LOT-009 - Zone 7 West - Occo Works (CH10040 - 10175)
ITP-009-A2-LOT-010 | ITP-009-A2-LOT-010 - Mickleham South (NB+SB) CH30316-CH30400
ITP-009-A2-LOT-011 | ITP-009-A2-LOT-011 - Mickleham North (NB) CH30430-CH30520
ITP-009-A2-LOT-013 | ITP-009-A2-LOT-013 - Zone 7 East (Gate 7.3-CH10650) (Class 4 Placement)
ITP-009-A2-LOT-015 | ITP-009-A2-LOT-015 - Mickleham North (SB) CH30435-CH30455
ITP-009-A2-LOT-017 | ITP-009-A2-LOT-017 - Mickleham North (Type 6) CH30785-CH30820
ITP-009-A2-LOT-018 | ITP-009-A2-LOT-018 - Mickleham South (Type 6) CH29980-CH30030
ITP-009-A2-LOT-021 | ITP-009-A2-LOT-021 - Mickleham North (SB) CH30450-CH30520
ITP-009-A2-LOT-022 | ITP-009-A2-LOT-022 - Mickleham Rd Intersection (EB) CH30400-CH30430
ITP-009-A2-LOT-024 | ITP-009-A2-LOT-024 - Mickleham Intersection (SE Lane +Slip Lane) CH10550-CH10600
ITP-009-A2-LOT-025 | ITP-009-A2-LOT-025 - Mickleham Intersection NE (North- Eastern Slip Lane) CH20540-CH20560
ITP-009-A2-LOT-026 | ITP-009-A2-LOT-026 - Mickleham Intersection NW (North-Western Slip Lane) CH20470-CH20490
ITP-009-A2-LOT-027 | ITP-009-A2-LOT-027 - Zone 7 East - Occo Works (CH10580 - CH10650)
ITP-009-A2-LOT-028 | ITP-009-A2-LOT-028 - Zone 7 East - Occo Works (CH10650 - CH10870)
ITP-009-A2-LOT-029 | ITP-009-A2-LOT-029 - Zone 7 West - Occo Works (CH10035 - 10050)
ITP-009-A2-LOT-030 | ITP-009-A2-LOT-030 - Zone 7 West - Occo Works (CH10000 - 10035)
ITP-009-A2-LOT-031 | ITP-009-A2-LOT-031 - Zone 7 West - Occo Works (CH10000 - 10040)
ITP-009-A2-LOT-035 | ITP-009-A2-LOT-035 - Zone 7 West CH10180-10400
ITP-010-A1-LOT-001 | ITP-010-A1-LOT-001 - Hume Hwy North - Ch 70320 - Ch 70460- SB - Double Sides
ITP-010-A1-LOT-002 | ITP-010-A1-LOT-002 - Hume Hwy South - Ch 70140 - Ch 70204 - NB - Double sides
ITP-010-A1-LOT-003 | ITP-010-A1-LOT-003 - Hume Hwy North - Ch 70315 - Ch 70386 - NB -Double sides
ITP-010-A1-LOT-004 | ITP-010-A1-LOT-004- Hume Hwy North - Ch 70386 - Ch 70436 - NB- One side
ITP-010-A1-LOT-005 | ITP-010-A1-LOT-005- Hume Hwy North - Ch 70460- Ch 70490 - SB- West side
ITP-010-A2-LOT-001 | ITP-010-A2-LOT-001 - Mickleham South CH30070-CH30234
ITP-010-A2-LOT-002 | ITP-010-A2-LOT-002 - Mickleham South CH30234-CH30316
ITP-010-A2-LOT-003 | ITP-010-A2-LOT-003 - Mickleham North Southbound ( CH 30520- 30785)
ITP-010-A2-LOT-004 | ITP-010-A2-LOT-004 - Mickleham North ( CH 30520- CH 30785 ) NB
ITP-010-A2-LOT-005 | ITP-010-A2-LOT-005 - Mickleham South CH30316-CH30370
ITP-010-A2-LOT-006 | ITP-010-A2-LOT-006 - Mickleham South (CH30316-CH30370)
ITP-010-A2-LOT-007 | ITP-010-A2-LOT-007 - Zone 7 West of mick Rd ( CH 20070- CH 20175 )
ITP-010-A2-LOT-008 | ITP-010-A2-LOT-008 - Zone 7 East (CH 10500 - CH 10850 ) - NOT USED
ITP-010-A2-LOT-009 | ITP-010-A2-LOT-009 - Zone 7 East (CH 10600- CH 10780)
ITP-010-A2-LOT-010 | ITP-010-A2-LOT-010 - Zone 7 West (CH 10050 - 10098)
ITP-010-A2-LOT-011 | ITP-010-A2-LOT-011 - Zone 7 East (CH 10780 - 10850)
ITP-010-A2-LOT-012 | ITP-010-A2-LOT-012 - Mickleham North - Pavement 6 (CH30785-CH30845)
ITP-010-A2-LOT-013 | ITP-010-A2-LOT-013 - Mickleham Intersection - SE Traffic Island (CH10550 - CH10560)
ITP-010-A2-LOT-014 | ITP-010-A2-LOT-014 - Zone 7 West CH10000-CH10180
ITP-010-A2-LOT-015 | ITP-010-A2-LOT-015 - Mickleham North (SB) + NE Traffic Island (CH40500-CH40360)
ITP-010-A2-LOT-016 | ITP-010-A2-LOT-016 - Mickleham South CH29980-CH30070
ITP-010-A2-LOT-017 | ITP-010-A2-LOT-017 - Mickleham North CH30430-CH30520 NB
ITP-010-A2-LOT-018 | ITP-010-A2-LOT-018 - Mickleham Intersection CH20475-CH20500 NW Island
ITP-010-A2-LOT-019 | ITP-010-A2-LOT-019 - Zone 7 East WB - CH10850 to CH10950
ITP-010-A2-LOT-020 | ITP-010-A2-LOT-020 - Zone 7 East WB - CH10920 to CH11020
ITP-010-A2-LOT-021 | ITP-010-A2-LOT-021 - Zone 7 East WB - CH11070 to CH11140
ITP-010-A2-LOT-022 | ITP-010-A2-LOT-022 - Zone 7 East WB - CH10880 to 11020
ITP-010-A2-LOT-023 | ITP-010-A2-LOT-023 - Zone 7 East WB - CH11020 to 11110
ITP-010-A2-LOT-024 | ITP-010-A2-LOT-024 - Craigieburn Rd WB - CH10910-10840
ITP-010-AX-LOT-XXX | ITP-010-AX-LOT-XXX - Desc
ITP-011-A2-LOT-001 | ITP-011-A2-LOT-001 - Mickleham South CH30070 - CH30234
ITP-011-A2-LOT-002 | ITP-011-A2-LOT-002 - Mickleham South CH30000 - CH30200
ITP-011-A2-LOT-003 | ITP-011-A2-LOT-003 - Mickleham South CH30234 - CH30316
ITP-011-A2-LOT-004 | ITP-011-A2-LOT-004 - Mickleham North (Northbound) CH30520 - CH30665
ITP-011-A2-LOT-005 | ITP-011-A2-LOT-005 - Mickleham North (Southbound) CH30520 - CH30575
ITP-011-A2-LOT-006 | ITP-011-A2-LOT-006 - Mickleham North CH30665 - CH30820
ITP-011-A2-LOT-007 | ITP-011-A2-LOT-007 - Mickleham North CH30575 - CH30665
ITP-011-A2-LOT-008 | ITP-011-A2-LOT-008 - Mickleham South (NB) CH30316 - CH30400
ITP-011-A2-LOT-012 | ITP-011-A2-LOT-012 - Mickleham South CH30316 - CH30375
ITP-011-A2-LOT-013 | ITP-011-A2-LOT-013 - Mickleham North (Northbound) CH30430 - CH30470
ITP-011-A2-LOT-014 | ITP-011-A2-LOT-014 - Mickleham North (Southbound) CH30400 - CH30520
ITP-011-A2-LOT-015 | ITP-011-A2-LOT-015 - Mickleham North (Northbound) CH30470 - CH30520
ITP-011-A2-LOT-016 | ITP-011-A2-LOT-016 - Mickleham Intersection CH30400 - CH30430
ITP-011-A2-LOT-017 | ITP-011-A2-LOT-017 - Zone 7 East (WB) CH10590 - CH10620
ITP-011-A2-LOT-018 | ITP-011-A2-LOT-018 - Mickleham Intersection (SE SLIP LANE + WB CARRIAGEWAY) CH10550 - CH10590
ITP-011-A2-LOT-019 | ITP-011-A2-LOT-019 - Mickleham Intersection (NE Slip Lane + East Bound Carriageway) CH20520 - CH20570
ITP-011-A2-LOT-020 | ITP-011-A2-LOT-020 - Mickleham Rd Intersection NW Slip Lane CH20470 - CH20490
ITP-011-A2-LOT-021 | ITP-011-A2-LOT-021 - Mickleham to Debonair CH10830-CH11300
ITP-012-A2-LOT-001 | ITP-012-A2-LOT-001 - Zone 7 West (CH 10050 - 10098)
ITP-012-A2-LOT-002 | ITP-012-A2-LOT-002 - Zone 7 East (CH 10600 - 10850)
ITP-012-A2-LOT-003 | ITP-012-A2-LOT-003 - Mickleham South (NB+SB) CH30105-CH30234
ITP-012-A2-LOT-004 | ITP-012-A2-LOT-004 - Mickleham North (Media) CH30510-CH30700
ITP-012-A2-LOT-005 | ITP-012-A2-LOT-005 - Mickleham North (SB + Verge) CH30510-CH30785
ITP-012-A2-LOT-006 | ITP-012-A2-LOT-006 - Mickleham North (NB) CH30510-CH30665
ITP-012-A2-LOT-007 | ITP-012-A2-LOT-007 - Mickleham South (NB) CH30234-CH30365
ITP-012-A2-LOT-008 | ITP-012-A2-LOT-008 - Mickleham South (Median) CH30285-CH30365
ITP-012-A2-LOT-009 | ITP-012-A2-LOT-009 - Mickleham North (SB + Verge) CH40190-CH40300
ITP-012-A2-LOT-010 | ITP-012-A2-LOT-010 - Mickleham North (NB) CH30455-CH30510
ITP-012-A2-LOT-011 | ITP-012-A2-LOT-011 - Mickleham North (SB) CH30455-CH30510
ITP-012-A2-LOT-012 | ITP-012-A2-LOT-012 - Mickleham South(Bullnose) CH30375-CH30385
ITP-012-A2-LOT-013 | ITP-012-A2-LOT-013 - Mickleham Intersection (NB+SB+EB) Traffic Islands - CH10490-CH10550
ITP-012-A2-LOT-014 | ITP-012-A2-LOT-014 - Mickleham Intersection (SE Verge) - CH10540-CH10600
ITP-012-A2-LOT-015 | ITP-012-A2-LOT-015 - Mickleham North (NB + SB) - CH40330-CH40470
ITP-017-A1-LOT-001 | ITP-017-A1-LOT-001 - Stormwater Drainage - Pit 1002 to Pit 1001 - Hume Hwy southbound Xing - Z1
ITP-017-A1-LOT-002 | ITP-017-A1-LOT-002 - Stormwater Drainage - Pit 1014 to Pit 1015
ITP-017-A1-LOT-003 | ITP-017-A1-LOT-003 - Stormwater Drainage - Pit 1015 to Pit 1016
ITP-017-A1-LOT-004 | ITP-017-A1-LOT-004 - Stormwater Drainage - Pit 1016 to Pit 1017
ITP-017-A1-LOT-005 | ITP-017-A1-LOT-005 - Stormwater Drainage - Pit 1017 to Pit 1018
ITP-017-A1-LOT-006 | ITP-017-A1-LOT-006 - Stormwater Drainage - Pit 1018 to Pit 1019
ITP-017-A1-LOT-007 | ITP-017-A1-LOT-007 - Stormwater Drainage - Pit 1019 to Pit 1020
ITP-017-A1-LOT-008 | ITP-017-A1-LOT-008 - Stormwater Drainage - Pit 1020 to Pit 1021
ITP-017-A1-LOT-009 | ITP-017-A1-LOT-009 - Stormwater Drainage - Pit 1021 to Pit 1022
ITP-017-A1-LOT-010 | ITP-017-A1-LOT-010 - Stormwater Drainage - Pit 1002 to Pit 1003
ITP-017-A1-LOT-011 | ITP-017-A1-LOT-011 - Stormwater Drainage - Pit 1002 to Pit 1007
ITP-017-A1-LOT-012 | ITP-017-A1-LOT-012 - Stormwater Drainage - Pit 1003 to Pit 1004
ITP-017-A1-LOT-013 | ITP-017-A1-LOT-013 - Stormwater Drainage - Pit 1003 to Pit 1006
ITP-017-A1-LOT-014 | ITP-017-A1-LOT-014 - Stormwater Drainage - Pit 1004 to Pit 1005
ITP-017-A1-LOT-015 | ITP-017-A1-LOT-015 - Stormwater Drainage - Pit 1007 to Pit 1008
ITP-017-A1-LOT-016 | ITP-017-A1-LOT-016 - Stormwater Drainage - Pit 1007 to Pit 1009
ITP-017-A1-LOT-017 | ITP-017-A1-LOT-017 - Stormwater Drainage - Pit 1009 to Pit 1010
ITP-017-A1-LOT-018 | ITP-017-A1-LOT-018 - Stormwater Drainage - Head wall 1000 to Pit 1001
ITP-017-A1-LOT-019 | ITP-017-A1-LOT-019 - Stormwater Drainage - Pit 226 to Pit 227
ITP-017-A1-LOT-020 | ITP-017-A1-LOT-020 - Stormwater Drainage - Pit 227 to Pit 228
ITP-017-A1-LOT-021 | ITP-017-A1-LOT-021 - Stormwater Drainage - Pit 228 to Pit 230
ITP-017-A1-LOT-022 | ITP-017-A1-LOT-022 - Stormwater Drainage - Pit 230 to Pit 231
ITP-017-A1-LOT-023 | ITP-017-A1-LOT-023 - Stormwater Drainage - Pit 231 to Pit 232
ITP-017-A1-LOT-024 | ITP-017-A1-LOT-024 - Stormwater Drainage - Pit 232 to Pit 233
ITP-017-A1-LOT-025 | ITP-017-A1-LOT-025 - Stormwater Drainage - Pit 233 to Pit 234
ITP-017-A1-LOT-026 | ITP-017-A1-LOT-026 - RCBC - Hume South Median - Pit 1011 to Pit 1012
ITP-017-A1-MI-005 | ITP-017-A1-MI-005 - Hume North & South Median 375mm RCP
ITP-017-A2-LOT-001 | ITP-017-A2-LOT-001 - Stormwater Drainage - Pit 582 to Pit 583 - Zone 7 East Mickleham to Debonair (Westbound)
ITP-017-A2-LOT-002 | ITP-017-A2-LOT-002 - Stormwater Drainage - Pit 578 to Pit 579 - Zone 7 East Mickleham to Debonair (Westbound)
ITP-017-A2-LOT-003 | ITP-017-A2-LOT-003 - Stormwater Drainage - Pit 579 to Pit 580 - Zone 7 East Mickleham to Debonair (Westbound)
ITP-017-A2-LOT-004 | ITP-017-A2-LOT-004 - Stormwater Drainage - Pit 580 to Pit 581A - Zone 7 East Mickleham to Debonair (Westbound)
ITP-017-A2-LOT-005 | ITP-017-A2-LOT-005 - Stormwater Drainage - Pit 581A to Pit 581 - Zone 7 East Mickleham to Debonair (Westbound)
ITP-017-A2-LOT-006 | ITP-017-A2-LOT-006 - Stormwater Drainage - Pit 581 to Pit 582 - Zone 7 East Mickleham to Debonair (Westbound)
ITP-017-A2-LOT-007 | ITP-017-A2-LOT-007 - Stormwater Drainage - Pit 577 to Pit 578 - Zone 7 East Mickleham to Debonair (Westbound)
ITP-017-A2-LOT-008 | ITP-017-A2-LOT-008 - Stormwater Drainage - Pit 583 to Pit 584 - Zone 7 East Mickleham to Debonair (Westbound)
ITP-017-A2-LOT-009 | ITP-017-A2-LOT-009 - Stormwater Drainage - Pit 584 to Pit 585 - Zone 7 East Mickleham to Debonair (Westbound)
ITP-017-A2-LOT-010 | ITP-017-A2-LOT-010 - Stormwater Drainage - Pit 573 to Pit 573a - Zone 7 East Mickleham to Debonair (Westbound)
ITP-017-A2-LOT-011 | ITP-017-A2-LOT-011 - Stormwater Drainage - Pit 575 to Pit 576 - Zone 7 East Mickleham to Debonair (Westbound)
ITP-017-A2-LOT-012 | ITP-017-A2-LOT-012 - Stormwater Drainage - Pit 576 to Pit 577 - Zone 7 East Mickleham to Debonair (Westbound)
ITP-017-A2-LOT-013 | ITP-017-A2-LOT-013 - Stormwater Drainage - Pit 999 to Pit 1000 - Zone 7 West Stage 1 (Westbound)
ITP-017-A2-LOT-014 | ITP-017-A2-LOT-014 - Mickleham North. ( Pit 1042-1041)
ITP-017-A2-LOT-015 | ITP-017-A2-LOT-015 - Mickleham North (Pit 1041-1040)
ITP-017-A2-LOT-016 | ITP-017-A2-LOT-016 - Mickleham North (Pit 1040-1039)
ITP-017-A2-LOT-017 | ITP-017-A2-LOT-017 - Mickleham North ( Pit 1039-1038)
ITP-017-A2-LOT-018 | ITP-017-A2-LOT-018 - Mickleham North (Pit 1038-1037)
ITP-017-A2-LOT-019 | ITP-017-A2-LOT-019 - Mickleham North (Pit 1037-1036)
ITP-017-A2-LOT-020 | ITP-017-A2-LOT-020 - Mickleham North (Pit 1036-1035)
ITP-017-A2-LOT-021 | ITP-017-A2-LOT-021 - Mickleham North (Pit 1035-1034)
ITP-017-A2-LOT-022 | ITP-017-A2-LOT-022 - Mickleham North (Pit 1034-1033)
ITP-017-A2-LOT-023 | ITP-017-A2-LOT-023 - Mickleham Intersection ( Pit 1048-1047)
ITP-017-A2-LOT-024 | ITP-017-A2-LOT-024 - Mickleham Intersection ( Pit 1047-1046)
ITP-017-A2-LOT-025 | ITP-017-A2-LOT-025 - Mickleham Intersection ( Pit 1046-1045)
ITP-017-A2-LOT-026 | ITP-017-A2-LOT-026 - Mickleham Intersection ( Pit 1045-1044 )
ITP-017-A2-LOT-027 | ITP-017-A2-LOT-027 - Mickleham Intersection ( Pit 1044-1043)
ITP-017-A2-LOT-028 | ITP-017-A2-LOT-028 - Mickleham Intersection ( M1-M2)
ITP-017-A2-LOT-029 | ITP-017-A2-LOT-029 - Mickleham Intersection ( 1049-1048)
ITP-017-A2-LOT-030 | ITP-017-A2-LOT-030 - Mickleham Intersection (1049-1050)
ITP-017-A2-LOT-031 | ITP-017-A2-LOT-031 - Mickleham Intersection (1191-1192)
ITP-017-A2-LOT-032 | ITP-017-A2-LOT-032 - Mickleham Intersection (1192-1193)
ITP-017-A2-LOT-033 | ITP-017-A2-LOT-033 - Mickleham Intersection (997-998)
ITP-017-A2-LOT-034 | ITP-017-A2-LOT-034 - Mickleham Intersection (996-997)
ITP-017-A2-LOT-037 | ITP-017-A2-LOT-037 - Mickleham Intersection SE (1193-998)
ITP-017-A2-LOT-038 | ITP-017-A2-LOT-038 - Mickleham Intersection NE (1050-994)
ITP-017-A2-LOT-039 | ITP-017-A2-LOT-039 - Mickleham Intersection (993-1088)
ITP-017-A2-LOT-040 | ITP-017-A2-LOT-040 - Mickleham Intersection (Pit 1013 - pit 1014)
ITP-017-A2-LOT-041 | ITP-017-A2-LOT-041 - Mickleham Intersection NW (1014-1015)
ITP-017-A2-LOT-042 | ITP-017-A2-LOT-042 - Mickleham Intersection SE (1178-1178a)
ITP-017-A2-LOT-043 | ITP-017-A2-LOT-043 - Mickleham Intersection (1178-1177)
ITP-017-A2-LOT-044 | ITP-017-A2-LOT-044 - Mickleham Intersection (1177-1066)
ITP-017-A2-LOT-045 | ITP-017-A2-LOT-045 - Mickleham Intersection (1177-1176)
ITP-017-A2-LOT-046 | ITP-017-A2-LOT-046 - Mickleham Intersection (1176-1015)
ITP-017-A2-LOT-047 | ITP-017-A2-LOT-047 - Mickleham North NB (1069-1116)
ITP-017-A2-LOT-048 | ITP-017-A2-LOT-048 - Mickleham North (1096-1097)
ITP-017-A2-LOT-049 | ITP-017-A2-LOT-049 - Mickleham North (1079-1080)
ITP-017-A2-LOT-050 | ITP-017-A2-LOT-050 - Mickleham North (1092-1093)
ITP-017-A2-LOT-051 | ITP-017-A2-LOT-051 - Mickleham North NB (1161-1162)
ITP-017-A2-LOT-052 | ITP-017-A2-LOT-052 - Mickleham Intersection (Pit 1014 - pit 1159)
ITP-017-A2-LOT-054 | ITP-017-A2-LOT-054 - Stormwater Drainage - Pit 573 to Pit 573a - Zone 7 East Mickleham to Debonair (Westbound)
ITP-017-A2-LOT-055 | ITP-017-A2-LOT-055 - Stormwater Drainage - Pit 573a to Pit 573b - Zone 7 East Mickleham to Debonair (Westbound)
ITP-017-A2-LOT-056 | ITP-017-A2-LOT-056 - Stormwater Drainage - Pit 573b to Pit 573c - Zone 7 East Mickleham to Debonair (Westbound)
ITP-017-A2-LOT-057 | ITP-017-A2-LOT-057 - Stormwater Drainage - Pit 573b to Pit 572a - Zone 7 East Mickleham to Debonair (Westbound)
ITP-017-A2-LOT-058 | ITP-017-A2-LOT-058 - Stormwater Drainage - Pit 572a to Pit 572 - Zone 7 East Mickleham to Debonair (Westbound)
ITP-017-A2-LOT-059 | ITP-017-A2-LOT-059 - Stormwater Drainage - Pit 572 to Pit 571 - Zone 7 East Mickleham to Debonair (Westbound)
ITP-017-A2-LOT-060 | ITP-017-A2-LOT-060 - Stormwater Drainage - Pit 571 to Pit 569 - Zone 7 East Mickleham to Debonair (Westbound)
ITP-017-A2-LOT-061 | ITP-017-A2-LOT-061 - Stormwater Drainage - Pit 569 to Pit 568 - Zone 7 East Mickleham to Debonair (Westbound)
ITP-017-A2-LOT-062 | ITP-017-A2-LOT-062 - Stormwater Drainage - Pit 568 to Pit 567 - Zone 7 East Mickleham to Debonair (Westbound)
ITP-017-A2-LOT-063 | ITP-017-A2-LOT-063 - Stormwater Drainage - Pit 567 to Pit 587a - Zone 7 East Mickleham to Debonair (Westbound)
ITP-017-A2-LOT-064 | ITP-017-A2-LOT-064 - Stormwater Drainage - Pit 567 to Pit 567a - Zone 7 East Mickleham to Debonair (Westbound)
ITP-017-A2-LOT-065 | ITP-017-A2-LOT-065 - Stormwater Drainage - Pit 567a to Pit 567b - Zone 7 East Mickleham to Debonair (Westbound)
ITP-017-A2-LOT-066 | ITP-017-A2-LOT-066 - Stormwater Drainage - Pit 567b to Pit 567c - Zone 7 East Mickleham to Debonair (Westbound)
ITP-017-A2-LOT-067 | ITP-017-A2-LOT-067 - Stormwater Drainage - Pit 567b to Pit 566a - Zone 7 East Mickleham to Debonair (Westbound)
ITP-017-A2-LOT-068 | ITP-017-A2-LOT-068 - Stormwater Drainage - Pit 566a to Pit 565 - Zone 7 East Mickleham to Debonair (Westbound)
ITP-017-A2-LOT-069 | ITP-017-A2-LOT-069 - Stormwater Drainage - Pit 565 to Pit 564 - Zone 7 East Mickleham to Debonair (Westbound)
ITP-017-A2-LOT-070 | ITP-017-A2-LOT-070 - Stormwater Drainage - Pit 564 to Pit 563 - Zone 7 East Mickleham to Debonair (Westbound)
ITP-017-A2-LOT-071 | ITP-017-A2-LOT-071 - Stormwater Drainage - Pit 563 to Pit 562 - Zone 7 East Mickleham to Debonair (Westbound)
ITP-017-A2-LOT-072 | ITP-017-A2-LOT-072 - Stormwater Drainage - Pit 562 to Pit 561 - Zone 7 East Mickleham to Debonair (Westbound)
ITP-017-A2-LOT-073 | ITP-017-A2-LOT-073 - Mickleham Intersection (Pit 994- pit 995)
ITP-017-A2-LOT-074 | ITP-017-A2-LOT-074 - Stormwater Drainage - Pit 557A to Pit 556 - Zone 7 East Debonair to Vantage (Westbound)
ITP-017-A2-LOT-075 | ITP-017-A2-LOT-075 - Stormwater Drainage - Pit 556 to Pit 556A - Zone 7 East Debonair to Vantage (Westbound)
ITP-017-A2-LOT-076 | ITP-017-A2-LOT-076 - Stormwater Drainage - Pit 556A to Pit 555 - Zone 7 East Debonair to Vantage (Westbound)
ITP-017-A2-LOT-077 | ITP-017-A2-LOT-077 - Stormwater Drainage - Pit 555 to Pit 554 - Zone 7 East Debonair to Vantage (Westbound)
ITP-017-A2-LOT-078 | ITP-017-A2-LOT-078 - Stormwater Drainage - Pit 554 to Pit 553 - Zone 7 East Debonair to Vantage (Westbound)
ITP-017-A2-LOT-079 | ITP-017-A2-LOT-079 - Stormwater Drainage - Pit 553 to Pit 552 - Zone 7 East Debonair to Vantage (Westbound)
ITP-017-A2-LOT-080 | ITP-017-A2-LOT-080 - Stormwater Drainage - Pit 552 to Pit 551 - Zone 7 East Debonair to Vantage (Westbound)
ITP-017-A2-LOT-081 | ITP-017-A2-LOT-081 - Stormwater Drainage - Pit 551 to Pit 550 - Zone 7 East Debonair to Vantage (Westbound)
ITP-017-A2-LOT-082 | ITP-017-A2-LOT-082 - Stormwater Drainage - Pit 550 to Pit 549 - Zone 7 East Debonair to Vantage (Westbound)
ITP-017-A2-LOT-083 | ITP-017-A2-LOT-083 - Stormwater Drainage - Pit 549 to Pit 548 - Zone 7 East Debonair to Vantage (Westbound)
ITP-017-A2-LOT-084 | ITP-017-A2-LOT-084 - Stormwater Drainage - Pit 548 to Pit 547 - Zone 7 East Debonair to Vantage (Westbound)
ITP-017-A2-LOT-085 | ITP-017-A2-LOT-085 - Stormwater Drainage - Pit 547 to Pit 546 - Zone 7 East Debonair to Vantage (Westbound)
ITP-017-A2-LOT-086 | ITP-017-A2-LOT-086 - Stormwater Drainage - Pit 546 to Pit 545 - Zone 7 East Debonair to Vantage (Westbound)
ITP-017-A2-LOT-087 | ITP-017-A2-LOT-087 - Stormwater Drainage - Pit 545 to Pit 545A - Zone 7 East Debonair to Vantage (Westbound)
ITP-017-A2-LOT-088 | ITP-017-A2-LOT-088 - Stormwater Drainage - Pit 545A to Pit 544 - Zone 7 East Debonair to Vantage (Westbound)
ITP-017-A2-LOT-089 | ITP-017-A2-LOT-089 - Mickleham North East ( Pit 992-993)
ITP-017-A2-LOT-090 | ITP-017-A2-LOT-090 - Mickleham North East ( Pit 993-1088)
ITP-017-A2-LOT-091 | ITP-017-A2-LOT-091 - Mickleham North East ( Pit 1088-1087)
ITP-017-A2-LOT-092 | ITP-017-A2-LOT-092 - Mickleham North East ( Pit 1087-1086)
ITP-017-A2-LOT-093 | ITP-017-A2-LOT-093 - Stormwater Drainage - Pit 1210 to Pit 1165 - Zone 7 West Stage 1 (Westbound)
ITP-017-A2-LOT-094 | ITP-017-A2-LOT-094 - Stormwater Drainage - Pit 1165 to Pit 1166 - Zone 7 West Stage 1 (Westbound)
ITP-017-A2-LOT-095 | ITP-017-A2-LOT-095 - Stormwater Drainage - Pit 1166 to Pit 1167 - Zone 7 West Stage 1 (Westbound)
ITP-017-A2-LOT-096 | ITP-017-A2-LOT-096 - Stormwater Drainage - Pit 1167 to Pit 1168 - Zone 7 West Stage 1 (Westbound)
ITP-017-A2-LOT-097 | ITP-017-A2-LOT-097 - Stormwater Drainage - Pit 1168 to Pit 1169 - Zone 7 West Stage 1 (Westbound)
ITP-017-A2-LOT-098 | ITP-017-A2-LOT-098 - Stormwater Drainage - Pit 1169 to Pit 1170 - Zone 7 West Stage 1 (Westbound)
ITP-017-A2-LOT-099 | ITP-017-A2-LOT-099 - Stormwater Drainage - Pit 1170 to Pit 1171 - Zone 7 West Stage 1 (Westbound)
ITP-017-A2-LOT-100 | ITP-017-A2-LOT-100 - Stormwater Drainage - Pit 1171 to Pit 1172 - Zone 7 West Stage 1 (Westbound)
ITP-017-A2-LOT-101 | ITP-017-A2-LOT-101 - Stormwater Drainage - Pit 1172 to Pit 1173 - Zone 7 West Stage 1 (Westbound)
ITP-017-A2-LOT-102 | ITP-017-A2-LOT-102 - Stormwater Drainage - Pit 1173 to Pit 1174 - Zone 7 West Stage 1 (Westbound)
ITP-017-A2-LOT-103 | ITP-017-A2-LOT-103 - Stormwater Drainage - Pit 1174 to Pit 1175 - Zone 7 West Stage 1 (Westbound)
ITP-017-A2-LOT-104 | ITP-017-A2-LOT-104 - Stormwater Drainage - Pit 1175 to Pit 1176 - Zone 7 West Stage 1 (Westbound)
ITP-017-A2-LOT-105 | ITP-017-A2-LOT-105 - Mickleham South East ( Pit 998-688ac)
ITP-017-A2-LOT-106 | ITP-017-A2-LOT-106 - Mickleham South East ( Pit 688ac-688ad)
ITP-017-A2-LOT-107 | ITP-017-A2-LOT-107 - Mickleham Intersection (NE) ( Pit 995-996)
ITP-017-A2-LOT-108 | ITP-017-A2-LOT-108 - Mickleham North ( Pit 1042-1043)
ITP-017-A2-LOT-109 | ITP-017-A2-LOT-109 - Mickleham South ( Pit 1180-1181)
ITP-017-A2-LOT-110 | ITP-017-A2-LOT-110 - Mickleham South ( Pit 1184-1185)
ITP-017-A2-LOT-111 | ITP-017-A2-LOT-111 - Mickleham South ( Pit 1186-1187)
ITP-017-A2-LOT-112 | ITP-017-A2-LOT-112 - Mickleham South ( Pit 1188-1189)
ITP-017-A2-LOT-113 | ITP-017-A2-LOT-113 - Mickleham Intersection (NE) ( Pit 994-1190)
ITP-017-A2-LOT-114 | ITP-017-A2-LOT-114 - Mickleham North ( Pit 1117-1118)
ITP-017-A2-LOT-115 | ITP-017-A2-LOT-115 - Zone 7 East - Mickleham to Debonair WB - Pit 561 to 560
ITP-017-A2-LOT-116 | ITP-017-A2-LOT-116 - Zone 7 East - Mickleham to Debonair WB - Pit 560 to 559
ITP-017-A2-LOT-117 | ITP-017-A2-LOT-117 - Zone 7 East - Mickleham to Debonair WB - Pit 559 to 558
ITP-017-A2-LOT-118 | ITP-017-A2-LOT-118 - Debonair Intersection WB - Pit 558 to 558b
ITP-017-A2-LOT-119 | ITP-017-A2-LOT-119 - Debonair Intersection WB - Pit 558b to 557a
ITP-017-A2-LOT-120 | ITP-017-A2-LOT-120 - Zone 7 East - Mickleham to Debonair WB - Pit 558a to 558
ITP-017-A2-LOT-121 | ITP-017-A2-LOT-121 - Debonair Intersection WB - Pit 450 to 450a
ITP-017-A2-LOT-122 | ITP-017-A2-LOT-122 - Stormwater Drainage - Pit 1176 to Pit 1177 - Zone 7 West Stage 1 (SW Intersection)
ITP-017-A2-LOT-123 | ITP-017-A2-LOT-123 - Stormwater Drainage - Pit 1177 to Pit 1178 - Zone 7 West Stage 1 (SW Intersection)
ITP-017-A2-LOT-124 | ITP-017-A2-LOT-124 - Stormwater Drainage - Pit 1177 to Pit 1066 - Zone 7 West Stage 1 (SW Intersection)
ITP-017-A2-LOT-125 | ITP-017-A2-LOT-125 - Stormwater Drainage - Pit 1176 to Pit 1015 - Zone 7 West Stage 1 (SW Intersection)
ITP-017-A2-LOT-126 | ITP-017-A2-LOT-126 - Stormwater Drainage - Pit 1049 to Pit 688ab - Zone 7 Mickleham Rd North (Southbound)
ITP-017-A2-LOT-127 | ITP-017-A2-LOT-127 - Stormwater Drainage - Pit 1047 to Pit 1047a - Zone 7 Mickleham Rd North (Southbound)
ITP-017-A2-LOT-128 | ITP-017-A2-LOT-128 - Stormwater Drainage - Pit 1045 to Pit 1163 - Zone 7 Mickleham Rd North (Southbound)
ITP-017-A2-LOT-129 | ITP-017-A2-LOT-129 - Stormwater Drainage - Pit 1043 to Pit 1160 - Zone 7 Mickleham Rd North (Southbound)
ITP-017-A2-LOT-130 | ITP-017-A2-LOT-130 - Stormwater Drainage - Pit 1041 to Pit 688aa - Zone 7 Mickleham Rd North (Southbound)
ITP-017-A2-LOT-131 | ITP-017-A2-LOT-131 - Stormwater Drainage - Pit 1037 to Pit 688a - Zone 7 Mickleham Rd North (Southbound)
ITP-017-A2-LOT-132 | ITP-017-A2-LOT-132 - Stormwater Drainage - Pit 1035 to Pit 1059 - Zone 7 Mickleham Rd North (Southbound)
ITP-017-A2-LOT-133 | ITP-017-A2-LOT-133 - Stormwater Drainage - Pit 847 to Pit 846 - Zone 7 East Debonair to Vantage (Westbound) (Superseded by 136)
ITP-017-A2-LOT-135 | ITP-017-A2-LOT-135 - Stormwater Drainage - Pit 558 to Pit 558C - Zone 7 East Mickleham to Debonair
ITP-017-A2-LOT-136 | ITP-017-A2-LOT-136 - Stormwater Drainage - Pit 847 to Pit 846 - Zone 7 East Debonair to vantage
ITP-017-A2-LOT-137 | ITP-017-A2-LOT-137 - Stormwater Drainage - Pit 846 to Pit 845A - Zone 7 East Debonair to vantage
ITP-017-A2-LOT-138 | ITP-017-A2-LOT-138 - Stormwater Drainage - Pit 845A to Pit 845 - Zone 7 East Debonair to vantage
ITP-017-A2-LOT-139 | ITP-017-A2-LOT-139 - Stormwater Drainage - Pit 845 to Pit 844A - Zone 7 East Debonair to vantage
ITP-017-A2-LOT-140 | ITP-017-A2-LOT-140 - Stormwater Drainage - Pit 844A to Pit 844 - Zone 7 East Debonair to vantage
ITP-026-A2-LOT-001 | ITP-026-A2-LOT-001- Mickleham South (NB) CH30000 - CH30234
ITP-026-A2-LOT-002 | ITP-026-A2-LOT-002 - Mickleham South (Median) CH30120 - CH30360
ITP-026-A2-LOT-003 | ITP-026-A2-LOT-003 - Mickleham South (SB) CH40050 - CH40280
ITP-026-A2-LOT-004 | ITP-026-A2-LOT-004 - Mickleham South (NB) CH30234 - CH30365
ITP-026-A2-LOT-005 | ITP-026-A2-LOT-005 - Mickleham North (SB) CH40640 - CH40720
ITP-026-A2-LOT-006 | ITP-026-A2-LOT-006 - Mickleham North (NB) CH30615 - CH30700
ITP-026-A2-LOT-007 | ITP-026-A2-LOT-007 - Mickleham North (Median) CH30433 - CH30680
ITP-026-A2-LOT-008 | ITP-026-A2-LOT-008 - Mickleham North (NB) CH30450 - CH30605
ITP-026-A2-LOT-009 | ITP-026-A2-LOT-009 - Mickleham North (SB) CH40490 - CH40560
ITP-026-A2-LOT-010 | ITP-026-A2-LOT-010 - Zone 7 West
ITP-026-A2-LOT-011 | ITP-026-A2-LOT-011 - Zone 7 East - CH10600-10820
ITP-040-UT-LOT-001 | ITP-040-UT-LOT-001 - G1747 Gas Protection Works - Waterview Blvd NW corner
ITP-040-UT-LOT-002 | ITP-040-UT-LOT-002 - G1753 - North-South crossing, intersection of CRG Rd & Champion Pde
ITP-040-UT-LOT-003 | ITP-040-UT-LOT-003- G1747 Gas Protection Works - water view NW corner
ITP-040-UT-LOT-004 | ITP-040-UT-LOT-004 - G1730 Gas Protection Bridgewater rd intersection
ITP-040-UT-LOT-005 | ITP-040-UT-LOT-005 - G1763 Gas Protection Debonair Pde
ITP-040-UT-LOT-006 | ITP-040-UT-LOT-006 - G1702 Gas Protection Hardy Ave
ITP-040-UT-LOT-007 | ITP-040-UT-LOT-007 - G1745 Gas Protection East Side of Aitken
ITP-040-UT-LOT-008 | ITP-040-UT-LOT-008 - G1709 & G1710 Gas Protection Crossing Benston St
ITP-040-UT-LOT-009 | ITP-040-UT-LOT-009 - G1712,G173,G1714 - Newbold Ave
ITP-040-UT-LOT-010 | ITP-040-UT-LOT-010 - G1718 Plumpton Ave
ITP-040-UT-LOT-011 | ITP-040-UT-LOT-011 - G1758 Highlander East
ITP-040-UT-LOT-012 | ITP-040-UT-LOT-012 - G1757 Highlander West
ITP-040-UT-LOT-013 | ITP-040-UT-LOT-013 - G1760 Vantage Blvd
ITP-041-UT-LOT-001 | ITP-041-UT-LOT-001 - Private water service - East of Selwyn Area 1 (50mm)
ITP-042-UT-LOT-001 | ITP-042-UT-LOT-001 - OF1738 - East of Bridgwater Rd - 35m
ITP-042-UT-LOT-002 | ITP-042-UT-LOT-002 - OF1707, OF1708, OF1709, OF17115 - Between Hardy Ave & Benston St - 120m
ITP-042-UT-LOT-003 | ITP-042-UT-LOT-003
ITP-042-UT-LOT-004 | ITP-042-UT-LOT-004 - OF1773 - East of Aitkens - 20m
ITP-042-UT-LOT-005 | ITP-042-UT-LOT-005 - OF17108 - North-South, east side of Mickleham Rd intersection
ITP-042-UT-LOT-006 | ITP-042-UT-LOT-006 - T1726 East - West Crossing Mickleham Rd
ITP-042-UT-LOT-007 | ITP-042-UT-LOT-007 - T1726 East-West Crossing Mickleham Rd Sub Lot 001
ITP-042-UT-LOT-008 | ITP-042-UT-LOT-008 - T1726 East-West Crossing Mickleham Rd Sub Lot 002
ITP-043-UT-LOT-001 | ITP-043-UT-LOT-001 - E1754 - North-East side of Waterview Blvd - 40m
ITP-043-UT-LOT-002 | ITP-043-UT-LOT-002 - E1748 - North-South, east of Aitken Blvd - 25m
ITP-043-UT-LOT-003 | ITP-043-UT-LOT-003 - E1738 - East-West crossing, west of Waterview Blvd & CRG Rd - 15m
ITP-043-UT-LOT-004 | ITP-043-UT-LOT-004 - E1769 - East of carpark entrance Area 1 - 7m
ITP-045-UT-LOT-001 | ITP-045-UT-LOT-001 - HUME HIGHWAY
ITP-045-UT-LOT-002 | ITP-045-UT-LOT-002 - CRAIGIEBURN ROAD/CRAIGIEBURN ROAD WEST
ITP-045-UT-LOT-003 | ITP-045-UT-LOT-003 - P.O.S BETWEEN BENSTON STREET AND HARD AVENUE
ITP-045-UT-LOT-004 | ITP-045-UT-LOT-004 - HANSON ROAD
ITP-045-UT-LOT-005 | ITP-045-UT-LOT-005 - P.O.S BETWEEN RAYFIELD AVENUE AND BELSAY PLACE
ITP-045-UT-LOT-006 | ITP-045-UT-LOT-006 - CFA STATION ACCESS
ITP-045-UT-LOT-007 | ITP-045-UT-LOT-007 - BRIDGEWATER ROAD
ITP-045-UT-LOT-008 | ITP-045-UT-LOT-008 - CIMBERWOOD DRIVE
ITP-045-UT-LOT-009 | ITP-045-UT-LOT-009 - DORCHESTER ROAD
ITP-045-UT-LOT-010 | ITP-045-UT-LOT-010 - LYGON DRIVE
ITP-045-UT-LOT-011 | ITP-045-UT-LOT-011 - MAIN STREET/BALYANG WAY
ITP-045-UT-LOT-012 | ITP-045-UT-LOT-012 - AITKEN BOULEVARD/SHOPPING CENTRE ACCESS
ITP-045-UT-LOT-013 | ITP-045-UT-LOT-013 - CRAIGIEBURN ROAD/AITKEN BOULEVARD
ITP-045-UT-LOT-014 | ITP-045-UT-LOT-014 - WATERVIEW BOULEVARD
ITP-045-UT-LOT-015 | ITP-045-UT-LOT-015 - HIGHLANDER DRIVE/VANTAGE BOULEVARD
ITP-045-UT-LOT-016 | ITP-045-UT-LOT-016 - MICKLEHAM ROAD
ITP-054-A2-LOT-011 | ITP-054-A2-LOT-011 - Maintenance Strip Install - Mickleham Road North, S/Bound CH40640-40685
ITP-054-A2-LOT-012 | ITP-054-A2-LOT-012 - Maintenance Strip Install - Mickleham Road North, S/Bound CH40685-40715
ITP-054-A2-LOT-013 | ITP-054-A2-LOT-013 - SUP - Zone 7 East, SE Corner of Mickleham Intersection (CH10545-10620)
ITP-054-A2-LOT-014 | ITP-054-A2-LOT-014 - SUP - Zone 7 East, SE Corner of Mickleham Intersection (CH10543-10551)
ITP-054-A2-LOT-015 | ITP-054-A2-LOT-015 - Maintenance Strip Install - Mickleham Road North, N/Bound CH30480-30605
ITP-060-UT-LOT-001 | ITP-060-UT-LOT-001 - Lighting Zone 1 - Hume Hwy to Hard Ave
ITP-060-UT-LOT-002 | ITP-060-UT-LOT-002 - Lighting Zone 2 - Hardy to Rayfield Ave
ITP-060-UT-LOT-003 | ITP-060-UT-LOT-003 - Lighting Zone 3 - Rayfield to Dorchester
ITP-060-UT-LOT-004 | ITP-060-UT-LOT-004 - Lighting Zone 4 - Dorchester to Aitken Blvd
ITP-060-UT-LOT-005 | ITP-060-UT-LOT-005 - Lighting Zone 5 - Aitken Blvd
ITP-060-UT-LOT-006 | ITP-060-UT-LOT-006 - Lighting Zone 6 - Aitken Blvd to Champion
ITP-060-UT-LOT-007 | ITP-060-UT-LOT-007 - Lighting Zone 7A - Champion to Debonair
ITP-060-UT-LOT-008 | ITP-060-UT-LOT-008 - Lighting Zone 7B - Mickleham Road
ITP-065-A1-LOT-001 | ITP-065-A1-LOT-001 - WRSB Anchor Block Pour - Hume Hwy North median - Northbound and Southbound
ITP-066-A1-LOT-001 | ITP-066-A1-LOT-001 - Directional Drilling
ITP-074-A2-LOT-001 | ITP-074-A2-LOT-001 - Zone 7 West - CH 10090-CH 10240
ITP-074-A2-LOT-002 | ITP-074-A2-LOT-002 - Zone 7 West - CH 10240 - CH 10295
ITP-074-A2-LOT-003 | ITP-074-A2-LOT-003 - Zone 7 West - CH 10360 - CH 10490
ITP-074-A2-LOT-004 | ITP-074-A2-LOT-004 - Zone 7 West - CH 10295 - CH 10360
ITP-075-A2-LOT-001 | ITP-075-A2-LOT-001 - Zone 7 West Craigieburn Rd - CH10040-10175 - Base Layer
ITP-075-A2-LOT-002 | ITP-075-A2-LOT-002 - Zone 7 West Craigieburn Rd - CH10040-10175 - Intermediate Layer
ITP-075-A2-LOT-003 | ITP-075-A2-LOT-003 - Zone 7 West Pavement 6 Area - CH10000-10040 - Base Layer
ITP-075-A2-LOT-004 | ITP-075-A2-LOT-004 - Zone 7 West Pavement 6 Area - CH10000-10040 - Intermediate Layer
ITP-075-A2-LOT-005 | ITP-075-A2-LOT-005 - Zone 7 East Type 1 base course - CH10650 to CH10780
ITP-075-A2-LOT-006 | ITP-075-A2-LOT-006 - Zone 7 East Type 1 base course - CH10780 to ch10850
ITP-075-A2-LOT-007 | ITP-075-A2-LOT-007 - Zone 7 East Type 1 intermediate - CH10650 to CH10780
ITP-075-A2-LOT-008 | ITP-075-A2-LOT-008 - Zone 7 East Type 1 intermediate layer - CH10780 to ch10850
ITP-075-A2-LOT-009 | ITP-075-A2-LOT-009 - Mickleham South (SB) Layer 1 SF - CH40050-CH40240
ITP-075-A2-LOT-010 | ITP-075-A2-LOT-010 - Mickleham South (NB) Layer 1 SF - CH30100-CH30320
ITP-075-A2-LOT-011 | ITP-075-A2-LOT-011 - Mickleham South (SB) Layer 2 SI - CH30102-CH30316
ITP-075-A2-LOT-012 | ITP-075-A2-LOT-012 - Mickleham South Layer1 SF - CH30020-CH30100
ITP-075-A2-LOT-013 | ITP-075-A2-LOT-013 - Mickleham South (NB) - Layer 2 (SI) - CH30020-CH30316
ITP-075-A2-LOT-014 | ITP-075-A2-LOT-014 - Mickleham North (SB+NB) - Layer 1 (SF) - CH40500-CH40750
ITP-075-A2-LOT-015 | ITP-075-A2-LOT-015 - Mickleham North (SB+NB) - Layer 2 (SI) - CH30520-CH30785
ITP-075-A2-LOT-016 | ITP-075-A2-LOT-016 - Mickleham South - Pavement 6 Area - Layer 1 (SI) - CH29980-CH30020
ITP-075-A2-LOT-017 | ITP-075-A2-LOT-017 - Mickleham Intersection (SB) - Layer 1 (SF) - CH40240-CH40500
ITP-075-A2-LOT-018 | ITP-075-A2-LOT-018 - Mickleham Intersection (NB) - Layer 1 (SF) - CH30320-CH30570
ITP-075-A2-LOT-019 | ITP-075-A2-LOT-019 - Mickleham Intersection (NB+SB) - Layer 2(SI) - CH30316-CH30520
ITP-075-A2-LOT-020 | ITP-075-A2-LOT-020 - Mickleham Intersection (West going EB) - Layer 1 (SF) - CH20470-CH20490
ITP-075-A2-LOT-021 | ITP-075-A2-LOT-021 - Mickleham Intersection (West Sliplane going WB) - Layer 2(SI) - CH10550-CH10570
ITP-075-A2-LOT-022 | ITP-075-A2-LOT-022 - Mickleham South - Pavement 6 Area - Layer 2 (SI) - CH29980-CH30020
ITP-075-A2-LOT-023 | ITP-075-A2-LOT-023 - Mickleham Intersection (SE Sliplane - WB) - Layer 1 (SF) - CH10550-CH10570
ITP-075-A2-LOT-024 | ITP-075-A2-LOT-024 - Mickleham South (SB) - Layer 2 (SI) - CH40210-CH40350
ITP-075-A2-LOT-025 | ITP-075-A2-LOT-025 - Mickleham Intersection (West - EB) - Layer 2 (SI) - CH20470-CH20490
ITP-075-A2-LOT-026 | ITP-075-A2-LOT-026 - Mickleham Intersection (North-West sliplane) - Layer 1 (SF) - CH20470-CH20490
ITP-075-A2-LOT-027 | ITP-075-A2-LOT-027 - Mickleham Intersection (EB lane) - Layer 1 (SF) - CH20515-CH20530
ITP-075-A2-LOT-028 | ITP-075-A2-LOT-028 - Mickleham Intersection (WB Lane) - Layer 1 (SF) - CH10570-CH10650
ITP-075-A2-LOT-029 | ITP-075-A2-LOT-029 - Mickleham Intersection (North-West sliplane) - Layer 2 (SI) - CH20470-CH20490
ITP-075-A2-LOT-030 | ITP-075-A2-LOT-030 - Mickleham Intersection (EB lane) - Layer 2 (S1) - CH20515-CH20555
ITP-075-A2-LOT-031 | ITP-075-A2-LOT-031 - Mickleham Intersection (WB Lane) - Layer 2 (SI) - CH10570-CH10650
ITP-075-A2-LOT-032 | ITP-075-A2-LOT-032 - Mickleham North - Regulation Layer (SI) - CH30785 - CH 30850
ITP-075-A2-LOT-033 | ITP-075-A2-LOT-033 - Mickleham North - Layer 1 (SI) - CH30785 - CH30850
ITP-075-A2-LOT-034 | ITP-075-A2-LOT-034 - Mickleham North - Layer 2 (SI) - CH30785 - CH30850
ITP-078-A2-LOT-004 | ITP-078-A2-LOT-004 - Zone 7 East Guard rail ground Beam ch10850 to CH10750, 10610 to 10630
ITP-078-A2-LOT-006 | ITP-078-A2-LOT-006 - Zone 7 East Guard rail ground Beam ch10750 to ch10720, 10630 to 10650
ITP-078-A2-LOT-007 | ITP-078-A2-LOT-007 - Zone 7 East Guard rail ground Beam ch10650 to ch10750
ITP-078-A2-LOT-008 | ITP-078-A2-LOT-008 (DUPLICATE) - Zone 7 East Guard rail ground Beam CH10550 to CH10650
ITP-078-A2-LOT-008 | ITP-078-A2-LOT-008 (DUPLICATE) - Zone 7 Mickleham Road - Pit 1088 Base
ITP-078-A2-LOT-009 | ITP-078-A2-LOT-009 - Zone 7 Mickleham Road - Pit 1088 - Walls
ITP-078-A2-LOT-010 | ITP-078-A2-LOT-010 - Zone 7 Mickleham Road - Pit 1088 - Soffit
ITP-078-A2-LOT-011 | ITP-078-A2-LOT-011 - Zone 7 Mickleham Road - Pit 1087 - Base
ITP-078-A2-LOT-012 | ITP-078-A2-LOT-012 - Zone 7 Mickleham Road - Pit 1087 - Walls
ITP-078-A2-LOT-013 | ITP-078-A2-LOT-013 - Zone 7 Mickleham Road - Pit 1087 - Soffit
ITP-078-A2-LOT-014 | ITP-078-A2-LOT-014 - Zone 7 Mickleham Road - Pit 993 - Base Slab + Walls
ITP-078-A2-LOT-015 | ITP-078-A2-LOT-015 - Zone 7 Mickleham Road - Pit 993 - Haunch + Slab
ITP-078-A2-LOT-016 | ITP-078-A2-LOT-016 - Zone 7 Mickleham Road - Pit 994 - Base Slab + Walls
ITP-078-A2-LOT-017 | ITP-078-A2-LOT-017 - Zone 7 Mickleham Road - Pit 994 - Haunch + Slab
ITP-078-A2-LOT-018 | ITP-078-A2-LOT-018 - Zone 7 Mickleham Road - Pit 995 - Base Slab
ITP-078-A2-LOT-019 | ITP-078-A2-LOT-019 - Zone 7 Mickleham Road - Pit 995 - Walls
ITP-078-A2-LOT-020 | ITP-078-A2-LOT-020 - In-situ Drainage Headwall 992 - Base
ITP-078-A2-LOT-021 | ITP-078-A2-LOT-021 - In-situ Drainage Headwall 992 - Wings
ITP-079-UT-LOT-001 | ITP-079-UT-LOT-001 - Church Watermain
ITP-079-UT-LOT-002 | ITP-079-UT-LOT-002 - Church Watermain
ITP-079-UT-LOT-003 | ITP-079-UT-LOT-003 - Church Watermain
ITP-079-UT-LOT-004 | ITP-079-UT-LOT-004 - Church Watermain
ITP-079-UT-LOT-005 | ITP-079-UT-LOT-005 - RW1712 Champion 180PE Recycled water
ITP-079-UT-LOT-006 | ITP-079-UT-LOT-006 - W1758 150mm Potable water Steel Main
ITP-079-UT-LOT-007 | ITP-079-UT-LOT-007 - RW1708 Recycled water relocation Aitken Blvd to Waterview Blvd
ITP-079-UT-LOT-008 | ITP-079-UT-LOT-008 - RW1707 Recycled Water Relocation 280PE - Balyang