## ITP
|  |  | Inspection and Test Plan - Topsoil Placement and Landscaping | [7 empty] | Document # 1145-C200-FUL-QAC-ITP-0049
[11 empty] | Revision: 00 | Date: 15/07/2022
Client: | MRPV |  | Construction Process: | Topsoil Placement and Landscaping |  | Prepared by: |  | Reviewed by: |  |  | Approved by:
Project: | Craigieburn Road Upgrade |  |  |  |  | Name: | Mario Jayaweera | Name: | Jonathon Rock |  | Name: | Babak Rudd
Contract No: | 1145 |  | Specifications: | Contract Specification Sections 3020 VicRoads Sections 720 (Nov 2018) |  | Position: Undergraduate Engineer |  | Position: Site Engineer |  |  | Position: Project Quality Manager
Structure / Component:
Date: |  |  | Location: | CRG Project-wide |  | Date: 15/07/2022 |  | Date: 15/07/2022 |  |  | Date: 15/07/2022
Lot No: | ITP-049-AX-LOT-XXX |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item No. | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
|  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Superintendent | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check that current revision drawings are being used |  | Prior to Commencing Work | Refer to latest drawings and latest available revision used | IFC Project Drawings/ Drawing Register | Document Review | Latest Revision Drawings | IP | Site Engineer / Site Foreman | N/A |  | N/A
1.2 | Submissions and records |  | Prior to commencing works | Samples, records and certificates shall be provided to the Superintendent at least 10 working days prior to bulk delivery. Following information shall be provided to the superintendent: Inspections: • Plant stock for all plant species Samples: • Mulch • Imported topsoil Records: • Evidence of origin of indigenous provenance plant material • Analysis certificates for grass seed • Details of suppliers • Soil tests on imported topsoil • Copies of fertiliser labels Enter Teambinder Approval #: [free text box] | VicRoads Standard Section 720.03 | Document Review | Records & Certificates uploaded to teambinder | AP | Site Engineer / VicRoads Superintendent |  |  | N/A
1.3 | Supply of mulch |  | Prior to commencing works | Site mulch available from the chipping of on-site indigenous or non-weed vegetation shall be used where possible. All wood mulch shall be supplied, delivered, handled and applied in accordance with AS 4454, and shall comply with Table 720.044 | VicRoads Standard Section 720.04 VicRoads Standard Table 720.044 AS4454 | Verify | This ITP signed off | IP | Site Engineer | N/A
1.4 | Supply of topsoil |  | Prior to commencing works | Site topsoil shall be used wherever possible, in preference to imported topsoil. Where imported topsoil is used, the topsoil must conform to the properties specified in Table 720.042 | VicRoads Standard Section 720.04 VicRoads Standard Table 720.042 | Verify | This ITP signed off | IP | Site Engineer | N/A
2 | Construction Works
2.1 | Setting out planting areas |  | Each applicable lot | Planting areas are to be set out to the location and shape specified in the landscape drawings. Plant density requirements and planting offsets established in the plant schedule are to be adhered to. Plants shall be placed as shown on the drawings. | VicRoads Standard Section 720.06 | Verify | This ITP signed off | IP | Site Engineer | N/A
2.2 | Site Preparation |  | Each applicable lot | Soil preparation shall be in accordance with Table 720.071 | VicRoads Standard Section 720.07 VicRoads Standard Table 720.071 | Verify | This ITP signed off | IP | Site Engineer | N/A
2.3 | Ripping of subsoil |  | Each applicable lot | All ripping works shall conform to the requirements of Cl 720.07 (b). Ripped areas of planting, individual tree planting and grassing are to be made available for inspection prior to mulching, planting or grassing, and shall not proceed until the Superintendent acknowledges requirements for ripping have been met. | VicRoads Standard Section 720.07(b) | Verify | This ITP signed off | HP | Site Engineer / VicRoads Superintendent
2.4 | Topsoil Placement |  | At completion of works | All disturbed and/or not paved areas shall be topsoiled according to Section 204 of VicRoads Standard for Roadworks and Bridge works, to the following minimum depths: • Batter slopes > 2:1 = 50mm • Tree and shrub plantation bed areas = 100mm • Verge, 50mm outer edge / 20mm when within 100mm of the edge of seal or asphalt surface treatment • All other areas - 75mm Following subsoil preparation, topsoil shall be spread on planting areas and grassed areas. Topsoil shall not be compacted. | Project Spec. Cl.3020.07(k) VicRoads Standard Section 204.17 VicRoads Standard Section 720.07 | Site Inspection | Signed ITP | IP | Site Engineer | N/A |  | N/A
2.5 | Cultivation |  | Each applicable lot | Cultivation shall be undertaken to break soil down to a tilth with 80% of the volume composed of clods less than 50 mm in diameter Prior to mulching, planting or grassing, area to be presented to Superintendent for approval. In areas where topsoiling or cultivation is not practicable, the Contractor shall submit alternative methods to achieve an equivalent result to the Superintendent for review. | VicRoads Standard Section 720.07 | Verify | This ITP signed off | HP | Site Engineer / VicRoads Superintendent
2.6 | Bulk density of soils for planting and grassing |  | Each applicable lot | After cultivation and trimming, the Contractor may lightly compress topsoil for stability on slopes. Vibrating plates shall not be used. Ensure the dry bulk density does not exceed the limits in Table 720.072 | VicRoads Standard Section 720.07 | Verify | This ITP signed off | IP | Site Engineer / Site Foreman | N/A
2.7 | Topsoil finished surface levels |  | Each applicable lot | The finished level of grassed areas shall be: (i) not higher than 125 mm below weep-holes or damp-proof courses in adjacent walls; (ii) level with the bottom of fence plinths; (iii) level with adjacent pavements, kerbs, pits and other structures. The finished level of garden bed mulch and/or topsoil shall be tapered so that the finished mulch and/or topsoil levels meet flush with the adjacent surfaces. | VicRoads Spec. Section 720.07 | Verify | This ITP signed off | IP | Site Engineer / Site Foreman | N/A
2.8 | Planting |  | Each applicable lot | Holes in heavy soils or on batters shall be prepared so as to ensure adequate drainage. Planting holes shall be backfilled with friable topsoil free of debris, rocks and clods greater than 50 mm in diameter. | VicRoads Standard Section 720.09 | Verify | This ITP signed off | IP | Site Engineer / Site Foreman | N/A
2.9 | Mulching |  | Each applicable lot | Install wood mulch to all Planting Areas unless otherwise specified. Mulch shall extend at least 1 metre beyond plant centres at the outer edges of all Planting Areas. If space does not permit this in median, separator or splitter-island planting, mulching shall extend to the back of kerb. The Contractor shall install 2 metre diameter mulch rings around all Individual Tree Plantings. Mulch depths in all situations shall be a minimum 75 mm and maximum 125 mm. | VicRoads Standard Section 720.08 | Verify | This ITP signed off | IP | Site Engineer / Site Foreman | N/A
2.1 | Grassing of disturbed areas |  | Once installation of assets completed | All disturbed areas shall be topsoiled and grassed, all areas to be cultivated to a minimum 50mm depth, and moistened prior to the application of grass seed and fertiliser. A joint inspection of all grassed areas shall be carried out between the contractor and superintendent three months after sowing has taken place. | VicRoads Spec. Cl.708.20 | Visual Inspection | Site Photos | HP | Site Engineer / Superintendent |  |  | N/A
2.11 | Grassing |  | Each applicable lot | Grass seed shall be sown at minimum 100 kg/Ha (if drilled) or 200 kg/Ha (if broadcast), distributed evenly to achieve an even and dense grass cover. Germination rate shall be minimum 80% cover within 8 weeks and 95% cover within 3 months of sowing. | VicRoads Standard Section 720.10 | Verify | This ITP signed off | IP | Site Engineer / Site Foreman | N/A
3 | Completion
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date:
Work Completed On:
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent