## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-049-AX-LOT-XXX - Desc | itp |  |  |  |  | ITP 0049 - TOPSOIL PLACEMENT AND LANDSCAPING
section | Lot Information
checkpoint | 1.0 Lot Information
textbox | Lot Created On
textbox | Lot Opened On
textbox | Work Commenced On
dropdown | Lot Type | CIL - Civil
textbox | From and To Chainage
dropdown | Construction Element | LAND - Landscaping
dropdown | Activity | CULT - Cultivation, HARD - Hardscaping, HYDR - Hydroseeding, MAIN - Maintenance, PLAN - Planting, RIPP - Ripping, TOPS - Topsoil, WEED - Weed/Grass Management, WSRD - WSRD
dropdown | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
dropdown | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
textbox | Engineer Responsible
textbox | comments
section | 1 - Preliminary Works
checkpoint | 1.1 - Check that current revision drawings are being used
note | Frequency - Prior to Commencing Work
note | - - - - - - - - -
note | Acceptance Criteria - Refer to latest drawings and latest available revision used
note | - - - - - - - - -
note | Reference Documents - IFC Project Drawings / Drawing Register
note | - - - - - - - - -
note | Inspection / Test Method - Document Review
note | - - - - - - - - -
note | Record of conformity - Latest Revision Drawings
note | - - - - - - - - -
note | IP
note | - - - - - - - - -
note | Responsibility - Site Engineer / Site Foreman
note | - - - - - - - - -
textbox | Date Completed:
checkpoint | 1.2 - Submissions and records
note | Frequency - Prior to commencing works
note | - - - - - - - - -
note | Acceptance Criteria - Samples, records and certificates shall be provided to the Superintendent at least 10 working days prior to bulk delivery.
note | Following information shall be provided to the superintendent:
note | Inspections:
note | • Plant stock for all plant species
note | Samples:
note | • Mulch
note | • Imported topsoil
note | Records:
note | • Evidence of origin of indigenous provenance plant material
note | • Analysis certificates for grass seed
note | • Details of suppliers
note | • Soil tests on imported topsoil
note | • Copies of fertiliser labels
textbox | Enter Teambinder Approval #:
note | - - - - - - - - -
note | Reference Documents - VicRoads Standard Section 720.03
note | - - - - - - - - -
note | Inspection / Test Method - Document Review
note | - - - - - - - - -
note | Record of conformity - Records & Certificates uploaded to teambinder
note | - - - - - - - - -
note | AP
note | - - - - - - - - -
note | Responsibility - Site Engineer / VicRoads Superintendent
note | - - - - - - - - -
textbox | Date Completed:
checkpoint | 1.3 - Supply of mulch
note | Frequency - Prior to commencing works
note | - - - - - - - - -
note | Acceptance Criteria - Site mulch available from the chipping of on-site indigenous or non-weed vegetation shall be used where possible.
note | All wood mulch shall be supplied, delivered, handled and applied in accordance with AS 4454, and shall comply with Table 720.044
note | - - - - - - - - -
note | Reference Documents - VicRoads Standard Section 720.04
note | VicRoads Standard Table 720.044
note | AS4454
note | - - - - - - - - -
note | Inspection / Test Method - Verify
note | - - - - - - - - -
note | Record of conformity - This ITP signed off
note | - - - - - - - - -
note | IP
note | - - - - - - - - -
note | Responsibility - Site Engineer
note | - - - - - - - - -
textbox | Date Completed:
checkpoint | 1.4 - Supply of topsoil
note | Frequency - Prior to commencing works
note | - - - - - - - - -
note | Acceptance Criteria - Site topsoil shall be used wherever possible, in preference to imported topsoil.
note | Where imported topsoil is used, the topsoil must conform to the properties specified in Table 720.042
note | - - - - - - - - -
note | Reference Documents - VicRoads Standard Section 720.04
note | VicRoads Standard Table 720.042
note | - - - - - - - - -
note | Inspection / Test Method - Verify
note | - - - - - - - - -
note | Record of conformity - This ITP signed off
note | - - - - - - - - -
note | IP
note | - - - - - - - - -
note | Responsibility - Site Engineer
note | - - - - - - - - -
textbox | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Setting out planting areas
note | Frequency - Each applicable lot
note | - - - - - - - - -
note | Acceptance Criteria - Planting areas are to be set out to the location and shape specified in the landscape drawings.
note | Plant density requirements and planting offsets established in the plant schedule are to be adhered to.
note | Plants shall be placed as shown on the drawings.
note | - - - - - - - - -
note | Reference Documents - VicRoads Standard Section 720.06
note | - - - - - - - - -
note | Inspection / Test Method - Verify
note | - - - - - - - - -
note | Record of conformity - This ITP signed off
note | - - - - - - - - -
note | IP
note | - - - - - - - - -
note | Responsibility - Site Engineer
note | - - - - - - - - -
textbox | Date Completed:
checkpoint | 2.2 - Site Preparation
note | Frequency - Each applicable lot
note | - - - - - - - - -
note | Acceptance Criteria - Soil preparation shall be in accordance with Table 720.071
note | - - - - - - - - -
note | Reference Documents - VicRoads Standard Section 720.07
note | VicRoads Standard Table 720.071
note | - - - - - - - - -
note | Inspection / Test Method - Verify
note | - - - - - - - - -
note | Record of conformity - This ITP signed off
note | - - - - - - - - -
note | IP
note | - - - - - - - - -
note | Responsibility - Site Engineer
note | - - - - - - - - -
textbox | Date Completed:
checkpoint | 2.3 - Ripping of subsoil
note | Frequency - Each applicable lot
note | - - - - - - - - -
note | Acceptance Criteria - All ripping works shall conform to the requirements of Cl 720.07 (b).
note | Ripped areas of planting, individual tree planting and grassing are to be made available for inspection prior to mulching, planting or grassing, and shall not proceed until the Superintendent acknowledges requirements for ripping have been met.
note | - - - - - - - - -
note | Reference Documents - VicRoads Standard Section 720.07(b)
note | - - - - - - - - -
note | Inspection / Test Method - Verify
note | - - - - - - - - -
note | Record of conformity - This ITP signed off
note | - - - - - - - - -
note | HP
note | - - - - - - - - -
note | Responsibility - Site Engineer / VicRoads Superintendent
note | - - - - - - - - -
textbox | Date Completed:
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Topsoil Placement
note | Frequency - At completion of works
note | - - - - - - - - -
note | Acceptance Criteria - All disturbed and/or not paved areas shall be topsoiled according to Section 204 of VicRoads Standard for Roadworks and Bridge works, to the following minimum depths:
note | • Batter slopes > 2:1 = 50mm
note | • Tree and shrub plantation bed areas = 100mm
note | • Verge, 50mm outer edge / 20mm when within 100mm of the edge of seal or asphalt surface treatment
note | • All other areas - 75mm
note | Following subsoil preparation, topsoil shall be spread on planting areas and grassed areas. Topsoil shall not be compacted.
note | - - - - - - - - -
note | Reference Documents - Project Spec. Cl.3020.07(k)
note | VicRoads Standard Section 204.17
note | VicRoads Standard Section 720.07
note | - - - - - - - - -
note | Inspection / Test Method - Site Inspection
note | - - - - - - - - -
note | Record of conformity - Signed ITP
note | - - - - - - - - -
note | IP
note | - - - - - - - - -
note | Responsibility - Site Engineer
note | - - - - - - - - -
textbox | Date Completed:
checkpoint | 2.5 - Cultivation
note | Frequency - Each applicable lot
note | - - - - - - - - -
note | Acceptance Criteria - Cultivation shall be undertaken to break soil down to a tilth with 80% of the volume composed of clods less than 50 mm in diameter
note | Prior to mulching, planting or grassing, area to be presented to Superintendent for approval.
note | In areas where topsoiling or cultivation is not practicable, the Contractor shall submit alternative methods to achieve an equivalent result to the Superintendent for review.
note | - - - - - - - - -
note | Reference Documents - VicRoads Standard Section 720.07
note | - - - - - - - - -
note | Inspection / Test Method - Verify
note | - - - - - - - - -
note | Record of conformity - This ITP signed off
note | - - - - - - - - -
note | HP
note | - - - - - - - - -
note | Responsibility - Site Engineer / VicRoads Superintendent
note | - - - - - - - - -
textbox | Date Completed:
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Bulk density of soils for planting and grassing
note | Frequency - Each applicable lot
note | - - - - - - - - -
note | Acceptance Criteria - After cultivation and trimming, the Contractor may lightly compress topsoil for stability on slopes.
note | Vibrating plates shall not be used. Ensure the dry bulk density does not exceed the limits in Table 720.072
note | - - - - - - - - -
note | Reference Documents - VicRoads Standard Section 720.07
note | - - - - - - - - -
note | Inspection / Test Method - Verify
note | - - - - - - - - -
note | Record of conformity - This ITP signed off
note | - - - - - - - - -
note | IP
note | - - - - - - - - -
note | Responsibility - Site Engineer / Site Foreman
note | - - - - - - - - -
textbox | Date Completed:
checkpoint | 2.7 - Topsoil finished surface levels
note | Frequency - Each applicable lot
note | - - - - - - - - -
note | Acceptance Criteria - The finished level of grassed areas shall be:
note | (i) not higher than 125 mm below weep-holes or damp-proof courses in adjacent walls;
note | (ii) level with the bottom of fence plinths;
note | (iii) level with adjacent pavements, kerbs, pits and other structures.
note | The finished level of garden bed mulch and/or topsoil shall be tapered so that the finished mulch and/or topsoil levels meet flush with the adjacent surfaces.
note | - - - - - - - - -
note | Reference Documents - VicRoads Spec. Section 720.07
note | - - - - - - - - -
note | Inspection / Test Method - Verify
note | - - - - - - - - -
note | Record of conformity - This ITP signed off
note | - - - - - - - - -
note | IP
note | - - - - - - - - -
note | Responsibility - Site Engineer / Site Foreman
note | - - - - - - - - -
textbox | Date Completed:
checkpoint | 2.8 - Planting
note | Frequency - Each applicable lot
note | - - - - - - - - -
note | Acceptance Criteria - Holes in heavy soils or on batters shall be prepared so as to ensure adequate drainage.
note | Planting holes shall be backfilled with friable topsoil free of debris, rocks and clods greater than 50 mm in diameter.
note | - - - - - - - - -
note | Reference Documents - VicRoads Standard Section 720.09
note | - - - - - - - - -
note | Inspection / Test Method - Verify
note | - - - - - - - - -
note | Record of conformity - This ITP signed off
note | - - - - - - - - -
note | IP
note | - - - - - - - - -
note | Responsibility - Site Engineer / Site Foreman
note | - - - - - - - - -
textbox | Date Completed:
checkpoint | 2.9 - Mulching
note | Frequency - Each applicable lot
note | - - - - - - - - -
note | Acceptance Criteria - Install wood mulch to all Planting Areas unless otherwise specified.
note | Mulch shall extend at least 1 metre beyond plant centres at the outer edges of all Planting Areas. If space does not permit this in median, separator or splitter-island planting, mulching shall extend to the back of kerb.
note | The Contractor shall install 2 metre diameter mulch rings around all Individual Tree Plantings.
note | Mulch depths in all situations shall be a minimum 75 mm and maximum 125 mm.
note | - - - - - - - - -
note | Reference Documents - VicRoads Standard Section 720.08
note | - - - - - - - - -
note | Inspection / Test Method - Verify
note | - - - - - - - - -
note | Record of conformity - This ITP signed off
note | - - - - - - - - -
note | IP
note | - - - - - - - - -
note | Responsibility - Site Engineer / Site Foreman
note | - - - - - - - - -
textbox | Date Completed:
checkpoint | 2.10 - Grassing of disturbed areas
note | Frequency - Once installation of assets completed
note | - - - - - - - - -
note | Acceptance Criteria - All disturbed areas shall be topsoiled and grassed, all areas to be cultivated to a minimum 50mm depth, and moistened prior to the application of grass seed and fertiliser.
note | A joint inspection of all grassed areas shall be carried out between the contractor and superintendent three months after sowing has taken place.
note | - - - - - - - - -
note | Reference Documents - VicRoads Spec. Cl.708.20
note | - - - - - - - - -
note | Inspection / Test Method - Visual Inspection
note | - - - - - - - - -
note | Record of conformity - Site Photos
note | - - - - - - - - -
note | HP
note | - - - - - - - - -
note | Responsibility - Site Engineer / Superintendent
note | - - - - - - - - -
textbox | Date Completed:
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.11 - Grassing
note | Frequency - Each applicable lot
note | - - - - - - - - -
note | Acceptance Criteria - Grass seed shall be sown at minimum 100 kg/Ha (if drilled) or 200 kg/Ha (if broadcast), distributed evenly to achieve an even and dense grass cover.
note | Germination rate shall be minimum 80% cover within 8 weeks and 95% cover within 3 months of sowing.
note | - - - - - - - - -
note | Reference Documents - VicRoads Standard Section 720.10
note | - - - - - - - - -
note | Inspection / Test Method - Verify
note | - - - - - - - - -
note | Record of conformity - This ITP signed off
note | - - - - - - - - -
note | IP
note | - - - - - - - - -
note | Responsibility - Site Engineer / Site Foreman
note | - - - - - - - - -
textbox | Date Completed:
section | 3 - Completion
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Work Completed On
textbox | Date:
section | Lot Verification
checkpoint | Lot Verification.
dropdown | Is the relevant RFI attached to the Lot? | YES,NO,N/A
dropdown | Is the relevant NCR attached to the Lot? | YES,NO,N/A
dropdown | Are any relevant Mails/ Transmittals attached to the Lot? | YES,NO,N/A
dropdown | Lot Plan or “Highlighted” IFC drawings (mud maps) attached to the Lot? | YES,NO,N/A
dropdown | Survey conformance records attached to the Lot? | YES,NO,N/A
dropdown | Subcontractor/ Supplier records attached to the Lot? | YES,NO,N/A
dropdown | Conforming Test Results attached to the Lot? | YES,NO,N/A
dropdown | As built records attached to the Lot? | YES,NO,N/A
dropdown | Lot verified By | Babak Rudd-Project Quality Manager, Steve Felsinger- Area Manager
dropdown | Lot Status | OUTSTANDING, CLOSED
textbox | Lot Closed On
textbox | comments