## ITP
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP009-11 - Electrical Fit-out of Existing SIT Pits | [5 empty] | ITP009-11 - Electrical Fit-out of Existing SIT Pits
section | 1.0 Electrical Fit-out of Existing SIT Pits
checkpoint | 1.1 - Isolation of Services and Preliminaries
label | Frequency: Prior to start
label | Acceptance Criteria: Prior to entering pit, power to be isolated to the satisfaction of the Principal and other relevant authorities. Equipment removed and pit cleaned.
label | Reference Documents:
label | • Drawing set ADE-EDAU21008-YMML-DD
label | • ADE-EDAU21008-TB-ver2.0
label | Inspection/ Test Method: Verify
label | Record of conformity: This ITP Signed / Avionics Checklist 011
label | HP*
label | Responsibility: Project Engineer / Avionics
text | Date Completed:
checkpoint | 1.2 - Installation
label | Frequency: Each Lot
label | Acceptance Criteria: Primary and secondary cables installed, along with transformers, primary connector joints, and earthing cable.
label | Reference Documents: Drawing set ADE-EDAU21008-YMML-DD
label | Inspection/ Test Method: Verify
label | Record of conformity: This ITP Signed / Avionics Checklist 011
label | IP
label | Responsibility: Project Engineer / Avionics
text | Date Completed:
checkpoint | 1.3 - Pit Closeout
label | Frequency: Each Lot
label | Acceptance Criteria: Earth cable terminated from lug and reposition SIT holder.
label | Reference Documents:
label | • Drawing set ADE-EDAU21008-YMML-DD
label | • ADE-EDAU21008-TB-ver2.0
label | Inspection/ Test Method: Verify
label | Record of conformity: This ITP Signed / Avionics Checklist 011
label | IP
label | Responsibility: Project Engineer / Avionics
text | Date Completed:
checkpoint | 1.4 - Testing
label | Frequency: Each Lot
label | Acceptance Criteria: Energise circuits and test lights.
label | Reference Documents: Drawing set ADE-EDAU21008-YMML-DD
label | Inspection/ Test Method: Verify
label | Record of conformity: This ITP Signed / Avionics Checklist 011
label | IP
label | Responsibility: Project Engineer / Avionics
text | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: