## ITP
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP009-3 - Demolition and Isolation Works | [5 empty] | ITP009-3 - Demolition and Isolation Works
section | 1.0 Preliminary Works
checkpoint | 1.1 - Preparation for the Works to be Undertaken
label | Frequency: Prior to Start
label | Acceptance Criteria:
label | • Notify the Airport’s Engineering personnel at least two days prior to removing the works area from service and prior to returning the works area to service.
label | • DWG ADE-EDAU21008-YMML-DD-002-2 used should additional information of works area be required.
label | Reference Documents:
label | • Drawing set ADE-EDAU21008-YMML-DD
label | • ADE-EDAU21008-TB-ver2.0
label | Inspection/ Test Method: Verify
label | Record of conformity: This ITP Signed / Aconex
label | HP*
label | Responsibility: Project Engineer
text | Date Completed:
checkpoint | 1.2 - AGL Continuity of Service
label | Frequency: Prior to Start
label | Acceptance Criteria:
label | • Ensure the continuity of service of the AGL facilities is maintained while undertaking the works.
label | • No outages of any facilities shall be permitted unless prior approval has been received by the Contractor from the Contract Administrator.
label | • DWG ADE-EDAU21008-YMML-DD-002-2 and technical specification used should additional information of works area be required.
label | Reference Documents:
label | • Drawing set ADE-EDAU21008-YMML-DD
label | • ADE-EDAU21008-TB-ver2.0
label | Inspection/ Test Method: Verify
label | Record of conformity: This ITP Signed
label | HP*
label | Responsibility: Project Engineer
text | Date Completed:
checkpoint | 1.3 - Check for correct documentation
label | Frequency: Prior to commencing any activity
label | Acceptance Criteria: Ensure that all employees and subcontractors are using the latest and complete set of drawings
label | Reference Documents: IFC Drawings
label | Inspection/ Test Method: Verify
label | Record of conformity: This ITP Signed
label | HP*
label | Responsibility: Project Engineer
text | Date Completed:
checkpoint | 1.4 - Implementation of all measures and controls
label | Frequency: Prior to commencing any activities
label | Acceptance Criteria:
label | • All necessary measures and controls are being implemented, that is PSP, EMP, TMP, SWMS & WP.
label | Reference Documents:
label | • PSP
label | • EMP
label | • TMP
label | • JSEA
label | • SWMS
label | • WP
label | Inspection/ Test Method: Verify
label | Record of conformity: Site and Office Inspection
label | HP*
label | Responsibility: Project Engineer / Site Supervisor
text | Date Completed:
section | 2.0 Demolition and Isolation Works
checkpoint | 2.1 - Investigation, Location, Identification, Protection, Modification, Isolation, Extension or Relocation of Existing Features
label | Frequency: Prior to commencing demolition works
label | Acceptance Criteria:
label | • The Contractor must:
label | – a. investigate and locate both above ground level features and below ground services that may be affected during the performance of the Work under the Contract;
label | – b. identify, protect, modify, extend or relocate existing features, services or facilities as necessary for the performance of the Work under the Contract to the satisfaction of the Principal and other relevant authorities;
label | – DWG ADE-EDAU21008-YMML-DD-002-2 used should additional information of works area be required.
label | Reference Documents:
label | • Drawing set ADE-EDAU21008-YMML-DD
label | • ADE-EDAU21008-TB-ver2.0
label | Inspection/ Test Method: Verify
label | Record of conformity: This ITP signed / Avionics Checklist 003
label | IP
label | Responsibility: Project Engineer/Avionics
text | Date Completed:
checkpoint | 2.2 - Demolition and/or removal of AGL
label | Frequency: Each Lot
label | Acceptance Criteria:
label | • Prior to any pavement overlay works, all light fittings and shallow bases impacted by the pavement reconstruction works shall be removed.
label | • The shallow bases shall be removed by neatly saw cutting a hole in the pavement slightly larger than the outside diameter of the light base.
label | Reference Documents:
label | • Drawing set ADE-EDAU21008-YMML-DD
label | • ADE-EDAU21008-TB-ver2.0
label | Inspection/ Test Method: Verify
label | Record of conformity: This ITP signed / Avionics Checklist 003
label | IP
label | Responsibility: Project Engineer/Avionics
text | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: