## ITP
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP009-4 - Installation of SIT Pits | [5 empty] | ITP009-4 - Installation of SIT Pits
section | 1.0 Installation of SIT Pits
checkpoint | 1.1 - Preparation for the Works to be Undertaken
label | Frequency: Prior to Start
label | Acceptance Criteria: Ensure survey set out is undergone, excavation permit obtained and (if required) services in work(s) area isolated.
label | Reference Documents:
label | • Drawing set ADE-EDAU21008-YMML-DD
label | • ADE-EDAU21008-TB-ver2.0
label | • Fulton Hogan Excavation Permit
label | Inspection/ Test Method: Verify
label | Record of conformity: This ITP Signed / Avionics Checklist 004
label | HP*
label | Responsibility: Project Engineer
text | Date Completed:
checkpoint | 1.2 - Pit excavation and placement
label | Frequency: Each Lot
label | Acceptance Criteria: Dig zone marked out and excavation undergone in accordance to relevant permit. Pit placed and levelled as per survey set out.
label | Reference Documents:
label | • Drawing set ADE-EDAU21008-YMML-DD
label | • ADE-EDAU21008-TB-ver2.0
label | Inspection/ Test Method: Verify
label | Record of conformity: This ITP Signed / Avionics Checklist 004
label | HP*
label | Responsibility: Project Engineer
text | Date Completed:
checkpoint | 1.3 - Conduit positioning
label | Frequency: Each Lot
label | Acceptance Criteria: Primary and secondary conduits positioned in pit according to IFC drawings.
label | Reference Documents: Drawing set ADE-EDAU21008-YMML-DD
label | Inspection/ Test Method: Verify
label | Record of conformity: This ITP Signed / Avionics Checklist 004
label | IP
label | Responsibility: Project Engineer
text | Date Completed:
checkpoint | 1.4 - Backfill and compaction of pit surrounds
label | Frequency: Each Lot
label | Acceptance Criteria: Each pit shall be backfilled and compacted as per specification.
label | Reference Documents: ADE-EDAU21008-TB-ver2.0
label | Inspection/ Test Method: Verify
label | Record of conformity: This ITP Signed / Avionics Checklist 004
label | IP
label | Responsibility: Project Engineer / Site Supervisor
text | Date Completed:
checkpoint | 1.5 - Pit close out
label | Frequency: Each Lot
label | Acceptance Criteria: Pits shall be labelled and directional markers placed. Lids to be secured and area cleaned/demolised.
label | Reference Documents: ADE-EDAU21008-TB-ver2.0
label | Inspection/ Test Method: Verify
label | Record of conformity: This ITP Signed / Avionics Checklist 004
label | IP
label | Responsibility: Project Engineer/Avionics
text | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: