## ITP
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP009-5 - Installation of Primary Cable | [5 empty] | ITP009-5 - Installation of Primary Cable
section | 1.0 Installation of Primary Cable
checkpoint | 1.1 - Isolation of Services
label | Frequency: Prior to start
label | Acceptance Criteria:
label | • Any services in the vicinity of work area(s) to be isolated to the satisfaction of the Principal and other relevant authorities.
label | • Ensure installation of primary cabling shall be made using latest revision of IFC drawing.
label | Reference Documents:
label | • Drawing set ADE-EDAU21008-YMML-DD
label | • ADE-EDAU21008-TB-ver2.0
label | Inspection/ Test Method: Verify
label | Record of conformity: This ITP Signed / Avionics Checklist 005
label | HP*
label | Responsibility: Project Engineer / Avionics
text | Date Completed:
checkpoint | 1.2 - Preparation and Setup
label | Frequency: Each Lot
label | Acceptance Criteria: Drums of cable set up, pit(s) opened, bollards placed to delineate open pit.
label | Reference Documents: Drawing set ADE-EDAU21008-YMML-DD
label | Inspection/ Test Method: Verify
label | Record of conformity: This ITP Signed / Avionics Checklist 005
label | IP
label | Responsibility: Project Engineer / Avionics
text | Date Completed:
checkpoint | 1.3 - Installation
label | Frequency: Each Lot
label | Acceptance Criteria: Draw rope installed in conduits to facilitate cable placement. Cables installed through pits with labels. SITs installed and cables tested.
label | Reference Documents:
label | • Drawing set ADE-EDAU21008-YMML-DD
label | • ADE-EDAU21008-TB-ver2.0
label | Inspection/ Test Method: Verify
label | Record of conformity: This ITP Signed / Avionics Checklist 005
label | IP
label | Responsibility: Project Engineer / Avionics
text | Date Completed:
checkpoint | 1.4 - Positioning and Demobilisation
label | Frequency: Each Lot
label | Acceptance Criteria: Equipment repositioned (if needed) ahead of closeout. Pit lids closed, bollards/other equipment removed and plant demobilised.
label | Reference Documents: Drawing set ADE-EDAU21008-YMML-DD
label | Inspection/ Test Method: Verify
label | Record of conformity: This ITP Signed / Avionics Checklist 005
label | IP
label | Responsibility: Project Engineer / Avionics
text | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: