## ITP
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP009-8 - Installation of Shallow Base Canister | [5 empty] | ITP009-8 - Installation of Shallow Base Canister
section | 1.0 Installation of Shallow Base Canister
checkpoint | 1.1 - Preparation for the Works to be Undertaken
label | Frequency: Prior to Start
label | Acceptance Criteria:
label | • Ensure survey set out is undergone, excavation permit obtained and (if required) services in work(s) area isolated.
label | • Lights, slot cuts, and aiming points marked out.
label | Reference Documents:
label | • Drawing set ADEEDAU21008-YMML-DD
label | • ADEEDAU21008-TB-ver2.0
label | Inspection/ Test Method: Verify
label | Record of conformity: This ITP Signed / Avionics Checklist 008
label | HP*
label | Responsibility: Project Engineer/Avionics
text | Date Completed:
checkpoint | 1.2 - Core and Cut
label | Frequency: Each Lot
label | Acceptance Criteria: Light base cored into pavement and slot from base cut to pavement edge/expansion joint
label | Reference Documents: Drawing set ADEEDAU21008-YMML-DD
label | Inspection/ Test Method: Verify
label | Record of conformity: This ITP Signed / Avionics Checklist 008
label | IP
label | Responsibility: Project Engineer/Avionics
text | Date Completed:
checkpoint | 1.3 - Base positioning
label | Frequency: Each Lot
label | Acceptance Criteria: Light base positioned and epoxy poured to secure. Installation of jig.
label | Reference Documents: Drawing set ADEEDAU21008-YMML-DD
label | Inspection/ Test Method: Verify
label | Record of conformity: This ITP Signed / Avionics Checklist 008
label | IP
label | Responsibility: Project Engineer/Avionics
text | Date Completed:
checkpoint | 1.4 - Cabling
label | Frequency: Each Lot
label | Acceptance Criteria: Cables ran and connected from new base via joints/slots/conduits to SIT pit.
label | Reference Documents: Drawing set ADEEDAU21008-YMML-DD
label | Inspection/ Test Method: Verify
label | Record of conformity: This ITP Signed / Avionics Checklist 008
label | IP
label | Responsibility: Project Engineer/Avionics
text | Date Completed:
checkpoint | 1.5 - Sealing
label | Frequency: Each Lot
label | Acceptance Criteria: Once cables installed, backing rod placed and expansion joints sealed with approved product.
label | Reference Documents: Drawing set ADEEDAU21008-YMML-DD
label | Inspection/ Test Method: Verify
label | Record of conformity: This ITP Signed / Avionics Checklist 008
label | IP
label | Responsibility: Project Engineer/Avionics
text | Date Completed:
checkpoint | 1.6 - Finishing, Testing, Demobilisation
label | Frequency: Each Lot
label | Acceptance Criteria: Gasket positioned on light top, light plugged and positioned to current orientation. Light tested and area cleaned before demobilisation.
label | Reference Documents:
label | • Drawing set ADEEDAU21008-YMML-DD
label | • ADEEDAU21008-TB-ver2.0
label | Inspection/ Test Method: Verify
label | Record of conformity: This ITP Signed / Avionics Checklist 008
label | IP
label | Responsibility: Project Engineer/Avionics
text | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: