## ITP
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP002 - Stripping, Bulk Exc, Fill and Subgrade Prep | [5 empty] | ITP002 - Stripping, Bulk Exc, Fill and Subgrade Prep
section | 1.0 Preliminary Activities
checkpoint | 1.1 - Inspection and Test Plan
label | Frequency: Prior to commencing works
label | Acceptance Criteria: Hold Point
label | • The Contractor must submit an Inspection and Test Plan to the Principal’s Representative for review, outlining the tests, frequencies of tests, certifications and Hold Points
label | Inspection/ Test Method: Verify
label | Record of conformity: This ITP signed
label | HP
label | Responsibility: Project Engineer/Principal's Representative
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Current Drawings being utilised
label | Frequency: Prior to commencing works
label | Acceptance Criteria:
label | • Current revision drawing is being used including the subcontractors copy.
label | • Current Revision to be obtained via Aconex
label | Reference Documents: Aconex
label | Inspection/ Test Method: Visual Inspection
label | Record of conformity: This ITP signed
label | IP
label | Responsibility: Project Engineer
text | Date Completed:
checkpoint | 1.3 - Survey
label | Frequency: Prior to commencing works
label | Acceptance Criteria: Area has been surveyed, highlighting any areas where excavations should not occur (e.g. exclusion zone)
label | Reference Documents:
label | • Drawings
label | • Permits
label | Inspection/ Test Method: Visual Inspection
label | Record of conformity: This ITP signed
label | IP
label | Responsibility: Project Engineer
text | Date Completed:
checkpoint | 1.4 - Native grass
label | Frequency: Prior to commencing works
label | Acceptance Criteria:
label | • APAM to confirm native grass permit.
label | • Surveyor to mark out the native grass area and place bollards/fencing along the boundary.
label | Reference Documents:
label | • EMP
label | • Native grass ITP No.29
label | Inspection/ Test Method: Visual Inspection
label | Record of conformity: This ITP signed
label | HP*
label | Responsibility: Project Engineer
text | Date Completed:
checkpoint | 1.5 - Implementation of all measures and controls
label | Frequency: Prior to works
label | Acceptance Criteria: All necessary measures and controls are being implemented, that is:
label | • PSP, EMP, TMP, SWMS and WP
label | Reference Documents:
label | • PSP
label | • EMP
label | • TMP
label | • SWMS
label | • WP
label | Inspection/ Test Method: Visual Inspection
label | Record of conformity: This ITP signed
label | HP*
label | Responsibility: Project Engineer
text | Date Completed:
checkpoint | 1.6 - APAM permits
label | Frequency: Prior to commencing works
label | Acceptance Criteria:
label | • Excavation permit and if working near HV electrical.
label | • An Electricity supply Isolation form and cabling permit has been issued from Melbourne Airport Fulton Hogan Excavation permit issued to plant operators prior to excavation works
label | Reference Documents:
label | • Excavation permit
label | Inspection/ Test Method: Approved permits
label | Record of conformity: This ITP signed
label | HP*
label | Responsibility: Project Engineer
text | Date Completed:
checkpoint | 1.7 - Maintenance of Pavements
label | Frequency: Prior to Commencing Works
label | Acceptance Criteria: Hold Point
label | • Prior to the use of any existing roads within the airport boundary and site access roads, the contractor shall carry out a site inspection and provide a dilapidation report.
label | Reference Documents: Aconex
label | Inspection/ Test Method: Verify
label | Record of conformity: This ITP signed
label | HP
label | Responsibility: Project Engineer/Principal's Representative
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.8 - Drainage of Earthworks
label | Frequency: Prior to Commencing Works
label | Acceptance Criteria:
label | • Fulton Hogan to submit dewatering plan for each area of the works prior to carrying out any excavations for pavement design subgrade level.
label | • As safely practical the contractor must keep all earthworks free from standing water and must provide sufficient pumps at low points and other special dewatering equipment for the disposal of all water encountered in the excavations.
label | • Including the installation of any design or temporary drainage works to allow for preparedness of pavement construction.
label | Inspection/ Test Method: Verify
label | Record of conformity: This ITP signed
label | HP*
label | Responsibility: Project Engineer
text | Date Completed:
checkpoint | 1.9 - Plant and Equipment
label | Frequency: Prior to Commencing Works
label | Acceptance Criteria:
label | • Plant and Equipment used in the works are appropriate to achieve specifications requirements.
label | • All plant inducted and inspected as per Fulton Hogan’s plant safety guidelines.
label | Inspection/ Test Method: Visual Inspection
label | Record of conformity: This ITP signed
label | HP*
label | Responsibility: Project Engineer
text | Date Completed:
section | 2.0 Stripping/Excavation to Subgrade
checkpoint | 2.1 - Site Preparation
label | Frequency: Each lot
label | Acceptance Criteria:
label | • All excavation and filling will be free draining to low points clear of the Works at all times;
label | • Sufficient pumps, well-points or other equipment for work area de-watered during the works shall be provided where required.
label | • Existing drainage lines and water mains found to be traversing the site must be removed as shown on drawings.
label | • Contractor must provide temporary pollution control devices or ponds in existing drainage systems and receiving waters.
label | Inspection/ Test Method: Visual Inspection
label | Record of conformity: This signed ITP
label | IP
label | Responsibility: Project Engineer
text | Date Completed:
checkpoint | 2.2 - Dust control
label | Frequency: Each Lot
label | Acceptance Criteria:
label | • Prevention of dust during earthworks and subgrade preparation (Water Cart, tarps etc.);
label | • Truck mounted water sprayer keeping dust moist to allow for reliable operation 24 hours per day.
label | Inspection/ Test Method: Visual Inspection
label | Record of conformity: This signed ITP
label | IP
label | Responsibility: Project Engineer
text | Date Completed:
checkpoint | 2.3 - Excavation
label | Frequency: Each Lot
label | Acceptance Criteria:
label | • Contractor shall excavate every type of material encountered within the limit of earthworks to the lines and levels indicated on the drawings.
label | • Where over-excavation occurs or filling is required the area must be filled with Class 3/4 crushed rock or profiling’s.
label | • All materials removed from excavations are to be classified by the contractor as topsoil, fill, concrete (for recycling) or unsuitable material.
label | Inspection/ Test Method: Inspection Point
label | Record of conformity: This signed ITP
label | IP
label | Responsibility: Project Engineer
text | Date Completed:
checkpoint | Final Inspection
label | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Print Name:
text | Position:
text | Date: