## ITP
|  |  | Inspection and Test Plan - Asphalt Placement | [7 empty] | Document # ITP-012
[11 empty] | Revision: 0.1 | Date : 22/8/2022
Client: | Melbourne Airport |  | Construction Process: | Asphalt Placement |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: | Melbourne Airport Runway 16-34 Overlay |  |  |  |  | Name: Noriko Wood |  | Name: |  |  | Name:
Contract: | 12554937 |  | Specifications: | Technical Specifications Melbourne Airport Runway 16-34 Overlay Schematic and Detailed Design GHD-DD-SPC-002 (14 June 2022) |  | Senior Pavement Engineer
|  |  | Location: | Fulton Hogan Infrastructure Services 500 Princes Hwy, Noble Park VIC 3174
Item No. | Task/Activity Description |  | Inspection / Controls and Verification Detail | [5 empty] | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility
|  |  | Frequency |  | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity
1 | Preliminary
1.01 | Supply of proprietary tack coat for use in asphalt placement works. |  | Prior to the commencement of asphalt placement works. |  | Submission of the properties, specifications and test requirements for proprietary tack coats. | GHD-DD-SPC-002 5107(g) HP5107-1 | Document | ITP | HP | Quality Manager
1.02 | Supply of asphalt to a nominated mix design. |  | Not less than twenty (20) working days prior to the scheduled commencement of asphalt production. |  | Submission of the proposed mix design for each nominal size asphalt mix including results of the mix design tests. | GHD-DD-SPC-002 5109(d) HP5109-1 | Document | NATA accredited test certificates, mix design report | HP | Quality Manager
1.03 | Calibration of straight edge. |  | Prior to the commencement of asphalt placement works. |  | Mobile straight edge equipment to be used in the asphalt laying works has been calibrated. | GHD-DD-SPC-002 5113(o) HP5113-2 | Calibration | Calibration report | HP | Quality Manager
1.04
1.05
2 | Trials
2.01 | Commencement of construction trial. |  | Not less than five (5) days prior to the scheduled commencement of asphalt paving works. Prior notice (minimum 48 hours) of commencement of trial to be given to Contract Administrator. |  | All resources required for a trial of minimum tonnage 40 t of each nominal mix size, placed in a minimum of two paving runs, with a joint suitable for testing, are available and all arrangements for the trial have been made. | GHD-DD-SPC-002 5111(a) HP5111-1 | Inspection | ITP | HP | Site Engineer
2.02 | Extraction of cores from construction trial sections. |  | At the completion of each construction trial, after the asphalt has cooled to ambient temperature and not more than 24 hours after construction. |  | A minimum of six (6) cores are cut from within lanes, and six (6) cores are cut over a joint. Cores are not less than 100 mm diameter and are cut from the finished asphalt construction trial section. | GHD-DD-SPC-002 5111(c), 5132(b) | AS 2891.1.2, AS 1289.1.4.2 | ITP | IP | Site Engineer
2.03 | Repair of core holes in construction trial sections. |  | At the completion of core extraction. |  | All debris, slurry and water has been removed from the core hole and the core walls and floor are completely dry prior to reinstatement. Tack coat has been applied to the walls and floor of core hole, and the hole reinstated with hot mix asphalt approved for use in this project and placed and compacted in lifts not more than 50 mm compacted thickness. The filled hole is flush to the surrounding pavement surface. | GHD-DD-SPC-002 5111(c), 5132(b) | Inspection | ITP | IP | Site Engineer
2.04 | Layer thickness of construction trial section. |  | At the completion of each construction trial and prior to the commencement of full scale production and placement of asphalt. |  | The average compacted layer thickness of a minimum of 4 cores is within the accepted range of: - Minimum of 40 mm and maximum of 85 mm for 14mm NMS asphalt, or - Minimum of 75 mm and maximum of 110 mm for 20mm NMS asphalt. | GHD-DD-SPC-002 5111(c), Table 5120-1, 5132(e) | AS 2891.1.2 | NATA accredited test certificates | TP | Site Engineer
2.05 | Compaction of construction trial section. |  | Within 24 hours after the completion of each construction trial. |  | Characteristic value of air voids are within the range of: - Surfacing layers: 3.0-6.5% inclusive for mat and 3.0-8.0% inclusive for joints, or - Base layers: 3.0-7.0% inclusive for mat. | GHD-DD-SPC-002 5111(c), 5121(c), 5132(c)(d) | AS 2891.9.1, AS 2891.9.2 | NATA accredited test certificates | TP | Site Engineer
2.06 | Finished surface levels of construction trial sections. |  | At the completion of each construction trial and prior to the commencement of full scale production and placement of asphalt. |  | All finished surface levels have been surveyed to an accuracy of 2 mm with readings to 1 mm by a licensed surveyor. | GHD-DD-SPC-002 5111(c), 5132(f) | Survey | Record of finished surface levels | IP | Site Engineer
2.07 | Surface smoothness of construction trial sections. |  | At the completion of each construction trial and prior to the commencement of full scale production and placement of asphalt. |  | Surface smoothness has been tested in each placing lane in longitudinal direction parallel to the centreline, and in the transverse direction at intervals not exceeding 10 m using a mobile straight edge operated at a speed not exceeding 5km/hr. The finished surface complies with Item 3.14 of this ITP. | GHD-DD-SPC-002 5111(c), 5132(g) | Straight edge | Record of location and extent of any surface irregularities | IP | Site Engineer
2.08 | Completion of construction trial. |  | At the completion of each construction trial and prior to the commencement of full scale production and placement of asphalt. |  | Submission of all test results and written advice to Contract Administrator regarding any alterations in procedures or adjustments to plant and equipment as necessary to produce asphalt in accordance with specified requirements. | GHD-DD-SPC-002 5111(c) HP5111-3 | Inspection | ITP | HP | Quality Manager
2.09 | Selection of reference area for surface finish. |  | After the completion of construction trials. |  | Agreement with Contract Administrator of reference area/s for each nominal size mix and photographs of each reference area. | GHD-DD-SPC-002 5111(e) HP5111-5 | Inspection | Photographs of reference areas | HP | Quality Manager
2.1 | Supply of asphalt as per job mix. |  | After the completion of construction trials and not less than two (2) working days prior to the planned commencement of full scale asphalt works. |  | Submission of the complete details of the job mix, job aggregate particle size distribution, job bitumen content, and job mix temperature for each nominal mix size. | GHD-DD-SPC-002 5111(e) HP5111-4 | Document | Job mix report | HP | Quality Manager
3 | Asphalt Placement
3.01 | Design of temporary ramps |  | Prior to the commencement of a shift. |  | Ramps are planned for all discontinuities greater than 25 mm in height. The maximum gradient is between 0.5% and 1.0% for discontinuities ≤50 mm in height, and ≤0.5% for discontinuities >50 mm in height. The distance between successive transverse ramps is not less than 60 m. Planned ramps on taxiways are no shorter than 4 m and have slope not exceeding 1.5% relative to the current slope. | GHD-DD-SPC-002 5123(b) HP5123-1 | Document | Temperary ramp design | HP | Site Engineer
3.02 | Commencement of asphalt placement. |  | Prior to the commencement of asphalt placement works in each work period. |  | All paving plant, tools and equipment, including standby plant and equipment, are in working condition and are free from leaks of oil, water, hydraulic fluid and fuel. Tyres and tracks of all equipment are clean and any build-up of bitumen or other material has been removed. | GHD-DD-SPC-002 5113(a) HP5113-1 | Inspection | Daily plant inspection verification checklist | HP | Site Engineer
3.03 | Weather conditions. |  | Prior to the commencement of asphalt placement works in each work period. |  | Surface to be paved is essentially dry and free from surface water. It is not raining and no rain is imminent. The surface temperature is at or above the minimum specified in Note 1. If the surface temperature is <15oC, the layer thickness is <30 mm or the winde speed is >20 knots, the cold weather paving plan has been implemented. | GHD-DD-SPC-002 5115, Table 5115-1 | Inspection | ITP | IP | Site Engineer
3.04 | Surface preparation. |  | Immediately before applying tack coat. |  | All loose and foreign materials have been removed from the surface to be paved to a distance of approximately 300 mm beyond the edge of the area. Any areas of oil or fuel spillage have been cleaned with detergent and flushed with clean water. | GHD-DD-SPC-002 5118 | Inspection | ITP | IP | Site Engineer
3.05 | Tack coating. |  | Prior to the commencement of asphalt placement in each work period. |  | A uniform cover of tack coat has been applied to all existing surfaces on or against which asphalt is to be placed, unless the surface is freshly placed asphalt not greater than 3 days old. Any vertical faces and edges have received 2 full applications. The residual bitumen is within the range 0.15-0.25 L/m2 and at least 80% of the surface has turned from brown to black. Any pooled tack coat has been brushed out prior to breaking. | GHD-DD-SPC-002 5119 | Inspection | ITP | IP | Site Engineer
3.06 | Commencement of paving. |  | Prior to the commencement of asphalt placement in each work period. |  | All necessary surface preparation and treatments within the paving lane and adjacent paving lane have been completed and inspected by Contract Administrator. | GHD-DD-SPC-002 5120(a) HP5120-1 | Inspection | ITP | HP | Site Engineer
3.07 | Longitudinal joints. |  | During asphalt placement works. |  | Cold joints are kept to a minimum. All joints are smooth, true, dense, free from segregation and have the same texture and smoothness as elsewhere on the finished surface. | GHD-DD-SPC-002 5120(d), 5122(a), 5124(e) | Inspection | ITP | IP | Site Engineer
3.08 | Delivery of asphalt. |  | Each load of asphalt delivered to site. |  | Asphalt temperature is ≥165oC for PMB or ≥150oC for residual C320 at point of delivery to paver. Load does not contain cold unworkabout material, is not contaminated with foreign material and has not been wetted by rain. | GHD-DD-SPC-002 5117(c) Table 5117-1 | Inspection | ITP | IP | Site Engineer
3.09 | Layer thickness. |  | During asphalt placement works at intervals not exceeding 10 m (except at the commencement of transverse joints where the interval must be not less than 5 m). |  | Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications. | GHD-DD-SPC-002 5120(b) | Dipstick and ruler | ITP | IP | Asphalt Foreman
3.1 | Compaction with vibratory steel wheel roller. |  | During asphalt placement works. |  | The temperature of the asphalt mat is ≥125oC for PMB or ≥95oC for residual C320 at the commencement of rolling with steel drum roller. Rolling is conducted as per defined rolled rolling pattern. The number of roller passes applied to each paving run has been recorded. | GHD-DD-SPC-002 5121(b), Table 5121-1 | Infrared thermometer | Shift report, ITP | IP | Site Engineer
3.11 | Compaction with pneumatic tyred roller. |  | During asphalt placement works. |  | Six (6) roller passes are completed prior to the temperature of the asphalt mat falling below 115oC for PMB or 70oC for residual C320. | GHD-DD-SPC-002 5121(b), 5121(f) Table 5121-1 | Infrared thermometer | ITP | IP | Site Engineer
3.12 | Finished layer thickness. |  | As soon as possible after the completion of asphalt placement works in each work period and prior to the next work period following completion of the course. |  | The average thickness of a nominal thickness layer is not more than 10% above or 6% below that specified, and has no part less than 85% of the specified thickness. The thickness of a variable thickness course complies with the specified finished surface levels. The average compacted layer thickness of a minimum of 4 cores is within the accepted range of: - Minimum of 40 mm and maximum of 85 mm for 14mm NMS asphalt, or - Minimum of 75 mm and maximum of 110 mm for 20mm NMS asphalt. | GHD-DD-SPC-002 5124(b) HP5132-1 | AS 2891.1.2 | NATA accredited test certificate | HP | Site Engineer
3.13 | Finished surface level. |  | As soon as possible after the completion of asphalt placement works in each work period and prior to the next work period following completion of the course. Record of finished surface levels to be submitted to Contract Administrator within one (1) working day of the completion of the level survey. |  | The finished surface coincides with the surface of abutting pavements, except where rolled over edges are specified. The finished surface level is not more than 7 mm above and 5 mm below the design finished surface levels shown on the Drawings. The absolute difference between the design surface level and the final surface level between two adjacent survey points in the longitudinal direction is not be more than 7 mm. A compliance rate of 97.5% of all the survey points has been achieved and no deviation in excess of 10 mm has been measured. | GHD-DD-SPC-002 5124(b) HP5124-1, HP5132-2 | Inspection and survey | Record of finished surface levels | HP | Site Engineer
3.14 | Surface smoothness. |  | After completion of compaction of asphalt with a pneumatic tyred roller and prior to back rolling. |  | The finished surface of all asphalt surfacing courses does not deviate from the testing edge of an approved 3.5 m straight edge by more than 3 mm (longitudinally) and 5 mm (transversely) on aircraft pavements, and 5 mm (longitudinally) and 7 mm (transversely) on shoulders. | GHD-DD-SPC-002 5124(c) HP5132-3 | Straight edge | Record of location and extent of any surface irregularities | HP | Site Engineer
3.15 | Finished surface appearance. |  | As soon as possible after the completion of asphalt placement works. |  | The finished surface is free from roller marks, vertical discontinuities, dragged areas, cracks, segregation, open textured patches and has a tightly bonded closed surface of uniform appearance. | GHD-DD-SPC-002 5124(d) | Inspection | Shift report, ITP | IP | Site Engineer
3.16 | Pavement cleaning. |  | Not less than 60 minutes prior to the scheduled time for opening pavements to aircraft operations. |  | Pavement surfaces are completely free of all loose material. | GHD-DD-SPC-002 5126 | Inspection | ITP | IP | Site Engineer
4 | Compaction Testing
4.01 | Extraction of cores. |  | At the completion of asphalt placement works, after the asphalt has cooled to ambient temperature throughout and not more than 24 hours after the lot was constructed. |  | From each lot of aircraft pavement, cores are cut at a rate of not less than one core per 500 m2 or a minimum of 6 cores within lanes (whichever yields the greater number of cores) and not less than one core every 150 m of joint, or a minimum of 4 cores on joints (whichever yields the greater number of cores). Cores are not less than 100 mm diameter and are cut from the finished lot after the asphalt has cooled to ambient temperature and not more than 24 hours after construction. | GHD-DD-SPC-002 5111(c), 5132(b) | AS 2891.1.2, AS 1289.1.4.2 | ITP | IP | Site Engineer
4.02 | Repair of core holes. |  | At the completion of core extraction. |  | All debris, slurry and water has been removed from the core hole and the core walls and floor are completely dry prior to reinstatement. Tack coat has been applied to the walls and floor of core hole, and the hole reinstated with hot mix asphalt approved for use in this project and placed and compacted in lifts not more than 50 mm compacted thickness. The filled hole is flush to the surrounding pavement surface. | GHD-DD-SPC-002 5111(c), 5132(b) | Inspection | ITP | IP | Site Engineer
4.03 | Compaction testing. |  | Within 24 hours after the construction of the lot. |  | Characteristic value of air voids are within the range of: - Surfacing layers: 3.0-6.5% inclusive for mat and 3.0-8.0% inclusive for joints, or - Base layers: 3.0-7.0% inclusive for mat. | GHD-DD-SPC-002 5111(c), 5121(c), 5132(c)(d) | AS 2891.14.2 (mat locations) or AS 2891.9.2 (joint locations) | NATA accredited test certificates | TP | Site Engineer
Note 1:
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Contract Administrator |  |  | IP Inspection point | Formal Inspection to be completed and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP Test Point | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which may be witnessed by the Contract Administrator or Client |  |  | NMS Nominal Mix Size | The nominal size of the asphalt mix
AP | Approval Point | Written or verbal approval given by the Contract Administrator
Document Control
Date | Author | Description of Change |  |  | Revision
2022-08-22 | N.Wood | Document published |  |  | 1