## ITP
|  |  | Inspection and Test Plan - Asphalt Production of Base Mixes | [7 empty] | Document # ITP-001
[11 empty] | Revision: 1.0 | Date : 3/10/2022
Client: | Melbourne Airport |  | Construction Process: | Asphalt Production of Base Mixes |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: | Melbourne Airport Runway 16-34 Overlay |  |  |  |  | Name: Noriko Wood |  | Name: Kevin Embleton |  |  | Name:
Contract: | 12554937 |  | Specifications: | Technical Specifications Melbourne Airport Runway 16-34 Overlay Schematic and Detailed Design GHD-DD-SPC-001 (10 June 2022), GHD-DD-SPC-002 (14 June 2022) |  | Senior Pavement Engineer |  | National Technical Solutions Manager
|  |  | Location: | Fulton Hogan Infrastructure Services 500 Princes Hwy, Noble Park VIC 3174
Item No. | Task/Activity Description |  | Inspection / Controls and Verification Detail | [5 empty] | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility
|  |  | Frequency |  | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity
1 | Mix Production
1.01 | Temperature of bitumen |  | Not less than once per work period. To be recorded at the time of taking bitumen volumetric readings. |  | Temperature to be within the below range for the relevant bitumen type when introduced into the mixer: - Residual bitumen C320: 140-165oC - Polymer modified bitumen: 160-175oC - Polymer modified bitumen with warm mix additives: 140-175oC | GHD-DD-SPC-001 5116(f) | Asphalt plant temperature probe | Production records | IP | Plant Operator
1.02 | Temperature of aggregates |  | Not less than once per work period. |  | Temperature to be not more than 10oC above or more than 15oC below the temperature of the bitumen. | GHD-DD-SPC-001 5116(f) | Asphalt plant temperature probe | Production records | IP | Plant Operator
1.03 | Temperature of asphalt |  | Not less than once per work period. |  | Temperature to be within 10oC of the job mix temperature | GHD-DD-SPC-001 5116(f) | Asphalt plant temperature probe | Production records | IP | Plant Operator
1.04 | Daily bitumen usage |  | Once per work period for each production run for each nominal size of asphalt mix. |  | To be reported. | GHD-DD-SPC-001 5131(e) | Inspection of plant digital readouts before and after each production run | Production records | IP | Plant Operator
1.05 | Supplementary bitumen content determination |  | Once per work period for each nominal size of asphalt mix. |  | Not less than the job bitumen content. | GHD-DD-SPC-001 5131(e) Table 5116-7 | Calculation: Daily bitumen usage divided by mass of asphalt produced for each mix type. | Production records | IP | Plant Operator
1.06 | Mass of asphalt produced |  | Once per work period for each nominal size of asphalt mix. |  | To be reported. | GHD-DD-SPC-001 5131(e) | Inspection of plant digital readouts | Production records | IP | Plant Operator
2 | Bitumen properties
2.01 | Viscosity at 165oC |  | One test prior to each work period (for PMB) or per 250 t of bitumen used (for residual class C320), completed no later than 1 hour prior to start of asphalt production. |  | To be reported. | GHD-DD-SPC-002 5131(c) Table SP5131-3 | AG:PT/T111 (for PMB) or AS 2341.2 (for C320) | NATA-accredited test certificate | TP | Laboratory Technician
2.02 | Torsional recovery at 25oC, 30 s (PMB only) |  | One test prior to each work period, completed no later than 1 hour prior to start of asphalt production. |  | To be reported. | GHD-DD-SPC-002 5131(c) Table SP5131-3 | AG:PT/T122 | NATA-accredited test certificate | TP | Laboratory Technician
2.03 | Softening point (PMB only) |  | One test prior to each work period, completed no later than 1 hour prior to start of asphalt production. |  | To be reported. | GHD-DD-SPC-002 5131(c) Table SP5131-3 | AG:PT/T131 | NATA-accredited test certificate | TP | Laboratory Technician
2.04 | PG MSCR |  | One test weekly conducted on a Monday sampled from storage tank, regardless of whether work proceeds that day or not. |  | To be reported. | GHD-DD-SPC-002 5131(c) Table SP5131-3 | AASHTO T350 | NATA-accredited test certificate | TP | Laboratory Technician
3 | Asphalt properties
3.01 | Mixing efficiency |  | Not less than once per work period. |  | Percentage of coating of particles in the mix, when sampled at the point of loading, must not be less than 97% and a homogeneous mixture must be obtained. | GHD-DD-SPC-001 5116(g) | Visual inspection | Inspection record | IP | Plant Operator
3.02 | Stability |  | Each test set sampled from asphalt delivery trucks (as per AS 2891.1). See Note 1 for sampling frequency. |  | ±3.0 compared to job mix but not less than 12.0 kN | GHD-DD-SPC-001 5116(j) Table 5116-5 HP5116-2 | AS/NZS 2891.5 (50 blows) | NATA-accredited test certificate | TP | Laboratory Technician
3.03 | Flow |  | Each test set sampled from asphalt delivery trucks (as per AS 2891.1). See Note 1 for sampling frequency. |  | Max 3.0 mm for unmodified binder; max ±1.0 mm compared to job mix for PMB | GHD-DD-SPC-001 5116(j) Table 5116-5 HP5116-2 | AS/NZS 2891.5 (50 blows) | NATA-accredited test certificate | TP | Laboratory Technician
3.04 | Minimum voids in mineral aggregate |  | Each test set sampled from asphalt delivery trucks (as per AS 2891.1). See Note 1 for sampling frequency. |  | 13.0% (for 20mm NMS) or 14.0% (for 14mm NMS) | GHD-DD-SPC-001 5116(j) Table 5116-5 HP5116-2 | AS/NZS 2891.5 (50 blows) | NATA-accredited test certificate | TP | Laboratory Technician
3.05 | Minimum and maximum air voids |  | Each test set sampled from asphalt delivery trucks (as per AS 2891.1). See Note 1 for sampling frequency. |  | 3.0-5.0% | GHD-DD-SPC-001 5116(j) Table 5116-5 HP5116-2 | AS/NZS 2891.5 (50 blows) | NATA-accredited test certificate | TP | Laboratory Technician
3.06 | Minimum and maximum voids filled with bitumen |  | Each test set sampled from asphalt delivery trucks (as per AS 2891.1). See Note 1 for sampling frequency. |  | 65.0-75.0% | GHD-DD-SPC-001 5116(j) Table 5116-5 HP5116-2 | AS/NZS 2891.5 (50 blows) | NATA-accredited test certificate | TP | Laboratory Technician
3.07 | Combined aggregate particle size distribution |  | Each test set sampled from asphalt delivery trucks (as per AS 2891.1). See Note 1 for sampling frequency. |  | Within acceptable range of deviation from job mix aggregate particle size distribution. For 14mm NMS: 13.2: ±6 1.18: ±4 9.5: ±6 0.6: ±3 6.7: ±6 0.3: ±2 4.75: ±5 0.15: ±2 2.36: ±5 0.075: ±1.5 For 20mm NMS: 19.0: ±7 13.2: ±6 1.18: ±4 9.5: ±6 0.6: ±4 6.7: ±6 0.3: ±3 4.75: ±6 0.15: ±2 2.36: ±5 0.075: ±1.5 | GHD-DD-SPC-001 5116(j) Table 5116-7 | AS/NZS 2891.3.3 | NATA-accredited test certificate | TP | Laboratory Technician
3.08 | Bitumen content in asphalt |  | Each test set sampled from asphalt delivery trucks (as per AS/NZS 2891.1.1). See Note 1 for sampling frequency. |  | Within ±0.3 of job bitumen content by mass. | GHD-DD-SPC-001 5116(j) Table 5116-7 | AS/NZS 2891.3.3 | NATA-accredited test certificate | TP | Laboratory Technician
3.09 | Maximum density |  | Each test set sampled from asphalt delivery trucks (as per AS/NZS 2891.1.1). See Note 1 for sampling frequency. |  | To be reported. | GHD-DD-SPC-001 5132(a) | AS/NZS 2891.7.1 | NATA-accredited test certificate | TP | Laboratory Technician
Note 1: Sampling frequency Number of test sets on asphalt of each nominal size in work period: Quantity of asphalt produced Number of sets of tests First 50t (0-50t) 1 Next 100t (50-150t) 1 Next 200t (150-350t) 1 Next 250t (350-600t) 1 Every 250t thereafter 1 Minimum number of tests per work period regardless of tonnes produced: 3
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Contract Administrator |  |  | IP Inspection point | Formal Inspection to be completed and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP Test Point | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which may be witnessed by the Contract Administrator or Client |  |  | NMS Nominal Mix Size | The nominal size of the asphalt mix
AP | Approval Point | Written or verbal approval given by the Contract Administrator
Document Control
Date | Author | Description of Change |  |  | Revision
2022-08-12 | N.Wood | Draft document published |  |  | 0.1
2022-10-03 | N.Wood | Updated Reference Documents to include reference to GHD-DD-SPC-001, added Table SP5131-3 to Items 2.01 to 2.04 Reference Documents, changed Item 2.04 from Penetration to PG MSCR testing, updated Item 3.01 Reference Documents to 5116(g), added Table 5116-5 to Items 3.02 to 3.06 Reference Documents, added limits for 19.0mm sieve to Item 3.07 Acceptance Criteria. Final document published. |  |  | 1