## ITP-
|  |  | Inspection and Test Plan - Coarse Aggregates for Asphalt Production | [7 empty] | Document # ITP-004
[11 empty] | Revision: 0.2 | Date: 30/9/2022
Client: | Melbourne Airport |  | Construction Process: | Coarse Aggregates for Asphalt Production |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: | Melbourne Airport Runway 16-34 Overlay |  |  |  |  | Name: Noriko Wood |  | Name: Joe Stella |  |  | Name:
Contract: | 12554937 |  | Specifications: | Technical Specifications Melbourne Airport Runway 16-34 Overlay Schematic and Detailed Design GHD-DD-SPC-001 (10 June 2022), GHD-DD-SPC-002 (14 June 2022) |  | Senior Pavement Engineer |  | Technical Manager
|  |  | Location: | Fulton Hogan Infrastructure Services 500 Princes Hwy, Noble Park VIC 3174
Item No. | Task/Activity Description |  | Inspection / Controls and Verification Detail | [5 empty] | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility
|  |  | Frequency |  | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity
1 | Quality Assurance - Prior to Commencement of Works
1.01 | Apparent particle density |  | Within 1 month prior to commencement of works |  | Not less than 2,300 kg/m3 | GHD-DD-SPC-001 5104(b) Table 5104-1, 5130(a) HP5130-1 | AS 1141.6.1 | NATA-accredited test certificate | HP | Technical Manager
1.02 | Water absorption |  | Within 1 month prior to commencement of works |  | Not more than 2.0% | GHD-DD-SPC-001 5104(b) Table 5104-1, 5130(a) HP5130-1 | AS 1141.6.1 | NATA-accredited test certificate | HP | Technical Manager
1.03 | Material finer than 0.075mm in aggregates (by washing) |  | Within 1 month prior to commencement of works |  | Not more than 2.0% | GHD-DD-SPC-001 5104(b) Table 5104-1, 5130(a) HP5130-1 | AS 1141.11.1 | NATA-accredited test certificate | HP | Technical Manager
1.04 | Flakiness Index (nominal 10mm and larger) |  | Within 1 month prior to commencement of works |  | Max 20% | GHD-DD-SPC-001 5104(b) Table 5104-1, 5130(a) HP5130-1 | AS 1141.15 | NATA-accredited test certificate | HP | Technical Manager
1.05 | Soudness (using sodium sulphate) |  | Within 1 month prior to commencement of works |  | Not more than 3% weighted loss | GHD-DD-SPC-001 5104(b) Table 5104-1, 5130(a) HP5130-1 | AS 1141.24 | NATA-accredited test certificate | HP | Technical Manager
1.06 | Unsound and marginal stone content |  | Within 1 month prior to commencement of works |  | Not more than 5% unsound; not more than 10% marginal and unsound | GHD-DD-SPC-001 5104(b) Table 5104-1, 5130(a), SP5104-1 HP5130-1 | RC372.01 | NATA-accredited test certificate | HP | Technical Manager
1.07 | Wet strength |  | Within 1 month prior to commencement of works |  | Not less than 150 kN | GHD-DD-SPC-001 5104(b) Table 5104-1, 5130(a) HP5130-1 | AS 1141.22 | NATA-accredited test certificate | HP | Technical Manager
1.08 | Wet/dry strength variation |  | Within 1 month prior to commencement of works |  | Not more than 30% | GHD-DD-SPC-001 5104(b) Table 5104-1, 5130(a) HP5130-1 | AS 1141.22 | NATA-accredited test certificate | HP | Technical Manager
1.09 | Los Angeles value |  | Within 1 month prior to commencement of works |  | Not more than 25% loss | GHD-DD-SPC-001 5104(b) Table 5104-1, 5130(a) HP5130-1 | AS 1141.23, B or K Grading | NATA-accredited test certificate | HP | Technical Manager
1.1 | Secondary mineral content |  | Within 1 month prior to commencement of works |  | Not more than 20% | GHD-DD-SPC-001 5104(b) Table 5104-1, 5130(a) HP5130-1 | AS 1141.26 | NATA-accredited test certificate | HP | Technical Manager
1.11 | Weak particles (including clay lumps, soft and friable particles) |  | Within 1 month prior to commencement of works |  | Not more than 0.2% | GHD-DD-SPC-001 5104(b) Table 5104-1, 5130(a) HP5130-1 | AS 1141.32 | NATA-accredited test certificate | HP | Technical Manager
1.12 | Supply of reference samples to the Contract Administrator |  | After acceptance of conformance certification for coarse aggregate properties has been accepted by Contract Administrator. Prior notice (minimum 48 hours) of time of inspection of sources provided to Contract Administrator. |  | Three split samples of each aggregate fraction to be bagged and labelled. Minimum quantities for each aggregate fraction: 14mm: 50kg 10mm: 40kg 7mm: 30kg | GHD-DD-SPC-001 5130(b) WP5130-1 | Inspection | Receipt of samples by the Contract Administrator | WP | Technical Manager
2 | Quality Assurance - Production
2.01 | Particle size distribution |  | 1 test per lot(1),(2) of 1000 tonnes aggregate, not less than 5 days prior to use in production of asphalt. |  | To be reported. | GHD-DD-SPC-001 5131(a) Table 5131-1 HP5131-1 | AS 1141.11.1 | NATA-accredited test certificate | HP | Laboratory Technician
2.02 | Material finer than 0.075mm in aggregates (by washing) |  | 1 test per lot(1) of 1000 tonnes aggregate, not less than 5 days prior to use in production of asphalt. |  | Not more than 2.0% | GHD-DD-SPC-001 5131(a) Table 5131-1, Table 5104-1 HP5131-1 | AS 1141.11.1 | NATA-accredited test certificate | HP | Laboratory Technician
2.03 | Flakiness Index (nominal 10mm and larger) |  | 1 test per lot(1),(3) of 500 tonnes aggregate, not less than 5 days prior to use in production of asphalt. |  | Max 20% | GHD-DD-SPC-001 5131(a) Table 5131-1, Table 5104-1 HP5131-1 | AS 1141.15 | NATA-accredited test certificate | HP | Laboratory Technician
2.04 | Weak particles (including clay lumps, soft and friable particles) in coarse aggregate |  | 1 test per lot(1) of 500 tonnes aggregate, not less than 5 days prior to use in production of asphalt. |  | Not more than 0.2% | GHD-DD-SPC-001 5131(a) Table 5131-1, Table 5104-1 HP5131-1 | AS 1141.32 | NATA-accredited test certificate | HP | Laboratory Technician
2.05 | Apparent particle density |  | 1 test per lot(1) of 1000 tonnes aggregate, not less than 5 days prior to use in production of asphalt. |  | Not less than 2,300 kg/m3 | GHD-DD-SPC-001 5131(a) Table 5131-1, Table 5104-1 HP5131-1 | AS 1141.6.1 | NATA-accredited test certificate | HP | Laboratory Technician
2.06 | Water absorption |  | 1 test per lot(1) of 1000 tonnes aggregate, not less than 5 days prior to use in production of asphalt. |  | Not more than 2.0% | GHD-DD-SPC-001 5131(a) Table 5131-1, Table 5104-1 HP5131-1 | AS 1141.6.1 | NATA-accredited test certificate | HP | Laboratory Technician
Note 1: A change in the source rock or face in the quarry will initiate the start of a new lot. Note 2: A change in the crusher plant screens will initiate the start of a new lot. Note 3: A change in crushing plant parameters will initiate the start of a new lot.
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Contract Administrator |  |  | IP Inspection point | Formal Inspection to be completed and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP Test Point | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which may be witnessed by the Contract Administrator or Client
AP | Approval Point | Written or verbal approval given by the Contract Administrator
Document Control
Date | Author | Description of Change |  |  | Revision
2022-08-11 | N.Wood | Document submitted for internal review |  |  | 0.1
2022-09-30 | N.Wood | Updated Reference Documents to include reference to GHD-DD-SPC-001, added SP5104-1 to Item 1.06 Reference Documents, added 48 hour notice period to Item 1.12 Frequency. |  |  | 0.2