## ITP
|  |  | Inspection and Test Plan - Pavement Marking | [7 empty] | Document # ITP-008
[11 empty] | Revision: 0.2 | Date : 29/9/2022
Client: | Melbourne Airport |  | Construction Process: | Pavement Marking |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: | Melbourne Airport Runway 16-34 Overlay |  |  |  |  | Name: Noriko Wood |  | Name: |  |  | Name:
Contract: | 12554937 |  | Specifications: | Technical Specifications Melbourne Airport Runway 16-34 Overlay Schematic and Detailed Design GHD-DD-SPC-001 (10 June 2022), GHD-DD-SPC-002 (14 June 2022) |  | Senior Pavement Engineer
|  |  | Location: | Fulton Hogan Infrastructure Services 500 Princes Hwy, Noble Park VIC 3174
Item No. | Task/Activity Description |  | Inspection / Controls and Verification Detail | [5 empty] | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility
|  |  | Frequency |  | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity
1 | Preliminary
1.01 | Supply of paints for pavement marking. |  | Not less than 1 month prior to the commencement of pavement marking. |  | Submission of conformance test reports for the proposed paints to the Contract Administrator which demonstrate compliance to Section 2 of this ITP. | GHD-DD-SPC-001 7103(b) HP7103-1 | Document | ITP | HP | Quality Manager
2 | Paint Properties
2.01 | Runway marking paint and taxiway and apron marking paint type and packaging |  | Prior to the commencement of pavement marking works. |  | Paint is pre-mixed acrylic co-polymer water based paint, packaged in 20 L containers. Containers are of durable construction and labelled with manufacturer's name and a complete description of the contents. Paint is of a consistency suitable for application by brushing and spraying, and capable of being used as supplied or diluted with water. Dilution information and coverage is stated by the manufacturer on the packaging. | GHD-DD-SPC-001 7103(a)(c)(d)(h) | Inspection | ITP | IP | Quality Manager
2.02 | Condition upon delivery |  | Prior to the commencement of pavement marking works, at the time of delivery of paint. |  | Hand stirring of the paint readily produces a smooth uniform product. | GHD-DD-SPC-001 7103(e) | Inspection | ITP | IP | Quality Manager
2.03 | Material properties: pick-up time, colour, bleeding, durability, and keeping properties. |  | Prior to the commencement of pavement marking works. |  | Information provided by the manufacturer or demonstrated by trial indicates: - The no-pick-up-time of the paint does not exceed 30 minutes. - The colour of the paint conforms to AS 2700, shows a high visibility against the pavement, is the correct colour as indicated on Drawings, does not react with bitumen and will not dull, fade or discolour within a period of 6 months after application. - The paint when stored in original sealed containers retains all specified properties for a period of not less than 12 months. - The paint shows resistance to weathering, stripping, abrasion, flaking, erosion, jetblast and scuffing under normal aircraft operations. | GHD-DD-SPC-001 7103(f)(g)(i)(j)(k) | Inspection | ITP | IP | Quality Manager
2.04 | Paint surface finish |  | Prior to the commencement of pavement marking works. |  | The dried surface of painted areas on aircraft aprons is not slippery under foot. The surface finish of the dried film of paint is a non-gloss matte finish. | GHD-DD-SPC-001 7103(l)(m) | Inspection | ITP | IP | Quality Manager
3 | Trials
3.01 | Demonstration of process and equipment for removal of pavement paint markings. |  | Not less than 1 working day prior to the commencement of full-scale paint removal works. Prior notice (24 hours minimum) of trial to be given to Contract Administrator. |  | A trial conducted in an area agreed with the Contract Administrator of not less than 5 m2 demonstrates removal of pavement marking without chemical methods, without causing disintegration of the pavement surface and in compliance with the requirements of Section 4 of this ITP. | GHD-DD-SPC-001 7104(f) HP7104-1 | Inspection | ITP | HP | Quality Manager
4 | Removal of Pavement Paint Markings
4.01 | Plant performance check |  | Prior to the commencement of paint marking removal work in each work period. |  | All plant is in working order, free from leaks, and capable of removing all paint from the pavement surface without filling voids with debris, removing joint sealants or otherwise damaging the pavement surface. | GHD-DD-SPC-001 7104(b)(c) WP7104-1 | Inspection | Daily plant verification checklist | WP | Site Engineer
4.02 | Weather conditions |  | Prior to the commencement of paint marking removal work in each work period. |  | Pavement surface is free of snow, ice or slush, with a surface temperature of at least 5oC and rising at the beginning of operations (except for where shot- or sand-blasting is used for which a lower surface temperature may be accepted). Work is not occurring during a thunderstorm. Work is not occurring during rainfall, except for water-blasting and removal of previously applied chemicals. | GHD-DD-SPC-001 7104(e) | Inspection | ITP | IP | Site Engineer
4.03 | Surface texture |  | At the completion of paint marking removal work in each work period. |  | The surface texture of the cleaned removal area is comparable to a standard area of pavement in the removal trial area selected by the Contract Administrator. | GHD-DD-SPC-001 7104(f) | Inspection | ITP | IP | Site Engineer
4.04 | Clean up and waste disposal |  | At the completion of paint marking removal work in each work period. |  | Debris and waste materials have been collected, removed from site and disposed of at an appropriately licensed waste disposal site. | GHD-DD-SPC-001 7104(f) | Inspection | ITP | IP | Site Engineer
5 | Application of Pavement Markings
5.01 | Setting out of pavement markings |  | At the completion of setting out and prior to application of pavement markings. Prior notice (minimum 24 hours) of commencement of setting out is given to the Contract Administrator. |  | Survey for setting out new pavement markings has been completed as shown on the Drawings by a suitably qualified surveyor, to a horizontal accuracy of ± 25 mm. Spotting indicates the location and extent of new markings in sufficient detail for the painting of the required markings to the tolerances specified. | GHD-DD-SPC-001 7105 HP7105-1 | Inspection | ITP | HP | Site Engineer
5.02 | Surface preparation |  | Prior to the commencement of pavement marking in each work period. Prior notice (minimum 24 hours) of the commencement of pavement marking is given to the Contract Administrator. |  | The surface to be painted has been thoroughly cleaned using vacuum sweepers, hand brooming, and/or high pressure water jetting as required, and all existing paint not strongly adhering to the pavement has been removed. | GHD-DD-SPC-001 7106(b) HP7106-1 | Inspection | ITP | HP | Site Engineer
5.03 | Weather conditions |  | Prior to the commencement of pavement marking in each work period. |  | The pavement surface is not wet and wet weather conditions are unlikely during the work period, the air and pavement temperatures are not less than 15oC, the relative humidity is not greater than 85%, the wind speed is not greater than 20km/hr, and wind conditions are unlikely to affect the application of the paint. | GHD-DD-SPC-001 7106(c) | Inspection | ITP | IP | Site Engineer
5.04 | Pavement marking adjacent to in-pavement light fittings |  | During pavement marking works. |  | Any in-pavement light fittings in the vicinity of pavement marking works have been protected to avoid contamination with paint. Markings in line with light fittings extend to the edge of the fitting but not on to the fitting. The gap between the end of painted line and edge of a light fitting is not more than 25 mm. | GHD-DD-SPC-001 7106(d) | Inspection | ITP | IP | Site Engineer
5.05 | Application of paint |  | During pavement marking works. |  | Paint is applied by spraying, except for small markings, isolated repairs, and stenciling of letters and numerals where brushing is permitted. Paint is applied in 2 even coats to give a minimum total dry film thickness of 120 µm. The edges of markings are straight or smooth even curves, with crisp even lines wihtout side spatter at the edges and ends of markings. | GHD-DD-SPC-001 7106(d) | Inspection | ITP | IP | Site Engineer
5.06 | Application of glass beads |  | During pavement marking works. |  | Glass beads are not used on any pavements with the exception of areas specified within standard MAS-CVL-002 for Pavement & Pavement Markings (Airside). Where glass beads are specified on taxiway pavement markings, the minimum application rate is 300 g/m2. | GHD-DD-SPC-001 7106(d) SP7103(n) | Inspection | ITP | IP | Site Engineer
5.07 | Paint application rates |  | At the completion of paint marking removal work in each work period. |  | Paint usage and area of coverage for each work period are recorded. | GHD-DD-SPC-001 7107 | Inspection | Shift report | IP | Site Engineer
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Contract Administrator |  |  | IP Inspection point | Formal Inspection to be completed and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP Test Point | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which may be witnessed by the Contract Administrator or Client |  |  | NMS Nominal Mix Size | The nominal size of the asphalt mix
AP | Approval Point | Written or verbal approval given by the Contract Administrator
Document Control
Date | Author | Description of Change |  |  | Revision
2022-08-15 | N.Wood | Document published |  |  | 0.1
2022-09-29 | N.Wood | Updated Reference Documents to include reference to GHD-DD-SPC-001, added final point to Item 2.03 Acceptance Criteria, removed Item 2.05, replaced reference to 7104(e) with reference to 7104(f) in Item 4.04 Reference Documents, added '24 hours' notification to Contract Administrator' to Item 5.01 Frequency. |  |  | 0.2