## ITP
|  |  | Inspection and Test Plan - Prime Coats and Primer Seals | [7 empty] | Document # ITP-010
[11 empty] | Revision: 0.1 | Date : 23/8/2022
Client: | Melbourne Airport |  | Construction Process: | Prime Coats and Primer Seals |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: | Melbourne Airport Runway 16-34 Overlay |  |  |  |  | Name: Noriko Wood |  | Name: |  |  | Name:
Contract: | 12554937 |  | Specifications: | Technical Specifications Melbourne Airport Runway 16-34 Overlay Schematic and Detailed Design GHD-DD-SPC-002 (14 June 2022) |  | Senior Pavement Engineer
|  |  | Location: | Fulton Hogan Infrastructure Services 500 Princes Hwy, Noble Park VIC 3174
Item No. | Task/Activity Description |  | Inspection / Controls and Verification Detail | [5 empty] | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility
|  |  | Frequency |  | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity
1 | Preliminary
1.01 | Calibration of bitumen sprayers. |  | Prior to the commencement of works. |  | Each bitumen sprayer used on the works has a current certificate of calibration. | GHD-DD-SPC-002 5004(b) | AP-T181/11, AGPT/T530-536 | Calibration certificate | IP | Quality Manager
2 | Compliance certification
2.01 | Blinding sand. |  | Within thirty (30) days of notification of the award of the Contract. |  | Sand is crushed or natural sand free from significant amounts of clay, organic matter, water or other foreign material and is non-plastic. The sand contains only sound, hard, dense, durable and clean particles. The particle size distribution of sand is within the below limits: 6.7: 100 4.75: 85-100 1.18: 40-100 0.425: 10-50 0.075: 0-5 | GHD-DD-SPC-002 5003(e), Table 5003-2 HP5013-1 | Inspection, AS 1289.3.3.1 (wet preparation) | NATA accredited test certificate | HP | Site Engineer
2.02 | Aggregates: wet strength |  | Within thirty (30) days of notification of the award of the Contract. |  | 150 kN minimum | GHD-DD-SPC-002 5003(f), Table 5003-3 HP5013-1 | AS 1141.22 | NATA accredited test certificate | HP | Site Engineer
2.03 | Aggregates: wet/dry strength variation |  | Within thirty (30) days of notification of the award of the Contract. |  | 35% maximum | GHD-DD-SPC-002 5003(f), Table 5003-3 HP5013-1 | AS 1141.22 | NATA accredited test certificate | HP | Site Engineer
2.04 | Aggregates: sulphate soundness |  | Within thirty (30) days of notification of the award of the Contract. |  | 10% maximum, and 3% maximum for weighted average percentage loss after 5 cycles | GHD-DD-SPC-002 5003(f), Table 5003-3 HP5013-1 | AS 1141.24 | NATA accredited test certificate | HP | Site Engineer
2.05 | Aggregates: flakiness index |  | Within thirty (30) days of notification of the award of the Contract. |  | 25 maximum | GHD-DD-SPC-002 5003(f), Table 5003-3 HP5013-1 | AS 1141.15 | NATA accredited test certificate | HP | Site Engineer
2.06 | Aggregates: fractured faces. |  | Within thirty (30) days of notification of the award of the Contract. |  | Not less than 100% by mass of particles must have 2 or more fractured faces | GHD-DD-SPC-002 5003(f), Table 5003-3 HP5013-1 | RMS NSW Test Method T239 or approved equivalent | NATA accredited test certificate | HP | Site Engineer
2.07 | Aggregates: degradation factor (igneous rock only) |  | Within thirty (30) days of notification of the award of the Contract. |  | 50 minimum | GHD-DD-SPC-002 5003(f), Table 5003-4 HP5013-1 | AS 1141.25.1 | NATA accredited test certificate | HP | Site Engineer
2.08 | Aggregates: secondary minerals content (igneous rock only) |  | Within thirty (30) days of notification of the award of the Contract. |  | 25% maximum | GHD-DD-SPC-002 5003(f), Table 5003-4 HP5013-1 | AS 1141.26 | NATA accredited test certificate | HP | Site Engineer
2.09 | Aggregates: accelerated soundness index by reflux (igneous rock only) |  | Within thirty (30) days of notification of the award of the Contract. |  | 94 minimum | GHD-DD-SPC-002 5003(f), Table 5003-4 HP5013-1 | AS 1141.29 | NATA accredited test certificate | HP | Site Engineer
2.1 | Aggregates: particle size distribution |  | Within thirty (30) days of notification of the award of the Contract. |  | The particle size distribution is within the specified range for the relevant nominal size aggregate shown in Note 1. | GHD-DD-SPC-002 5003(f), Table 5003-5 HP5013-1 | AS 1289.3.6.1 | NATA accredited test certificate | HP | Site Engineer
2.11 | Aggregates: average least dimension |  | Within thirty (30) days of notification of the award of the Contract. |  | Nominal 10 mm: 5-6 mm Nominal 7 mm: 3.5-4.5 mm Nominal 5 mm: Report only | GHD-DD-SPC-002 5003(f), Table 5003-6 HP5013-1 | AS 1141.20.1 or AS 1141.20.2 | NATA accredited test certificate | HP | Site Engineer
2.12 | Proprietary prime products. |  | Prior to the use of proprietary prime products. |  | Proprietary products have proven performance on similar airport or heavy duty pavement applications for at least 5 years. Material data sheet, record of proven performance and specification has been submitted to the Contract Administrator. | GHD-DD-SPC-002 5003(h) HP5003-1 | Document | Materials data sheet, record of proven performance | HP | Quality Manager
3 | Materials
3.01 | Storage temperature of primer. |  | Each delivery of bituminous primer. |  | Primer has not been held at storage temperatures greater than the limits below for more than 6 hours: - AMC00: 40oC - AMC0: 60oC - AMC1: 80oC | GHD-DD-SPC-002 5003(d), Table 5003-1 | Inspection | ITP | IP | Site Engineer
3.02 | Sand: particle size distribution. |  | Each stockpile of sand proposed to be used for absorbing excess primer. Test certificates to be submitted to Contract Administrator at least fourteen (14) working days before proposed commencement of priming. |  | Material complies with Item 2.02 of this ITP. | GHD-DD-SPC-002 5013(c) HP5013-2 | AS 1141.3, AS 1289.3.6.1 | NATA accredited test certificate | HP | Site Engineer
3.03 | Sand: plasticity index. |  | Each stockpile of sand proposed to be used for absorbing excess primer. Test certificates to be submitted to Contract Administrator at least fourteen (14) working days before proposed commencement of priming. |  | Non-plastic | GHD-DD-SPC-002 5013(c) HP5013-2 | AS 1289.3.3.1 (wet preparation) | NATA accredited test certificate | HP | Site Engineer
3.04 | Aggregates: particle size distribution |  | Each stockpile of aggregates to be used in primer seals. Test certificates to be submitted to Contract Administrator at least fourteen (14) working days before proposed commencement of priming. |  | The particle size distribution is within the specified range for the relevant nominal size aggregate shown in Note 1. | GHD-DD-SPC-002 5013(d) HP5013-2 | AS 1141.11.1 | NATA accredited test certificate | HP | Site Engineer
3.05 | Aggregates: apparent particle density. |  | Each stockpile of aggregates to be used in primer seals. Test certificates to be submitted to Contract Administrator at least fourteen (14) working days before proposed commencement of priming. |  | To be reported. | GHD-DD-SPC-002 5013(d) HP5013-2 | AS 1141.6.1 | NATA accredited test certificate | HP | Site Engineer
3.06 | Aggregates: flakiness index. |  | Each stockpile of aggregates to be used in primer seals. Test certificates to be submitted to Contract Administrator at least fourteen (14) working days before proposed commencement of priming. |  | 25 maximum | GHD-DD-SPC-002 5013(d) HP5013-2 | AS 1141.15 | NATA accredited test certificate | HP | Site Engineer
3.07 | Bituminous prime: material properties. |  | Each homogenous lot of primer. |  | Material complies with AS 2157 specification. | GHD-DD-SPC-002 5013(f) HP5013-3 | AS 2157 | NATA accredited test certificate | HP | Site Engineer
3.08 | Bituminous prime: temperature. |  | For each delivery of primer, immediately prior to the transfer of primer to storage tanks from the delivery vehicle, and at least once per day that the primer is being stored, or at least once per hour when the primer is being heated. |  | To be reported. | GHD-DD-SPC-002 5013(i) | Thermometer | Temperature log | IP | Site Engineer
3.09 | Reference samples. |  | At least one (1) day prior to commencement of work. |  | The reference sample is representative of the material to be used in the works and complies in all respects with the requirement of the specification. The sample is dividied into two representattive portions. Each portion is not less than one litre. | GHD-DD-SPC-002 5013(h) HP5013-4 | AS 2157 | Sample receipt | HP | Site Engineer
4 | Trials
4.01 | Construction trial of primer. |  | At least three (3) working days prior to the proposed commencement of the initial application of prime coat or primer seal. Prior notice (minimum two (2) working days) of intention to construct the test area to be given to Contract Administrator. |  | Approximately 1000 L of primer and all necessary plant, labour and equipment is available to perform a construction trial of prime coat and/or primer seal. | GHD-DD-SPC-002 5009 HP5009-1 | Notification | ITP | HP | Quality Manager
5 | Application of Primer
5.01 | Surface preparation. |  | Immediately prior to application of primer. Prior notice (minimum 2 (two) working days) to be given to Contract Administrator of intention to commence con |  | All loose material, excess aggregate, dirt, clay, dust, oil, or any other deleterious substance has been removed from the surface to be primed. | GHD-DD-SPC-002 5006(b) WP5006-1 | Inspection | ITP | WP | Site Engineer
5.02 | Moisture content of surface to be primed. |  | Immediately prior to application of primer. |  | The prepared surface is dry and the moisture content within the top 25 mm of the base material is 2% or more below the Modified Optimum Moisture Content. | GHD-DD-SPC-002 5007 | AS 1289.5.2.1 | ITP | IP | Site Engineer
5.03 | Weather conditions. |  | Immediately prior to application of primer. |  | The pavement temperature is in excess of 15oC and is likely to remain in excess of 15oC during the entire priming operation. The surface is not moist or wet, it is not raining, and rain is not imminent. | GHD-DD-SPC-002 5008 | Inspection | ITP | IP | Site Engineer
5.04 | Temperature of primer. |  | Immediately prior to the commencement of each spray run. |  | The temperature of the primer is at or above the temperatures specified below and has been recorded: - AMC00: 10oC - AMC0: 35oC - AMC1: 60oC | GHD-DD-SPC-002 5010(a), Table 5010-1 | Thermometer | Spray run sheet, ITP | IP | Site Engineer
5.05 | Spray nozzle check. |  | Upon filling or refilling the mechanical sprayer with primer and prior to commencing or recommencing spraying. |  | Spray nozzles are working correctly and distributing primer evenly when tested on an area other than the pavement to be primed. | GHD-DD-SPC-002 5010(a) | Inspection | ITP | IP | Site Engineer
5.06 | Marking up. |  | Before each spray run. |  | The pavement to be primed has been marked with paint to indicate the line along which the sprayer will drive. | GHD-DD-SPC-002 5010(a) | Inspection | ITP | IP | Site Engineer
5.07 | Application rate: cutback primer. |  | Each spray run. |  | The application rate is 1.3 L/m2 of surface area, measured at 15oC. | GHD-DD-SPC-002 5010(b)(c)(d), Table 5010-2, 5013(k) HP5010-1 | Sprayer dippings | Certificates indicating binder application rate | HP | Site Engineer
5.08 | Application and spread rates: primer seals. |  | After each spray run and before the commencement of any subsequent spray run. |  | Dippings of the sprayer tank indicate an average application rate of primer on any spray run not less than 92.5% or more than 107.5% of the application rate specified in Note 2. | GHD-DD-SPC-002 5010(b)(c)(d), Table 5010-2, 5013(k) HP5010-1 | Sprayer dippings | Certificates indicating binder application rate | HP | Site Engineer
5.09 | Location of spray runs. |  | Each spray run. |  | The location and date of each spray run, together with the actual average application rate of primer, is recorded on a plan of the works and in as-built documentation. | GHD-DD-SPC-002 5013(l) | Document | As-built documentation | IP | Site Engineer
Note 1:
Note 2: Multiply the measured volume by the 'Multiplier' value below to compare measurements with the values in the table. Where T = temperature of the material when the volume was measured (in degrees Celsius)
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Contract Administrator |  |  | IP Inspection point | Formal Inspection to be completed and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP Test Point | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which may be witnessed by the Contract Administrator or Client |  |  | NMS Nominal Mix Size | The nominal size of the asphalt mix
AP | Approval Point | Written or verbal approval given by the Contract Administrator
Document Control
Date | Author | Description of Change |  |  | Revision
2022-08-23 | N.Wood | Document published |  |  | 0.1