## ITP
|  |  | Inspection and Test Plan - Reclaimed Asphalt Pavement (RAP) | [7 empty] | Document # ITP-011
[11 empty] | Revision: 0.1 | Date : 23/8/2022
Client: | Melbourne Airport |  | Construction Process: | Reclaimed Asphalt Pavement (RAP) |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: | Melbourne Airport Runway 16-34 Overlay |  |  |  |  | Name: Noriko Wood |  | Name: |  |  | Name:
Contract: | 12554937 |  | Specifications: | Technical Specifications Melbourne Airport Runway 16-34 Overlay Schematic and Detailed Design GHD-DD-SPC-002 (14 June 2022) |  | Senior Pavement Engineer
|  |  | Location: | Fulton Hogan Infrastructure Services 500 Princes Hwy, Noble Park VIC 3174
Item No. | Task/Activity Description |  | Inspection / Controls and Verification Detail | [5 empty] | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility
|  |  | Frequency |  | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity
1 | Material properties
2.01 | Material composition. |  | Each 1.000 t stockpile. |  | The RAP is free from foreign material such as unbound granular base, broken concrete, or other contaminants. | GHD-DD-SPC-002 5105 | Inspection | ITP | IP | Laboratory Technician
2.02 | Binder content. |  | Each 1.000 t stockpile. |  | To be reported. | GHD-DD-SPC-002 5105 | AS 2891.3.3 | NATA accredited test certificate | TP | Laboratory Technician
2.03 | Particle size distribution. |  | Each 1.000 t stockpile. |  | To be reported. | GHD-DD-SPC-002 5105 | AS 2891.3.3 | NATA accredited test certificate | TP | Laboratory Technician
2.04 | Moisture content. |  | Each 1.000 t stockpile. |  | To be reported. | GHD-DD-SPC-002 5105 | AS 2891.10 | NATA accredited test certificate | TP | Laboratory Technician
2 | Binder blend viscosity
2.01 | Binder blend viscosity (for asphalt mixes containing >15% RAP content only) |  | Each 1.000 t stockpile. |  | The blended binder viscosity is within the range of: - 320-500 Pas for a target binder class of C320, - 450-680 Pas for a target binder class of C450, or - 600-880 Pas for a target binder class of C600 | AfPA RAP Management Plan Section 8.5.2 | AGPT/T191, AGPT/T192, AGPT/T193 | NATA accredited test certificate | TP | Laboratory Technician
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Contract Administrator |  |  | IP Inspection point | Formal Inspection to be completed and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP Test Point | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which may be witnessed by the Contract Administrator or Client |  |  | NMS Nominal Mix Size | The nominal size of the asphalt mix
AP | Approval Point | Written or verbal approval given by the Contract Administrator
Document Control
Date | Author | Description of Change |  |  | Revision
2022-08-23 | N.Wood | Document published |  |  | 1