## ITP
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP001 - Asphalt Production of Base Mixes | [5 empty] | ITP001 - Asphalt Production of Base Mixes
section | 1 Mix Production
checkpoint | 1.01 - Temperature of bitumen
label | Frequency: Not less than once per work period. To be recorded at the time of taking bitumen volumetric readings.
label | Acceptance Criteria:
label | • Temperature to be within the below range for the relevant bitumen type when introduced into the mixer:
label | – Residual bitumen C320: 140-165°C
label | – Polymer modified bitumen: 160-175°C
label | – Polymer modified bitumen with warm mix additives: 140-175°C
label | Reference Documents: GHD-DD-SPC-001 5116(f)
label | Inspection/ Test Method: Asphalt plant temperature probe
label | Record of conformity: Production records
label | IP
label | Responsibility: Plant Operator
text | Date Completed:
checkpoint | 1.02 - Temperature of aggregates
label | Frequency: Not less than once per work period.
label | Acceptance Criteria: Temperature to be not more than 10°C above or more than 15°C below the temperature of the bitumen.
label | Reference Documents: GHD-DD-SPC-001 5116(f)
label | Inspection/ Test Method: Asphalt plant temperature probe
label | Record of conformity: Production records
label | IP
label | Responsibility: Plant Operator
text | Date Completed:
checkpoint | 1.03 - Temperature of asphalt
label | Frequency: Not less than once per work period.
label | Acceptance Criteria: Temperature to be within 10°C of the job mix temperature
label | Reference Documents: GHD-DD-SPC-001 5116(f)
label | Inspection/ Test Method: Asphalt plant temperature probe
label | Record of conformity: Production records
label | IP
label | Responsibility: Plant Operator
text | Date Completed:
checkpoint | 1.04 - Daily bitumen usage
label | Frequency: Once per work period for each production run for each nominal size of asphalt mix.
label | Acceptance Criteria: To be reported.
label | Reference Documents: GHD-DD-SPC-001 5131(e)
label | Inspection/ Test Method: Inspection of plant digital readouts before and after each production run
label | Record of conformity: Production records
label | IP
label | Responsibility: Plant Operator
text | Date Completed:
checkpoint | 1.05 - Supplementary bitumen content determination
label | Frequency: Once per work period for each nominal size of asphalt mix.
label | Acceptance Criteria: Not less than the job bitumen content.
label | Reference Documents:
label | • GHD-DD-SPC-001 5131(e)
label | • Table 5116-7
label | Inspection/ Test Method: Calculation: Daily bitumen usage divided by mass of asphalt produced for each mix type.
label | Record of conformity: Production records
label | IP
label | Responsibility: Plant Operator
text | Date Completed:
checkpoint | 1.06 - Mass of asphalt produced
label | Frequency: Once per work period for each nominal size of asphalt mix.
label | Acceptance Criteria: To be reported.
label | Reference Documents: GHD-DD-SPC-001 5131(e)
label | Inspection/ Test Method: Inspection of plant digital readouts
label | Record of conformity: Production records
label | IP
label | Responsibility: Plant Operator
text | Date Completed:
section | 2 Bitumen properties
checkpoint | 2.01 - Viscosity at 165°C
label | Frequency: One test prior to each work period (for PMB) or per 250 t of bitumen used (for residual class C320), completed no later than 1 hour prior to start of asphalt production.
label | Acceptance Criteria: To be reported.
label | Reference Documents:
label | • GHD-DD-SPC-002 5131(c)
label | • Table SP5131-3
label | Inspection/ Test Method: AG:PT/T111 (for PMB) or AS 2341.2 (for C320)
label | Record of conformity: NATA-accredited test certificate
label | TP
label | Responsibility: Laboratory Technician
text | Date Completed:
checkpoint | 2.02 - Torsional recovery at 25°C, 30 s (PMB only)
label | Frequency: One test prior to each work period, completed no later than 1 hour prior to start of asphalt production.
label | Acceptance Criteria: To be reported.
label | Reference Documents:
label | • GHD-DD-SPC-002 5131(c)
label | • Table SP5131-3
label | Inspection/ Test Method: AG:PT/T122
label | Record of conformity: NATA-accredited test certificate
label | TP
label | Responsibility: Laboratory Technician
text | Date Completed:
checkpoint | 2.03 - Softening point (PMB only)
label | Frequency: One test prior to each work period, completed no later than 1 hour prior to start of asphalt production.
label | Acceptance Criteria: To be reported.
label | Reference Documents:
label | • GHD-DD-SPC-002 5131(c)
label | • Table SP5131-3
label | Inspection/ Test Method: AG:PT/T131
label | Record of conformity: NATA-accredited test certificate
label | TP
label | Responsibility: Laboratory Technician
text | Date Completed:
checkpoint | 2.04 - PG MSCR
label | Frequency: One test weekly conducted on a Monday sampled from storage tank, regardless of whether work proceeds that day or not.
label | Acceptance Criteria: To be reported.
label | Reference Documents:
label | • GHD-DD-SPC-002 5131(c)
label | • Table SP5131-3
label | Inspection/ Test Method: AASHTO T350
label | Record of conformity: NATA-accredited test certificate
label | TP
label | Responsibility: Laboratory Technician
text | Date Completed:
section | 3 Asphalt properties
checkpoint | 3.01 - Mixing efficiency
label | Frequency: Not less than once per work period.
label | Acceptance Criteria:
label | • Percentage of coating of particles in the mix, when sampled at the point of loading, must not be less than 97% and a homogeneous mixture must be obtained.
label | Reference Documents: GHD-DD-SPC-001 5116(g)
label | Inspection/ Test Method: Visual inspection
label | Record of conformity: Inspection record
label | IP
label | Responsibility: Plant Operator
text | Date Completed:
checkpoint | 3.02 - Stability
label | Frequency: Each test set sampled from asphalt delivery trucks (as per AS 2891.1). See Note 1 for sampling frequency.
label | Acceptance Criteria: ±3.0 compared to job mix but not less than 12.0 kN
label | Reference Documents:
label | • GHD-DD-SPC-001 5116(j)
label | • Table 5116-5
label | • HP5116-2
label | Inspection/ Test Method: AS/NZS 2891.5 (50 blows)
label | Record of conformity: NATA-accredited test certificate
label | TP
label | Responsibility: Laboratory Technician
text | Date Completed:
checkpoint | 3.03 - Flow
label | Frequency: Each test set sampled from asphalt delivery trucks (as per AS 2891.1). See Note 1 for sampling frequency.
label | Acceptance Criteria: Max 3.0 mm for unmodified binder; max ±1.0 mm compared to job mix for PMB
label | Reference Documents:
label | • GHD-DD-SPC-001 5116(j)
label | • Table 5116-5
label | • HP5116-2
label | Inspection/ Test Method: AS/NZS 2891.5 (50 blows)
label | Record of conformity: NATA-accredited test certificate
label | TP
label | Responsibility: Laboratory Technician
text | Date Completed:
checkpoint | 3.04 - Minimum voids in mineral aggregate
label | Frequency: Each test set sampled from asphalt delivery trucks (as per AS 2891.1). See Note 1 for sampling frequency.
label | Acceptance Criteria: 13.0% (for 20mm NMS) or 14.0% (for 14mm NMS)
label | Reference Documents:
label | • GHD-DD-SPC-001 5116(j)
label | • Table 5116-5
label | • HP5116-2
label | Inspection/ Test Method: AS/NZS 2891.5 (50 blows)
label | Record of conformity: NATA-accredited test certificate
label | TP
label | Responsibility: Laboratory Technician
text | Date Completed:
checkpoint | 3.05 - Minimum and maximum air voids
label | Frequency: Each test set sampled from asphalt delivery trucks (as per AS 2891.1). See Note 1 for sampling frequency.
label | Acceptance Criteria: 3.0-5.0%
label | Reference Documents:
label | • GHD-DD-SPC-001 5116(j)
label | • Table 5116-5
label | • HP5116-2
label | Inspection/ Test Method: AS/NZS 2891.5 (50 blows)
label | Record of conformity: NATA-accredited test certificate
label | TP
label | Responsibility: Laboratory Technician
text | Date Completed:
checkpoint | 3.06 - Minimum and maximum voids filled with bitumen
label | Frequency: Each test set sampled from asphalt delivery trucks (as per AS 2891.1). See Note 1 for sampling frequency.
label | Acceptance Criteria: 65.0-75.0%
label | Reference Documents:
label | • GHD-DD-SPC-001 5116(j)
label | • Table 5116-5
label | • HP5116-2
label | Inspection/ Test Method: AS/NZS 2891.5 (50 blows)
label | Record of conformity: NATA-accredited test certificate
label | TP
label | Responsibility: Laboratory Technician
text | Date Completed:
checkpoint | 3.07 - Combined aggregate particle size distribution
label | Frequency: Each test set sampled from asphalt delivery trucks (as per AS 2891.1). See Note 1 for sampling frequency.
label | Acceptance Criteria:
label | • Within acceptable range of deviation from job mix aggregate particle size distribution.
label | ○ For 14mm NMS:
label | 13.2: ±6 ¦¦ 1.18: ±4
label | 9.5: ±6 ¦¦ 0.6: ±3
label | 6.7: ±6 ¦¦ 0.3: ±2
label | 4.75: ±5 ¦¦ 0.15: ±2
label | 2.36: ±5 ¦¦ 0.075: ±1.5
label | ○ For 20mm NMS:
label | 19.0: ±7
label | 13.2: ±6 ¦¦ 1.18: ±4
label | 9.5: ±6 ¦¦ 0.6: ±4
label | 6.7: ±6 ¦¦ 0.3: ±3
label | 4.75: ±6 ¦¦ 0.15: ±2
label | 2.36: ±5 ¦¦ 0.075: ±1.5
label | Reference Documents:
label | • GHD-DD-SPC-001 5116(j)
label | • Table 5116-7
label | Inspection/ Test Method: AS/NZS 2891.3.3
label | Record of conformity: NATA-accredited test certificate
label | TP
label | Responsibility: Laboratory Technician
text | Date Completed:
checkpoint | 3.08 - Bitumen content in asphalt
label | Frequency: Each test set sampled from asphalt delivery trucks (as per AS/NZS 2891.1.1). See Note 1 for sampling frequency.
label | Acceptance Criteria: Within ±0.3 of job bitumen content by mass.
label | Reference Documents:
label | • GHD-DD-SPC-001 5116(j)
label | • Table 5116-7
label | Inspection/ Test Method: AS/NZS 2891.3.3
label | Record of conformity: NATA-accredited test certificate
label | TP
label | Responsibility: Laboratory Technician
text | Date Completed:
checkpoint | 3.09 - Maximum density
label | Frequency: Each test set sampled from asphalt delivery trucks (as per AS/NZS 2891.1.1). See Note 1 for sampling frequency.
label | Acceptance Criteria: To be reported.
label | Reference Documents: GHD-DD-SPC-001 5132(a)
label | Inspection/ Test Method: AS/NZS 2891.7.1
label | Record of conformity: NATA-accredited test certificate
label | TP
label | Responsibility: Laboratory Technician
text | Date Completed:
checkpoint-no-status | Note 1: Sampling frequency
label | • Number of test sets on asphalt of each nominal size in work period:
label | Quantity of asphalt produced ¦¦ Number of sets of tests
label | First 50t (0-50t) ¦¦ 1
label | Next 100t (50-150t) ¦¦ 1
label | Next 200t (150-350t) ¦¦ 1
label | Next 250t (350-600t) ¦¦ 1
label | Every 250t thereafter ¦¦ 1
label | • Minimum number of tests per work period regardless of tonnes produced: 3
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: