## ITP
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP004 - Coarse Aggregates for Asphalt Production | [5 empty] | ITP004 - Coarse Aggregates for Asphalt Production
section | 1 Quality Assurance - Prior to Commencement of Works
checkpoint | 1.01 - Apparent particle density
label | Frequency: Within 1 month prior to commencement of works
label | Acceptance Criteria: Not less than 2,300 kg/m3
label | Reference Documents:
label | • GHD-DD-SPC-001 5104(b)
label | • Table 5104-1, 5130(a)
label | • HP5130-1
label | Inspection/ Test Method: AS 1141.6.1
label | Record of conformity: NATA-accredited test certificate
label | HP
label | Responsibility: Technical Manager
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.02 - Water absorption
label | Frequency: Within 1 month prior to commencement of works
label | Acceptance Criteria: Not more than 2.0%
label | Reference Documents:
label | • GHD-DD-SPC-001 5104(b)
label | • Table 5104-1, 5130(a)
label | • HP5130-1
label | Inspection/ Test Method: AS 1141.6.1
label | Record of conformity: NATA-accredited test certificate
label | HP
label | Responsibility: Technical Manager
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.03 - Material finer than 0.075mm in aggregates (by washing)
label | Frequency: Within 1 month prior to commencement of works
label | Acceptance Criteria: Not more than 2.0%
label | Reference Documents:
label | • GHD-DD-SPC-001 5104(b)
label | • Table 5104-1, 5130(a)
label | • HP5130-1
label | Inspection/ Test Method: AS 1141.11.1
label | Record of conformity: NATA-accredited test certificate
label | HP
label | Responsibility: Technical Manager
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.04 - Flakiness Index (nominal 10mm and larger)
label | Frequency: Within 1 month prior to commencement of works
label | Acceptance Criteria: Max 20%
label | Reference Documents:
label | • GHD-DD-SPC-001 5104(b)
label | • Table 5104-1, 5130(a)
label | • HP5130-1
label | Inspection/ Test Method: AS 1141.15
label | Record of conformity: NATA-accredited test certificate
label | HP
label | Responsibility: Technical Manager
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.05 - Soudness (using sodium sulphate)
label | Frequency: Within 1 month prior to commencement of works
label | Acceptance Criteria: Not more than 3% weighted loss
label | Reference Documents:
label | • GHD-DD-SPC-001 5104(b)
label | • Table 5104-1, 5130(a)
label | • HP5130-1
label | Inspection/ Test Method: AS 1141.24
label | Record of conformity: NATA-accredited test certificate
label | HP
label | Responsibility: Technical Manager
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.06 - Unsound and marginal stone content
label | Frequency: Within 1 month prior to commencement of works
label | Acceptance Criteria: Not more than 5% unsound; not more than 10% marginal and unsound
label | Reference Documents:
label | • GHD-DD-SPC-001 5104(b)
label | • Table 5104-1, 5130(a)
label | • SP5104-1
label | • HP5130-1
label | Inspection/ Test Method: RC372.01
label | Record of conformity: NATA-accredited test certificate
label | HP
label | Responsibility: Technical Manager
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.07 - Wet strength
label | Frequency: Within 1 month prior to commencement of works
label | Acceptance Criteria: Not less than 150 kN
label | Reference Documents:
label | • GHD-DD-SPC-001 5104(b)
label | • Table 5104-1, 5130(a)
label | • HP5130-1
label | Inspection/ Test Method: AS 1141.22
label | Record of conformity: NATA-accredited test certificate
label | HP
label | Responsibility: Technical Manager
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.08 - Wet/dry strength variation
label | Frequency: Within 1 month prior to commencement of works
label | Acceptance Criteria: Not more than 30%
label | Reference Documents:
label | • GHD-DD-SPC-001 5104(b)
label | • Table 5104-1, 5130(a)
label | • HP5130-1
label | Inspection/ Test Method: AS 1141.22
label | Record of conformity: NATA-accredited test certificate
label | HP
label | Responsibility: Technical Manager
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.09 - Los Angeles value
label | Frequency: Within 1 month prior to commencement of works
label | Acceptance Criteria: Not more than 25% loss
label | Reference Documents:
label | • GHD-DD-SPC-001 5104(b)
label | • Table 5104-1, 5130(a)
label | • HP5130-1
label | Inspection/ Test Method: AS 1141.23, B or K Grading
label | Record of conformity: NATA-accredited test certificate
label | HP
label | Responsibility: Technical Manager
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.10 - Secondary mineral content
label | Frequency: Within 1 month prior to commencement of works
label | Acceptance Criteria: Not more than 20%
label | Reference Documents:
label | • GHD-DD-SPC-001 5104(b)
label | • Table 5104-1, 5130(a)
label | • HP5130-1
label | Inspection/ Test Method: AS 1141.26
label | Record of conformity: NATA-accredited test certificate
label | HP
label | Responsibility: Technical Manager
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.11 - Weak particles (including clay lumps, soft and friable particles)
label | Frequency: Within 1 month prior to commencement of works
label | Acceptance Criteria: Not more than 0.2%
label | Reference Documents:
label | • GHD-DD-SPC-001 5104(b)
label | • Table 5104-1, 5130(a)
label | • HP5130-1
label | Inspection/ Test Method: AS 1141.32
label | Record of conformity: NATA-accredited test certificate
label | HP
label | Responsibility: Technical Manager
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.12 - Supply of reference samples to the Contract Administrator
label | Frequency:
label | • After acceptance of conformance certification for coarse aggregate properties has been accepted by Contract Administrator.
label | • Prior notice (minimum 48 hours) of time of inspection of sources provided to Contract Administrator.
label | Acceptance Criteria:
label | • Three split samples of each aggregate fraction to be bagged and labelled. Minimum quantities for each aggregate fraction:
label | ○ 14mm: 50kg
label | ○ 10mm: 40kg
label | ○ 7mm: 30kg
label | Reference Documents:
label | • GHD-DD-SPC-001 5130(b)
label | • WP5130-1
label | Inspection/ Test Method: Inspection
label | Record of conformity: Receipt of samples by the Contract Administrator
label | WP
label | Responsibility: Technical Manager
text | Date Completed:
section | 2 Quality Assurance - Production
checkpoint | 2.01 - Particle size distribution
label | Frequency: 1 test per lot, of 1000 tonnes aggregate, not less than 5 days prior to use in production of asphalt.
label | Acceptance Criteria: To be reported.
label | Reference Documents:
label | • GHD-DD-SPC-001 5131(a)
label | • Table 5131-1
label | • HP5131-1
label | Inspection/ Test Method: AS 1141.11.1
label | Record of conformity: AS 1141.11.1
label | HP
label | Responsibility: Laboratory Technician
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.02 - Material finer than 0.075mm in aggregates (by washing)
label | Frequency: 1 test per lot of 1000 tonnes aggregate, not less than 5 days prior to use in production of asphalt.
label | Acceptance Criteria: Not more than 2.0%
label | Reference Documents:
label | • GHD-DD-SPC-001 5131(a)
label | • Table 5131-1, Table 5104-1
label | • HP5131-1
label | Inspection/ Test Method: AS 1141.11.1
label | Record of conformity: NATA-accredited test certificate
label | HP
label | Responsibility: Laboratory Technician
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.03 - Flakiness Index (nominal 10mm and larger)
label | Frequency: 1 test per lot, of 500 tonnes aggregate, not less than 5 days prior to use in production of asphalt.
label | Acceptance Criteria: Max 20%
label | Reference Documents:
label | • GHD-DD-SPC-001 5131(a)
label | • Table 5131-1, Table 5104-1
label | • HP5131-1
label | Inspection/ Test Method: AS 1141.15
label | Record of conformity: NATA-accredited test certificate
label | HP
label | Responsibility: Laboratory Technician
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.04 - Weak particles (including clay lumps, soft and friable particles) in coarse aggregate
label | Frequency: 1 test per lot of 500 tonnes aggregate, not less than 5 days prior to use in production of asphalt.
label | Acceptance Criteria: Not more than 0.2%
label | Reference Documents:
label | • GHD-DD-SPC-001 5131(a)
label | • Table 5131-1, Table 5104-1
label | • HP5131-1
label | Inspection/ Test Method: AS 1141.32
label | Record of conformity: NATA-accredited test certificate
label | HP
label | Responsibility: Laboratory Technician
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.05 - Apparent particle density
label | Frequency: 1 test per lot of 1000 tonnes aggregate, not less than 5 days prior to use in production of asphalt.
label | Acceptance Criteria: Not less than 2,300 kg/m3
label | Reference Documents:
label | • GHD-DD-SPC-001 5131(a)
label | • Table 5131-1, Table 5104-1
label | • HP5131-1
label | Inspection/ Test Method: AS 1141.6.1
label | Record of conformity: NATA-accredited test certificate
label | HP
label | Responsibility: Laboratory Technician
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.06 - Water absorption
label | Frequency: 1 test per lot of 1000 tonnes aggregate, not less than 5 days prior to use in production of asphalt.
label | Acceptance Criteria: Not more than 2.0%
label | Reference Documents:
label | • GHD-DD-SPC-001 5131(a)
label | • Table 5131-1, Table 5104-1
label | • HP5131-1
label | Inspection/ Test Method: AS 1141.6.1
label | Record of conformity: NATA-accredited test certificate
label | HP
label | Responsibility: Laboratory Technician
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint-no-status | Notes
label | Note 1: A change in the source rock or face in the quarry will initiate the start of a new lot.
label | Note 2: A change in the crusher plant screens will initiate the start of a new lot.
label | Note 3: A change in crushing plant parameters will initiate the start of a new lot.
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: