## ITP
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP006 - Fine Aggregates for Asphalt Production | [5 empty] | ITP006 - Fine Aggregates for Asphalt Production
section | 1 Quality Assurance - Prior to Commencement of Works
checkpoint | 1.01 - Bulk (particle) density
label | Frequency: Within 1 month prior to commencement of works
label | Acceptance Criteria: Not less than 2,300 kg/m3
label | Reference Documents:
label | • GHD-DD-SPC-002 5104(c)
label | • Table 5104-2, 5130(a)
label | • HP5130-1
label | Inspection/ Test Method: AS 1141.5
label | Record of conformity: NATA-accredited test certificate
label | HP
label | Responsibility: Technical Manager
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.02 - Water absorption
label | Frequency: Within 1 month prior to commencement of works
label | Acceptance Criteria: Not more than 2.5% for crushed aggregate; not more than 2.0% for uncrushed aggregate
label | Reference Documents:
label | • GHD-DD-SPC-002 5104(c)
label | • Table 5104-2, 5130(a)
label | • HP5130-1
label | Inspection/ Test Method: AS 1141.5
label | Record of conformity: NATA-accredited test certificate
label | HP
label | Responsibility: Technical Manager
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.03 - Linear shrinkage
label | Frequency: Within 1 month prior to commencement of works
label | Acceptance Criteria: Not more than 1%
label | Reference Documents:
label | • GHD-DD-SPC-002 5104(c)
label | • Table 5104-2, 5130(a)
label | • HP5130-1
label | Inspection/ Test Method: AS 1289.3.4.1
label | Record of conformity: NATA-accredited test certificate
label | HP
label | Responsibility: Technical Manager
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.04 - Methylene blue adsorption value (MBV mg/g)
label | Frequency: Within 1 month prior to commencement of works
label | Acceptance Criteria: Not more than 10
label | Reference Documents:
label | • GHD-DD-SPC-002 5104(c)
label | • Table 5104-2, 5130(a)
label | • HP5130-1
label | Inspection/ Test Method: AS 1141.66
label | Record of conformity: NATA-accredited test certificate
label | HP
label | Responsibility: Technical Manager
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.05 - Supply of reference samples to the Contract Administrator
label | Frequency:
label | • After acceptance of conformance certification for coarse aggregate properties has been accepted by Contract Administrator.
label | Acceptance Criteria:
label | • Three split samples of each aggregate fraction to be bagged and labelled. Minimum quantities for each aggregate fraction:
label | ○ Crushed fine aggregate: 20kg
label | ○ Natural sand: 20kg
label | Reference Documents:
label | • GHD-DD-SPC-002 5130(b)
label | • WP5130-1
label | Inspection/ Test Method: Inspection
label | Record of conformity: Receipt of samples by the Contract Administrator
label | WP
label | Responsibility: Technical Manager
text | Date Completed:
section | 2 Quality Assurance - Production
checkpoint | 2.01 - Particle size distribution
label | Frequency: 1 test per lot of 500 tonnes aggregate, not less than 5 days prior to use in production of asphalt.
label | Acceptance Criteria: To be reported.
label | Reference Documents:
label | • GHD-DD-SPC-002 5131(a)
label | • Table 5131-2
label | • HP5131-1
label | Inspection/ Test Method: AS 1141.11.1
label | Record of conformity: NATA-accredited test certificate
label | HP
label | Responsibility: Laboratory Technician
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.02 - Plasticity Index (wet preparation method)
label | Frequency: 1 test per lot of 1000 tonnes aggregate, not less than 5 days prior to use in production of asphalt.
label | Acceptance Criteria: To be reported.
label | Reference Documents:
label | • GHD-DD-SPC-002 5131(a)
label | • Table 5131-2
label | • HP5131-1
label | Inspection/ Test Method: AS 1289.3.3.1
label | Record of conformity: NATA-accredited test certificate
label | HP
label | Responsibility: Laboratory Technician
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.03 - Linear shrinkage (wet preparation method)
label | Frequency: 1 test per lot of 1000 tonnes aggregate, not less than 5 days prior to use in production of asphalt.
label | Acceptance Criteria: Not more than 1%
label | Reference Documents:
label | • GHD-DD-SPC-002 5131(a)
label | • Table 5131-2, Table 5104-2
label | • HP5131-1
label | Inspection/ Test Method: AS 1289.3.4.1
label | Record of conformity: NATA-accredited test certificate
label | HP
label | Responsibility: Laboratory Technician
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.04 - Apparent particle density
label | Frequency: 1 test per lot of 1000 tonnes aggregate, not less than 5 days prior to use in production of asphalt.
label | Acceptance Criteria: Not less than 2,300 kg/m3
label | Reference Documents:
label | • GHD-DD-SPC-002 5131(a)
label | • Table 5131-2, Table 5104-2
label | • HP5131-1
label | Inspection/ Test Method: AS 1141.5
label | Record of conformity: NATA-accredited test certificate
label | HP
label | Responsibility: Laboratory Technician
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.05 - Water absorption
label | Frequency: 1 test per lot of 1000 tonnes aggregate, not less than 5 days prior to use in production of asphalt.
label | Acceptance Criteria: Not more than 2.5% for crushed aggregate; not more than 2.0% for uncrushed aggregate
label | Reference Documents:
label | • GHD-DD-SPC-002 5131(a)
label | • Table 5131-2, Table 5104-2
label | • HP5131-1
label | Inspection/ Test Method: AS 1141.5
label | Record of conformity: NATA-accredited test certificate
label | HP
label | Responsibility: Laboratory Technician
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint-no-status | Notes
label | Note 1: A change in crushing plant parameters will initiate the start of a new lot.
label | Note 2: A change in the crusher plant screens will initiate the start of a new lot.
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: