## ITP
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP008 - Pavement Marking | [5 empty] | ITP008 - Pavement Marking
section | 1 Preliminary
checkpoint | 1.01 - Supply of paints for pavement marking.
label | Frequency:
label | • Not less than 1 month prior to the commencement of pavement marking.
label | Acceptance Criteria:
label | • Submission of conformance test reports for the proposed paints to the Contract Administrator which demonstrate compliance to Section 2 of this ITP.
label | Reference Documents:
label | • GHD-DD-SPC-001 7103(b)
label | • HP7103-1
label | Inspection/ Test Method: Document
label | Record of conformity: ITP
label | HP
label | Responsibility: Quality Manager
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2 Paint Properties
checkpoint | 2.01 - Runway marking paint and taxiway and apron marking paint type and packaging
label | Frequency: Prior to the commencement of pavement marking works.
label | Acceptance Criteria:
label | • Paint is pre-mixed acrylic co-polymer water based paint, packaged in 20 L containers.
label | • Containers are of durable construction and labelled with manufacturer's name and a complete description of the contents.
label | • Paint is of a consistency suitable for application by brushing and spraying, and capable of being used as supplied or diluted with water.
label | • Dilution information and coverage is stated by the manufacturer on the packaging.
label | Reference Documents: GHD-DD-SPC-001 7103(a)(c)(d)(h)
label | Inspection/ Test Method: Inspection
label | Record of conformity: ITP
label | IP
label | Responsibility: Quality Manager
text | Date Completed:
checkpoint | 2.02 - Condition upon delivery
label | Frequency: Prior to the commencement of pavement marking works, at the time of delivery of paint.
label | Acceptance Criteria: Hand stirring of the paint readily produces a smooth uniform product.
label | Reference Documents: GHD-DD-SPC-001 7103(e)
label | Inspection/ Test Method: Inspection
label | Record of conformity: ITP
label | IP
label | Responsibility: Quality Manager
text | Date Completed:
checkpoint | 2.03 - Material properties: pick-up time, colour, bleeding, durability, and keeping properties.
label | Frequency: Prior to the commencement of pavement marking works.
label | Acceptance Criteria:
label | • Information provided by the manufacturer or demonstrated by trial indicates:
label | – The no-pick-up-time of the paint does not exceed 30 minutes.
label | – The colour of the paint conforms to AS 2700, shows a high visibility against the pavement, is the correct colour as indicated on Drawings, does not react with bitumen and will not dull, fade or discolour within a period of 6 months after application.
label | – The paint when stored in original sealed containers retains all specified properties for a period of not less than 12 months.
label | – The paint shows resistance to weathering, stripping, abrasion, flaking, erosion, jetblast and scuffing under normal aircraft operations.
label | Reference Documents: GHD-DD-SPC-001 7103(f)(g)(i)(j)(k)
label | Inspection/ Test Method: Inspection
label | Record of conformity: ITP
label | IP
label | Responsibility: Quality Manager
text | Date Completed:
checkpoint | 2.04 - Paint surface finish
label | Frequency: Prior to the commencement of pavement marking works.
label | Acceptance Criteria:
label | • The dried surface of painted areas on aircraft aprons is not slippery under foot.
label | • The surface finish of the dried film of paint is a non-gloss matte finish.
label | Reference Documents: GHD-DD-SPC-001 7103(l)(m)
label | Inspection/ Test Method: Inspection
label | Record of conformity: ITP
label | IP
label | Responsibility: Quality Manager
text | Date Completed:
section | 3 Trials
checkpoint | 3.01 - Demonstration of process and equipment for removal of pavement paint markings.
label | Frequency:
label | • Not less than 1 working day prior to the commencement of full-scale paint removal works.
label | • Prior notice (24 hours minimum) of trial to be given to Contract Administrator.
label | Acceptance Criteria:
label | • A trial conducted in an area agreed with the Contract Administrator of not less than 5 m2 demonstrates removal of pavement marking without chemical methods, without causing disintegration of the pavement surface and in compliance with the requirements of Section 4 of this ITP.
label | Reference Documents:
label | • GHD-DD-SPC-001 7104(f)
label | • HP7104-1
label | Inspection/ Test Method: Inspection
label | Record of conformity: ITP
label | HP
label | Responsibility: Quality Manager
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 4 Removal of Pavement Paint Markings
checkpoint | 4.01 - Plant performance check
label | Frequency: Prior to the commencement of paint marking removal work in each work period.
label | Acceptance Criteria:
label | • All plant is in working order, free from leaks, and capable of removing all paint from the pavement surface without filling voids with debris, removing joint sealants or otherwise damaging the pavement surface.
label | Reference Documents:
label | • GHD-DD-SPC-001 7104(b)(c)
label | • WP7104-1
label | Inspection/ Test Method: Inspection
label | Record of conformity: Daily plant verification checklist
label | WP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 4.02 - Weather conditions
label | Frequency: Prior to the commencement of paint marking removal work in each work period.
label | Acceptance Criteria:
label | • Pavement surface is free of snow, ice or slush, with a surface temperature of at least 5°C and rising at the beginning of operations (except for where shot- or sand-blasting is used for which a lower surface temperature may be accepted).
label | • Work is not occurring during a thunderstorm.
label | • Work is not occurring during rainfall, except for water-blasting and removal of previously applied chemicals.
label | Reference Documents: GHD-DD-SPC-001 7104(e)
label | Inspection/ Test Method: Inspection
label | Record of conformity: ITP
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 4.03 - Surface texture
label | Frequency: At the completion of paint marking removal work in each work period.
label | Acceptance Criteria:
label | • The surface texture of the cleaned removal area is comparable to a standard area of pavement in the removal trial area selected by the Contract Administrator.
label | Reference Documents: GHD-DD-SPC-001 7104(f)
label | Inspection/ Test Method: Inspection
label | Record of conformity: ITP
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 4.04 - Clean up and waste disposal
label | Frequency: At the completion of paint marking removal work in each work period.
label | Acceptance Criteria:
label | • Debris and waste materials have been collected, removed from site and disposed of at an appropriately licensed waste disposal site.
label | Reference Documents: GHD-DD-SPC-001 7104(f)
label | Inspection/ Test Method: Inspection
label | Record of conformity: ITP
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
section | 5 Application of Pavement Markings
checkpoint | 5.01 - Setting out of pavement markings
label | Frequency:
label | • At the completion of setting out and prior to application of pavement markings.
label | • Prior notice (minimum 24 hours) of commencement of setting out is given to the Contract Administrator.
label | Acceptance Criteria:
label | • Survey for setting out new pavement markings has been completed as shown on the Drawings by a suitably qualified surveyor, to a horizontal accuracy of ± 25 mm.
label | • Spotting indicates the location and extent of new markings in sufficient detail for the painting of the required markings to the tolerances specified.
label | Reference Documents:
label | • GHD-DD-SPC-001 7105
label | • HP7105-1
label | Inspection/ Test Method: Inspection
label | Record of conformity: ITP
label | HP
label | Responsibility: Site Engineer
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.02 - Surface preparation
label | Frequency:
label | • Prior to the commencement of pavement marking in each work period.
label | • Prior notice (minimum 24 hours) of the commencement of pavement marking is given to the Contract Administrator.
label | Acceptance Criteria:
label | • The surface to be painted has been thoroughly cleaned using vacuum sweepers, hand brooming, and/or high pressure water jetting as required, and all existing paint not strongly adhering to the pavement has been removed.
label | Reference Documents:
label | • GHD-DD-SPC-001 7106(b)
label | • HP7106-1
label | Inspection/ Test Method: Inspection
label | Record of conformity: ITP
label | HP
label | Responsibility: Site Engineer
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.03 - Weather conditions
label | Frequency: Prior to the commencement of pavement marking in each work period.
label | Acceptance Criteria:
label | • The pavement surface is not wet and wet weather conditions are unlikely during the work period, the air and pavement temperatures are not less than 15°C, the relative humidity is not greater than 85%, the wind speed is not greater than 20km/hr, and wind conditions are unlikely to affect the application of the paint.
label | Reference Documents: GHD-DD-SPC-001 7106(c)
label | Inspection/ Test Method: Inspection
label | Record of conformity: ITP
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 5.04 - Pavement marking adjacent to in-pavement light fittings
label | Frequency: During pavement marking works.
label | Acceptance Criteria:
label | • Any in-pavement light fittings in the vicinity of pavement marking works have been protected to avoid contamination with paint.
label | • Markings in line with light fittings extend to the edge of the fitting but not on to the fitting.
label | • The gap between the end of painted line and edge of a light fitting is not more than 25 mm.
label | Reference Documents: GHD-DD-SPC-001 7106(d)
label | Inspection/ Test Method: Inspection
label | Record of conformity: ITP
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 5.05 - Application of paint
label | Frequency: During pavement marking works.
label | Acceptance Criteria:
label | • Paint is applied by spraying, except for small markings, isolated repairs, and stenciling of letters and numerals where brushing is permitted.
label | • Paint is applied in 2 even coats to give a minimum total dry film thickness of 120 µm.
label | • The edges of markings are straight or smooth even curves, with crisp even lines wihtout side spatter at the edges and ends of markings.
label | Reference Documents: GHD-DD-SPC-001 7106(d)
label | Inspection/ Test Method: Inspection
label | Record of conformity: ITP
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 5.06 - Application of glass beads
label | Frequency: During pavement marking works.
label | Acceptance Criteria:
label | • Glass beads are not used on any pavements with the exception of areas specified within standard MAS-CVL-002 for Pavement & Pavement Markings (Airside).
label | • Where glass beads are specified on taxiway pavement markings, the minimum application rate is 300 g/m2.
label | Reference Documents: GHD-DD-SPC-001 7106(d) SP7103(n)
label | Inspection/ Test Method: Inspection
label | Record of conformity: ITP
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 5.07 - Paint application rates
label | Frequency: At the completion of paint marking removal work in each work period.
label | Acceptance Criteria: Paint usage and area of coverage for each work period are recorded.
label | Reference Documents: GHD-DD-SPC-001 7107
label | Inspection/ Test Method: Inspection
label | Record of conformity: Shift report
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: