## ITP
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP009 - Runway Grooving of Asphalt Surfacing | [5 empty] | ITP009 - Runway Grooving of Asphalt Surfacing
section | 1 Trials
checkpoint | 1.01 - Trial section of grooving in new asphalt surfacing
label | Frequency: Prior to the commencement of grooving works.
label | Acceptance Criteria: Construction of a trial section of grooving that complies with the requirements of Sections 2 and 3 of this ITP.
label | Reference Documents:
label | • GHD-DD-SPC-001 7005
label | • HP7005-1
label | Inspection/ Test Method: Inspection
label | Record of conformity: ITP
label | HP
label | Responsibility: Quality Manager
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2 Grooving
checkpoint | 2.01 - Commencement of grooving in new asphalt surfacing.
label | Frequency: Prior to the commencement of grooving works.
label | Acceptance Criteria: Grooving of asphalt surfacing commenced no less than 8 weeks after the completion of the construction of the asphalt surfacing.
label | Reference Documents: GHD-DD-SPC-001 7004(a)
label | Inspection/ Test Method: Inspection
label | Record of conformity: ITP
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.02 - Grooving of new asphalt surfacing as per specified dimensions, length, extent and shape.
label | Frequency:
label | • During grooving works, on at least 15 randomly selected grooves within a lot. Submission of groove lots to be within 48 hours of completion of a lot.
label | Acceptance Criteria:
label | • Width, depth and spacing of grooves are as indicated on Drawings.
label | • Floor of grooves are parallel to the finished surface of the pavement.
label | • Square grooves are square with sides perpendicular to the surface of the runway; trapezoidal grooves are a consistent trapezoidal shape and not round or semi-circle.
label | • The deviation from specified groove shape is not more than specified in Note 1.
label | • Grooves are cut continuously across the width of the pavement and are cut to extend over the length of the pavement, as shown on the Drawings.
label | Reference Documents:
label | • GHD-DD-SPC-001 7004(c)(d)(f)(g)
label | • Table 7007-1
label | • WP7007-1
label | Inspection/ Test Method: Inspection; random selection in accordance with AS 1289.1.4.2
label | Record of conformity: Conformance report
label | WP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.03 - Grooving of new asphalt surfacing as per specified alignment.
label | Frequency:
label | • During grooving works, on at least 15 randomly selected grooves within a lot.
label | • Submission of groove lots to be within 48 hours of completion of a lot.
label | Acceptance Criteria:
label | • Alignment of grooves reset to truly perpendicular to the runway centreline at 150 m intervals along the runway.
label | • Grooves are cut in parallel straight lines perpendicular to the runway centreline and comply with the requirements of Note 1.
label | • Grooves on rapid exit taxiways are in straight lines and oriented as indicated on Drawings.
label | Reference Documents:
label | • GHD-DD-SPC-001 7004(e)
label | • Table 7007-1
label | • WP7007-1
label | Inspection/ Test Method: Inspection; random selection in accordance with AS 1289.1.4.2
label | Record of conformity: Conformance report
label | WP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.04 - Grooving of new asphalt surfacing near inset light fittings.
label | Frequency: During grooving works adjacent to inset light fittings.
label | Acceptance Criteria:
label | • Grooving is stopped to leave a regular (rectangular or square) ungrooved area symmetrically surrounding the light fitting.
label | • Grooves are not sawn closer than 150 mm and not more than 900 mm from the edge of any inset light.
label | Reference Documents: GHD-DD-SPC-001 7004(h)
label | Inspection/ Test Method: Inspection
label | Record of conformity: ITP
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.05 - Grooving of new asphalt surfacing near cable slots.
label | Frequency: During grooving works adjacent to cable slots.
label | Acceptance Criteria: Grooves are not sawn closer than 150 mm and not more than 900 mm from the edge of any cable slots.
label | Reference Documents: GHD-DD-SPC-001 7004(i)
label | Inspection/ Test Method: Inspection
label | Record of conformity: ITP
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.06 - Grooving of new asphalt surfacing near cable arrestors.
label | Frequency: During grooving works adjacent to cable arrestors.
label | Acceptance Criteria: Grooves are not sawn closer than 3,000 mm each side of a cable arrestor system.
label | Reference Documents: GHD-DD-SPC-001 7004(j)
label | Inspection/ Test Method: Inspection
label | Record of conformity: ITP
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
section | 3 Slurry Removal
checkpoint | 3.01 - Cleaning of grooved surface.
label | Frequency: Progressively during grooving and at the completion of grooving works.
label | Acceptance Criteria:
label | • Slurry produced by grooving equipment is flushed from grooves as it is produced and removed by suction into a mobile container.
label | • Residual slurry is removed to produce a clean pavement free from all material arising from the cutting of grooves.
label | Reference Documents: GHD-DD-SPC-001 7006
label | Inspection/ Test Method: Inspection
label | Record of conformity: ITP
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 3.02 - Notification of completion of cleaning of pavement surface.
label | Frequency: At the end of each work period in which grooving works have been undertaken.
label | Acceptance Criteria: Contract Administor is notified of completion of cleaning of pavement surface.
label | Reference Documents:
label | • GHD-DD-SPC-001 7006
label | • WP7006-1
label | Inspection/ Test Method: Inspection
label | Record of conformity: ITP
label | WP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint-no-status | Notes
label | Note 1: Table 7007-1 Groove Tolerances and compliances requirements.
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: