## ITP
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP010 - Prime Coats and Primer Seals | [5 empty] | ITP010 - Prime Coats and Primer Seals
section | 1 Preliminary
checkpoint | 1.01 - Calibration of bitumen sprayers.
label | Frequency: Prior to the commencement of works.
label | Acceptance Criteria: Each bitumen sprayer used on the works has a current certificate of calibration.
label | Reference Documents: GHD-DD-SPC-002 5004(b)
label | Inspection/ Test Method: AP-T181/11, AGPT/T530-536
label | Record of conformity: Calibration certificate
label | IP
label | Responsibility: Quality Manager
text | Date Completed:
section | 2 Compliance certification
checkpoint | 2.01 - Blinding sand.
label | Frequency: Within thirty (30) days of notification of the award of the Contract.
label | Acceptance Criteria:
label | • Sand is crushed or natural sand free from significant amounts of clay, organic matter, water or other foreign material and is non-plastic.
label | • The sand contains only sound, hard, dense, durable and clean particles. The particle size distribution of sand is within the below limits:
label | 6.7: 100
label | 4.75: 85-100
label | 1.18: 40-100
label | 0.425: 10-50
label | 0.075: 0-5
label | Reference Documents:
label | • GHD-DD-SPC-002 5003(e), Table 5003-2
label | • HP5013-1
label | Inspection/ Test Method: Inspection, AS 1289.3.3.1 (wet preparation)
label | Record of conformity: NATA accredited test certificate
label | HP
label | Responsibility: Site Engineer
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.02 - Aggregates: wet strength
label | Frequency: Within thirty (30) days of notification of the award of the Contract.
label | Acceptance Criteria: 150 kN minimum
label | Reference Documents:
label | • GHD-DD-SPC-002 5003(f), Table 5003-3
label | • HP5013-1
label | Inspection/ Test Method: AS 1141.22
label | Record of conformity: NATA accredited test certificate
label | HP
label | Responsibility: Site Engineer
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.03 - Aggregates: wet/dry strength variation
label | Frequency: Within thirty (30) days of notification of the award of the Contract.
label | Acceptance Criteria: 35% maximum
label | Reference Documents:
label | • GHD-DD-SPC-002 5003(f), Table 5003-3
label | • HP5013-1
label | Inspection/ Test Method: AS 1141.22
label | Record of conformity: NATA accredited test certificate
label | HP
label | Responsibility: Site Engineer
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.04 - Aggregates: sulphate soundness
label | Frequency: Within thirty (30) days of notification of the award of the Contract.
label | Acceptance Criteria: 10% maximum, and 3% maximum for weighted average percentage loss after 5 cycles
label | Reference Documents:
label | • GHD-DD-SPC-002 5003(f), Table 5003-3
label | • HP5013-1
label | Inspection/ Test Method: AS 1141.24
label | Record of conformity: NATA accredited test certificate
label | HP
label | Responsibility: Site Engineer
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.05 - Aggregates: flakiness index
label | Frequency: Within thirty (30) days of notification of the award of the Contract.
label | Acceptance Criteria: 25 maximum
label | Reference Documents:
label | • GHD-DD-SPC-002 5003(f), Table 5003-3
label | • HP5013-1
label | Inspection/ Test Method: AS 1141.15
label | Record of conformity: NATA accredited test certificate
label | HP
label | Responsibility: Site Engineer
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.06 - Aggregates: fractured faces.
label | Frequency: Within thirty (30) days of notification of the award of the Contract.
label | Acceptance Criteria: Not less than 100% by mass of particles must have 2 or more fractured faces
label | Reference Documents:
label | • GHD-DD-SPC-002 5003(f), Table 5003-3
label | • HP5013-1
label | Inspection/ Test Method: RMS NSW Test Method T239 or approved equivalent
label | Record of conformity: NATA accredited test certificate
label | HP
label | Responsibility: Site Engineer
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.07 - Aggregates: degradation factor (igneous rock only)
label | Frequency: Within thirty (30) days of notification of the award of the Contract.
label | Acceptance Criteria: 50 minimum
label | Reference Documents:
label | • GHD-DD-SPC-002 5003(f), Table 5003-4
label | • HP5013-1
label | Inspection/ Test Method: AS 1141.25.1
label | Record of conformity: NATA accredited test certificate
label | HP
label | Responsibility: Site Engineer
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.08 - Aggregates: secondary minerals content (igneous rock only)
label | Frequency: Within thirty (30) days of notification of the award of the Contract.
label | Acceptance Criteria: 25% maximum
label | Reference Documents:
label | • GHD-DD-SPC-002 5003(f), Table 5003-4
label | • HP5013-1
label | Inspection/ Test Method: AS 1141.26
label | Record of conformity: NATA accredited test certificate
label | HP
label | Responsibility: Site Engineer
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.09 - Aggregates: accelerated soundness index by reflux (igneous rock only)
label | Frequency: Within thirty (30) days of notification of the award of the Contract.
label | Acceptance Criteria: 94 minimum
label | Reference Documents:
label | • GHD-DD-SPC-002 5003(f), Table 5003-4
label | • HP5013-1
label | Inspection/ Test Method: AS 1141.29
label | Record of conformity: NATA accredited test certificate
label | HP
label | Responsibility: Site Engineer
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.10 - Aggregates: particle size distribution
label | Frequency: Within thirty (30) days of notification of the award of the Contract.
label | Acceptance Criteria: The particle size distribution is within the specified range for the relevant nominal size aggregate shown in Note 1.
label | Reference Documents:
label | • GHD-DD-SPC-002 5003(f), Table 5003-5
label | • HP5013-1
label | Inspection/ Test Method: AS 1289.3.6.1
label | Record of conformity: NATA accredited test certificate
label | HP
label | Responsibility: Site Engineer
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.11 - Aggregates: average least dimension
label | Frequency: Within thirty (30) days of notification of the award of the Contract.
label | Acceptance Criteria:
label | • Nominal 10 mm: 5-6 mm
label | • Nominal 7 mm: 3.5-4.5 mm
label | • Nominal 5 mm: Report only
label | Reference Documents:
label | • GHD-DD-SPC-002 5003(f), Table 5003-6
label | • HP5013-1
label | Inspection/ Test Method: AS 1141.20.1 or AS 1141.20.2
label | Record of conformity: NATA accredited test certificate
label | HP
label | Responsibility: Site Engineer
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.12 - Proprietary prime products.
label | Frequency: Prior to the use of proprietary prime products.
label | Acceptance Criteria:
label | • Proprietary products have proven performance on similar airport or heavy duty pavement applications for at least 5 years.
label | • Material data sheet, record of proven performance and specification has been submitted to the Contract Administrator.
label | Reference Documents:
label | • GHD-DD-SPC-002 5003(h)
label | • HP5003-1
label | Inspection/ Test Method: Document
label | Record of conformity: Materials data sheet, record of proven performance
label | HP
label | Responsibility: Quality Manager
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3 Materials
checkpoint | 3.01 - Storage temperature of primer.
label | Frequency: Each delivery of bituminous primer.
label | Acceptance Criteria:
label | • Primer has not been held at storage temperatures greater than the limits below for more than 6 hours:
label | – AMC00: 40°C
label | – AMC0: 60°C
label | – AMC1: 80°C
label | Reference Documents: GHD-DD-SPC-002 5003(d), Table 5003-1
label | Inspection/ Test Method: Inspection
label | Record of conformity: ITP
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 3.02 - Sand: particle size distribution.
label | Frequency:
label | • Each stockpile of sand proposed to be used for absorbing excess primer.
label | • Test certificates to be submitted to Contract Administrator at least fourteen (14) working days before proposed commencement of priming.
label | Acceptance Criteria: Material complies with Item 2.02 of this ITP.
label | Reference Documents:
label | • GHD-DD-SPC-002 5013(c)
label | • HP5013-2
label | Inspection/ Test Method: AS 1141.3, AS 1289.3.6.1
label | Record of conformity: NATA accredited test certificate
label | HP
label | Responsibility: Site Engineer
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.03 - Sand: plasticity index.
label | Frequency:
label | • Each stockpile of sand proposed to be used for absorbing excess primer.
label | • Test certificates to be submitted to Contract Administrator at least fourteen (14) working days before proposed commencement of priming.
label | Acceptance Criteria: Non-plastic
label | Reference Documents:
label | • GHD-DD-SPC-002 5013(c)
label | • HP5013-2
label | Inspection/ Test Method: AS 1289.3.3.1 (wet preparation)
label | Record of conformity: NATA accredited test certificate
label | HP
label | Responsibility: Site Engineer
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.04 - Aggregates: particle size distribution
label | Frequency:
label | • Each stockpile of aggregates to be used in primer seals.
label | • Test certificates to be submitted to Contract Administrator at least fourteen (14) working days before proposed commencement of priming.
label | Acceptance Criteria:
label | • The particle size distribution is within the specified range for the relevant nominal size aggregate shown in Note 1.
label | Reference Documents:
label | • GHD-DD-SPC-002 5013(d)
label | • HP5013-2
label | Inspection/ Test Method: AS 1141.11.1
label | Record of conformity: NATA accredited test certificate
label | HP
label | Responsibility: Site Engineer
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.05 - Aggregates: apparent particle density.
label | Frequency:
label | • Each stockpile of aggregates to be used in primer seals.
label | • Test certificates to be submitted to Contract Administrator at least fourteen (14) working days before proposed commencement of priming.
label | Acceptance Criteria: To be reported.
label | Reference Documents:
label | • GHD-DD-SPC-002 5013(d)
label | • HP5013-2
label | Inspection/ Test Method: AS 1141.6.1
label | Record of conformity: NATA accredited test certificate
label | HP
label | Responsibility: Site Engineer
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.06 - Aggregates: flakiness index.
label | Frequency:
label | • Each stockpile of aggregates to be used in primer seals.
label | • Test certificates to be submitted to Contract Administrator at least fourteen (14) working days before proposed commencement of priming.
label | Acceptance Criteria: 25 maximum
label | Reference Documents:
label | • GHD-DD-SPC-002 5013(d)
label | • HP5013-2
label | Inspection/ Test Method: AS 1141.15
label | Record of conformity: NATA accredited test certificate
label | HP
label | Responsibility: Site Engineer
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.07 - Bituminous prime: material properties.
label | Frequency: Each homogenous lot of primer.
label | Acceptance Criteria: Material complies with AS 2157 specification.
label | Reference Documents:
label | • GHD-DD-SPC-002 5013(f)
label | • HP5013-3
label | Inspection/ Test Method: AS 2157
label | Record of conformity: NATA accredited test certificate
label | HP
label | Responsibility: Site Engineer
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.08 - Bituminous prime: temperature.
label | Frequency:
label | • For each delivery of primer, immediately prior to the transfer of primer to storage tanks from the delivery vehicle, and at least once per day that the primer is being stored, or at least once per hour when the primer is being heated.
label | Acceptance Criteria: To be reported.
label | Reference Documents: GHD-DD-SPC-002 5013(i)
label | Inspection/ Test Method: Thermometer
label | Record of conformity: Temperature log
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 3.09 - Reference samples.
label | Frequency: At least one (1) day prior to commencement of work.
label | Acceptance Criteria:
label | • The reference sample is representative of the material to be used in the works and complies in all respects with the requirement of the specification.
label | • The sample is dividied into two representattive portions. Each portion is not less than one litre.
label | Reference Documents:
label | • GHD-DD-SPC-002 5013(h)
label | • HP5013-4
label | Inspection/ Test Method: AS 2157
label | Record of conformity: Sample receipt
label | HP
label | Responsibility: Site Engineer
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 4 Trials
checkpoint | 4.01 - Construction trial of primer.
label | Frequency:
label | • At least three (3) working days prior to the proposed commencement of the initial application of prime coat or primer seal.
label | • Prior notice (minimum two (2) working days) of intention to construct the test area to be given to Contract Administrator.
label | Acceptance Criteria:
label | • Approximately 1000 L of primer and all necessary plant, labour and equipment is available to perform a construction trial of prime coat and/or primer seal.
label | Reference Documents:
label | • GHD-DD-SPC-002 5009
label | • HP5009-1
label | Inspection/ Test Method: Notification
label | Record of conformity: ITP
label | HP
label | Responsibility: Quality Manager
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 5 Application of Primer
checkpoint | 5.01 - Surface preparation.
label | Frequency:
label | • Immediately prior to application of primer.
label | • Prior notice (minimum 2 (two) working days) to be given to Contract Administrator of intention to commence con
label | Acceptance Criteria:
label | • All loose material, excess aggregate, dirt, clay, dust, oil, or any other deleterious substance has been removed from the surface to be primed.
label | Reference Documents:
label | • GHD-DD-SPC-002 5006(b)
label | • WP5006-1
label | Inspection/ Test Method: Inspection
label | Record of conformity: ITP
label | WP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 5.02 - Moisture content of surface to be primed.
label | Frequency: Immediately prior to application of primer.
label | Acceptance Criteria:
label | • The prepared surface is dry and the moisture content within the top 25 mm of the base material is 2% or more below the Modified Optimum Moisture Content.
label | Reference Documents: GHD-DD-SPC-002 5007
label | Inspection/ Test Method: AS 1289.5.2.1
label | Record of conformity: ITP
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 5.03 - Weather conditions.
label | Frequency: Immediately prior to application of primer.
label | Acceptance Criteria:
label | • The pavement temperature is in excess of 15°C and is likely to remain in excess of 15°C during the entire priming operation.
label | • The surface is not moist or wet, it is not raining, and rain is not imminent.
label | Reference Documents: GHD-DD-SPC-002 5008
label | Inspection/ Test Method: Inspection
label | Record of conformity: ITP
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 5.04 - Temperature of primer.
label | Frequency: Immediately prior to the commencement of each spray run.
label | Acceptance Criteria:
label | • The temperature of the primer is at or above the temperatures specified below and has been recorded:
label | – AMC00: 10°C
label | – AMC0: 35°C
label | – AMC1: 60°C
label | Reference Documents: GHD-DD-SPC-002 5010(a), Table 5010-1
label | Inspection/ Test Method: Thermometer
label | Record of conformity: Spray run sheet, ITP
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 5.05 - Spray nozzle check.
label | Frequency:
label | • Upon filling or refilling the mechanical sprayer with primer and prior to commencing or recommencing spraying.
label | Acceptance Criteria:
label | • Spray nozzles are working correctly and distributing primer evenly when tested on an area other than the pavement to be primed.
label | Reference Documents: GHD-DD-SPC-002 5010(a)
label | Inspection/ Test Method: Inspection
label | Record of conformity: ITP
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 5.06 - Marking up.
label | Frequency: Before each spray run.
label | Acceptance Criteria: The pavement to be primed has been marked with paint to indicate the line along which the sprayer will drive.
label | Reference Documents: GHD-DD-SPC-002 5010(a)
label | Inspection/ Test Method: Inspection
label | Record of conformity: ITP
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 5.07 - Application rate: cutback primer.
label | Frequency: Each spray run.
label | Acceptance Criteria: The application rate is 1.3 L/m2 of surface area, measured at 15°C.
label | Reference Documents:
label | • GHD-DD-SPC-002 5010(b)(c)(d), Table 5010-2, 5013(k)
label | • HP5010-1
label | Inspection/ Test Method: Sprayer dippings
label | Record of conformity: Certificates indicating binder application rate
label | HP
label | Responsibility: Site Engineer
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.08 - Application and spread rates: primer seals.
label | Frequency:
label | • After each spray run and before the commencement of any subsequent spray run.
label | Acceptance Criteria:
label | • Dippings of the sprayer tank indicate an average application rate of primer on any spray run not less than 92.5% or more than 107.5% of the application rate specified in Note 2.
label | Reference Documents:
label | • GHD-DD-SPC-002 5010(b)(c)(d), Table 5010-2, 5013(k)
label | • HP5010-1
label | Inspection/ Test Method: Sprayer dippings
label | Record of conformity: Certificates indicating binder application rate
label | HP
label | Responsibility: Site Engineer
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.09 - Location of spray runs.
label | Frequency: Each spray run.
label | Acceptance Criteria:
label | • The location and date of each spray run, together with the actual average application rate of primer, is recorded on a plan of the works and in as-built documentation.
label | Reference Documents: GHD-DD-SPC-002 5013(l)
label | Inspection/ Test Method: Document
label | Record of conformity: As-built documentation
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint-no-status | Notes
label | Note 1: Table 5003-5 Primer seal Aggregate Particle Size Distribution
label | Note 2: Table 5010-2 Primer Seal Spread Rates
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: