## ITP
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP011 - Reclaimed Asphalt Pavement (RAP) | [5 empty] | ITP011 - Reclaimed Asphalt Pavement (RAP)
section | 1 Material properties
checkpoint | 1.01 - Material composition.
label | Frequency: Each 1.000 t stockpile.
label | Acceptance Criteria: The RAP is free from foreign material such as unbound granular base, broken concrete, or other contaminants.
label | Reference Documents: GHD-DD-SPC-002 5105
label | Inspection/ Test Method: Inspection
label | Record of conformity: ITP
label | IP
label | Responsibility: Laboratory Technician
text | Date Completed:
checkpoint | 1.02 - Binder content.
label | Frequency: Each 1.000 t stockpile.
label | Acceptance Criteria: To be reported.
label | Reference Documents: GHD-DD-SPC-002 5105
label | Inspection/ Test Method: AS 2891.3.3
label | Record of conformity: NATA accredited test certificate
label | TP
label | Responsibility: Laboratory Technician
text | Date Completed:
checkpoint | 1.03 - Particle size distribution.
label | Frequency: Each 1.000 t stockpile.
label | Acceptance Criteria: To be reported.
label | Reference Documents: GHD-DD-SPC-002 5105
label | Inspection/ Test Method: AS 2891.3.3
label | Record of conformity: NATA accredited test certificate
label | TP
label | Responsibility: Laboratory Technician
text | Date Completed:
checkpoint | 1.04 - Moisture content.
label | Frequency: Each 1.000 t stockpile.
label | Acceptance Criteria: To be reported.
label | Reference Documents: GHD-DD-SPC-002 5105
label | Inspection/ Test Method: AS 2891.10
label | Record of conformity: NATA accredited test certificate
label | TP
label | Responsibility: Laboratory Technician
text | Date Completed:
section | 2 Binder blend viscosity
checkpoint | 2.01 - Binder blend viscosity (for asphalt mixes containing >15% RAP content only)
label | Frequency: Each 1.000 t stockpile.
label | Acceptance Criteria:
label | • The blended binder viscosity is within the range of:
label | – 320-500 Pas for a target binder class of C320,
label | – 450-680 Pas for a target binder class of C450, or
label | – 600-880 Pas for a target binder class of C600
label | Reference Documents: AfPA RAP Management Plan Section 8.5.2
label | Inspection/ Test Method: AGPT/T191, AGPT/T192, AGPT/T193
label | Record of conformity: NATA accredited test certificate
label | TP
label | Responsibility: Laboratory Technician
text | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: