## Summerset St John Block A
Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Instruction to CONQA | Checklist Name
Site Summerset St John QA
Block A
Level 2
|  |  | Zone 1 |  |  |  | add this checklist:
|  |  | Zone 2 |  |  |  | add this checklist:
|  |  | Zone 3 |  |  |  | add this checklist:
|  |  | Zone 4 |  |  |  | add this checklist:
Level 3
|  |  | Zone 1 |  |  |  | add this checklist: |  | Type | Name | Values
|  |  | Zone 2 |  |  |  | add this checklist: |  | checklist-flat | QA - Brickwork
|  |  | Zone 3 |  |  |  | add this checklist: |  | section | Prestart
|  |  | Zone 4 |  |  |  | add this checklist: |  | checkpoint | Approval from Summerset foreman to begin blocklaying
[9 empty] | checkpoint | Setting out checked back to grid and datum as per architect setting out drawings
[9 empty] | checkpoint | DPC installed and checked before works commence*
|  | Level 4 | [6 empty] | section | Brick/ block work Installation
|  |  | Zone 1 |  |  |  | add this checklist: |  | checkpoint | Mortar mixed correctly and colour consistent
|  |  | Zone 2 |  |  |  | add this checklist: |  | checkpoint | Premium white mortar is used as per specification plan
|  |  | Zone 3 |  |  |  | add this checklist: |  | checkpoint | Mortar joints are in alignment
|  |  | Zone 4 |  |  |  | add this checklist: |  | checkpoint | Cavity width correct
[9 empty] | checkpoint | Cavity insulation installed as per plan
|  | Level 5 | [6 empty] | checkpoint | Standard Brick ties installed as per the specifications with correct spacing*
|  |  | Zone 1 |  |  |  | add this checklist: |  | checkpoint | Fero brick ties and retaining clips installed as per the manufactures recommendations*
|  |  | Zone 2 |  |  |  | add this checklist: |  | checkpoint | Cavity and brick ties free of mortar and debris
|  |  | Zone 3 |  |  |  | add this checklist: |  | checkpoint | Weep-holes checked and accurate (required every 3 bricks at base and sills)
|  |  | Zone 4 |  |  |  | add this checklist: |  | checkpoint | Brick sill installed and checked – 15 degree consistent fall
[9 empty] | checkpoint | Façade bricks are installed as per plan
|  | Level 6 | [6 empty] | checkpoint | Double layers of bricks are installed as per plan
|  |  | Zone 1 |  |  |  | add this checklist: |  | checkpoint | Both Horizontal and vertical fire cavity barrier installed - this is to be offered to Summerset before work scontinue to check and ensure verything is installed correctly*
|  |  | Zone 2 |  |  |  | add this checklist: |  | checkpoint | Brickwork line and level t ospecification tolerances*
|  |  | Zone 3 |  |  |  | add this checklist: |  | checkpoint | Movement joints installed as pers etting out drawings
|  |  | Zone 4 |  |  |  | add this checklist: |  | section | Hand over
[9 empty] | checkpoint | Final clean and handover
[9 empty] | section | Brick shelf Angle
[9 empty] | checkpoint | Installed to sepecification and drawings
[9 empty] | checkpoint | Correct Fixing used*
[9 empty] | checkpoint | Brick support angle is line and level*
[9 empty] | checkpoint | Toque check carried out on fixings and record results on checksheet*
[9 empty] | checkpoint | Any damaged to galvanis3 finish has been made good with correct galvanised spray*
Visual Representation in Web App (Block A Sample)
(Please leave the * as it is)

## Summerset St John Block B
Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Instruction to CONQA | Checklist Name
Site Summerset St John QA
Block B
Level 2
|  |  | Zone 1 |  |  |  | add this checklist:
|  |  | Zone 2 |  |  |  | add this checklist:
Level 3
|  |  | Zone 1 |  |  |  | add this checklist: |  | Type | Name | Values
|  |  | Zone 2 |  |  |  | add this checklist: |  | checklist-flat | QA - Brickwork
[9 empty] | section | Prestart
[9 empty] | checkpoint | Approval from Summerset foreman to begin blocklaying
[9 empty] | checkpoint | Setting out checked back to grid and datum as per architect setting out drawings
[9 empty] | checkpoint | DPC installed and checked before works commence*
|  | Level 4 | [6 empty] | section | Brick/ block work Installation
|  |  | Zone 1 |  |  |  | add this checklist: |  | checkpoint | Mortar mixed correctly and colour consistent
|  |  | Zone 2 |  |  |  | add this checklist: |  | checkpoint | Premium white mortar is used as per specification plan
[9 empty] | checkpoint | Mortar joints are in alignment
[9 empty] | checkpoint | Cavity width correct
[9 empty] | checkpoint | Cavity insulation installed as per plan
|  | Level 5 | [6 empty] | checkpoint | Standard Brick ties installed as per the specifications with correct spacing*
|  |  | Zone 1 |  |  |  | add this checklist: |  | checkpoint | Fero brick ties and retaining clips installed as per the manufactures recommendations*
|  |  | Zone 2 |  |  |  | add this checklist: |  | checkpoint | Cavity and brick ties free of mortar and debris
[9 empty] | checkpoint | Weep-holes checked and accurate (required every 3 bricks at base and sills)
[9 empty] | checkpoint | Brick sill installed and checked – 15 degree consistent fall
[9 empty] | checkpoint | Façade bricks are installed as per plan
|  | Level 6 | [6 empty] | checkpoint | Double layers of bricks are installed as per plan
|  |  | Zone 1 |  |  |  | add this checklist: |  | checkpoint | Both Horizontal and vertical fire cavity barrier installed - this is to be offered to Summerset before work scontinue to check and ensure verything is installed correctly*
|  |  | Zone 2 |  |  |  | add this checklist: |  | checkpoint | Brickwork line and level t ospecification tolerances*
[9 empty] | checkpoint | Movement joints installed as pers etting out drawings
[9 empty] | section | Hand over
[9 empty] | checkpoint | Final clean and handover
Level 7
|  |  | Zone 1 |  |  |  | add this checklist: |  | section | Brick shelf Angle
|  |  | Zone 2 |  |  |  | add this checklist: |  | checkpoint | Installed to sepecification and drawings
[9 empty] | checkpoint | Correct Fixing used*
[9 empty] | checkpoint | Brick support angle is line and level*
[9 empty] | checkpoint | Toque check carried out on fixings and record results on checksheet*
[9 empty] | checkpoint | Any damaged to galvanis3 finish has been made good with correct galvanised spray*
Visual Representation in Web App (Block A Sample)

## Summerset St John Block D
Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Instruction to CONQA | Checklist Name
Site Summerset St John QA
Block D
Level 3
|  |  | Zone 1 |  |  |  | add this checklist:
|  |  | Zone 2 |  |  |  | add this checklist:
|  |  | Zone 3 |  |  |  | add this checklist:
|  |  | Zone 4 |  |  |  | add this checklist:
Level 4
|  |  | Zone 1 |  |  |  | add this checklist: |  | Type | Name | Values
|  |  | Zone 2 |  |  |  | add this checklist: |  | checklist-flat | QA - Brickwork
|  |  | Zone 3 |  |  |  | add this checklist: |  | section | Prestart
|  |  | Zone 4 |  |  |  | add this checklist: |  | checkpoint | Approval from Summerset foreman to begin blocklaying
[9 empty] | checkpoint | Setting out checked back to grid and datum as per architect setting out drawings
[9 empty] | checkpoint | DPC installed and checked before works commence*
|  | Level 5 | [6 empty] | section | Brick/ block work Installation
|  |  | Zone 1 |  |  |  | add this checklist: |  | checkpoint | Mortar mixed correctly and colour consistent
|  |  | Zone 2 |  |  |  | add this checklist: |  | checkpoint | Premium white mortar is used as per specification plan
|  |  | Zone 3 |  |  |  | add this checklist: |  | checkpoint | Mortar joints are in alignment
|  |  | Zone 4 |  |  |  | add this checklist: |  | checkpoint | Cavity width correct
[9 empty] | checkpoint | Cavity insulation installed as per plan
|  | Level 6 | [6 empty] | checkpoint | Standard Brick ties installed as per the specifications with correct spacing*
|  |  | Zone 1 |  |  |  | add this checklist: |  | checkpoint | Fero brick ties and retaining clips installed as per the manufactures recommendations*
|  |  | Zone 2 |  |  |  | add this checklist: |  | checkpoint | Cavity and brick ties free of mortar and debris
|  |  | Zone 3 |  |  |  | add this checklist: |  | checkpoint | Weep-holes checked and accurate (required every 3 bricks at base and sills)
|  |  | Zone 4 |  |  |  | add this checklist: |  | checkpoint | Brick sill installed and checked – 15 degree consistent fall
[9 empty] | checkpoint | Façade bricks are installed as per plan
|  | Level 7 | [6 empty] | checkpoint | Double layers of bricks are installed as per plan
|  |  | Zone 1 |  |  |  | add this checklist: |  | checkpoint | Both Horizontal and vertical fire cavity barrier installed - this is to be offered to Summerset before work scontinue to check and ensure verything is installed correctly*
|  |  | Zone 2 |  |  |  | add this checklist: |  | checkpoint | Brickwork line and level t ospecification tolerances*
|  |  | Zone 3 |  |  |  | add this checklist: |  | checkpoint | Movement joints installed as pers etting out drawings
|  |  | Zone 4 |  |  |  | add this checklist: |  | section | Hand over
[9 empty] | checkpoint | Final clean and handover
[9 empty] | section | Brick shelf Angle
[9 empty] | checkpoint checkpoint checkpoint checkpoint checkpoint | Installed to sepecification and drawings
Correct Fixing used*
Brick support angle is line and level*
Toque check carried out on fixings and record results on checksheet*
Any damaged to galvanis3 finish has been made good with correct galvanised spray*
Visual Representation in Web App (Block A Sample)

## Summerset St John Block E
Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Instruction to CONQA | Checklist Name
Site Summerset St John QA
Block E
Level 3
|  |  | Zone 1 |  |  |  | add this checklist:
|  |  | Zone 2 |  |  |  | add this checklist:
|  |  | Zone 3 |  |  |  | add this checklist:
|  |  | Zone 4 |  |  |  | add this checklist:
Level 4
|  |  | Zone 1 |  |  |  | add this checklist: |  | Type | Name | Values
|  |  | Zone 2 |  |  |  | add this checklist: |  | checklist-flat | QA - Brickwork
|  |  | Zone 3 |  |  |  | add this checklist: |  | section | Prestart
|  |  | Zone 4 |  |  |  | add this checklist: |  | checkpoint | Approval from Summerset foreman to begin blocklaying
[9 empty] | checkpoint | Setting out checked back to grid and datum as per architect setting out drawings
[9 empty] | checkpoint | DPC installed and checked before works commence*
|  | Level 5 | [6 empty] | section | Brick/ block work Installation
|  |  | Zone 1 |  |  |  | add this checklist: |  | checkpoint | Mortar mixed correctly and colour consistent
|  |  | Zone 2 |  |  |  | add this checklist: |  | checkpoint | Premium white mortar is used as per specification plan
|  |  | Zone 3 |  |  |  | add this checklist: |  | checkpoint | Mortar joints are in alignment
|  |  | Zone 4 |  |  |  | add this checklist: |  | checkpoint | Cavity width correct
[9 empty] | checkpoint | Cavity insulation installed as per plan
|  | Level 6 | [6 empty] | checkpoint | Standard Brick ties installed as per the specifications with correct spacing*
|  |  | Zone 1 |  |  |  | add this checklist: |  | checkpoint | Fero brick ties and retaining clips installed as per the manufactures recommendations*
|  |  | Zone 2 |  |  |  | add this checklist: |  | checkpoint | Cavity and brick ties free of mortar and debris
|  |  | Zone 3 |  |  |  | add this checklist: |  | checkpoint | Weep-holes checked and accurate (required every 3 bricks at base and sills)
|  |  | Zone 4 |  |  |  | add this checklist: |  | checkpoint | Brick sill installed and checked – 15 degree consistent fall
[9 empty] | checkpoint | Façade bricks are installed as per plan
|  | Level 7 | [6 empty] | checkpoint | Double layers of bricks are installed as per plan
|  |  | Zone 1 |  |  |  | add this checklist: |  | checkpoint | Both Horizontal and vertical fire cavity barrier installed - this is to be offered to Summerset before work scontinue to check and ensure verything is installed correctly*
|  |  | Zone 2 |  |  |  | add this checklist: |  | checkpoint | Brickwork line and level t ospecification tolerances*
|  |  | Zone 3 |  |  |  | add this checklist: |  | checkpoint | Movement joints installed as pers etting out drawings
|  |  | Zone 4 |  |  |  | add this checklist: |  | section | Hand over
[9 empty] | checkpoint | Final clean and handover
Level 8
|  |  | Zone 1 |  |  |  | add this checklist: |  | section | Brick shelf Angle
|  |  | Zone 2 |  |  |  | add this checklist: |  | checkpoint | Installed to sepecification and drawings
|  |  | Zone 3 |  |  |  | add this checklist: |  | checkpoint | Correct Fixing used*
|  |  | Zone 4 |  |  |  | add this checklist: |  | checkpoint | Brick support angle is line and level*
[9 empty] | checkpoint | Toque check carried out on fixings and record results on checksheet*
[9 empty] | checkpoint | Any damaged to galvanis3 finish has been made good with correct galvanised spray*
Visual Representation in Web App (Block A Sample)

## Blank - New Project Structure
Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Instruction to CONQA | Checklist Name

## Checklists
Type | Name | Values
checklist-flat | QA - Brickwork - Block A
checkpoint | Mortar mixed correctly and colour consistent
checkpoint | Premium white mortar is used as per specification plan
checkpoint | Mortar joints are in alignment
checkpoint | Cavity width correct
checkpoint | Cavity insulation installed as per plan
checkpoint | Standard Brick ties used are as per the specifications, correct length and installed correctly – 5 degree
checkpoint | Fero brick ties installed as per the specifications
checkpoint | Cavity and brick ties free of mortar and debris
checkpoint | Weep-holes checked and accurate (required every 3 bricks at base and sills)
checkpoint | Brick sill installed and checked – 15 degree consistent fall
checkpoint | Façade bricks are installed as per plan
checkpoint | Double layers of bricks are installed as per plan
checklist | QA - Blocklaying
section | Prestart
checkpoint | Approval from Summerset foreman to begin blocklaying
checkpoint | Set up accurate stringline for entire face
section | Blocking Installation
checkpoint | Check blocks and any broken ones discarded
checkpoint | Temporary bracing has been installed as required
checkpoint | Walls have been properly grouted
checkpoint | Any openings are temporarily braced / Supported
checkpoint | Space is warm, with proper air flow to promote drying of mortar
checkpoint | Temporary lighting has been installed on both sides of wall(to avoid dark spaces)
checkpoint | Any reinforcement including lintels, rebar etc have been installed as per engineering design
checkpoint | Wash holes in tidy conditions
checkpoint | Wall is installed true / plumb and in line with layout
section | Handover
checkpoint | Block installation completed to specified satandard & finish