## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | QA - Brickwork - Block A |  |  |  |  | Yes | QA - Brickwork - Block A | 117c7bad-ceaa-4b75-ae1d-79ed4b890395
checkpoint-status |  |  | checkpoint | Mortar mixed correctly and colour consistent
checkpoint-status |  |  | checkpoint | Premium white mortar is used as per specification plan
checkpoint-status |  |  | checkpoint | Mortar joints are in alignment
checkpoint-status |  |  | checkpoint | Cavity width correct
checkpoint-status |  |  | checkpoint | Cavity insulation installed as per plan
checkpoint-status |  |  | checkpoint | Standard Brick ties used are as per the specifications, correct length and installed correctly – 5 degree
checkpoint-status |  |  | checkpoint | Fero brick ties installed as per the specifications
checkpoint-status |  |  | checkpoint | Cavity and brick ties free of mortar and debris
checkpoint-status |  |  | checkpoint | Weep-holes checked and accurate (required every 3 bricks at base and sills)
checkpoint-status |  |  | checkpoint | Brick sill installed and checked – 15 degree consistent fall
checkpoint-status |  |  | checkpoint | Façade bricks are installed as per plan
checkpoint-status |  |  | checkpoint | Double layers of bricks are installed as per plan
checklist-sectioned |  |  | checklist | QA - Blocklaying |  |  |  |  | Yes | QA - Blocklaying | c3d0fb45-59a8-4440-ad81-0ebc129620bc
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Approval from Summerset foreman to begin blocklaying
checkpoint-status |  |  | checkpoint | Set up accurate stringline for entire face
checkpoint-group |  |  | section | Blocking Installation
checkpoint-status |  |  | checkpoint | Check blocks and any broken ones discarded
checkpoint-status |  |  | checkpoint | Temporary bracing has been installed as required
checkpoint-status |  |  | checkpoint | Walls have been properly grouted
checkpoint-status |  |  | checkpoint | Any openings are temporarily braced / Supported
checkpoint-status |  |  | checkpoint | Space is warm, with proper air flow to promote drying of mortar
checkpoint-status |  |  | checkpoint | Temporary lighting has been installed on both sides of wall(to avoid dark spaces)
checkpoint-status |  |  | checkpoint | Any reinforcement including lintels, rebar etc have been installed as per engineering design
checkpoint-status |  |  | checkpoint | Wash holes in tidy conditions
checkpoint-status |  |  | checkpoint | Wall is installed true / plumb and in line with layout
checkpoint-group |  |  | section | Handover
checkpoint-status |  |  | checkpoint | Block installation completed to specified satandard & finish