## Structure
Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Instruction to CONQA | Checklist Name
TAMAKI HEALTH
Open space
Cable containment
Tier 4: Catenaries | please add: | Catenaries
Tier 4: Cable tray | please add: | Cable tray
Tier 4: conduit | please add: | conduit
Tier 4: floor boxes | please add: | floor box
Tier 4: trunking | please add: | trunking
First fix
Tier 4: Flush boxes | please add: | Flush box
Tier 4: Cabling; Tier 5: Power | please add: | Power circuits first fix
Tier 5: Lighting | please add: | Lighting circuits first fix
Second fix
Tier 4: Switchboard | please add: | Switchboard
Tier 4: Power | please add: | Power circuits second fix
Tier 4: Lighting | please add: | Lighting circuits second fix
Tier 3: Documentation | please add: | Documentation
| Meeting rooms | same as common
Tier 2: lunch room /kitchen; Tier 4: kitchen | please add: | kitchen checklist

## Checklists
Type | Name | Values
checklist-flat | Catenaries
checkpoint | Supported correctly
checkpoint | Correct locations
checklist-flat | Cable tray
checkpoint | Installed correct location
checkpoint | Installed correct height
checkpoint | Installed correctly
checklist-flat | floor box
checkpoint | floor box type identified Surface/ recessed
checkpoint | cut out size correctly marked for bulider
checkpoint | location marked
checkpoint | duct size correct
checklist-flat | Trunking
checkpoint | size / type / category correct
checkpoint | location and height confirmed
checkpoint | droppers / cable acess installed
checkpoint | installed level and flush
checklist-flat | Conduit
checkpoint | level / square
checkpoint | correct size
checkpoint | fixings
checklist-flat | Flush box
checkpoint | Correct location
checkpoint | Correct height
checklist-flat | Power circuits first fix
checkpoint | Cable schedule
checkpoint | Cable size correct
checkpoint | Cabling to correct locations
checkpoint | droppers / starters wired
checkpoint | Tv locations wired
checklist-flat | Lighting circuits first fix
checkpoint | Cabling to correct location as per plan
checkpoint | Emergency lighting cabelled
checkpoint | Number of fittings correct
checkpoint | Local switch wire installed
checkpoint | Sensor control wire installed
checkpoint | Cabinet lighting confirmed / cabled
checklist-flat | Power circuits second fix
checkpoint | Outlets installed, level and labelled
checkpoint | Starters installed
checkpoint | Floor boxes fit off
checkpoint | droppers / starters wired and installed
checkpoint | Tv locations fit off
checklist-flat | Lighting circuits second fix
checkpoint | Correct light type installed
checkpoint | Correct number installed
checkpoint | Correct location
checkpoint | Local switching installed
checkpoint | Sensor installed
checkpoint | Emergency lighting type installed
checklist-flat | Switchboard
checkpoint | Cables dressed
checkpoint | All cables terminated
checkpoint | Circuits labelled
checkpoint | Circuits tested
tickbox | IRT Mohm
tickbox | Earth Loop
tickbox | Rcd
tickbox | Polarity
tickbox | Visual
tickbox | bonding
tickbox | Earth cont.
checklist-flat | Documentation
checkpoint | C.O.C.
checkpoint | R.O.I.
checkpoint | Test sheets complete
checkpoint | As builts complete
checkpoint | PS3
checkpoint | Emergency lighting labelled
checkpoint | EM test sheets
checklist-flat | kitchen
checkpoint | elevations reviewed
checkpoint | equipment schedule reviewed
checkpoint | loading / cable sizes correct
checkpoint | flush boxes correct height above / below bench
checkpoint | isolator postitions identified and wired
checkpoint | outlets fit off and level
checkpoint | isolators installed / tested
checkpoint | under bench / cabinet LED

## Blank - New Project Structure
Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Instruction to CONQA | Checklist Name