## Structure
Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Instruction to CONQA | Checklist Name
Ignite college
stage 1
Tier 3: demolition / isolations |  | demolition / isolations
Tier 3: Cable containment | please add: | Catenaries
Tier 4: Catenaries | please add: | Cable tray
Tier 4: Cable tray | please add: | Floor penetrations
Floor penetrations
Tier 3: First fix | please add: | Flush box
Tier 4: Flush boxes | please add: | Power circuits first fix
Tier 4: Cabling; Tier 5: Power | please add: | Lighting circuits first fix
Tier 5: Lighting | please add: | Data first fix
Data
Tier 3: Second fix | please add: | Switchboard
Tier 4: Switchboard | please add: | Power circuits second fix
Tier 4: Power | please add: | Lighting circuits second fix
Tier 4: Lighting | please add: | Data second fix
Tier 4: Data | please add: | Documentation
Documentation
Tier 2: stgate 2 | Same stage 1
Tier 2: stage 3 | Same as stage 1

## Checklists
Type | Name | Values
checklist-flat | demolitions / isolations
checkpoint | all circuts identified
checkpoint | power circuts for removal identified
checkpoint | circuts removed from switchboard / isolated
checkpoint | lighting circuts identified
checkpoint | lighting removed from switchboard / isolated
checkpoint | all cables removed and tied above ceiling level
checkpoint | all cables checked DEAD!
checklist-flat | Catenaries
checkpoint | Supported correctly
checkpoint | Correct locations
checklist-flat | Cable tray
checkpoint | Installed correct location
checkpoint | Installed correct height
checkpoint | Installed correctly
checklist-flat | Floor penetrations
checkpoint | Penetration/chase marked as per plan
checkpoint | Depth/width correct for conduit/floor box
checklist-flat | Flush box
checkpoint | Correct location
checkpoint | Correct height
checklist-flat | Power circuits first fix
checkpoint | Cable schedule
checkpoint | Cable size correct
checkpoint | Cabling to correct locations
checkpoint | Cables to isolators ie kitchen outlets
checkpoint | Position on elevations confirmed
checklist-flat | Lighting circuits first fix
checkpoint | Cabling to correct location as per plan
checkpoint | Emergency lighting cabelled
checkpoint | Number of fittings correct
checkpoint | Local switch wire installed
checkpoint | Sensor control wire installed
checkpoint | Cabinet lighting confirmed/cabled
checklist-flat | Data first fix
checkpoint | Data cables in place to location
checkpoint | Labelled correctly x 2
checkpoint | Cables to floor box
checkpoint | Data tv locations
checkpoint | Wap locations wired
checklist-flat | Power circuits second fix
checkpoint | Outlets installed, level and labelled
checkpoint | Starters installed
checkpoint | Floor boxes fit off
checkpoint | Kitchen outlets/isolators/hw kits
checklist-flat | Lighting circuits second fix
checkpoint | Correct light type installed
checkpoint | Correct number installed
checkpoint | Correct location
checkpoint | Local switching installed
checkpoint | Sensor installed
checkpoint | Emergency lighting type installed
checklist-flat | Data second fix
checkpoint | Outlets installed and labeled
checkpoint | Data floor boxes installed
checkpoint | Cabinet fit off
checkpoint | Wap installed
checklist | Switchboard Checklist
checkpoint | switchboard securly fastened
checkpoint | switcboard bonded
checkpoint | teminals correctly crimped
checkpoint | lugs heat shrinked
checkpoint | lugs torqued
checkpoint | polarity correct
checkpoint | All cables tested
checkpoint | All labels installed
checkpoint | Test sheets complete
checkpoint | C.O.C complete
checkpoint | R.O.I required
checkpoint | live tests complete

## Blank - New Project Structure
Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Instruction to CONQA | Checklist Name