## FOUNDATIONS
checklist | Site Establishment Checklist
checkpoint | Any relevant dilapidation requirements captured
checkpoint | Attach relevant site establishment photos/ documents
checkpoint | Appropriate isolation of site (hoardings / fencing)
checkpoint | Sufficient & Appropriate site/H&S signage erected
checkpoint | Site establishment completed
checklist | Concrete Pour Checklist (Self Perform)
section | Pour Details
text | Area to be poured:
text | Date of pour:
checkpoint | Latest drawings available, checked and referenced
section | Formwork and Embedded Items
checkpoint | Formwork - location, height, falls and dimensions checked and accurate
checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint | All surfaces correctly prepared (e.g. joints to existing concrete, release agent to formwork etc)
checkpoint | Any control joints/ stop ends installed accurately and correctly braced
section | Reinforcing
checkpoint | Trades QA received, attached, reviewed and approved
hold point | Raise Remedial / Request trades QA / Signoff
checkpoint | Size and type correct to specification
checkpoint | Reinforcing spacing and location correct
checkpoint | Specified covers checked/correct
checkpoint | Splice laps checked/correct
checkpoint | All couplers installed correctly (if reid bar couplers have been used, has epconC8 epoxy been used as specified)
checkpoint | Any starter bars are installed correctly (location, size and spacing )
checkpoint | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
checkpoint | Welding certificates sited and attached
checkpoint | Mill certificate reviewed, attached and approved
checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
section | Pre-Pour Completion (Approval to pour)
checkpoint | Any waterproofing elements have been correctly installed and checked
checkpoint | Any relevant service requirements completed (locations checked and accurate)
checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
checkpoint | All relevant inspections completed and attached
checkpoint | Main contractor inspection completed - Approval given to pour concrete
section | Concrete Supplier Specifics
text | Supplier Name:
text | Specified concrete strength:
text | Concrete strength ordered:
text | Concrete quantity ordered:
checkpoint | Test blocks booked
checkpoint | All concrete dockets photographed/ attached
checkpoint | Concrete strength test reports attached and required concrete strength achieved
section | Concrete Distribution
checkpoint | General distribution photos, documents and observations attached
checkpoint | All concrete distributed correctly (area left clean and tidy)
section | Placement Method
checkpoint | Placement methodology confirmed and necessary plant and equipment on site
checkpoint | Heights and falls checked/confirmed before placement
button | Is the cover correct to specification | Yes, No
checkpoint | Heights and falls checked/ confirmed after placement
checkpoint | Any curing compound applied correctly
checkpoint | Concrete placement completed - specified level of finish achieved
checkpoint | Area left clean and tidy
section | Post Pour Checks/Sign Off
checkpoint | Any remedial work completed
checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
checklist | Timber Framing (Audit)
checkpoint | Approval given to install timber framing
checkpoint | Dimensions / locations checked and accurate
checkpoint | All frames are square
checkpoint | Frames are straight and level
checkpoint | Fixings are correct
checkpoint | Any bracing requirements installed
checkpoint | Any additional photos, comments and observations
checkpoint | Trades QA received, attached, reviewed and approved
hold point | Raise Remedial / Request trades QA / Signoff
checkpoint | All framing completed correctly within tolerance in respective area
checklist | Site Concrete Checklist
checkpoint | Excavation depth and location checked and correct
checkpoint | Ground conditions acceptable
checkpoint | Concrete specifications checked, correct and delivery docket photographed
checkpoint | Site concrete placed
text | Placed by:
checkpoint | Concrete placed to the correct height
checkpoint | Site concrete pour completed and finish acceptable
checklist | Piling Pre-Start Checklist
checkpoint | Piles setout, surveyed and clearly marked
checkpoint | Accurate RL confirmed for piling reference
checkpoint | Acceptable site conditions and access for piling rig
checkpoint | Additional photos/ observations / reports attached
checkpoint | Approval given to commence piling
bool | approval given to dig
bool | relevant services identified and isolated / clearly marked
bool | relevant information communicated to piling trade
bool | any environmental requirements considered and enacted
checklist | Piling Checklist (Audit)
checkpoint | Trades QA received, attached, reviewed and approved
checkpoint | Relevant inspections completed and attached - any observations recorded and closed out
checkpoint | Piling spoil removed and work area left clean and tidy
checkpoint | Any additional completion/handover documents completed and attached
checkpoint | All piles completed (locations and heights checked and correct within tolerance)

## FOUNDATIONS SERVICES
checklist | Underground Services Checklist (Audit)
checkpoint | Electrical services/ conduits installed, fixed in correct location, backfilled and correct as per design
checkpoint | Hydraulic services installed, fixed in correct location, backfilled and correct as per design
checkpoint | Telecommunication/Fibre installed, fixed in correct location, backfilled and correct as per design
checkpoint | Any other relevant services installed, fixed in correct location, backfilled and correct as per design
checkpoint | Any relevant inspections carried out and attached - observations documented and closed out
checkpoint | All subfloor services correctly installed to respective area
checklist | Manhole Install Checklist
checkpoint | Latest construction drawings referenced and followed
text | Drawing & Revision Number
checkpoint | Setout & Excavation completed checked and accurate
checkpoint | Correct manhole size installed to specified Invert Level
checkpoint | Manhole benching completed and acceptable (photo required)
checkpoint | CCTV test complete
checkpoint | Manhole Installation reviewed and approved (photo required)
checkpoint | Backfill completed & compacted as specified (Photos during backfill required)
checklist | Stormwater (Main Line) - Pipeline Installation Checklist
checkpoint | Latest construction drawings referenced and followed
text | Drawing & Revision Number
checkpoint | Setout & Excavation completed checked and accurate
checkpoint | Bedding depth and material correct (photo required)
checkpoint | Correct pipe (size, material & class) laid to specified level, grade and jointed as specified
text | Grade of Pipe-Line %
checkpoint | Connections to manholes complete and approved (photo required)
checkpoint | Backfill completed & compacted as specified (Photos during backfill required)
checkpoint | Relevant tests, photos & as-built information provided
checklist | Waste Water (Main Line) - Pipeline Installation Checklist
checkpoint | Latest construction drawings referenced and followed
text | Drawing & Revision Number
checkpoint | Setout & Excavation completed checked and accurate
checkpoint | Bedding depth and material correct (photo required)
checkpoint | Correct pipe (size, material & class) laid to specified level, grade and jointed as specified
text | Grade of Pipe-Line %
checkpoint | Connections to manholes complete and approved (photo required)
checkpoint | Air/water test completed (photo of pressure gauge taken at START & FINISH)
checkpoint | Backfill completed & compacted as specified
checkpoint | Relevant tests, photos & as-built information attached
checklist | Watermain - Pipeline Installation Checklist
checkpoint | Latest construction drawings referenced and followed
text | Drawing & Revision Number
checkpoint | Setout & Excavation completed checked and accurate
checkpoint | Correct pipe (size, material & class) laid to specified level, grade and jointed as specified
checkpoint | Connections complete and approved (photo required)
checkpoint | Relevant test completed (photos required)
checkpoint | Backfill completed & compacted as specified
checkpoint | Relevant tests, photos & as-built information attached
checklist | Cold Water Checklist
section | Cold water main
checkpoint | Connections brazed correctly
checkpoint | Clip Spacing to manufacturer's specs horizontal/ vertical
checkpoint | Valves fitted correctly
section | Hot water main
checkpoint | Connections welded correctly
checkpoint | Clip spacing to manufacturer's specs horizontal/ vertical
checkpoint | Expansion allowed for
checkpoint | Lagging installed and neat
checkpoint | Valves fitted correctly
section | General
checkpoint | Open ends of riser capped for testing
checkpoint | Checked for crossovers
checkpoint | Pressure test to 1500kpa for 30mins
checkpoint | Seismic bracing for pipework longitude and latitude
checkpoint | Lateral labelling of pipework backflow devices fitted
checkpoint | Pre Line Inspection Passed
checkpoint | Installers name & date works completed
text | Installers name
text | Date:
checkpoint | Tested by & date
text | Tested by:
text | Date tested:
checkpoint | Council inspector sign off and date
checklist | In Ground Water & Gas Mains Checklist
section | Water mains
checkpoint | All fittings scrapped correctly
checkpoint | Iso used on fittings
checkpoint | Valves fitted correctly
checkpoint | Fittings welded & weld indicator has popped out
checkpoint | Trace wire and ID tape installed
section | Gas main
checkpoint | All fittings scrapped correctly
checkpoint | Iso used on fittings
checkpoint | Valves fitted correctly
checkpoint | Fittings welded & weld indicator has popped out
checkpoint | Trace wire and ID tape installed
section | General
checkpoint | All open ends capped
checkpoint | Pipework bedded correctly
checkpoint | Tidy work areas
checkpoint | Pressure test pipework
checkpoint | Visual check (for leeks from valves, tees, saddles, etc)
checkpoint | Backfill around pipework with fines
checkpoint | as-built completed and photo
checkpoint | Installers name & date works completed
text | Installers name
text | Date:
checkpoint | Tested by & date
text | Tested by:
text | Date tested:
checkpoint | Council inspector sign off and date
section | General
checkpoint | Mains water change over
checkpoint | Flow test pump
checkpoint | Pressure tests pipework
checkpoint | Visual check (for leaks from valves, tees, saddles, etc)
checkpoint | Non return valves fitted
checkpoint | Installers name & date works completed
text | Installers name
text | Date:
checkpoint | Tested by & date
text | Tested by:
text | Date tested:
checkpoint | Council inspector sign off and date
checklist | Sewer - Pipeline Installation Checklist
section | Pipe Laying
checkpoint | Latest consented drawings
text | Drawing Ref No.
checkpoint | Setout completed checked and accurate
checkpoint | Excavation Accurate - Location & Depth
checkpoint | Bedding depth and material correct
checkpoint | Correct pipe laid to specified level and grade (all joints sealed correctly as specified)
text | Grade of Pre-Line %
text | Product Type
checkpoint | Install Tests completed, reviewed & approved
text | Local Authority Inspection Passed
text | Name of inspector
text | Date
checkpoint | Pipe Laying Completed
bool | Bedding Sound
bool | Soil Removed
bool | Trench Compacted
bool | Hard Filled
checkpoint | Connections to manholes complete and approved
checkpoint | Air Test Complete
section | Backfill
checkpoint | Backfill methodology and material confirmed
checkpoint | Any waterproofing/ drainage / service requirements completed and inspected
checkpoint | Approval given to commence backfill - attach any other relevant inspections and observations closed out
checkpoint | General photos and observations during backfill
checkpoint | Backfill completed correctly and heights checked/ correct

## STRUCTURE
checklist | Backfill
checkpoint | Backfill methodology and material confirmed
checkpoint | Any formwork/ debris removed from area
checkpoint | Any waterproofing/ drainage / service requirements completed and inspected
checkpoint | Approval given to commence backfill - attach any other relevant inspections and observations closedout
checkpoint | General photos and observations during backfill
checkpoint | Trades QA received, attached, reviewed and approved
checkpoint | Backfill completed correctly and heights checked/ correct - desired compaction achieved
checklist | Waterproofing
checkpoint | Trades QA received, attached, reviewed and approved
checkpoint | Preparation / Substrate acceptable
checkpoint | Correct product delivered and checked - approval given to install
checkpoint | General photos/comments during install
checkpoint | Any inspections / observations documented, reviewed and closed out
checkpoint | Waterproofing install completed, reviewed and approved to meet required specifications
checklist | Concrete Pour
section | Formwork and Embedded Items
checkpoint | Latest drawings available, checked and referenced
checkpoint | Trades QA received, attached, reviewed and approved
checkpoint | Grids and RLs clearly marked for reference
checkpoint | Formwork - location, height, falls and dimensions checked and accurate
checkpoint | Formwork sufficiently fixed and braced (incl any propping)
checkpoint | Shear studs installed as-per shop drawings & check ring test
checkpoint | Any rebates/ nibs / cast in items are correctly positioned, sized and appropriately fixed in place
checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint | All surfaces correctly prepared (e.g joints to exisiting concrete, release agent to formwork etc)
checkpoint | Any control joints/ stop ends installed accurately and correctly braced
checkpoint | Any additional formwork photos and observations
checkpoint | All formwork elements completed and ready for concrete pour ( excess debris removed )
section | Reinforcing
checkpoint | Trades QA received, attached, reviewed and approved
checkpoint | Size and type correct to specification
checkpoint | Reinforcing spacing and location correct
checkpoint | Specified covers checked/correct
checkpoint | Splice laps checked/correct
checkpoint | Any starter bars are installed correctly (location, size and spacing )
checkpoint | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
section | Pre-Pour Completion (Approval to pour)
checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
checkpoint | Council inspection completed and attached
checkpoint | All relevant inspections completed and attached
checkpoint | Main contractor inspection completed - Approval given to pour concrete
checkpoint | Heights and falls checked/confirmed before placement
button | Is the cover correct to specification
checkpoint | General photos and observations of concrete placement attached
section | Pour / Post-Pour Checks/Sign Off
checkpoint | Concrete checked on arrival & correct (slump, MPa etc)
checkpoint | Heights and falls checked/ confirmed after placement
checkpoint | Any curing compound applied correctly
checkpoint | Concrete surface to specifications
checkpoint | Area left clean and tidy
checkpoint | Any remedial work completed
checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
checklist | Structure - Concrete Pour - Modified (NB: Only to be used upon Approval by PM)
section | Formwork and Embedded Items
checkpoint | Latest drawings available, checked and referenced
checkpoint | Any additional formwork photos and observations
checkpoint | All formwork elements completed and ready for concrete pour ( excess debris removed )
section | Reinforcing
checkpoint | Trades QA received, attached, reviewed and approved
checkpoint | Verified Size and type correct to specification
checkpoint | Any additional photos and observations
section | Pre-Pour Completion (Approval to pour)
checkpoint | Heights and falls checked/confirmed before placement
button | Is the cover correct to specification
checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
checkpoint | Main contractor inspection completed - Approval given to pour concrete
checkpoint | General photos and observations of concrete placement attached
section | Pour / Post-Pour Checks/Sign Off
checkpoint | Concrete checked on arrival & correct (slump, MPa, approved mix, etc)
checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
checkpoint | Concrete surface to specifications
checkpoint | Concrete results 7D & 28D Passed
checkpoint | Trades QA received, attached, reviewed and approved
checkpoint | Any remedial work completed
checklist | Drypacking and Grouting
checkpoint | Trades QA received, attached, reviewed and approved
checkpoint | Preparation / Substrate acceptable
checkpoint | Installed as per installation requirements
checkpoint | General photos/comments during install
checkpoint | Any inspections / observations documented, reviewed and closed out
checkpoint | All drypacking and grouting completed , reviewed and approved to meet required specifications
checklist | CFRP Strengthening
checkpoint | Has the concrete been prepared
checkpoint | Has the product been installed as per manufacturers requirement
checkpoint | Trades QA received, attached, reviewed and approved
button | Is this an architectural area requiring attention
checklist | Intumescent Painting
checkpoint | Steel Erection completed and approval given to apply Intumescent Paint
checkpoint | Paint specifications and product checked
checkpoint | Paint applied using correct methodology
checkpoint | Positector readings uploaded
checkpoint | General photos, comments and observations during paint application
checkpoint | Trades QA received, attached, reviewed and approved
checkpoint | Paint application complete - area inspected, checked and correct to required specification
checklist | Blockwork
section | Pre-Pour Checks
checkpoint | Location Recorded
text | Zone / Level / Grid(s) recorded
checkpoint | Starter bars: correct size, length, position, clean
checkpoint | Control joints/construction joints/expansion joints are located and provided
checkpoint | Penetrations/embedded items - Overall Pass
button | Penetrations located and formed/allowed for (i.e openings, services penetrations)
button | Embedded items (i.e anchor bolts etc) are correct and at the correct location
checkpoint | Blockwork specification and quality - Overall Pass
button | Block type, quality, moisture content, finish
button | Mortar condition, specification, finish
button | Course type, square cuts, aligned
button | Cleanout ports provided
button | Debris and droppings removed
checkpoint | Reinforcement - Overall Pass
button | Bars: Correct location, quantity, diameter, grade, spacing,
button | Reinforcement is clean and securely tied Laps and bends correct
button | Lintel and trimmer reinforcing above and around openings and penetrations etc
button | Control joint reinforcing, dowel bars, tape provided
button | Bond beam reinforcing provided at the top of wall
button | Earthing bars present where required, including cable connections
button | Grout compressive strength, condition and admixtures (20MPa min., 5mm - 12mm agg.)
checkpoint | Engineer informed of pour (see consultant folder and ensure observations are closed out)
holdpoint | All inspectors comments addressed
section | Pour /Post Pour
checkpoint | General photos/comments/observations during placement
checkpoint | Trades QA received & complete
button | Grout dockets & test cylinder results recorded
checklist | Structural Steel
checkpoint | Steel inspected on arrival, checked and correct and no significant damage
checkpoint | Trades QA received, attached, reviewed and approved
checkpoint | Correct location and orientation
checkpoint | All drypacking and grouting completed , reviewed and approved to meet required specifications
checkpoint | General photos / comments / observations during install

## FACADE
checklist | Service Penetrations to Rigid Air Barriers
checkpoint | All pipes should be sealed with caulk, a gap between the pipe and air barrier should be between 3-8mm
checkpoint | Ducts are sealed with caulking and backing rods for gaps under 35mm. Gaps over 35mm is sealed with rubber gaskets or flashing with caulking. All seals on duct penetrations require photographic evident particularly the top seal and be signed off.
checkpoint | Cables penetrations are sealed with caulking.
button | Caulking material should be applied between cables before packing the bundle, a minimum of 2 cable ties should be tightly applied between 5 and 10mm apart to minimise movement where the caulking material is applied.
button | Bundling of cables should be limited to 8 cables.
button | Spacer (backing rods) with a minimum size of 5mm should be placed between cable bundles.
checkpoint | Cable trays are expected to be treated similar to fire/smoke penetration which the red highlighting the caulking material.
checklist | Envelope - Warm roof
checkpoint | Substrate clear of debris (no sharp edges/ air pockets)
checkpoint | Vapour barrier installed (up parapet)
checkpoint | PIR insulation (brick pattern, tight joint)
checkpoint | Cement board (Perma base Dek correct fixing)
checkpoint | Soprema Sopradere quick primer
checkpoint | Membrane installed (80mm min lap)
checkpoint | Duo Capsheet installed
checkpoint | Internal gutters (ply installed, lap of membrane and capsheet into drain)
checkpoint | Seal around drain
checklist | Envelope - Internal gutter
checkpoint | 17mm C-D structural plywood
checkpoint | minimum fall of 1:100 (0.57°)
checkpoint | 5 mm fillets
checkpoint | Locations for outlets and sumps
checkpoint | Correct width and level/depth
checkpoint | General photos, comments and observations during paint application
checkpoint | Trades QA received, attached, reviewed and approved
checklist | Timber Framing
checkpoint | Dimensions / locations checked and accurate
checkpoint | All frames are square
checkpoint | Frames are straight and level
checkpoint | Fixings are correct including seizmac requirements
checkpoint | Any additional photos, comments and observations
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | All framing completed correctly within tolerance in respective area
checkpoint | Signed Off
checklist | Envelope - Parapet
checkpoint | Structural stee level and in correct location
checkpoint | Dry packing complete
checkpoint | Timber/DPC adequately fixed to framing
checkpoint | Timber framing @ 400 c/c
checkpoint | Ply correctly fixed (21mm H3.2)
checkpoint | Insulation correctly installed
checkpoint | Curtain wall bracket checked
checkpoint | Curtain wall checked
checkpoint | Photograph curtain wall junctions
checkpoint | Steel top plate (parapet build up)
checkpoint | Parapet ply installed (21mm H3.2)
checkpoint | EDPM installed to parapet
checkpoint | Integrity of the EPDM airseals. All corner junctions must be photographed and signed off
checkpoint | The connection between the EPDM airseal and the EQUUS SOPREMA DUOTHERM warm roof cap sheet requires sign off.
checkpoint | Membrane installed to EPDM (check laps and junctions 150mm to roofing)
checkpoint | Integrity of the membrane to the EPDM. All corner junctions must be photographed and signed off
checkpoint | Cap flashing installed
checklist | Envelope - Anchors
checkpoint | Installed as per drwg
checkpoint | sealed/waterproofed
checkpoint | General photos, comments and observations during paint application
checkpoint | Trades QA received, attached, reviewed and approved
checklist | Profile Metal Checklist
checkpoint | Product checked and correct as per specification
checkpoint | All prestart checks completed and approval given to install
checkpoint | General photos, comments and observations during install
checkpoint | Relevant Services considered, checked and approved where applicable
checkpoint | All cladding elements completed, checked and approved as per specifications
holdpoint | Request Signoff
checklist | Envelope - Sills
section | Sills
checkpoint | No sharp edges
checkpoint | Substrate applied (membrane applied)
checkpoint | Sill try to be sealed (check for backing rod and sealant)
checkpoint | Sill tray fixed at correct centres
checkpoint | Check workmanship of junctions and seals
checkpoint | Check lap of membrane
section | Airtightness
checkpoint | All unexposed caulking should use light colour caulk (eg, Light gray, or white)
checkpoint | Check corner junctions for quality. (Typically, the lab test only covers typical panels.) Particularly without factory made corners.
checkpoint | Mounting brackets sealed to the slab with caulking, tolerance slots should also be sealed
checklist | Aluminium Joinery / Glazing
section | Joinery Install
checkpoint | Opening approved (ready for install)
checkpoint | Joinery in correct location
checkpoint | Appropriate fixings installed
checkpoint | Any air/ weather seals completed
checkpoint | Appropriate external flashings installed and sealed
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | Inspection completed and joinery install completed as per specification
section | Final Inspection/Sign Off
checkpoint | Install completed, reviewed and approved
checkpoint | Item checked, functioning and damage free
checklist | Curtain Walls
section | Pre-construction
checkpoint | Inspected and accepted the work area and surfaces ready to commence work
checkpoint | Confirmed site storage requirements, packaging and preservation
section | Opening Handover
checkpoint | Visual check of opening is completed
checkpoint | Steel flat plates or sill have been installed correctly
checkpoint | Trade inspected and opening handed over
section | Installation
checkpoint | Stud welds completed in the area
checkpoint | Brackets installed and welded off
checkpoint | Curtain wall panel installed correctly
checkpoint | 150mm depth rockwool fire insulation installed with 33% compression with 50mm LG zed clips at 600mm centers
checkpoint | Hilti CFS-SP Sil silicone based joint sealant spray min 15mm overlap with 2mm min film thickness
checkpoint | 1.2mm THK continuous galvanised pressing on top of HILTI spray
checkpoint | Aluminum flashing installed and sealed with silicone
section | Airtightness
checkpoint | Top and bottom of all mullions capped and sealed
checkpoint | Smoke seals are sealed with a light coloured caulk
checkpoint | Beware of smoke seals near columns where the installers are restricted in applying caulk
section | Completion
checkpoint | Removal of temporary fixings, spacers & packers
checkpoint | Panel cleaned to remove installation marks
checkpoint | Panel surface are defects free
section | Final Inspection
checkpoint | All defects complete and “signed off”
checkpoint | Issued Façade Maintenance Manuals, service agreements & all warrantees and guarantees
section | Subcontractor Sign Off
checkpoint | Subcontractor Sign Off

## FITOUT
checklist | Ceiling Preline incl High Level Services
section | QA - Plumbing First Fix
checkpoint | Reference Drawings ( add numbers and revisions)
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | Consultants Inspection sign off
checkpoint | Any additional photos, comments and observations
checkpoint | Council inspection and testing complete and signed off
checkpoint | Engineer has signed off Seismic restraints
checkpoint | Witness testing of pipework by Hawkins
section | Fire Protection (Sprinklers & Alarms) First Fix
checkpoint | Reference Drawings ( add numbers and revisions)
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | Consultant inspection sign off
checkpoint | Any additional photos, comments and observations
checkpoint | Engineer has signed off Seismic restraints
checkpoint | Witness testing of pipework by Hawkins
section | Mechanical Services First Fix
checkpoint | Reference Drawings ( add numbers and revisions)
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | Any additional photos, comments and observations
checkpoint | All required testing complete
checkpoint | Engineer has signed off Seismic restraints
checkpoint | Consultant sign off
checkpoint | All ends covered/protected to reduce debris
checkpoint | Witness testing of compliance check by Hawkins
section | Electrical First Fix
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | All required testing complete
checkpoint | Any additional photos, comments and observations
checkpoint | Consultant sign off
checkpoint | Engineer has signed off Seismic restraints
checkpoint | Witness testing of compliance check by Hawkins
section | Data First Fix
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | All required testing complete
checkpoint | Any additional photos, comments and observations
checkpoint | Consultant sign off
checkpoint | Engineer has signed off Seismic restraints
checkpoint | Witness testing of compliance check by Hawkins
section | Security First Fix
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | All required testing complete
checkpoint | Any additional photos, comments and observations
checkpoint | Consultant sign off
checkpoint | Engineer has signed off Seismic restraints
checkpoint | Witness testing of compliance check by Hawkins
section | Rondo Ceiling Grid Installation
checkpoint | Service penetrations mark out completed, checked and acceptable (clashes considered)
checkpoint | Ceiling Grid ( pass when all below ticked)
bool | Ceiling height correct
bool | Appropriate fixings used and installed as per required specification
bool | Appropriate spacings for respective grid elements
bool | Perimeter channel/angle installed correctly
bool | All strong backs installed where required to meet specification
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | Any additional photos, comments and observations
section | Insulation Prior to Lining
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | Insulation pre lining works completed, checked & approved
bool | Correct product & R value as per specification
bool | Fitting Snug
checkpoint | Any additional photos, comments and observations
section | Council Sign Off
checkpoint | Council preline inspection passed
checklist | Final Sign Off
checkpoint | Doors Installed including drop down seals if applicable
checkpoint | Hardware as per approved schedule
checkpoint | Architraves and skirtings installed
checkpoint | Electrical Power/Lighting second fix installed
checkpoint | Sprinkler/Alarm second fix installed
checkpoint | Security second fix installed
checkpoint | Data second fix installed
checkpoint | HVAC second fix installed
checkpoint | Floor finishes installed as per architectural plan
checkpoint | Paint correct colour
checkpoint | Door signage installed
checkpoint | Manifestations on glazing
checkpoint | Joinery installed correctly
checklist | Walls Postline
checkpoint | Correct linings installed as per linings plan
checkpoint | Bracing fixings installed correctly as per requirements
checkpoint | Linings cut out for flush boxes neat and tidy
checkpoint | All screws installed flush
checkpoint | Wall approved for stopping
checkpoint | Stopping light check complete ready for paint
checklist | Flooring
checkpoint | Floor substrate clean, dry, ready for finishes
checkpoint | Finishes as per architectural plans
checkpoint | Trim thresholds junction as per detail
checkpoint | Any additional photos, comments and observations
checklist | Wall Preline
section | Interior Framing
checkpoint | Reference Drawings ( add numbers and revisions)
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | All framing setout correctly & surveyed in respective area
bool | Spot checks on frames for square
bool | Spot checks on frame level
bool | Fixings are correct including seismic requirements
bool | Service Nogs installed
checkpoint | Any additional photos, comments and observations
section | Plumbing Walls First Fix
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | Plumbing install First fix complete - checks done based on elevations of current drawings
checkpoint | Any additional photos, comments and observations
checkpoint | Council inspection and testing complete and signed off
section | Fire Protection Walls (Alarms) First Fix
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | First Fix checks with Subcontractor (alarms)
checkpoint | All required 1st fix testing complete
checkpoint | Any additional photos, comments and observations
section | Mechanical Services Wall First Fix
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | First Fix checks with subcontractor
checkpoint | Any additional photos, comments and observations
section | Electrical Wall First Fix
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | First Fix checks with Subcontractor
checkpoint | All required first fix testing complete
checkpoint | Any additional photos, comments and observations
section | Data Wall First Fix
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | All required first fix completed
checkpoint | Any additional photos, comments and observations
section | Security Wall First Fix
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | All required first fix completed
checkpoint | Any additional photos, comments and observations
section | AV Wall First Fix
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | All required first fix completed
checkpoint | Any additional photos, comments and observations
section | Insulation/Acoustic
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | Spot checks on correct product
checkpoint | Spot checks on correct R value
checkpoint | Fitting Snug
checkpoint | Any additional photos, comments and observations
section | Council Sign Off
checkpoint | Council preline inspection passed
checklist | Ceiling Postline
checkpoint | Correct linings installed as per linings plan
checkpoint | Fixings as per specification including if glue required
checkpoint | Service penetrations cut out as per architecture RCP
checkpoint | Any ceiling hatches installed & fixed correctly
checkpoint | Ceiling approved for stopping
checkpoint | Stopping light check complete ready for paint